## Sheet1
MINOR INSPECTION | [12 empty] | อัตรากำลัง (จำนวนคน)
REMARK | ใบแม่ | เป็นลูกของใบแม่อะไร? | KKS | EQUIPMENT | TASK_ORDERd | TASK_XX | TASK | RESPONSE | DURATION_(HR.) | START_DATE | FINISH_DATE | SUPERVISOR | FOREMAN | SKILL | RESPONSE_CRAFT | ประเภทของ_PERMIT_TO_WORK | TYPE | COMMENT
| X1 | X | SNR-H00SMH01 | POWERHOUSE CRANE TEST BEFORE SHUT DOWN - MAIN HOIST 440 ตัน/เครน 2 ชุด - AUX. HOIST 34.56 ตัน |  | xx | POWERHOUSE CRANE TEST BEFORE SHUT DOWN - MAIN HOIST 440 ตัน/เครน 2 ชุด - AUX. HOIST 34.56 ตัน | หบนม-ธ. | 88 | 2024-08-20 | 2024-08-24 |  |  |  | MSP0-MH20 |  | M
| X1.1 | X1 | SNR-H00SMH01AE100 | OVERHEAD CRANE NO.1 | 10 | 10 | VISUAL INSPECTION | หบนม-ธ. | 3 | 20/8/2024 | 20/8/2024 |  | 1 | 4 | MSP0-MH20 | PTW งาน Station Crane | M
|  |  | SNR-H00SMH01AE100 |  | 20 | 20 | CLEAN | หบนม-ธ. | 3 | 20/8/2024 | 20/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE100 |  | 30 | 30 | EQUIPMENT TEST | หบนม-ธ. | 14 | 20/8/2024 | 21/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE100 |  | 40 | 40 | FUNCTION TEST | หบนม-ธ. | 14 | 20/8/2024 | 21/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE100 |  | 50 | 50 | LOAD TEST | หบนม-ธ. | 7 | 22/8/2024 | 22/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE100 |  | 60 | 60 | INSPECTION REPORT | หบนม-ธ. | 3 | 24/8/2024 | 24/8/2024 |  |  |  | MSP0-MH20 |  | M
| X1.2 | X1 | SNR-H00SMH01AE200 | OVERHEAD CRANE NO.2 | 10 | 10 | VISUAL INSPECTION | หบนม-ธ. | 3 | 20/8/2024 | 20/8/2024 |  | 1 | 4 | MSP0-MH20 | PTW งาน Station Crane | M
|  |  | SNR-H00SMH01AE200 |  | 20 | 20 | CLEAN | หบนม-ธ. | 3 | 20/8/2024 | 20/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE200 |  | 30 | 30 | EQUIPMENT TEST | หบนม-ธ. | 14 | 20/8/2024 | 21/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE200 |  | 40 | 40 | FUNCTION TEST | หบนม-ธ. | 14 | 20/8/2024 | 21/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE200 |  | 50 | 50 | LOAD TEST | หบนม-ธ. | 7 | 22/8/2024 | 22/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH01AE200 |  | 60 | 60 | INSPECTION REPORT | หบนม-ธ. | 3 | 24/8/2024 | 24/8/2024 |  |  |  | MSP0-MH20 |  | M
| X2 | X | SNR-H00SMH31 | GANTRY CRANE TEST BEFORE SHUT DOWN (24 ตัน) |  | xx | GANTRY CRANE TEST BEFORE SHUT DOWN (24 ตัน) | หบนม-ธ. | 14 | 22/8/2024 | 24/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH31 |  | 10 | 10 | VISUAL INSPECTION | หบนม-ธ. | 1 | 22/8/2024 | 22/8/2024 |  | 1 | 4 | MSP0-MH20 | PTW งาน Station Crane | M
|  |  | SNR-H00SMH31 |  | 20 | 20 | CLEAN | หบนม-ธ. | 2 | 22/8/2024 | 22/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH31 |  | 30 | 30 | EQUIPMENT TEST | หบนม-ธ. | 2 | 2024-08-23 | 2024-08-23 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH31 |  | 40 | 40 | FUNCTION TEST | หบนม-ธ. | 2 | 2024-08-23 | 2024-08-23 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH31 |  | 50 | 50 | LOAD TEST | หบนม-ธ. | 4 | 23/8/2024 | 23/8/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H00SMH31 |  | 60 | 60 | INSPECTION REPORT | หบนม-ธ. | 3 | 24/8/2024 | 24/8/2024 |  |  |  | MSP0-MH20 |  | M
| A |  | SNR-H03M | MECHANICAL EQUIPMENT |  | xx | MECHANICAL EQUIPMENT | อขศ.+อบค.+อรอ. | 1017.25 | 26/8/2024 | 12/9/2024 | [5 empty] | M
| A0 | A | SNR-H03LPB10AB001KB01 | INTAKE GATE |  | xx | INTAKE GATE | หบศ-ฟ. | 10 | 3/9/2024 | 2024-09-10 |  |  |  | SNR0-2M0 |  | M
| A0.1 | A0 | SNR-H03LPB10AB001KB01 | INTAKE GATE (หบศ-ฟ.) |  | xx | INTAKE GATE (หบศ-ฟ.) | หบศ-ฟ. | 7 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03LPB10AB001KB01 |  | 10 | 10 | CLOSE INTAKE GATE & DRAIN WATER FROM SPIRAL CASE | หบศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งาน Station Crane | M
|  |  | SNR-H03LPB10AB001KB01 |  | 20 | 20 | FILL WATER & OPEN INTAKE GATE | หบศ-ฟ. | 5 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A0.2 | A0 | SNR-H03LPB10AB001KB01 | INTAKE GATE (หฟศ-ฟ.) |  | xx | INTAKE GATE (หฟศ-ฟ.) | หฟศ-ฟ. | 3 | 3/9/2024 | 2024-09-10 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03LPB10AB001KB01 |  | 10 | 10 | CLOSE INTAKE GATE | หฟศ-ฟ. | 1.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2E0 | PTW งาน Station Crane | M
|  |  | SNR-H03LPB10AB001KB01 |  | 20 | 20 | OPEN INTAKE GATE | หฟศ-ฟ. | 1.5 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | M
| A1 | A | SNR-H13LQC10 | TAILRACE GATE |  | xx | TAILRACE GATE | หบศ-ฟ. | 26 | 3/9/2024 | 2024-09-10 |  |  |  | SNR0-2M0 |  | M
| A1.1 | A1 | SNR-H13LQC10 | DIVING at TAILRACE GATE |  | xx | DIVING at TAILRACE GATE | หบตน-ธ. | 8 | 3/9/2024 | 10/9/2024 |  |  |  | MSP0-MH30 |  | M
| A1.1.1 | A1.1 | SNR-H13LQC10AB001 | DIVING at TAILRACE GATE No.1 |  | xx | DIVING at TAILRACE GATE No.1 | หบตน-ธ. | 4 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-MH30 |  | M
|  |  | SNR-H13LQC10AB001 |  | 10 | 10 | STAND BY CLOSE TAILRACE GATE | หบตน-ธ. | 2 | 3/9/2024 | 3/9/2024 |  | 2 | 4 | MSP0-MH30 | PTW งานประดาน้ำ | M
|  |  | SNR-H13LQC10AB001 |  | 20 | 20 | INSPECTION AND REMOVE MUD AND WASTE THRESHOLD AREA | หบตน-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-MH30 |  | M
| A1.1.2 | A1.1 | SNR-H13LQC10AB002 | DIVING at TAILRACE GATE No.2 |  | xx | DIVING at TAILRACE GATE No.2 | หบตน-ธ. | 4 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-MH30 |  | M
|  |  | SNR-H13LQC10AB002 |  | 10 | 10 | STAND BY CLOSE TAILRACE GATE | หบตน-ธ. | 2 | 3/9/2024 | 3/9/2024 |  | 2 | 4 | MSP0-MH30 | PTW งานประดาน้ำ | M
|  |  | SNR-H13LQC10AB002 |  | 20 | 20 | INSPECTION AND REMOVE MUD AND WASTE THRESHOLD AREA | หบตน-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-MH30 |  | M
| A1.2 | A1 | SNR-H13LQC10 | TAILRACE GATE CHECK |  | xx | TAILRACE GATE CHECK | หบศ-ฟ. | 18 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A1.2.1 | A1.2 | SNR-H13LQC10AB001 | TAILRACE GATE No.1 |  | xx | TAILRACE GATE No.1 | หบศ-ฟ. | 9 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB001 |  | 10 | 10 | CLOSE TAILRACE GATE | หบศ-ฟ. | 3 | 3/9/2024 | 3/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งาน Station Crane | M
|  |  | SNR-H13LQC10AB001 |  | 20 | 20 | VISUAL INSPECTION | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB001 |  | 30 | 30 | SEAL INSPECTION | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB001 |  | 40 | 40 | LEAKAGE CHECK | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB001 |  | 50 | 50 | FILL WATER & OPEN TAILRACE GATE | หบศ-ฟ. | 3 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A1.2.2 | A1.2 | SNR-H13LQC10AB002 | TAILRACE GATE No.2 |  | xx | TAILRACE GATE No.2 | หบศ-ฟ. | 9 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB002 |  | 10 | 10 | CLOSE TAILRACE GATE | หบศ-ฟ. | 3 | 3/9/2024 | 3/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งาน Station Crane | M
|  |  | SNR-H13LQC10AB002 |  | 20 | 20 | VISUAL INSPECTION | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB002 |  | 30 | 30 | SEAL INSPECTION | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB002 |  | 40 | 40 | LEAKAGE CHECK | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LQC10AB002 |  | 50 | 50 | FILL WATER & OPEN TAILRACE GATE | หบศ-ฟ. | 3 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A2 | A | SNR-H03MK | GENERATOR |  | xx | GENERATOR | หบศ-ฟ. | 176.25 | 2024-08-26 | 2024-09-12 |  |  |  | SNR0-2M0 |  | M
| A2.1 | A2 | SNR-H03MKA20 | GENERATOR ROTOR |  | xx | GENERATOR ROTOR | หบศ-ฟ. | 4 | 26/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA20 |  | 10 | 10 | ROTOR LEVELLING CHECK | หบศ-ฟ. | 3 | 26/8/2024 | 26/8/2024 | 1 | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MKA20 |  | 20 | 20 | ROTOR LIFT UP TEST | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A2.2 | A2 | SNR-H03MKA30HA005 | GENERATOR FLOOR PLATE |  | xx | GENERATOR FLOOR PLATE | หบศ-ฟ. | 11 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MKA30HA005 |  | 10 | 10 | REMOVE GEN. FLOOR PLATE | หบศ-ฟ. | 4 | 3/9/2024 | 3/9/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA30HA005 |  | 20 | 20 | INSTALL GEN. FLOOR PLATE | หบศ-ฟ. | 7 | 9/9/2024 | 9/9/2024 |  |  |  | SNR0-2M0 |  | M
| A2.3 | A2 | SNR-H03MKA41 | GENERATOR. AIR COOLER NO.1-12 |  | xx | GENERATOR AIR COOLER NO.1-12 | หบศ-ฟ. | 47 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MKA41 |  | 10 | 10 | DRAIN WATER AND REMOVE WATER PIPE LINE | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKA41 |  | 20 | 20 | DISASSEMBLY & REMOVE AIR COOLER | หบศ-ฟ. | 7 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MKA41 |  | 30 | 30 | MOVE AIR COOLER TO CLEANING AREA | หบศ-ฟ. | 3 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA41 |  | 40 | 40 | CLEAN AND INSPECT | หบศ-ฟ. | 7 | 5/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA41 |  | 50 | 50 | REPAIR IF NECESSARY | หบศ-ฟ. | 7 | 5/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA41 |  | 60 | 60 | ASSEMBLY AND PRESSURE TEST | หบศ-ฟ. | 3 | 5/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA41 |  | 70 | 70 | INSTALL AIR COOLER | หบศ-ฟ. | 17 | 7/9/2024 | 9/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MKA41 |  | 80 | 80 | PRESSURE TEST AND LEAKAGE CHECK (ON SYSTEM LINE) | หบศ-ฟ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.4 | A2 | SNR-H03MKU10 | GENERATOR OIL COOLER NO.A-B |  | xx | GENERATOR. OIL COOLER NO.A-B | หบศ-ฟ. | 4 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10 |  | 10 | 10 | DRAIN WATER | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10 |  | 20 | 20 | DISASSEMBLY AND CLEAN | หบศ-ฟ. | 2 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10 |  | 30 | 30 | ASSEMBLY & INSPECT | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10 |  | 40 | 40 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.5 | A2 | SNR-H03MKU10AT001 | GENERATOR OIL STRAINER |  | xx | GENERATOR OIL STRAINER | หบศ-ฟ. | 3.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10AT001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10AT001 |  | 20 | 20 | CLEAN STRAINER | หบศ-ฟ. | 2 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKU10AT001 |  | 30 | 30 | LEAKAGE CHECK OIL STRAINER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
| A2.6 | A2 | SNR-H03MKY10 | HIGH PRESSURE OIL LIFTING EQUIPMENT |  | xx | HIGH PRESSURE OIL LIFTING EQUIPMENT | หบศ-ฟ. | 9 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.6.1 | A2.6 | SNR-H03MKY10AP001 | HIGH PRESSURE OIL LIFT PUMP NO.1 |  | xx | HIGH PRESSURE OIL LIFT PUMP NO.1 | หบศ-ฟ. | 4.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 10 | 10 | OPERATION AND PERFORMANCE TEST (BEFORE) | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 20 | 20 | DISASSEMBLY & REMOVE FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 30 | 30 | CLEANING FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 40 | 40 | ASSEMBLY FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 50 | 50 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP001 |  | 60 | 60 | OPERATION AND PERFORMANCE TEST (AFTER) | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.6.2 | A2.6 | SNR-H03MKY10AP002 | HIGH PRESSURE OIL LIFT PUMP NO.2 |  | xx | HIGH PRESSURE OIL LIFT PUMP NO.2 | หบศ-ฟ. | 4.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 10 | 10 | OPERATION AND PERFORMANCE TEST (BEFORE) | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 20 | 20 | DISASSEMBLY & REMOVE FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 30 | 30 | CLEANING FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 40 | 40 | ASSEMBLY FILTER | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 50 | 50 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKY10AP002 |  | 60 | 60 | OPERATION AND PERFORMANCE TEST (AFTER) | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.7 | A2 | SNR-H03MKA50 | FRICTION BRAKE |  | xx | FRICTION BRAKE | หบศ-ฟ. | 12 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.7.1 | A2.7 | SNR-H03MKA50 | FRICTION BRAKE (หบศ-ฟ.) |  | xx | FRICTION BRAKE (หบศ-ฟ.) | หบศ-ฟ. | 9 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 10 | 10 | CLEANING | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 20 | 20 | GAP CHECK BETWEEN BRAKE RING AND BRAKE SHOES | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 30 | 30 | VISUAL INSPECTION AT BRAKE RING AND BRAKE SHOES | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 40 | 40 | BRAKE SHOES THICKNESS CHECK | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA50 |  | 60 | 60 | INSPECTION REPORT | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A2.7.2 | A2.7 | SNR-H03MKA50 | FRICTION BRAKE (หงศ-ฟ.) |  | xx | FRICTION BRAKE (หงศ-ฟ.) | หงศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2S0 |  | M
|  |  | SNR-H03MKA50 |  | 10 | 10 | PT CHECK BRAKE RING | หงศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  | 1 | 3 | SNR0-2S0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. | A2.8 | A2 | SNR-H03MKA80AU001 | BRAKE DUST EXHAUST PLANT |  | xx | BRAKE DUST EXHAUST PLANT | หบศ-ฟ. | 2.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA80AU001 |  | 10 | 10 | OPERATION TEST | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA80AU001 |  | 20 | 20 | CLEAN FILTER | หบศ-ฟ. | 2 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.9 | A2 | SNR-H03MKD10BB001 | GEN. OIL PAN |  | xx | GEN. OIL PAN | หบศ-ฟ. | 22 | 3/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 10 | 10 | OIL DRAIN | หบศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 20 | 20 | OPEN MANHOLE | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 30 | 30 | OIL PURIFY | หบศ-ฟ. | 7 | 3/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 40 | 40 | CLEAN OIL PAN | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 50 | 50 | VISUAL INSPECTION | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน CM โดย หบศ-ฟ./แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 60 | 60 | REPAIR LEAK SIGHTGLASS LEVEL GAUGE | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 70 | 70 | REPLACE NEW SEAL | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 80 | 80 | CLOSE MANHOLE | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD10BB001 |  | 90 | 90 | OIL FILL AND LEAK CHECK | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.10 | A2 | SNR-H03MKA30HA001 | LOWER BRACKET |  | xx | LOWER BRACKET | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA30HA001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA30HA001 |  | 20 | 20 | CLEANING | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKA30HA001 |  | 30 | 30 | LOOSEN CHECK AT BASE OF LOWER BRACKET | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A2.11 | A2 | SNR-H03MKD11GH001 | OIL VAPOR |  | xx | OIL VAPOR | หบศ-ฟ. | 2 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD11GH001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  | 1 | 5 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD11GH001 |  | 20 | 20 | DRAIN OIL&CLEANING | หบศ-ฟ. | 1 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MKD11GH001 |  | 30 | 30 | OPERATION TEST | หบศ-ฟ. | 0.5 | 26/8/2024 | 26/8/2024 |  |  |  | SNR0-2M0 |  | M
| A2.12 | A2 | SNR-H03MKD10 | INSTRUMENT (LCB RTD) |  | xx | INSTRUMENT (LCB RTD) | หฟศ-ฟ. | 15.75 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.12.1 | A2.12 | SNR-H03MKD10CT001 | RTD TEMPERATURE GUIDE PAD LCB MKD30CT001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.12.2 | A2.12 | SNR-H03MKD10CT002 | RTD TEMPERATURE GUIDE PAD LCB MKD30CT002 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.12.3 | A2.12 | SNR-H03MKD10CT003 | RTD TEMPERATURE GUIDE PAD LCB MKD30CT003 | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.12.4 | A2.12 | SNR-H03MKD10CT004 | RTD TEMPERATURE THRUST PAD LCB MKD30CT004 | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.12.5 | A2.12 | SNR-H03MKD10CT005 | RTD TEMPERATURE THRUST PAD LCB MKD30CT005 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 | A2.12.6 | A2.12 | SNR-H03MKD10CT006 | RTD TEMPERATURE THRUST PAD LCB MKD30CT006 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.12.7 | A2.12 | SNR-H03MKD10CT010 | RTD TEMPERATURE BEARING OIL LCB MKD30CT007 | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.13 | A2 | SNR-H03MKD10 | INSTRUMENT (LCB DIAL TEMP.) |  | xx | INSTRUMENT (GEN. OIL COOLER DIAL TEMP.) | หฟศ-ฟ. | 6 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.13.1 | A2.13 | SNR-H03MKD10CT007 | TEMPERATURE GUIDE PAD LCB PCB30CT001-C01/C02 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.13.2 | A2.13 | SNR-H03MKD10CT008 | TEMPERATURE THRUST PAD LCB PCB30CT002-C01/C02 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.13.3 | A2.13 | SNR-H03MKD10CT009 | TEMPERATURE SUMP OIL LCB PCB30CT003-C01/C02 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.14 | A2 | SNR-H03MKD10CL001 | INSTRUMENT (OIL LEVEL LOWER COMBINED BEARING MKD30CL301) |  | xx | INSTRUMENT (OIL LEVEL LOWER COMBINED BEARING MKD30CL301) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD10CL001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKD10CL001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD10CL001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD10CL001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD10CL001 |  | 50 | 50 | ADJUSTMENT(SW) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD10CL001 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MKD10CL001 |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MKD10CL001 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.15 | A2 | SNR-H03MKD30CM001 | INSTRUMENT (MOISTURE in OIL DETECTORLCB MKV30CP501) |  | xx | INSTRUMENT (MOISTURE in OIL DETECTORLCB MKV30CP501) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD30CM001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKD30CM001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD30CM001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD30CM001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD30CM001 |  | 50 | 50 | ADJUSTMENT(SW) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKD30CM001 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MKD30CM001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.16 | A2 | SNR-H03MKU10CF001 | INSTRUMENT (LCB OIL FLOW MONITOR MKV30CF001-S01/S02 ) |  | xx | INSTRUMENT (LCB OIL FLOW MONITOR MKV30CF001-S01/S02 ) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CF001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKU10CF001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CF001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CF001 |  | 40 | 40 | TESTING FOR AS FOUND (LIMIT SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CF001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MKU10CF001 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CF001 |  | 70 | 70 | ADJUSTMENT (SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MKU10CF001 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.17 | A2 | SNR-H03MKU10 | INSTRUMENT (GEN. OIL COOLER RTD) |  | xx | INSTRUMENT (GEN. OIL COOLER RTD) | หฟศ-ฟ. | 4.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.17.1 | A2.17 | SNR-H03MKU10CT003 | COLD OIL OUTLET to OIL COOLERS LCB TEMP. (LUB OIL PLANT) MKV30CP005 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.17.2 | A2.17 | SNR-H03MKU10CT004 | HOT OIL INLET to OIL COOLERS LCB TEMP. (LUB OIL PLANT) MKV30CP006 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.18 | A2 | SNR-H03MKU10 | INSTRUMENT (GEN. OIL COOLER DIAL TEMP.) |  | xx | INSTRUMENT (GEN. OIL COOLER DIAL TEMP.) | หฟศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.18.1 | A2.18 | SNR-H03MKU10CT001 | TEMPERATURE OIL INLET to OIL COOLERS LCB LUBE OIL PLANT MKV30CP003 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.18.2 | A2.18 | SNR-H03MKU10CT002 | TEMPERATURE OIL OUTLET From OIL COOLERS LCB LUBE OIL PLANT MKV30CP004) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.19 | A2 | SNR-H03MKU10CP003-S01 | INSTRUMENT (GEN. OIL COOLER DIFF. PRESSURE SWITCH ACROSS DUPLEX OIL FILTER LCB MKV30CP301-S01) |  | xx | INSTRUMENT (GEN. OIL COOLER DIFF. PRESSURE SWITCH ACROSS DUPLEX OIL FILTER LCB MKV30CP301-S01) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CP003-S01 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKU10CP003-S01 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CP003-S01 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CP003-S01 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CP003-S01 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MKU10CP003-S01 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKU10CP003-S01 |  | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MKU10CP003-S01 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.20 | A2 | SNR-H03MKU10 | INSTRUMENT (GEN. OIL COOLER PRESSURE GAUGE) |  | xx | INSTRUMENT (GEN. OIL COOLER PRESSURE GAUGE) | หฟศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.20.1 | A2.20 | SNR-H03MKU10CP004 | PRESSURE OIL OUTLET to OIL COOLERS LCB LUBE OIL PLANT MKV30CP007 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.20.2 | A2.20 | SNR-H03MKU10CP001 | PRESSURE OIL INLET to OIL COOLERS LCB LUBE OIL PLANT MKV30CP008 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.21 | A2 | SNR-H03MKY10 | INSTRUMENT (HP OIL LIFT PUMP PRESSURE SWITCH & DIFF PRESSURE SWITCH) |  | xx | INSTRUMENT (HP OIL LIFT PUMP PRESSURE SWITCH & DIFF PRESSURE SWITCH) | หฟศ-ฟ. | 10 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.21.1 | A2.21 | SNR-H03MKY10CP001-S03 | DIFF. PRESSURE ACROSS HP OIL FILTER MKV50CP302-S01 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A2.21.2 | A2.21 | SNR-H03MKY10CP001-S04 | HIGH PRESSURE OIL INLET LINE to LCB MKV50CP301-S01 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.21.3 | A2.21 | SNR-H03MKY10CP001-S02 | HIGH PRESSURE OIL INLET LINE to LCB MKV50CP303-S01 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.21.4 | A2.21 | SNR-H03MKY10CP001-S01 | HIGH PRESSURE OIL INLET LINE to LCB MKV50CP304-S01 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A2.22 | A2 | SNR-H03MKY10CP003 | INSTRUMENT (HP OIL LIFT PUMP PRESSURE OIL INLET LINE to LCB MKV50CP502) |  | xx | INSTRUMENT (HP OIL LIFT PUMP PRESSURE OIL INLET LINE to LCB MKV50CP502) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKY10CP003 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MKY10CP003 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKY10CP003 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKY10CP003 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKY10CP003 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MKY10CP003 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MKY10CP003 |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MKY10CP003 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3 | A | SNR-H03ME | TURBINE |  | xx | TURBINE | หบศ-ฟ. | 359 | 27/8/2024 | 12/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.1 | A3 | SNR-H03MEA40 | DRAFT TUBE, SPIRAL CASE&STAY VANE |  | xx | DRAFT TUBE, SPIRAL CASE & STAY VANE | หบศ-ฟ. | 34 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.1.1 | A3.1 | SNR-H03MEA40HA004 | DRAFT TUBE (หบศ-ฟ.) |  | xx | DRAFT TUBE (หบศ-ฟ.) | หบศ-ฟ. | 16 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA004 |  | 10 | 10 | DRAIN WATER FROM DRAFT TUBE | หบศ-ฟ. | 4 | 3/9/2024 | 3/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA40HA004 |  | 20 | 20 | OPEN MANHOLE | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หวปศ-ฟ. |  |  | SNR-H03MEA40HA004 |  | 30 | 30 | INSTALL STEEL SCAFFOLDING | หบศ-ฟ. | 4 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA004 |  | 40 | 40 | CLEANING | หบศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA004 |  | 50 | 50 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA004 |  | 60 | 60 | PAINTING REPAIR | หบศ-ฟ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หวปศ-ฟ. |  |  | SNR-H03MEA40HA004 |  | 70 | 70 | REMOVE STEEL SCAFFOLDING | หบศ-ฟ. | 2 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEA40HA004 |  | 80 | 80 | CLOSE MANHOLE AND LEAK CHECK | หบศ-ฟ. | 1 | 9/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.1.2 | A3.1 | SNR-H03MEA40HA004 | DRAFT TUBE (หขศ-ฟ.) |  | xx | DRAFT TUBE (หขศ-ฟ.) | หขศ-ฟ. | 4 | 3/9/2024 | 8/9/2024 |  |  |  | SNR0-3D0 |  | M
|  |  | SNR-H03MEA40HA004 |  | 10 | 10 | INSTALL SCAFFOLD | หขศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  | 1 | 7 | SNR0-3D0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | M
|  |  | SNR-H03MEA40HA004 |  | 20 | 20 | REMOVE SCAFFOLD | หขศ-ฟ. | 2 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-3D0 |  | M
| A3.1.3 | A3.1 | SNR-H03MEA10HA001 | SPIRAL CASE |  | xx | SPIRAL CASE | หบศ-ฟ. | 6 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA10HA001 |  | 10 | 10 | OPEN MANHOLE | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA10HA001 |  | 20 | 20 | CLEANING | หบศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA10HA001 |  | 30 | 30 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA10HA001 |  | 40 | 40 | PAINTING REPAIR | หบศ-ฟ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEA10HA001 |  | 50 | 50 | CLOSE MANHOLE AND LEAK CHECK | หบศ-ฟ. | 1 | 9/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.1.4 | A3.1 | SNR-H03MEA40 | STAY VANE No.1-12 |  | xx | STAY VANE No.1-12 | หบศ-ฟ. | 54 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.1.4.1 | A3.1.4 | SNR-H03MEA40HA101 |  | 10 | 10 | CLEANING | หบศ-ฟ. | 2 | 8/9/2024 | 8/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
| A3.1.4.2 | A3.1.4 | SNR-H03MEA40HA102 |  | 20 | 20 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 | [5 empty] | M
| A3.1.4.3 | A3.1.4 | SNR-H03MEA40HA103 |  | 30 | 30 | PAINTING REPAIR | หบศ-ฟ. | 2 | 8/9/2024 | 8/9/2024 | [5 empty] | M
| A3.1.4.4 | A3.1.4 | SNR-H03MEA40HA104 | [13 empty] | M
| A3.1.4.5 | A3.1.4 | SNR-H03MEA40HA105 | [13 empty] | M
| A3.1.4.6 | A3.1.4 | SNR-H03MEA40HA106 | [13 empty] | M
| A3.1.4.7 | A3.1.4 | SNR-H03MEA40HA107 | [13 empty] | M
| A3.1.4.8 | A3.1.4 | SNR-H03MEA40HA108 | [13 empty] | M
| A3.1.4.9 | A3.1.4 | SNR-H03MEA40HA109 | [11 empty] | SNR0-2M0 |  | M
| A3.1.4.10 | A3.1.4 | SNR-H03MEA40HA110 | [11 empty] | SNR0-2M0 |  | M
| A3.1.4.11 | A3.1.4 | SNR-H03MEA40HA111 | [13 empty] | M
| A3.1.4.12 | A3.1.4 | SNR-H03MEA40HA112 | [13 empty] | M
| A3.1.5 | A3.1 | SNR-H03MEA40HA003 | HEAD COVER |  | xx | HEAD COVER | หบศ-ฟ. | 5.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA003 |  | 10 | 10 | CLEANING | หบศ-ฟ. | 3 | 7/9/2024 | 7/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA40HA003 |  | 20 | 20 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA003 |  | 30 | 30 | PAINTING REPAIR | หบศ-ฟ. | 2 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2 | A3 | SNR-H03MEA20 | GUIDE VANE MECHANISM |  | xx | GUIDE VANE MECHANISM & SERVOMOTOR | หบศ-ฟ. | 112.5 | 3/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.1 | A3.2 | SNR-H03MEA20 | G/V MECHANISM |  | xx | G/V MECHANISM | หบศ-ฟ. | 12.5 | 3/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 6 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA20 |  | 20 | 20 | SQUEEZE UN-SQUEEZE CHECK | หบศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 30 | 30 | SIDE GAP, CLOSING GAP, AO, BG CHECK (BEFORE) | หบศ-ฟ. | 2 | 3/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 40 | 40 | AXIAL THRUST GAP CHECK | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 50 | 50 | ADJUST CLOSING GAP AND SIDE GAP (IF NECESSARY) | หบศ-ฟ. | 3 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 60 | 60 | GUIDE STRIP CLEARANCE CHECK | หบศ-ฟ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA20 |  | 70 | 70 | CLEANING | หบศ-ฟ. | 2 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.2 | A3.2 | SNR-H03MEA20 | PIN NO.1-24 (หบศ-ฟ.) |  | xx | PIN NO.1-24 (หบศ-ฟ.) | หบศ-ฟ. | 24 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.2.1 | A3.2.2 | SNR-H03MEA20HA101KE02 |  | 10 | 10 | REMOVE PIN OF GV MECHANISM (SAMPLING 4 EA) | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
| A3.2.2.2 | A3.2.2 | SNR-H03MEA20HA102KE02 |  | 20 | 20 | INSPECTION & CLEAN | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.2.3 | A3.2.2 | SNR-H03MEA20HA103KE02 |  | 30 | 30 | INSTALL PIN OF GV MECHANISM | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.2.4 | A3.2.2 | SNR-H03MEA20HA104KE02 | [13 empty] | M
| A3.2.2.5 | A3.2.2 | SNR-H03MEA20HA105KE02 | [13 empty] | M
| A3.2.2.6 | A3.2.2 | SNR-H03MEA20HA106KE02 | [13 empty] | M
| A3.2.2.7 | A3.2.2 | SNR-H03MEA20HA107KE02 | [13 empty] | M
| A3.2.2.8 | A3.2.2 | SNR-H03MEA20HA108KE02 | [13 empty] | M
| A3.2.2.9 | A3.2.2 | SNR-H03MEA20HA109KE02 | [13 empty] | M
| A3.2.2.10 | A3.2.2 | SNR-H03MEA20HA110KE02 | [13 empty] | M
| A3.2.2.11 | A3.2.2 | SNR-H03MEA20HA111KE02 | [13 empty] | M
| A3.2.2.12 | A3.2.2 | SNR-H03MEA20HA112KE02 | [13 empty] | M
| A3.2.2.13 | A3.2.2 | SNR-H03MEA20HA113KE02 | [13 empty] | M
| A3.2.2.14 | A3.2.2 | SNR-H03MEA20HA114KE02 | [13 empty] | M
| A3.2.2.15 | A3.2.2 | SNR-H03MEA20HA115KE02 | [13 empty] | M
| A3.2.2.16 | A3.2.2 | SNR-H03MEA20HA116KE02 | [13 empty] | M
| A3.2.2.17 | A3.2.2 | SNR-H03MEA20HA117KE02 | [13 empty] | M
| A3.2.2.18 | A3.2.2 | SNR-H03MEA20HA118KE02 | [13 empty] | M
| A3.2.2.19 | A3.2.2 | SNR-H03MEA20HA119KE02 | [13 empty] | M
| A3.2.2.20 | A3.2.2 | SNR-H03MEA20HA120KE02 | [13 empty] | M
| A3.2.2.21 | A3.2.2 | SNR-H03MEA20HA121KE02 | [13 empty] | M
| A3.2.2.22 | A3.2.2 | SNR-H03MEA20HA122KE02 | [13 empty] | M
| A3.2.2.23 | A3.2.2 | SNR-H03MEA20HA123KE02 | [13 empty] | M
| A3.2.2.24 | A3.2.2 | SNR-H03MEA20HA124KE02 | [13 empty] | M
| A3.2.2.25 | A3.2.2 | SNR-H03MEA20 | PIN NO.1-24 (หงศ-ฟ.) |  | xx | PIN NO.1-24 (หงศ-ฟ.) | หงศ-ฟ. | 8 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2S0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEA20 |  | 10 | 10 | PT CHECK ON PIN (SAMPLING 4 EA) | หงศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 3 | SNR0-2S0 | PTW งานทั่วไป | M
| A3.2.3 | A3.2 | SNR-H03MEA20 | ECCENTRIC PIN NO.1-24 (หบศ-ฟ.) |  | xx | ECCENTRIC PIN NO.1-24 (หบศ-ฟ.) | หบศ-ฟ. | 24 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.3.1 | A3.2.3 | SNR-H03MEA20HA101KE03 |  | 10 | 10 | REMOVE ECCENTRIC PIN OF GV MECHANISM (SAMPLING 4 EA) | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
| A3.2.3.2 | A3.2.3 | SNR-H03MEA20HA102KE03 |  | 20 | 20 | INSPECTION & CLEAN | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.3.3 | A3.2.3 | SNR-H03MEA20HA103KE03 |  | 30 | 30 | INSTALL ECCENTRIC PIN OF GV MECHANISM | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.3.4 | A3.2.3 | SNR-H03MEA20HA104KE03 | [13 empty] | M
| A3.2.3.5 | A3.2.3 | SNR-H03MEA20HA105KE03 | [13 empty] | M
| A3.2.3.6 | A3.2.3 | SNR-H03MEA20HA106KE03 | [13 empty] | M
| A3.2.3.7 | A3.2.3 | SNR-H03MEA20HA107KE03 | [13 empty] | M
| A3.2.3.8 | A3.2.3 | SNR-H03MEA20HA108KE03 | [13 empty] | M
| A3.2.3.9 | A3.2.3 | SNR-H03MEA20HA109KE03 | [13 empty] | M
| A3.2.3.10 | A3.2.3 | SNR-H03MEA20HA110KE03 | [13 empty] | M
| A3.2.3.11 | A3.2.3 | SNR-H03MEA20HA111KE03 | [13 empty] | M
| A3.2.3.12 | A3.2.3 | SNR-H03MEA20HA112KE03 | [13 empty] | M
| A3.2.3.13 | A3.2.3 | SNR-H03MEA20HA113KE03 | [13 empty] | M
| A3.2.3.14 | A3.2.3 | SNR-H03MEA20HA114KE03 | [13 empty] | M
| A3.2.3.15 | A3.2.3 | SNR-H03MEA20HA115KE03 | [13 empty] | M
| A3.2.3.16 | A3.2.3 | SNR-H03MEA20HA116KE03 | [13 empty] | M
| A3.2.3.17 | A3.2.3 | SNR-H03MEA20HA117KE03 | [13 empty] | M
| A3.2.3.18 | A3.2.3 | SNR-H03MEA20HA118KE03 | [13 empty] | M
| A3.2.3.19 | A3.2.3 | SNR-H03MEA20HA119KE03 | [13 empty] | M
| A3.2.3.20 | A3.2.3 | SNR-H03MEA20HA120KE03 | [13 empty] | M
| A3.2.3.21 | A3.2.3 | SNR-H03MEA20HA121KE03 | [13 empty] | M
| A3.2.3.22 | A3.2.3 | SNR-H03MEA20HA122KE03 | [13 empty] | M
| A3.2.3.23 | A3.2.3 | SNR-H03MEA20HA123KE03 | [13 empty] | M
| A3.2.3.24 | A3.2.3 | SNR-H03MEA20HA124KE03 | [13 empty] | M
| A3.2.3.25 | A3.2.3 | SNR-H03MEA20 | ECCENTRIC PIN NO.1-24 (หงศ-ฟ.) |  | xx | ECCENTRIC PIN NO.1-24 (หงศ-ฟ.) | หงศ-ฟ. | 8 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2S0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEA20 |  | 10 | 10 | PT CHECK ON ECCENTRIC PIN (SAMPLING 4 EA) | หงศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 3 | SNR0-2S0 | PTW งานทั่วไป | M
| A3.2.4 | A3.2 | SNR-H03MEA20 | BENDING LINK No.2, 4, 6, 8, 10,12, 14, 16, 18, 20, 22, 24 |  | xx | BENDING LINK No.2, 4, 6, 8, 10,12, 14, 16, 18, 20, 22, 24 | หบศ-ฟ. | 36 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.2.4.1 | A3.2.4 | SNR-H03MEA20HA102MU01 |  | 10 | 10 | MECHANISM LINK, LEVEL AND ROD PIN, ECCENTRIC PIN INSPECTION AND DIMENSION CHECK (SAMPLING 4 EA) | หบศ-ฟ. | 3 | 5/9/2024 | 5/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
| A3.2.4.2 | A3.2.4 | SNR-H03MEA20HA104MU01 | [13 empty] | M
| A3.2.4.3 | A3.2.4 | SNR-H03MEA20HA106MU01 | [13 empty] | M
| A3.2.4.4 | A3.2.4 | SNR-H03MEA20HA108MU01 | [13 empty] | M
| A3.2.4.5 | A3.2.4 | SNR-H03MEA20HA110MU01 | [13 empty] | M
| A3.2.4.6 | A3.2.4 | SNR-H03MEA20HA112MU01 | [13 empty] | M
| A3.2.4.7 | A3.2.4 | SNR-H03MEA20HA114MU01 | [13 empty] | M
| A3.2.4.8 | A3.2.4 | SNR-H03MEA20HA116MU01 | [13 empty] | M
| A3.2.4.9 | A3.2.4 | SNR-H03MEA20HA118MU01 | [13 empty] | M
| A3.2.4.10 | A3.2.4 | SNR-H03MEA20HA120MU01 | [13 empty] | M
| A3.2.4.11 | A3.2.4 | SNR-H03MEA20HA122MU01 | [13 empty] | M
| A3.2.4.12 | A3.2.4 | SNR-H03MEA20HA124MU01 | [13 empty] | M
| A3.3 | A3 | SNR-H03MEA30HB100 | RUNNER |  | xx | RUNNER | หบศ-ฟ. | 20 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.3.1 | A3.3 | SNR-H03MEA30HB100 | RUNNER (หบศ-ฟ.) |  | xx | RUNNER (หบศ-ฟ.) | หบศ-ฟ. | 10 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA30HB100 |  | 10 | 10 | RUNNER GAP CHECK | หบศ-ฟ. | 2 | 5/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA30HB100 |  | 20 | 20 | CLEANING (BY GRINDING) | หบศ-ฟ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA30HB100 |  | 30 | 30 | CAVITATION AND PITTING CHECK | หบศ-ฟ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA30HB100 |  | 40 | 40 | REPAIR IF NECESSARY | หบศ-ฟ. | 4 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 | PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | M
| A3.3.2 | A3.3 | SNR-H03MEA30HB100 | RUNNER (หงศ-ฟ.) |  | xx | RUNNER (หงศ-ฟ.) | หงศ-ฟ. | 10 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2S0 |  | M
|  |  | SNR-H03MEA30HB100 |  | 10 | 10 | PT CHECK ON RUNNER BLADES | หงศ-ฟ. | 10 | 5/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2S0 | PTW งานในที่อับอากาศ | M
| A3.4 | A3 | SNR-H03MEA40HA007 | TURBINE SHAFT SEALING BOX |  | xx | TURBINE SHAFT SEALING BOX | หบศ-ฟ. | 15 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.4.1 | A3.4 | SNR-H03MEA40HA007KK01 | SQUARE PACKING SEAL |  | xx | SQUARE PACKING SEAL | หบศ-ฟ. | 4 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK01 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA40HA007KK01 |  | 20 | 20 | REMOVE SEAL | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK01 |  | 30 | 30 | SEAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK01 |  | 40 | 40 | INSTALL SEAL | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.4.2 | A3.4 | SNR-H03MEA30HB300 | SHAFT SLEEVE (หบศ-ฟ.) |  | xx | SHAFT SLEEVE (หบศ-ฟ.) | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA30HB300 |  | 10 | 10 | CLEANING | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA30HB300 |  | 20 | 20 | SHAFT SLEEVE INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.4.3 | A3.4 | SNR-H03MEA30HB100 | SHAFT SLEEVE (หงศ-ฟ.) |  | xx | SHAFT SLEEVE (หงศ-ฟ.) | หงศ-ฟ. | 3 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2S0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEA30HB100 |  | 10 | 10 | PT CHECK ON SHAFT SLEEVE | หงศ-ฟ. | 3 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2S0 | PTW งานในที่อับอากาศ | M
| A3.4.4 | A3.4 | SNR-H03MEA40HA007KK02 | PACKING GLAND |  | xx | PACKING GLAND | หบศ-ฟ. | 3.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK02 |  | 10 | 10 | REMOVE PACKING GLAND | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA40HA007KK02 |  | 20 | 20 | INSPECT PACKING GLAND (REPAIR IF NECESSARY) | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK02 |  | 30 | 30 | INSTALL PACKING GLAND | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.4.5 | A3.4 | SNR-H03MEA40HA007KK03 | LANTERN RING |  | xx | LANTERN RING | หบศ-ฟ. | 3.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK03 |  | 10 | 10 | REMOVE LANTERN RING | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEA40HA007KK03 |  | 20 | 20 | INSPECT LANTERN RING (REPAIR IF NECESSARY) | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEA40HA007KK03 |  | 30 | 30 | INSTALL LANTERN RING | หบศ-ฟ. | 1.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.5 | A3 | SNR-H03MED | TURBINE GUIDE BEARING |  | xx | TURBINE GUIDE BEARING | หบศ-ฟ. | 25.5 | 4/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน 8/8/67 | A3.5.1 | A3.5 | SNR-H03MED20 | TURBINE GUIDE BEARING (หบศ-ฟ.) |  | xx | TURBINE GUIDE BEARING (หบศ-ฟ.) | หบศ-ฟ. | 12 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.1 | A3.5.1 | SNR-H03MED20HD101 |  | 10 | 10 | LIFT UP OIL PAN COVER | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.2 | A3.5.1 | SNR-H03MED20HD102 |  | 20 | 20 | SAMPLING TURBINE GUIDE BEARING 4 EA | หบศ-ฟ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.3 | A3.5.1 | SNR-H03MED20HD103 |  | 30 | 30 | INSTALL TURBINE GUIDE BEARING | หบศ-ฟ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.4 | A3.5.1 | SNR-H03MED20HD104 |  | 40 | 40 | LIFT DOWN OIL PAN COVER | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.5 | A3.5.1 | SNR-H03MED20HD105 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.6 | A3.5.1 | SNR-H03MED20HD106 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.7 | A3.5.1 | SNR-H03MED20HD107 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.8 | A3.5.1 | SNR-H03MED20HD108 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.9 | A3.5.1 | SNR-H03MED20HD109 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.10 | A3.5.1 | SNR-H03MED20HD110 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.11 | A3.5.1 | SNR-H03MED20HD111 | [13 empty] | M
เพิ่มเติมงาน 8/8/67 | A3.5.1.12 | A3.5.1 | SNR-H03MED20HD112 | [13 empty] | M
| A3.5.2 | A3.5 | SNR-H03MED10BB001 | TURBINE OIL PAN |  | xx | TURBINE OIL PAN | หบศ-ฟ. | 14.5 | 4/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MED10BB001 |  | 10 | 10 | OIL DRAIN 100% | หบศ-ฟ. | 4 | 4/9/2024 | 4/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MED10BB001 |  | 20 | 20 | CLEAN TURBINE OIL PAN | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MED10BB001 |  | 30 | 30 | OIL PURIFY | หบศ-ฟ. | 4 | 4/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MED10BB001 |  | 40 | 40 | OIL FILL | หบศ-ฟ. | 4 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MED10BB001 |  | 50 | 50 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.6 | A3 | SNR-H03MEV10 | TURBINE OIL COOLER |  | xx | TURBINE OIL COOLER | หบศ-ฟ. | 11 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.6.1 | A3.6 | SNR-H03MEV10AC001 | TURBINE OIL COOLER NO.1 |  | xx | TURBINE OIL COOLER NO.1 | หบศ-ฟ. | 2.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEV10AC001 |  | 10 | 10 | CLEAN TURBINE OIL COOLER | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEV10AC001 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
| A3.6.2 | A3.6 | SNR-H03MEV10AC002 | TURBINE OIL COOLER NO.2 |  | xx | TURBINE OIL COOLER NO.2 | หบศ-ฟ. | 2.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEV10AC002 |  | 10 | 10 | CLEAN TURBINE OIL COOLER | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEV10AC002 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A3.6.3 | A3.6 | SNR-H03MEV10AP001 | TURBINE OIL PUMP NO.1 |  | xx | TURBINE OIL PUMP NO.1 | หบศ-ฟ. | 3 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP001 |  | 10 | 10 | INSPECTION & CLEAN | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP001 |  | 20 | 20 | CLEAN STRAINER | หบศ-ฟ. | 2 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP001 |  | 30 | 30 | OPERATION TEST | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. | A3.6.4 | A3.6 | SNR-H03MEV10AP002 | TURBINE OIL PUMP NO.2 |  | xx | TURBINE OIL PUMP NO.2 | หบศ-ฟ. | 3 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP002 |  | 10 | 10 | INSPECTION & CLEAN | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP002 |  | 20 | 20 | CLEAN STRAINER | หบศ-ฟ. | 2 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEV10AP002 |  | 30 | 30 | OPERATION TEST | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7 | A3 | SNR-H03MES10 | AUXILIARY (WATER SUPPLY FOR SEALING BOX) |  | xx | AUXILIARY (WATER SUPPLY FOR SEALING BOX) | หบศ-ฟ. | 8.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7.1 | A3.7 | SNR-H03MES10AT001 | SHAFT SEAL STATIONARY WASHING STRAINER NO.1 |  | xx | SHAFT SEAL STATIONARY WASHING STRAINER NO.1 | หบศ-ฟ. | 2.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT001 |  | 10 | 10 | CLEANING STRAINER | หบศ-ฟ. | 2 | 27/8/2024 | 27/8/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT001 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7.2 | A3.7 | SNR-H03MES10AT002 | SHAFT SEAL STATIONARY WASHING STRAINER NO.2 |  | xx | SHAFT SEAL STATIONARY WASHING STRAINER NO.2 | หบศ-ฟ. | 2.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT002 |  | 10 | 10 | CLEANING STRAINER | หบศ-ฟ. | 2 | 27/8/2024 | 27/8/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT002 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7.3 | A3.7 | SNR-H03MES10AT003 | SHAFT SEAL AUTO SAND SEPERATOR NO.1 |  | xx | SHAFT SEAL AUTO SAND SEPERATOR NO.1 | หบศ-ฟ. | 1.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT003 |  | 10 | 10 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 1 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT003 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7.4 | A3.7 | SNR-H03MES10AT004 | SHAFT SEAL AUTO SAND SEPERATOR NO.2 |  | xx | SHAFT SEAL AUTO SAND SEPERATOR NO.2 | หบศ-ฟ. | 1.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT004 |  | 10 | 10 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 1 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10AT004 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.7.5 | A3.7 | SNR-H03MES10BR001 | PIPE LINE |  | xx | PIPE LINE | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MES10BR001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
| A3.8 | A3 | SNR-H03MEW10 | AUXILIARY (WATER SUPPLY FOR RUNNER SEAL) |  | xx | AUXILIARY (WATER SUPPLY FOR RUNNER SEAL) | หบศ-ฟ. | 4.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.8.1 | A3.8 | SNR-H03MEW10AA002 | VALVE 20RM |  | xx | VALVE 20RM | หบศ-ฟ. | 1 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEW10AA002 |  | 10 | 10 | OPERATION TEST | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEW10AA002 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.8.2 | A3.8 | SNR-H03MEW10AT001 | RUNNER SEAL STRAINER |  | xx | RUNNER SEAL STRAINER | หบศ-ฟ. | 3 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEW10AT001 |  | 10 | 10 | INSPECTION & CLEAN | หบศ-ฟ. | 2 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEW10AT001 |  | 20 | 20 | DRAIN VALVE OPERATION TEST | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEW10AT001 |  | 30 | 30 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
| A3.8.3 | A3.8 | SNR-H03MEW10BR001 | PIPE LINE |  | xx | PIPE LINE | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEW10BR001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 27/8/2024 | 27/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
| A3.9 | A3 | SNR-H03MEA | INSTRUMENT (TURBINE PRESSURE TRANSMITTER) |  | xx | INSTRUMENT (TURBINE PRESSURE TRANSMITTER) | หฟศ-ฟ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.9.1 | A3.9 | SNR-H03MEA10CP001 | TURBINE CORE PRESSURE (SPIRALCASE) MEA11CP001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.9.2 | A3.9 | SNR-H03MEA40CP001 | DRAFT TUBE PRESSURE MEA15CP001 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.10 | A3 | SNR-H03MEA | INSTRUMENT (TURBINE PRESSURE GAUGE) |  | xx | INSTRUMENT (TURBINE PRESSURE GAUGE) | หฟศ-ฟ. | 10 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.10.1 | A3.10 | SNR-H03MEA40HA007QP01 | SEALING BOX PRESSURE MES10CP501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.10.2 | A3.10 | SNR-H03MEA30CP001 | RUNNER TOP PRESSURE MEA20CP501 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.10.3 | A3.10 | SNR-H03MEA30CP002 | RUNNER SIDE PRESSURE MEA20CP511 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.10.4 | A3.10 | SNR-H03MEA10CP002 | SPIRAL CASE PRESSURE MEA11CP501 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.10.5 | A3.10 | SNR-H03MEA40CP001 | DRAFT TUBE PRESSURE MEA15CP501 | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.11 | A3 | SNR-H03MEA10CL001 | INSTRUMENT (TURBINE LEVEL SWITCH) |  | xx | INSTRUMENT (TURBINE LEVEL SWITCH) | หฟศ-ฟ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.11.1 | A3.11 | SNR-H03MEA10CL001-S01 | TURBINE PIT FLOODED ALARM 1, 2 MEA11CL301-S01 (Switch) | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.11.2 | A3.11 | SNR-H03MEA10CL001-S02 | TURBINE PIT FLOODED TRIP MEA11CL302-S01 (Switch) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.12 | A3 | SNR-H03MED10CT004 | INSTRUMENT (SUMP OIL TURBINE BEARING DIAL TEMP. MED20CT501) |  | xx | INSTRUMENT (SUMP OIL TURBINE BEARING DIAL TEMP. MED20CT501) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CT004 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MED10CT004 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CT004 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CT004 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CT004 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CT004 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MED10CT004 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.13 | A3 | SNR-H03MED10 | INSTRUMENT (TGB RTD) |  | xx | INSTRUMENT (TGB RTD) | หฟศ-ฟ. | 4.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.13.1 | A3.13 | SNR-H03MED10CT001 | TGB METAL TEMP.1 MED20CT001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.13.2 | A3.13 | SNR-H03MED10CT002 | TGB METAL TEMP.2 MED20CT002 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.14 | A3 | SNR-H03MED10 | INSTRUMENT (TGB LEVEL SWITCH) |  | xx | INSTRUMENT (TGB LEVEL SWITCH) | หฟศ-ฟ. | 10 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.14.1 | A3.14 | SNR-H03MED10CL002-S01 | TGB OIL LEVEL TOO HIGH MED20CL301-S01 (Switch) | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.14.2 | A3.14 | SNR-H03MED10CL002-S02 | TGB OIL LEVEL HIGH MED20CL302-S01 (Switch) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.14.3 | A3.14 | SNR-H03MED10CL002-S03 | TGB OIL LEVEL LOW MED20CL303-S01 (Switch) | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.14.4 | A3.14 | SNR-H03MED10CL002-S04 | TGB OIL LEVEL TOO LOW MED20CL304-S01 (Switch) | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 50 | 50 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.15 | A3 | SNR-H03MED10CM001 | INSTRUMENT (TGB WATER DETECTOR TGB LUB OIL MED20CL311) |  | xx | INSTRUMENT (TGB WATER DETECTOR TGB LUB OIL MED20CL311) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CM001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MED10CM001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CM001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CM001 |  | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CM001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MED10CM001 |  | 60 | 60 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MED10CM001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.16 | A3 | SNR-H03MES10 | INSTRUMENT (SHAFT SEALING BOX PRESSURE SWITCH) |  | xx | INSTRUMENT (TUR. SHAFT SEALING BOX PRESSURE SWITCH) | หฟศ-ฟ. | 7.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.16.1 | A3.16 | SNR-H03MES10CP002 | SHAFT SEAL WATER PRESSURE MES10CP301-S01 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.16.2 | A3.16 | SNR-H03MES10CP004 | SS.WATER CENTRIFUGAL SEPERATOR1 CLOGGED MES12AT001-S01 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.16.3 | A3.16 | SNR-H03MES10CP005 | SS.WATER CENTRIFUGAL SEPERATOR2 CLOGGED MES11AT001-S01 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.17 | A3 | SNR-H03MES10CP003 | INSTRUMENT (SHAFT SEAL CW. PRESSURE MES10CP502) |  | xx | INSTRUMENT (SHAFT SEAL CW. PRESSURE MES10CP502) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP003 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MES10CP003 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP003 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP003 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP003 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP003 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MES10CP003 |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MES10CP003 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.18 | A3 | SNR-H03MES10CP001 | INSTRUMENT (SHAFT SEAL WATER FLOW MES10CF311) |  | xx | INSTRUMENT (SHAFT SEAL WATER FLOW MES10CF311) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MES10CP001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP001 |  | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MES10CP001 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MES10CP001 |  | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MES10CP001 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.19 | A3 | SNR-H03MEV10CP001 | INSTRUMENT (TGB OIL FLOW TRANSMITTER MED20CF001) |  | xx | INSTRUMENT (TGB OIL FLOW TRANSMITTER MED20CF001) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEV10CP001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEV10CP001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEV10CP001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEV10CP001 |  | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEV10CP001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MEV10CP001 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEV10CP001 |  | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MEV10CP001 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.20 | A3 | SNR-H03MEW10 | FLOW TRANSMITTER & FLOW SWITCH |  | xx | FLOW TRANSMITTER & FLOW SWITCH | หฟศ-ฟ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.20.1 | A3.20 | SNR-H03MEW10CF001 | UPPER RUNNER SEAL FLOW MEA20CF301 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.20.2 | A3.20 | SNR-H03MEW10CF002 | LOWER RUNNER SEAL FLOW MEA20CF311 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.21 | A3 | SNR-H03MEW20CL001 | INSTRUMENT (DRAFT TUBE LEVEL SWITCH) |  | xx | INSTRUMENT (DRAFT TUBE LEVEL SWITCH) | หฟศ-ฟ. | 12.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.21.1 | A3.21 | SNR-H03MEW20CL001QP05 | DRAFT TUBE LEVEL LOW2 MEA15CL301-S01 (Switch) | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A3.21.2 | A3.21 | SNR-H03MEW20CL001QP04 | DRAFT TUBE LEVEL LOW1 MEA15CL302-S01 (Switch) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.21.3 | A3.21 | SNR-H03MEW20CL001QP03 | DRAFT TUBE LEVEL HIGH1 MEA15CL303-S01 (Switch) | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.21.4 | A3.21 | SNR-H03MEW20CL001QP02 | DRAFT TUBE LEVEL HIGH2 MEA15CL304-S01 (Switch) | 40 | 40 | TESTING FOR ASFOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.21.5 | A3.21 | SNR-H03MEW20CL001QP01 | DRAFT TUBE LEVEL TOO HIGH MEA15CL305-S01 (Switch) | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A3.22 | A3 | SNR-H03MEW10CP001 | INSTRUMENT (TUR. RUNNER SEAL CW. PRESSURE MEA20CP521) |  | xx | INSTRUMENT (TUR. RUNNER SEAL CW. PRESSURE MEA20CP521) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEW10CP001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEW10CP001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEW10CP001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEW10CP001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEW10CP001 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEW10CP001 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MEW10CP001 |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MEW10CP001 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4 | A | SNR-H03MEX | GOVERNOR SYSTEM |  | xx | GOVERNOR SYSTEM | หบศ-ฟ. | 138.75 | 28/8/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.1 | A4 | SNR-H03MEX11 | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES |  | xx | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES | หบศ-ฟ. | 18 | 4/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.1.1 | A4.1 | SNR-H03MEX11 | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หบศ-ฟ.) |  | xx | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หบศ-ฟ.) | หบศ-ฟ. | 16.5 | 4/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX11 |  | 20 | 20 | DRAIN PRESSURE TANK | หบศ-ฟ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 30 | 30 | INTERNAL CLEANING & INSPECTION | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEX11 |  | 40 | 40 | PAINTING INSPECT & REPAIR (IF NECESSARY) | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 50 | 50 | FILL OIL | หบศ-ฟ. | 3 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 60 | 60 | MAKE UP PRESSURE TANK | หบศ-ฟ. | 4 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 70 | 70 | INSTRUMENTATION DEVICE INSPECTION | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX11 |  | 80 | 80 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไข Final 6/8/67 | A4.1.2 | A4.1 | SNR-H03MEX11 | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หวผอ-ธ.) |  | xx | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หวผอ-ธ.) | หวผอ-ธ. | 0.5 | 3/9/2024 | 5/9/2024 |  |  |  | MWD0-SM10 |  | M
แก้ไข Final 6/8/67 |  |  | SNR-H03MEX11 |  | 10 | 10 | THICKNESS MEASUREMENT ON TANK | หวผอ-ธ. | 0.5 | 3/9/2024 | 5/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
เพิ่มเติม Worklist 11/6/67 | A4.1.3 | A4.1 | SNR-H03MEX11 | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หขศ-ฟ.) |  | xx | GOVERNOR OIL PRESSURE TANK AND ACCESSORIES (หขศ-ฟ.) | หขศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-3D0 |  | M
|  |  | SNR-H03MEX11 |  | 10 | 10 | INSTALL SCAFFOLD | หขศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 4 | SNR0-3D0 |  | M
|  |  | SNR-H03MEX11 |  | 20 | 20 | REMOVE SCAFFOLD | หขศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-3D0 |  | M
| A4.2 | A4 | SNR-H03MEX10BB001 | GOV. OIL SUMP TANK |  | xx | GOV. OIL SUMP TANK | หบศ-ฟ. | 21 | 28/8/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BB001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX10BB001 |  | 20 | 20 | DRAIN OIL | หบศ-ฟ. | 4 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BB001 |  | 30 | 30 | INTERNAL CLEANING & INSPECTION | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEX10BB001 |  | 40 | 40 | PAINTING INSPECT & REPAIR (IF NECESSARY) | หบศ-ฟ. | 2 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10BB001 |  | 50 | 50 | CLEAN/REPLACE STRAINER | หบศ-ฟ. | 2 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10BB001 |  | 60 | 60 | CLEAN HEAT EXCHANGER | หบศ-ฟ. | 2 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BB001 |  | 70 | 70 | OIL PURIFY | หบศ-ฟ. | 4 | 6/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10BB001 |  | 80 | 80 | FILL OIL AND LEAKAGE CHECK | หบศ-ฟ. | 4 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BB001 |  | 90 | 90 | INSTRUMENTATION DEVICE INSPECTION | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.3 | A4 | SNR-H03MEX10 | GOV. OIL PUMP |  | xx | GOV. OIL PUMP | หบศ-ฟ. | 13.5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.3.1 | A4.3 | SNR-H03MEX10AP002 | GOVERNOR OIL PUMP NO.A |  | xx | GOVERNOR OIL PUMP NO.A | หบศ-ฟ. | 3.5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP002 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10AP002 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP002 |  | 30 | 30 | NOISE INSPECT | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP002 |  | 40 | 40 | UNLOAD/ONLOAD CLEAN & CHECK VALVE INSPECT. | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP002 |  | 50 | 50 | OPERATION & PERFORMANCE TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP002 |  | 60 | 60 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.3.2 | A4.3 | SNR-H03MEX10AP003 | GOVERNOR OIL PUMP NO.B |  | xx | GOVERNOR OIL PUMP NO.B | หบศ-ฟ. | 3.5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP003 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10AP003 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP003 |  | 30 | 30 | NOISE INSPECT | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP003 |  | 40 | 40 | UNLOAD/ONLOAD CLEAN & CHECK VALVE INSPECT. | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP003 |  | 50 | 50 | OPERATION & PERFORMANCE TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP003 |  | 60 | 60 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.3.3 | A4.3 | SNR-H03MEX10BN001 | JOCKEY OIL PUMP |  | xx | JOCKEY OIL PUMP | หบศ-ฟ. | 3.5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BN001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10BN001 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BN001 |  | 30 | 30 | NOISE INSPECT | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BN001 |  | 40 | 40 | UNLOAD/ONLOAD CLEAN & CHECK VALVE INSPECT. | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BN001 |  | 50 | 50 | OPERATION & PERFORMANCE TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10BN001 |  | 60 | 60 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.3.4 | A4.3 | SNR-H03MEX10AP001 | GOV. OIL CIRCULATING PUMP |  | xx | GOV. OIL CIRCULATING PUMP | หบศ-ฟ. | 3 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX10AP001 |  | 20 | 20 | CLEAN FILTER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP001 |  | 30 | 30 | NOISE INSPECT | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP001 |  | 40 | 40 | UNLOAD/ONLOAD CLEAN & CHECK VALVE INSPECT. | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX10AP001 |  | 50 | 50 | OPERATION & PERFORMANCE TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.4 | A4 | SNR-H03MEX51 | GOV. ACTUATOR |  | xx | GOV. ACTUATOR | หบศ-ฟ. | 5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX51 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX51 |  | 20 | 20 | DISASSEMBLY INSPECTION | หบศ-ฟ. | 2 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX51 |  | 30 | 30 | CLEANING | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX51 |  | 40 | 40 | CLEAN/REPLACE STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX51 |  | 50 | 50 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.5 | A4 | SNR-H03MEX52 | DISTRIBUTING VALVE |  | xx | DISTRIBUTING VALVE | หบศ-ฟ. | 2.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX52 |  | 10 | 10 | FLUSHING OPERATION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX52 |  | 20 | 20 | DIMENSION CHECK ORIFICE (IF REQUIRED) | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX52 |  | 30 | 30 | CLEANING | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX52 |  | 40 | 40 | ASSEMBLY | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.6 | A4 | SNR-H03MEX53 | GUIDE VANE SERVOMOTOR |  | xx | GUIDE VANE SERVOMOTOR | หบศ-ฟ. | 8.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX53 |  | 10 | 10 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEX53 |  | 20 | 20 | CHECK STROKE GV SERVOMOTOR | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEX53 |  | 30 | 30 | GV SERVOMOTOR SQUEEZE UN-SQUEEZE CHECK | หบศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX53 |  | 40 | 40 | PACKING SEAL OF GUIDE VANE STEM INSPECTION AND REPLACE (IF NECESSARY) | หบศ-ฟ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A4.7 | A4 | SNR-H03MEX10 | INSTRUMENT (GOV. DIAL TEMP.) |  | xx | INSTRUMENT (GOV. DIAL TEMP.) | หฟศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.7.1 | A4.7 | SNR-H03MEX10CT001 | TEMP. GAUGE COOLER of TURBINE SUMP TANK MEX30CT501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A4.7.2 | A4.7 | SNR-H03MEX10CT002 | TEMP. GAUGE of TURBINE SUMP TANK MEX10CT501 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.8 | A4 | SNR-H03MEX10CT003 | INSTRUMENT (TURBINE OPU OIL TANK TEMPERATURE RTD MEX10CT001) |  | xx | INSTRUMENT (TURBINE OPU OIL TANK TEMPERATURE RTD MEX10CT001) | หฟศ-ฟ. | 2.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT003 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX10CT003 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT003 |  | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT003 |  | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT003 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MEX10CT003 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MEX10CT003 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9 | A4 | SNR-H03MEX | INSTRUMENT (GOV. PRESSURE SWITCH & DIFF PRESSURE SWITCH) |  | xx | INSTRUMENT (GOV. PRESSURE SWITCH & DIFF PRESSURE SWITCH) | หฟศ-ฟ. | 30 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.1 | A4.9 | SNR-H03MEX11CP007-S02 | TURBINE AIR OIL TANK PRESSURE TOO LOW MEX40CP107-S01 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A4.9.2 | A4.9 | SNR-H03MEX10CP004-S01 | SERVO VALVE OIL PRESSURE TO LOW MEX13CP101-S01 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.3 | A4.9 | SNR-H03MEX11CP002 | TURBINE START CONDITION MEX40CP101-S01 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.4 | A4.9 | SNR-H03MEX11CP003 | OIL PRESSURE LOW MEX40CP102-S01 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.5 | A4.9 | SNR-H03MEX11CP004 | OIL PRESSURE HIGH / AIR SUPPLY OFF MEX40CP103-S01 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 | A4.9.6 | A4.9 | SNR-H03MEX11CP005 | MAIN PUMP CONTROL MEX40CP104-S01 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.7 | A4.9 | SNR-H03MEX11CP006 | STANDBY PUMP CONTROL MEX40CP105-S01 | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. | A4.9.8 | A4.9 | SNR-H03MEX11CP007-S01 | JOCKEY PUMP CONTROL MEX40CP106-S01 | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.9.9 | A4.9 | SNR-H03MEX10CP003-S01 | DIFF PRESSURE SWITCH of PRESSURE FILTER MEX13CP201-S01 | [12 empty] | M
| A4.9.10 | A4.9 | SNR-H03MEX10CP003-S02 | DIFF PRESSURE SWITCH of PRESSURE FILTER MEX13CP202-S01 | [12 empty] | M
| A4.9.11 | A4.9 | SNR-H03MEX10CP002-S01 | DIFF PRESSURE SWITCH of OFFLINE UNIT FILTER MEX30CP201-S01 | [12 empty] | M
| A4.9.12 | A4.9 | SNR-H03MEX10CP002-S02 | DIFF PRESSURE SWITCH of OFFLINE UNIT FILTER MEX30CP202-S01 | [12 empty] | M
| A4.10 | A4 | SNR-H03MEX10 | INSTRUMENT (GOV. PRESSURE GAUGE) |  | xx | INSTRUMENT (GOV. PRESSURE GAUGE) | หฟศ-ฟ. | 12 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.10.1 | A4.10 | SNR-H03MEX10CP005 | TURBINE AIR OIL TANK PRESSURE GAUGE MEX13CP501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A4.10.2 | A4.10 | SNR-H03MEX11CP001 | TURBINE AIR OIL TANK PRESSURE GAUGE MEX40CP501 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.10.3 | A4.10 | SNR-H03MEX10AP002QP01 | PRESSURE of MAIN PUMP1 MEX11CP501 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.10.4 | A4.10 | SNR-H03MEX10AP003QP01 | PRESSURE of MAIN PUMP2 MEX11CP502 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.10.5 | A4.10 | SNR-H03MEX10BN001QP01 | PRESSURE of JOCKEY PUMP MEX11CP503 | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.10.6 | A4.10 | SNR-H03MEX10CP001 | PRESSURE of CIRCULATING PUMP MEX30CP501 | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11 | A4 | SNR-H03MEX | INSTRUMENT (GOV. LEVEL TRANSMITTER & LEVEL SWITCH) |  | xx | INSTRUMENT (GOV. LEVEL TRANSMITTER & LEVEL SWITCH) | หฟศ-ฟ. | 17.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11.1 | A4.11 | SNR-H03MEX11CL003-B01 | TURBINE AIR+OIL TANK LEVEL MEX40CL001 (Transmitter) | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A4.11.2 | A4.11 | SNR-H03MEX11CL002-S01 | TURBINE AIR+OIL TANK LEVEL HIGH ALARM MEX40CL101-S01 (Switch) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11.3 | A4.11 | SNR-H03MEX11CL002-S02 | TURBINE AIR+OIL TANK LEVEL for AIR SUPPLY ON MEX40CL102-S01 (Switch) | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11.4 | A4.11 | SNR-H03MEX11CL002-S03 | TURBINE AIR+OIL TANK LEVEL for AIR SUPPLY OFF MEX40CL103-S01 (Switch) | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11.5 | A4.11 | SNR-H03MEX11CL002-S04 | TURBINE AIR+OIL TANK LEVEL LOW ALARM MEX40CL104-S01 (Switch) | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 | A4.11.6 | A4.11 | SNR-H03MEX11CL002-S05 | TURBINE AIR+OIL TANK LEVEL TOO LOW (ESD) MEX40CL105-S01 (Switch) | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.11.7 | A4.11 | SNR-H03MEX10CL002 | TURBINE OPU OIL TANK LEVEL MEX10CL101-S01 (Transmitter) | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. | A4.11.8 | A4.11 | SNR-H03MEX30CL001 | LEAKAGE OIL TANK LEVEL MEX80CL101-S01 (Switch) | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.12 | A4 | SNR-H03MEX10CL001 | INSTRUMENT (TURBINE OPU WATER in OIL DETECTOR MEX10CL151-S01) |  | xx | INSTRUMENT (TURBINE OPU WATER in OIL DETECTOR MEX10CL151-S01) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CL001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX10CL001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CL001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CL001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CL001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CL001 |  | 60 | 60 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MEX10CL001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A4.13 | A4 | SNR-H03MEX10CT004 | INSTRUMENT (TURBINE SUMP TANK TEMPERATURE TRANSMITTER MEX10CT001-B01) |  | xx | INSTRUMENT (TURBINE SUMP TANK TEMPERATURE TRANSMITTER MEX10CT001-B01) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT004 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX10CT004 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT004 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT004 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT004 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MEX10CT004 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX10CT004 |  | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03MEX10CT004 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5 | A | SNR-H03MEB | INLET VALVE |  | xx | INLET VALVE | หบศ-ฟ. | 125.25 | 2024-08-28 | 2024-09-10 |  |  |  | SNR0-2M0 |  | M
| A5.1 | A5 | SNR-H03MEB10AA001 | INLET VALVE BODY & INLET VALVE DISC |  | xx | INLET VALVE BODY & INLET VALVE DISC | หบศ-ฟ. | 19.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.1.1 | A5.1 | SNR-H03MEB10AA001 | INLET VALVE BODY & INLET VALVE DISC (หบศ-ฟ.) |  | xx | INLET VALVE BODY & INLET VALVE DISC (หบศ-ฟ.) | หบศ-ฟ. | 15.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 10 | 10 | CLEANING INLET VALVE DISC | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEB10AA001 |  | 20 | 20 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 30 | 30 | CHECK GAP BETWEEN I/V DISC AND CASING (BEFORE) | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 40 | 40 | RUBBER SEAL INSPECTION | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEB10AA001 |  | 50 | 50 | BODY AND PACKING GLAND REPAIR | หบศ-ฟ. | 4 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 60 | 60 | REPLACE RUBBER SEAL (IF REQUIRED) | หบศ-ฟ. | 4 | 5/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 70 | 70 | INLET VALVE DISC PAINTING REPAIR (IF REQUIRED) | หบศ-ฟ. | 2 | 6/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 80 | 80 | CHECK GAP BETWEEN I/V DISC AND CASING (AFTER CHANGE NEW SEAL) | หบศ-ฟ. | 1 | 7/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 90 | 90 | OPERATION TEST | หบศ-ฟ. | 0.5 | 7/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 100 | 100 | LEAKAGE CHECKING | หบศ-ฟ. | 0.5 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.1.2 | A5.1 | SNR-H03MEB10AA001 | INLET VALVE BODY & INLET VALVE DISC (หขศ-ฟ.) |  | xx | INLET VALVE BODY & INLET VALVE DISC (หขศ-ฟ.) | หขศ-ฟ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2S0 |  | M
|  |  | SNR-H03MEB10AA001 |  | 10 | 10 | INSTALL SCAFFOLDING | หขศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  | 1 | 7 | SNR0-2S0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | M
|  |  | SNR-H03MEB10AA001 |  | 20 | 20 | REMOVE SCAFFOLDING | หขศ-ฟ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2S0 |  | M
| A5.2 | A5 | SNR-H03MEB20AA002MU01 | INLET VALVE SERVOMOTOR & HYDRAULIC EQUIPMENT |  | xx | INLET VALVE SERVOMOTOR & HYDRAULIC EQUIPMENT | หบศ-ฟ. | 2.5 | 4/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002MU01 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEB20AA002MU01 |  | 20 | 20 | LEAKAGE CHECKING | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002MU01 |  | 30 | 30 | THROTTLE VALVE CHECK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002MU01 |  | 40 | 40 | OPERATION TEST | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002MU01 |  | 50 | 50 | TRAVELLING TIME | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.3 | A5 | SNR-H03MEB20AA002KA01 | BY PASS VALVE |  | xx | BY PASS VALVE | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002KA01 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEB20AA002KA01 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002KA01 |  | 30 | 30 | CLEANING | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEB20AA002KA01 |  | 40 | 40 | TRAVELLING TIME | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.4 | A5 | SNR-H03MEX30BB001 | INLET VALVE SUMP TANK AND AUX. EQUIPMENT |  | xx | INLET VALVE SUMP TANK AND AUX. EQUIPMENT | หบศ-ฟ. | 10 | 5/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30BB001 |  | 10 | 10 | DRAIN OIL AND OPEN MANHOLE | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX30BB001 |  | 20 | 20 | INSPECTION AND CLEAN INSIDE | หบศ-ฟ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEX30BB001 |  | 30 | 30 | CLEANING / REPLACE FILTER | หบศ-ฟ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30BB001 |  | 40 | 40 | CLEAN MIV HEAT EXCHANGER | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30BB001 |  | 50 | 50 | INSPECT PLATE HEAT EXCHANGER | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30BB001 |  | 60 | 60 | CLOSE MANHOLE AND FILL OIL | หบศ-ฟ. | 2.5 | 6/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEX30BB001 |  | 70 | 70 | LEAK CHECK | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30BB001 |  | 80 | 80 | OPERATION TEST | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.5 | A5 | SNR-H03MEX30AP001 | LEAKAGE OIL PUMP |  | xx | LEAKAGE OIL PUMP | หบศ-ฟ. | 2.5 | 28/8/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30AP001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ./แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX30AP001 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30AP001 |  | 30 | 30 | PRESSURE RELIEF VALVE OPERATION CHECK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX30AP001 |  | 40 | 40 | OPERATION TEST | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.6 | A5 | SNR-H03MEX21 | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT |  | xx | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT | หบศ-ฟ. | 13 | 3/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.6.1 | A5.6 | SNR-H03MEX21 | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หบศ-ฟ.) |  | xx | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หบศ-ฟ.) | หบศ-ฟ. | 11.5 | 4/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX21 |  | 10 | 10 | DRAIN OIL AND OPEN MANHOLE | หบศ-ฟ. | 3 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX21 |  | 20 | 20 | INSPECTION AND CLEAN | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 | PTW งานในที่อับอากาศ | M
|  |  | SNR-H03MEX21 |  | 30 | 30 | CLOSE MANHOLE AND FILL OIL | หบศ-ฟ. | 3 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX21 |  | 40 | 40 | MAKEUP PRESSURE | หบศ-ฟ. | 4 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หบศ-ฟ. |  |  | SNR-H03MEX21 |  | 50 | 50 | LEAK CHECK | หบศ-ฟ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไข Final 6/8/67 | A5.6.2 | A5.6 | SNR-H03MEX21 | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หวผอ-ธ.) |  | xx | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หวผอ-ธ.) | หวผอ-ธ. | 0.5 | 3/9/2024 | 5/9/2024 |  |  |  | MWD0-SM10 |  | M
แก้ไข Final 6/8/67 |  |  | SNR-H03MEX21 |  | 10 | 10 | THICKNESS MEASUREMENT ON TANK | หวผอ-ธ. | 0.5 | 3/9/2024 | 5/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
เพิ่มเติม Worklist 11/6/67 | A5.6.3 | A5.6 | SNR-H03MEX21 | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หขศ-ฟ.) |  | xx | INLET VALVE PRESSURE TANK AND AUX. EQUIPMENT (หขศ-ฟ.) | หขศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-3D0 |  | M
|  |  | SNR-H03MEX21 |  | 10 | 10 | INSTALL SCAFFOLDING | หขศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 4 | SNR0-3D0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | M
|  |  | SNR-H03MEX21 |  | 20 | 20 | REMOVE SCAFFOLDING | หขศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-3D0 |  | M
| A5.7 | A5 | SNR-H03MEX20AP001 | INLET VALVE MAIN PUMP |  | xx | INLET VALVE MAIN PUMP | หบศ-ฟ. | 2 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ./แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX20AP001 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP001 |  | 30 | 30 | UNLOADING VALVE OPERATION CHECK | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP001 |  | 40 | 40 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP001 |  | 50 | 50 | PUMP CAPACITY TEST (AFTER MAKEUP PRESSURE TANK) | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A5.8 | A5 | SNR-H03MEX20AP002 | CIRCULATION PUMP |  | xx | CIRCULATION PUMP | หบศ-ฟ. | 2.5 | 28/8/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP002 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
เพิ่มเติมโดย หบศ-ฟ./แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03MEX20AP002 |  | 20 | 20 | CLEAN SUCTION STRAINER | หบศ-ฟ. | 1 | 28/8/2024 | 28/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP002 |  | 30 | 30 | UNLOADING VALVE OPERATION CHECK | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03MEX20AP002 |  | 40 | 40 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.9 | A5 | SNR-H03MEX20 | INSTRUMENT (MIV. DIAL TEMP.) |  | xx | INSTRUMENT (MIV. DIAL TEMP.) | หฟศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.9.1 | A5.9 | SNR-H03MEX20CT001 | TEMP. GAUGE COOLER OF MIV SUMP MEX35CT501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A5.9.2 | A5.9 | SNR-H03MEX20CT002 | TEMP. GAUGE OF MIV SUMP TANK MEX50CT501 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.10 | A5 | SNR-H03MEX20CT003 | INSTRUMENT (MIV OPU OIL TANK TEMPERATURE RTD MEX50CT001) |  | xx | INSTRUMENT (MIV OPU OIL TANK TEMPERATURE RTD MEX50CT001) | หฟศ-ฟ. | 2.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX20CT003 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT003 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.11 | A5 | SNR-H03MEX | INSTRUMENT (MIV. PRESSURE SWITCH & DIFF PRESSURE SWITCH) |  | xx | INSTRUMENT (MIV. PRESSURE SWITCH & DIFF PRESSURE SWITCH) | หฟศ-ฟ. | 35 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.1 | A5.11 | SNR-H03MEX21CP006-S02 | OIL PRESSURE TOO LOW EMERGENCY SHUTDOWN (ESD) MEX53CP101-S01 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A5.11.2 | A5.11 | SNR-H03MEX21CP006-S01 | OIL PRESSURE TOO LOW EMERGENCY SHUTDOWN (ESD) MEX60CP105-S01 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.3 | A5.11 | SNR-H03MEX21CP002 | INV. OIL PRESSURE TANK OK MEX60CP101-S01 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.4 | A5.11 | SNR-H03MEX21CP003 | INV. OIL PRESSURE LOW ALARM MEX60CP102-S01 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.5 | A5.11 | SNR-H03MEX21CP004 | OIL. PRESSURE HIGH/AIR SUPPLY OFF MEX60CP103-S01 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.6 | A5.11 | SNR-H03MEX21CP005 | OIL PUMP CONTROL MEX60CP104-S01 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.7 | A5.11 | SNR-H03MEX20CP003-S01 | DIFF. PRESSURE SWITCH OF PRESSURE FILTER MEX53CP201-S01 | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.8 | A5.11 | SNR-H03MEX20CP003-S02 | DIFF. PRESSURE SWITCH OF PRESSURE FILTER MEX53CP202-S01 | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.11.9 | A5.11 | SNR-H03MEX30CP002-S01 | DIFF. PRESSURE SWITCH OF LEAKAGE UNIT FILTER MEX80CP201-S01 | [12 empty] | M
| A5.11.10 | A5.11 | SNR-H03MEX30CP002-S02 | DIFF. PRESSURE SWITCH OF LEAKAGE UNIT FILTER MEX80CP202-S01 | [12 empty] | M
| A5.11.11 | A5.11 | SNR-H03MEX20CP002-S01 | DIFF. PRESSURE SWITCH OF OFFLINE UNIT FILTER MEX35CP201-S01 | [12 empty] | M
| A5.11.12 | A5.11 | SNR-H03MEX20CP002-S02 | DIFF. PRESSURE SWITCH OF OFFLINE UNIT FILTER MEX35CP202-S01 | [12 empty] | M
| A5.11.13 | A5.11 | SNR-H03MEX20CP004-S01 | INLET VALVE DIFF. PRESSURE BALANCE | [12 empty] | M
| A5.11.14 | A5.11 | SNR-H03MEX21CP007 | MIV AIR-OIL TANK PRESSURE MEX60CP001-B01 | [12 empty] | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.12 | A5 | SNR-H03MEX | INSTRUMENT (MIV. PRESSURE GAUGE) |  | xx | INSTRUMENT (MIV. PRESSURE GAUGE) | หฟศ-ฟ. | 8 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.12.1 | A5.12 | SNR-H03MEX21CP008 | MIV AIR-OIL TANK PRESSURE GAUGE MEX53CP501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A5.12.2 | A5.12 | SNR-H03MEX21CP001 | MIV AIR-OIL TANK PRESSURE GAUGE MEX60CP501 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.12.3 | A5.12 | SNR-H03MEX20AP001QP01 | PRESSURE OF MAIN PUMP MEX51CP501 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.12.4 | A5.12 | SNR-H03MEX20CP001 | PRESSURE OF CIRCULATING PUMP MEX35CP501 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.13 | A5 | SNR-H03MEX | INSTRUMENT (MIV. LEVEL TRANSMITTER & LEVEL SWITCH) |  | xx | INSTRUMENT (MIV. LEVEL TRANSMITTER & LEVEL SWITCH) | หฟศ-ฟ. | 17.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.1 | A5.13 | SNR-H03MEX21CL003-B01 | MIV AIR+OIL TANK LEVEL MEX60CL001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A5.13.2 | A5.13 | SNR-H03MEX21CL002-S01 | MIV AIR+OIL TANK LEVEL HIGH ALARM MEX60CL101-S01 (Switch) | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.3 | A5.13 | SNR-H03MEX21CL002-S02 | MIV AIR+OIL TANK LEVEL FOR AIR SUPPLY ON MEX60CL102-S01 (Switch) | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.4 | A5.13 | SNR-H03MEX21CL002-S03 | MIV AIR+OIL TANK LEVEL FOR AIR SUPPLY OFF MEX60CL103-S01 (Switch) | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.5 | A5.13 | SNR-H03MEX21CL002-S04 | MIV AIR+OIL TANK LEVEL LOW ALARM MEX60CL104-S01 (Switch) | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.6 | A5.13 | SNR-H03MEX21CL002-S05 | MIV AIR+OIL TANK LEVEL TOO LOW (ESD) MEX60CL105-S01 (Switch) | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A5.13.7 | A5.13 | SNR-H03MEX20CL002 | MIV OPU OIL TANK LEVEL MEX50CL101-S01 (Transmitter) | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.14 | A5 | SNR-H03MEX20CL001 | INSTRUMENT (MIV OPU WATER in OIL DETECTOR MEX50CL151-S01) |  | xx | INSTRUMENT (MIV OPU WATER in OIL DETECTOR MEX50CL151-S01) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX20CL001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 60 | 60 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CL001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หฟศ-ฟ. 15/7/67 | A5.15 | A5 | SNR-H03MEX20CT004 | INSTRUMENT (MIV SUMP TANK TEMPERATURE TRANSMITTER MEX50CT001-B01) |  | xx | INSTRUMENT (MIV SUMP TANK TEMPERATURE TRANSMITTER MEX50CT001-B01) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03MEX20CT004 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 70 | 70 | ADJUSTMENT | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03MEX20CT004 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6 | A | SNR-H03PAG | AUXILIARY (COOLING WATER SYSTEM) |  | xx | AUXILIARY (COOLING WATER SYSTEM) | หบศ-ฟ. | 88 | 2024-08-29 | 2024-09-10 |  |  |  | SNR0-2M0 |  | M
| A6.1 | A6 | SNR-H03PAG11 | MAIN COOLING FROM DRAFT TUBE |  | xx | MAIN COOLING FROM DRAFT TUBE | หบศ-ฟ. | 4.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.1.1 | A6.1 | SNR-H03PAG11AP001 | WATER PUMP |  | xx | WATER PUMP | หบศ-ฟ. | 2.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG11AP001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG11AP001 |  | 20 | 20 | CLEANING | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG11AP001 |  | 30 | 30 | FILL GREASE (IF REQUIRED) | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG11AP001 |  | 40 | 40 | OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.1.2 | A6.1 | SNR-H03PAG11AT001 | AUTO WASHING STRAINER NO.1 |  | xx | AUTO WASHING STRAINER NO.1 | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG11AT001 |  | 10 | 10 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG11AT001 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.1.3 | A6.1 | SNR-H03PAG11AT002 | AUTO WASHING STRAINER NO.2 |  | xx | AUTO WASHING STRAINER NO.2 | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG11AT002 |  | 10 | 10 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG11AT002 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2 | A6 | SNR-H03PAG10 | MAIN COOLING WATER SUPPLY |  | xx | MAIN COOLING WATER SUPPLY | หบศ-ฟ. | 10.5 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.1 | A6.2 | SNR-H03PAG10AA002 | MAIN AUTO. CONTROL VALVE (20PM) |  | xx | MAIN AUTO. CONTROL VALVE (20PM) | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA002 |  | 10 | 10 | OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG10AA002 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.2 | A6.2 | SNR-H03PAG10AT001 | AUTO WASHING STRAINER NO.1 |  | xx | AUTO WASHING STRAINER NO.1 | หบศ-ฟ. | 2 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG10AT001 |  | 10 | 10 | CLEAN STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG10AT001 |  | 20 | 20 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AT001 |  | 30 | 30 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.3 | A6.2 | SNR-H03PAG10AT002 | AUTO WASHING STRAINER NO.2 |  | xx | AUTO WASHING STRAINER NO.2 | หบศ-ฟ. | 2 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG10AT002 |  | 10 | 10 | CLEAN STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG10AT002 |  | 20 | 20 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AT002 |  | 30 | 30 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.4 | A6.2 | SNR-H03PAG10AA013 | REDUCING VALVE |  | xx | REDUCING VALVE | หบศ-ฟ. | 3.5 | 29/8/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA013 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG10AA013 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG10AA013 |  | 30 | 30 | CLEANING DUPLEX STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA013 |  | 40 | 40 | ADJUSTMENT FOR REDUCING VALVE (IF REQUIRED) | หบศ-ฟ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA013 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 10/9/2024 | 10/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.5 | A6.2 | SNR-H03PAG10AA015 | PRESSURE RELIEF VALVE |  | xx | PRESSURE RELIEF VALVE | หบศ-ฟ. | 1.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA015 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG10AA015 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10AA015 |  | 30 | 30 | OPERATION TEST | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.2.6 | A6.2 | SNR-H03PAG10BR001 | PIPE LINE |  | xx | PIPE LINE | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG10BR001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
| A6.3 | A6 | SNR-H03PAG20 | AUX. COOLING WATER SYSTEM |  | xx | AUX. COOLING WATER SYSTEM | หบศ-ฟ. | 10.5 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.3.1 | A6.3 | SNR-H03PAG20AA001 | MAIN VALVE FOR WATER SUPPLY |  | xx | MAIN VALVE FOR WATER SUPPLY | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA001 |  | 10 | 10 | OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG20AA001 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.3.2 | A6.3 | SNR-H03PAG20AA003 | AUX. REDUCING VALVE |  | xx | AUX. REDUCING VALVE | หบศ-ฟ. | 3.5 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA003 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG20AA003 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG20AA003 |  | 30 | 30 | CLEANING DUPLEX STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA003 |  | 40 | 40 | ADJUSTMENT FOR REDUCING VALVE (IF REQUIRED) | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA003 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.3.3 | A6.3 | SNR-H03PAG20AA005 | AUX. RELIEF VALVE |  | xx | AUX. RELIEF VALVE | หบศ-ฟ. | 3.5 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA005 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG20AA005 |  | 20 | 20 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG20AA005 |  | 30 | 30 | CLEANING DUPLEX STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA005 |  | 40 | 40 | ADJUSTMENT FOR RELIEF VALVE (IF REQUIRED) | หบศ-ฟ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AA005 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.3.4 | A6.3 | SNR-H03PAG20AT001 | AUX. AUTO WASHING STRAINER |  | xx | AUX. AUTO WASHING STRAINER | หบศ-ฟ. | 2 | 29/8/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขโดย หบศ-ฟ. |  |  | SNR-H03PAG20AT001 |  | 10 | 10 | CLEAN STRAINER | หบศ-ฟ. | 1 | 29/8/2024 | 29/8/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03PAG20AT001 |  | 20 | 20 | FLUSHING MOTOR OPERATION TEST | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03PAG20AT001 |  | 30 | 30 | LEAKAGE CHECK | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
| A6.3.5 | A6.3 | SNR-H03PAG20BR001 | PIPE LINE |  | xx | PIPE LINE | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03PAG20BR001 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
| A6.4 | A6 | SNR-H03PAG | INSTRUMENT (COOLING WATER RTD) |  | xx | INSTRUMENT (COOLING WATER RTD) | หฟศ-ฟ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.4.1 | A6.4 | SNR-H03PAG12CT001 | TEMPERATURE COOLING WATER INLET to STATOR AIR COOLERS (COMHEADER) PCB80CT002 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A6.4.2 | A6.4 | SNR-H03PAG12CT030 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLER (COMHEADER) PCB80CT005 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.4.3 | A6.4 | SNR-H03PAG13CT001 | TEMPERATURE COOLING WATER INLET to OIL COOLER LCB LUBE OIL PLANT PCB30CT001 | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.4.4 | A6.4 | SNR-H03PAG13CT004 | TEMPERATURE COOLING WATER OUTLET from OIL COOLER LCB LUBE OIL PLANT PCB30CT002 | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5 | A6 | SNR-H03PAG12 | INSTRUMENT (COOLING WATER DIAL TEMP.) |  | xx | INSTRUMENT (COOLING WATER DIAL TEMP.) | หฟศ-ฟ. | 28 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.1 | A6.5 | SNR-H03PAG12CT002 | TEMPERATURE COOLING WATER INLET to STATOR AIR COOLERS (COMHEADER) PCB80CT003-C01/C02 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A6.5.2 | A6.5 | SNR-H03PAG12CT005 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT013-C01/C02 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.3 | A6.5 | SNR-H03PAG12CT007 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT014-C01/C02 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.4 | A6.5 | SNR-H03PAG12CT009 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT015-C01/C02 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.5 | A6.5 | SNR-H03PAG12CT011 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT016-C01/C02 | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.6 | A6.5 | SNR-H03PAG12CT013 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT017-C01/C02 | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. | A6.5.7 | A6.5 | SNR-H03PAG12CT015 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT018-C01/C02 | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.5.8 | A6.5 | SNR-H03PAG12CT017 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT019-C01/C02 | [12 empty] | M
| A6.5.9 | A6.5 | SNR-H03PAG12CT019 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT020-C01/C02 | [12 empty] | M
| A6.5.10 | A6.5 | SNR-H03PAG12CT021 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT021-C01/C02 | [12 empty] | M
| A6.5.11 | A6.5 | SNR-H03PAG12CT023 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT022-C01/C02 | [12 empty] | M
| A6.5.12 | A6.5 | SNR-H03PAG12CT025 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT023-C01/C02 | [12 empty] | M
| A6.5.13 | A6.5 | SNR-H03PAG12CT027 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS MKA80CT024-C01/C02 | [12 empty] | M
| A6.5.14 | A6.5 | SNR-H03PAG12CT029 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS (COMHEADER) PCB80CT004-C01/C02 | [12 empty] | M
| A6.6 | A6 | SNR-H03PAG | INSTRUMENT (COOLING WATER FLOW) |  | xx | INSTRUMENT (COOLING WATER FLOW) | หฟศ-ฟ. | 7.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.6.1 | A6.6 | SNR-H03PAG12CF001 | FLOW COOLING WATER INLET to STATOR AIR COOLER (COMHEADER) PCB80CF001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A6.6.2 | A6.6 | SNR-H03PAG13CF001 | FLOW COOLING WATER OUTLET to OIL COOLER LCB LUBE OIL PLANT MKF30CF001 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.6.3 | A6.6 | SNR-H03PAG14CF001 | TGB WATER FLOW TRANSDUCER MED23CF001 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND (LIMIT SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | ADJUSTMENT (SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.7 | A6 | SNR-H03PAG | INSTRUMENT (COOLING WATER PRESSURE GAUGE) |  | xx | INSTRUMENT (COOLING WATER PRESSURE GAUGE) | หฟศ-ฟ. | 8 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.7.1 | A6.7 | SNR-H03PAG12CP001 | CONTACT PRESSURE GAUGE COOLING WATER INLET TO STATOR AIR COOLERS (COMHEADER) PCB80CP001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A6.7.2 | A6.7 | SNR-H03PAG12CP004 | CONTACT PRESSURE GAUGE COOLING WATER OUTLET TO STATOR AIR COOLERS (COMHEADER) PCB80CP002 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.7.3 | A6.7 | SNR-H03PAG13CP001 | CONTACT PRESSURE GAUGE COOLING WATER INLET TO OIL COOLERS LCB LUBE OIL PLANT PCB30CP501 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.7.4 | A6.7 | SNR-H03PAG13CP004 | CONTACT PRESSURE GAUGE COOLING WATER OUTLET TO OIL COOLERS LCB LUBE OIL PLANT PCB30CP502 | 40 | 40 | TESTING FOR AS FOUND (LIMIT SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | ADJUSTMENT (SW.) | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.8 | A6 | SNR-H03PAG | INSTRUMENT (COOLING WATER DIAL TEMP.) |  | xx | INSTRUMENT (COOLING WATER DIAL TEMP.) | หฟศ-ฟ. | 10 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.8.1 | A6.8 | SNR-H03PAG13CT002 | TEMPERATURE COOLING WATER INLET to OIL COOLERS LCB LUBE OIL PLANT PCB30CT501 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
| A6.8.2 | A6.8 | SNR-H03PAG13CT003 | TEMPERATURE COOLING WATER OUTLET from OIL COOLERS LCB LUBE OIL PLANT PCB30CT502 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.8.3 | A6.8 | SNR-H03PAG12CT003 | TEMPERATURE COOLING WATER INLET to STATOR AIR COOLERS (COMHEADER) PCB80CT001 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.8.4 | A6.8 | SNR-H03PAG12CT028 | TEMPERATURE COOLING WATER OUTLET to STATOR AIR COOLERS (COMHEADER) PCB80CT003 | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A6.8.5 | A6.8 | SNR-H03PAG14CT001 | TGB WATER TEMPERATURE (TGB LUB OIL) MED23CT501 | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A7 | A | SNR-H13LSL10 | AUXILIARY (DRAINAGE PUMP) |  | xx | AUXILIARY (DRAINAGE PUMP) | หบศ-ฟ. | 1.5 | 2024-09-07 | 2024-09-07 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LSL10 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H13LSL10 |  | 20 | 20 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13LSL10 |  | 30 | 30 | OPERATION TEST | หบศ-ฟ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8 | A | SNR-H13QE | AUXILIARY (COMPRESSED AIR SYSTEM) |  | xx | AUXILIARY (COMPRESSED AIR SYSTEM) | หบศ-ฟ. | 34.5 | 2024-09-06 | 2024-09-08 |  |  |  | SNR0-2M0 |  | M
| A8.1 | A8 | SNR-H13QEA10 | AIR COMPRESSOR A |  | xx | AIR COMPRESSOR A | หบศ-ฟ. | 3.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA10 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H13QEA10 |  | 20 | 20 | CLEAN SUCTION FILTER | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA10 |  | 30 | 30 | CHANGE LUB OIL (IF NECESSARY) | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA10 |  | 40 | 40 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA10 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.2 | A8 | SNR-H13QEA20 | AIR COMPRESSOR B |  | xx | AIR COMPRESSOR B | หบศ-ฟ. | 3.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA20 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H13QEA20 |  | 20 | 20 | CLEAN SUCTION FILTER | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA20 |  | 30 | 30 | CHANGE LUB OIL (IF NECESSARY) | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA20 |  | 40 | 40 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA20 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.3 | A8 | SNR-H13QEA30 | AIR COMPRESSOR C |  | xx | AIR COMPRESSOR C | หบศ-ฟ. | 3.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA30 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H13QEA30 |  | 20 | 20 | CLEAN SUCTION FILTER | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA30 |  | 30 | 30 | CHANGE LUB OIL (IF NECESSARY) | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA30 |  | 40 | 40 | CAPACITY TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H13QEA30 |  | 50 | 50 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.4 | A8 | SNR-H03QEB60 | AIR ADMISSION EQUIPMENT |  | xx | AIR ADMISSION EQUIPMENT | หบศ-ฟ. | 4 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB60 |  | 10 | 10 | VISUAL INSPECTION | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEB60 |  | 20 | 20 | CLEANING | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB60 |  | 30 | 30 | CORROSION, CAVITATION CHECK | หบศ-ฟ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB60 |  | 40 | 40 | LEAKAGE TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB60 |  | 50 | 50 | INSPECT SWING CHECK VALVE (REPAIR IF NECESSARY) | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB60 |  | 60 | 60 | OPERATION TEST | หบศ-ฟ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.5 | A8 | SNR-H03QEA10 | BRAKE AIR TANK |  | xx | BRAKE AIR TANK | หบศ-ฟ. | 1.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.5.1 | A8.5 | SNR-H03QEA10 | BRAKE AIR TANK (หบศ-ฟ.) |  | xx | BRAKE AIR TANK (หบศ-ฟ.) | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEA10 |  | 10 | 10 | CHECK LEAK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEA10 |  | 20 | 20 | DRAIN CONDENSATE WATER | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไข Final 6/8/67 | A8.5.2 | A8.5 | SNR-H03QEA10 | BRAKE AIR TANK (หวผอ-ธ.) |  | xx | BRAKE AIR TANK (หวผอ-ธ.) | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MWD0-SM10 |  | M
แก้ไข Final 6/8/67 |  |  | SNR-H03QEA10 |  | 10 | 10 | THICKNESS MEASUREMENT ON TANK | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
| A8.6 | A8 | SNR-H03QEB10 | MAIN AIR TANK (951) |  | xx | MAIN AIR TANK (951) | หบศ-ฟ. | 2.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.6.1 | A8.6 | SNR-H03QEB10 | MAIN AIR TANK (951) (หบศ-ฟ.) |  | xx | MAIN AIR TANK (951) (หบศ-ฟ.) | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB10 |  | 10 | 10 | CHECK LEAK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEB10 |  | 20 | 20 | DRAIN CONDENSATE WATER | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไข Final 6/8/67 | A8.6.2 | A8.6 | SNR-H03QEB10 | MAIN AIR TANK (951) (หวผอ-ธ.) |  | xx | MAIN AIR TANK (951) (หวผอ-ธ.) | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MWD0-SM10 |  | M
แก้ไข Final 6/8/67 |  |  | SNR-H03QEB10 |  | 10 | 10 | THICKNESS MEASUREMENT ON TANK | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
เพิ่มเติม Worklist 11/6/67 | A8.6.3 | A8.6 | SNR-H03QEB10 | MAIN AIR TANK (951) (หขศ-ฟ.) |  | xx | MAIN AIR TANK (951) (หขศ-ฟ.) | หขศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-3D0 |  | M
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03QEB10 |  | 10 | 10 | INSTALL SCAFFOLDING | หขศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 4 | SNR0-3D0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | M
|  |  | SNR-H03QEB10 |  | 20 | 20 | REMOVE SCAFFOLDING | หขศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-3D0 |  | M
| A8.7 | A8 | SNR-H03QEB11 | AUX. AIR TANK (641) |  | xx | AUX. AIR TANK (641) | หบศ-ฟ. | 1.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
| A8.7.1 | A8.7 | SNR-H03QEB11 | AUX. AIR TANK (641) (หบศ-ฟ.) |  | xx | AUX. AIR TANK (641) (หบศ-ฟ.) | หบศ-ฟ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
|  |  | SNR-H03QEB11 |  | 10 | 10 | CHECK LEAK | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | SNR0-2M0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEB11 |  | 20 | 20 | DRAIN CONDENSATE WATER | หบศ-ฟ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | SNR0-2M0 |  | M
แก้ไข Final 6/8/67 | A8.7.2 | A8.7 | SNR-H03QEB11 | AUX. AIR TANK (641) (หวผอ-ธ.) |  | xx | AUX. AIR TANK (641) (หวผอ-ธ.) | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MWD0-SM10 |  | M
แก้ไข Final 6/8/67 |  |  | SNR-H03QEB11 |  | 10 | 10 | THICKNESS MEASUREMENT ON TANK | หวผอ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
| A8.8 | A8 | SNR-H03QEA10CP003 | INSTRUMENT (PRESSURE SWITCH AIR INLET to BRAKING PLANT (BEFORE AIR TANK) MKA91CP007) |  | xx | INSTRUMENT (PRESSURE SWITCH AIR INLET to BRAKING PLANT (BEFORE AIR TANK) MKA91CP007) | หฟศ-ฟ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP003 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEA10CP003 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP003 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP003 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP003 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03QEA10CP003 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP003 |  | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03QEA10CP003 |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A8.9 | A8 | SNR-H03QEA10CP001 | INSTRUMENT (PRESSURE GAUGE AIR INLET to AIR TANK BRAKING PLANT MKA91CP509) |  | xx | INSTRUMENT (PRESSURE GAUGE AIR INLET to AIR TANKBRAKING PLANT MKA91CP509) | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEA10CP001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP001 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEA10CP001 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  | SNR-H03QEA10CP001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A8.10 | A8 | SNR-H03QEB40 | INSTRUMENT (AIR for BRAKE PRESSURE SWITCH) |  | xx | INSTRUMENT (AIR for BRAKE PRESSURE SWITCH) | หฟศ-ฟ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEB40CP002 | PRESSURE AIR INLET to BRAKING PLANT (BEFORE 3/2 WAY SOLENOID VALVE) MKA91CP003 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEB40CP004 | PRESSURE AIR INLET to BRAKING JACKS (AFTER 3/2 WAY SOLENOID VALVE) MKA91CP004 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 70 | 70 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A8.11 | A8 | SNR-H03QEB40 | INSTRUMENT (AIR for BRAKE PRESSURE GAUGE) |  | xx | INSTRUMENT (AIR for BRAKE PRESSURE GAUGE) | หฟศ-ฟ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
|  |  | SNR-H03QEB40CP005 | PRESSURE AIR INLET to BRAKING PLANT (BEFORE SOLENOID VALVE) MKA91CP505 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | M
|  |  | SNR-H03QEB40CP006 | PRESSURE AIR INLET to BRAKE JACKSBRAKING PLANT (AFTER SOLENOID VALVE) MKA91CP506 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
[5 empty] | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.25 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติม 15/7/67 |  |  |  |  | 70 | 70 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
เพิ่มเติมโดย หวปศ-ฟ. |  |  |  |  | 80 | 80 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | M
| A9 | A | SNR-H03MEY10 | MECHANICAL GOVERNOR CONTROL (MACHINE & VIBRATION TEST) |  | xx | MECHANICAL GOVERNOR CONTROL (MACHINE & VIBRATION TEST) | หบนม-ธ. | 58 | 2024-09-10 | 12/9/2024 |  |  |  | MSP0-MH20 |  | M
| A9.1 | A9 | SNR-H03MEY10 | MECHINE TEST OF GOVERNOR CONTROL (หบนม-ธ.) |  | xx | MECHINE TEST OF GOVERNOR CONTROL (หบนม-ธ.) | หบนม-ธ. | 32 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H03MEY10 |  | 10 | 10 | CHARACTERISTIC CHECK (DRY TEST) | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  | 1 | 1 | MSP0-MH20 | PTW งานทั่วไป | M
|  |  | SNR-H03MEY10 |  | 20 | 20 | NEUTRAL TEST | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H03MEY10 |  | 30 | 30 | G/V RELATION CHECK (DRY TEST) | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H03MEY10 |  | 40 | 40 | G/V TRAVELING TIME CHECK (DRY TEST) | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H03MEY10 |  | 50 | 50 | G/V FRICTION FORCE CHECK (DRY TEST) | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
|  |  | SNR-H03MEY10 |  | 60 | 60 | OIL LAPPING TEST | หบนม-ธ. | 2 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-MH20 |  | M
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MEY10 |  | 70 | 70 | TUR. START UP TEST (WET TEST) -AUTO START-STOP TEST -PROTEC for UNIT TRIP TEST -PULS TEST for TUR | หบนม-ธ. | 20 | 11/9/2024 | 12/9/2024 |  |  |  | MSP0-MH20 |  | M
| A9.2 | A9 | SNR-H03MEY10 | MECHINE TEST OF GOVERNOR CONTROL (หบศ-ฟ.) |  | xx | MECHINE TEST OF GOVERNOR CONTROL (หบศ-ฟ.) | หบศ-ฟ. | 30 | 10/9/2024 | 12/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H03MEY10 |  | 10 | 10 | ร่วมปฏิบัติงานเพื่อเป็น Specialist (ลง Group) | หบศ-ฟ. | 30 | 10/9/2024 | 12/9/2024 |  |  | 1 | SNR0-2M0 | PTW งานทั่วไป | M
| A9.3 | A9 | SNR-H04MEY10 | VIBRATION TEST (หวผอ-ธ.) |  | xx | VIBRATION TEST (หวผอ-ธ.) | หวผอ-ธ. | 26 | 10/9/2024 | 12/9/2024 |  |  |  | MWD0-SM10 |  | M
|  |  | SNR-H04MEY10 |  | 10 | 10 | INSTALL EQUIPMENT FOR MEASUREMENT | หวผอ-ธ. | 3 | 10/9/2024 | 10/9/2024 |  | 1 | 1 | MWD0-SM10 | PTW งานทั่วไป | M
|  |  | SNR-H04MEY10 |  | 20 | 20 | TEST DURING UNIT OPERATION TEST | หวผอ-ธ. | 20 | 11/9/2024 | 12/9/2024 |  |  |  | MWD0-SM10 |  | M
|  |  | SNR-H04MEY10 |  | 30 | 30 | INSPECTION REPORT | หวผอ-ธ. | 3 | 11/9/2024 | 12/9/2024 |  |  |  | MWD0-SM10 |  | M
| A9.4 | A9 | SNR-H04MEY10 | VIBRATION TEST (หบศ-ฟ.) |  | xx | VIBRATION TEST (หบศ-ฟ.) | หบศ-ฟ. | 30 | 10/9/2024 | 12/9/2024 |  |  |  | SNR0-2M0 |  | M
เพิ่มเติม 15/7/67 |  |  | SNR-H04MEY10 |  | 10 | 10 | ร่วมปฏิบัติงานเพื่อเป็น Specialist (ลง Group) | หบศ-ฟ. | 30 | 10/9/2024 | 12/9/2024 |  |  | 1 | SNR0-2M0 | PTW งานทั่วไป | M
| B |  |  | ELECTRICAL EQUIPMENT |  | xx | ELECTRICAL EQUIPMENT | อบฟ.+อขศ. | 1283 | 3/9/2024 | 12/9/2024 | [5 empty] | E
| B1 | B | SNR-H03MKA | GENERATOR |  | xx | GENERATOR | หฟศ-ฟ. | 437 | 2024-09-03 | 2024-09-09 |  |  |  | SNR0-2E0 |  | E
| B1.1 | B1 | SNR-H03MKA40HA001 | GENERATOR STATOR |  | xx | GENERATOR STATOR | หฟศ-ฟ. | 40 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.1.1 | B1.1 | SNR-H03MKA40HA001 | GENERATOR STATOR (หกฟ-ธ.) |  | xx | GENERATOR STATOR (หกฟ-ธ.) | หกฟ-ธ. | 28 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 10 | 10 | PREPARATION EQUIPMENT & FACILITY | หกฟ-ธ. | 8 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-E220 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA40HA001 |  | 20 | 20 | SHORT CIRCUIT RTD. & CT. | หกฟ-ธ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 30 | 30 | DISCONNECTION & REMOVE MAIN LEAD | หกฟ-ธ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 40 | 40 | DISCONNECTION & REMOVE NEUTRAL POINT | หกฟ-ธ. | 4 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 50 | 50 | VISUAL INSPECTION END COILS | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 60 | 60 | VISUAL INSPECTION INSULATION CAPS | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 70 | 70 | VISUAL INSPECTION BUS CONNECTION | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 80 | 80 | VISUAL INSPECTION WEDGES | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 90 | 90 | VISUAL INSPECTION SPACER,CORE,BOLTS,SUPPORT & LOOSEN PART | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 100 | 100 | ASSEMBLY & CONNECT MAIN LEAD/NEUTRAL POINT | หกฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 110 | 110 | OPEN CIRCUIT OF RTD. & CT | หกฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA40HA001 |  | 120 | 120 | FINAL INSPECTION & FINAL WORK | หกฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B1.1.2 | B1.1 | SNR-H03MKA40HA001 | GENERATOR STATOR (หขศ-ฟ.) |  | xx | GENERATOR STATOR (หขศ-ฟ.) | หขศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-3D0 |  | E
|  |  | SNR-H03MKA40HA001 |  | 10 | 10 | SCAFFOLD ASSEMBLY (GEN. TERMINAL) | หขศ-ฟ. | 2 | 3/9/2024 | 3/9/2024 |  | 1 | 7 | SNR0-3D0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | E
|  |  | SNR-H03MKA40HA001 |  | 20 | 20 | DISASSEMBLY SCAFFOLD (GEN. TERMINAL) | หขศ-ฟ. | 2 | 9/9/2024 | 9/9/2024 |  |  |  | SNR0-3D0 |  | E
| B1.1.3 | B1.1 | SNR-H03MKA40HA001 | GENERATOR STATOR (หทอฟ-ธ.) |  | xx | GENERATOR STATOR (หทอฟ-ธ.) | หทอฟ-ธ. | 8 | 5/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA40HA001 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT (PRETEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA40HA001 |  | 20 | 20 | D.C. RESISTANCE MEASUREMENT (PRETEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA40HA001 |  | 30 | 30 | CAPACITANCE MEASUREMENT (PRETEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA40HA001 |  | 40 | 40 | INSULATION RESISTANCE MEASUREMENT (FINAL TEST) | หทอฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA40HA001 |  | 50 | 50 | INSULATION POWER FACTOR TIP UP MEASUEMENT (FINAL TEST) | หทอฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
| B1.2 | B1 | SNR-H03MKA20 | GENERATOR ROTOR |  | xx | GENERATOR ROTOR | หกฟ-ธ. | 19 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B1.2.1 | B1.2 | SNR-H03MKA20 | GENERATOR ROTOR (หกฟ-ธ.) |  | xx | GENERATOR ROTOR (หกฟ-ธ.) | หกฟ-ธ. | 11 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 10 | 10 | PREPARATION EQUIPMENT & FACILITY | หกฟ-ธ. | 1 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-E220 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA20 |  | 20 | 20 | DISCONNECT & REMOVE ROTOR LEAD | หกฟ-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 30 | 30 | VISUAL INSPECTION COILS INSULATION | หกฟ-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 40 | 40 | VISUAL INSPECTION CONNECTION | หกฟ-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 50 | 50 | VISUAL INSPECTION AMORTISSEUR WINDING (DAMPER WINDING) | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 60 | 60 | VISUAL INSPECTION BOLTS, NUTS AND LOOSEN PART | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 70 | 70 | CLEANING | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 80 | 80 | POLES IMPROVEMENT | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 90 | 90 | VARNISH TREATMENT | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 100 | 100 | ASSEMBLY & CONNECT ROTOR LEAD | หกฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA20 |  | 110 | 110 | FINAL INSPECTION & FINAL WORK | หกฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B1.2.2 | B1.2 | SNR-H03MKA20 | GENERATOR ROTOR (หทอฟ-ธ.) |  | xx | GENERATOR ROTOR (หทอฟ-ธ.) | หทอฟ-ธ. | 8 | 5/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA20 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT (PRE TEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA20 |  | 20 | 20 | DC. RESISTANCE MEASUREMENT (PRE TEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA20 |  | 30 | 30 | CAPACITANCE MEASUREMENT (PRE TEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA20 |  | 40 | 40 | IMPEDANCE MEASUREMENT (PRE TEST) | หทอฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKA20 |  | 50 | 50 | INSULATION RESISTANCE MEASUREMENT (FINAL TEST) | หทอฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. | B1.3 | B1 | SNR-H03MKA70CY001 | VIBRATION MONITORING |  | xx | VIBRATION MONITORING | หฟศ-ฟ. | 17 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. |  |  | SNR-H03MKA70CY001 |  | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขโดย หฟศ-ฟ. |  |  | SNR-H03MKA70CY001 |  | 20 | 20 | CLEANING | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. |  |  | SNR-H03MKA70CY001 |  | 30 | 30 | DRY TEST WITH MECHANICAL EQUIPMENT | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. |  |  | SNR-H03MKA70CY001 |  | 40 | 40 | WET TEST | หฟศ-ฟ. | 8 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.4 | B1 | SNR-H03MKA10HB001-F01 | ROTOR EARTH BRUSH |  | xx | ROTOR EARTH BRUSH | หกฟ-ธ. | 9 | 6/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 10 | 10 | INSULATION RESISTANCE TEST 1 (PRETEST) | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-E220 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA10HB001-F01 |  | 20 | 20 | VISUAL INSPECTION | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 30 | 30 | CLEANING | หกฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 40 | 40 | RECONDITION | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 50 | 50 | PREADJUSTMENT | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 60 | 60 | CHECK BRUSH HOLDER PRESSURE | หกฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 70 | 70 | INSULATION RESISTANCE TEST 2 (FINAL TEST) | หกฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 80 | 80 | CONNECT WIRING OR CABLE OR BUS | หกฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKA10HB001-F01 |  | 90 | 90 | FINAL INSPECTION & FINAL WORK | หกฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B1.5 | B1 | SNR-H03MKA40 | INSTRUMENT (STATOR RTD) |  | xx | INSTRUMENT (STATOR RTD) | หฟศ-ฟ. | 220.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.1 | B1.5 | SNR-H03MKA40CT001-F01 | TEMPERATOR STATOR WINDING MKA20CT001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
| B1.5.2 | B1.5 | SNR-H03MKA40CT001-F02 | TEMPERATOR STATOR WINDING MKA20CT002 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.3 | B1.5 | SNR-H03MKA40CT001-F03 | TEMPERATOR STATOR WINDING MKA20CT003 | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.4 | B1.5 | SNR-H03MKA40CT001-F04 | TEMPERATOR STATOR WINDING MKA20CT004 | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.5 | B1.5 | SNR-H03MKA40CT001-F05 | TEMPERATOR STATOR WINDING MKA20CT005 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติม 15/7/67 | B1.5.6 | B1.5 | SNR-H03MKA40CT001-F06 | TEMPERATOR STATOR WINDING MKA20CT006 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.7 | B1.5 | SNR-H03MKA40CT001-F07 | TEMPERATOR STATOR WINDING MKA20CT007 | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.5.8 | B1.5 | SNR-H03MKA40CT001-F08 | TEMPERATOR STATOR WINDING MKA20CT008 | [12 empty] | E
| B1.5.9 | B1.5 | SNR-H03MKA40CT001-F09 | TEMPERATOR STATOR WINDING MKA20CT009 | [12 empty] | E
| B1.5.10 | B1.5 | SNR-H03MKA40CT001-F10 | TEMPERATOR STATOR WINDING MKA20CT010 | [12 empty] | E
| B1.5.11 | B1.5 | SNR-H03MKA40CT001-F11 | TEMPERATOR STATOR WINDING MKA20CT011 | [12 empty] | E
| B1.5.12 | B1.5 | SNR-H03MKA40CT001-F12 | TEMPERATOR STATOR WINDING MKA20CT012 | [12 empty] | E
| B1.5.13 | B1.5 | SNR-H03MKA40CT001-F13 | TEMPERATOR STATOR WINDING MKA20CT013 | [12 empty] | E
| B1.5.14 | B1.5 | SNR-H03MKA40CT001-F14 | TEMPERATOR STATOR WINDING MKA20CT014 | [12 empty] | E
| B1.5.15 | B1.5 | SNR-H03MKA40CT001-F15 | TEMPERATOR STATOR WINDING MKA20CT015 | [12 empty] | E
| B1.5.16 | B1.5 | SNR-H03MKA40CT001-F16 | TEMPERATOR STATOR WINDING MKA20CT016 | [12 empty] | E
| B1.5.17 | B1.5 | SNR-H03MKA40CT001-F17 | TEMPERATOR STATOR WINDING MKA20CT017 | [12 empty] | E
| B1.5.18 | B1.5 | SNR-H03MKA40CT001-F18 | TEMPERATOR STATOR WINDING MKA20CT018 | [12 empty] | E
| B1.5.19 | B1.5 | SNR-H03MKA40CT004-F01 | TEMPERATOR STATOR CORE MKA20CT001 | [12 empty] | E
| B1.5.20 | B1.5 | SNR-H03MKA40CT004-F02 | TEMPERATOR STATOR CORE MKA20CT002 | [12 empty] | E
| B1.5.21 | B1.5 | SNR-H03MKA40CT004-F03 | TEMPERATOR STATOR CORE MKA20CT003 | [12 empty] | E
| B1.5.22 | B1.5 | SNR-H03MKA40CT004-F04 | TEMPERATOR STATOR CORE MKA20CT004 | [12 empty] | E
| B1.5.23 | B1.5 | SNR-H03MKA40CT004-F05 | TEMPERATOR STATOR CORE MKA20CT005 | [12 empty] | E
| B1.5.24 | B1.5 | SNR-H03MKA40CT004-F06 | TEMPERATOR STATOR CORE MKA20CT006 | [12 empty] | E
| B1.5.25 | B1.5 | SNR-H03MKA40CT004-F07 | TEMPERATOR STATOR CORE MKA20CT007 | [12 empty] | E
| B1.5.26 | B1.5 | SNR-H03MKA40CT004-F08 | TEMPERATOR STATOR CORE MKA20CT008 | [12 empty] | E
| B1.5.27 | B1.5 | SNR-H03MKA40CT004-F09 | TEMPERATOR STATOR CORE MKA20CT009 | [12 empty] | E
| B1.5.28 | B1.5 | SNR-H03MKA40CT002-F01 | TEMPERATOR STATOR WINDING NDE MKA25CT001 | [12 empty] | E
| B1.5.29 | B1.5 | SNR-H03MKA40CT002-F02 | TEMPERATOR STATOR WINDING NDE MKA25CT002 | [12 empty] | E
| B1.5.30 | B1.5 | SNR-H03MKA40CT002-F03 | TEMPERATOR STATOR WINDING NDE MKA25CT003 | [12 empty] | E
| B1.5.31 | B1.5 | SNR-H03MKA40CT003-F01 | TEMPERATOR STATOR WINDING DE MKA25CT004 | [12 empty] | E
| B1.5.32 | B1.5 | SNR-H03MKA40CT003-F02 | TEMPERATOR STATOR WINDING DE MKA25CT005 | [12 empty] | E
| B1.5.33 | B1.5 | SNR-H03MKA40CT003-F03 | TEMPERATOR STATOR WINDING DE MKA25CT006 | [12 empty] | E
| B1.5.34 | B1.5 | SNR-H03MKA40CT005-F01 | TEMPERATOR STATOR CORE NDE MKA25CT001 | [12 empty] | E
| B1.5.35 | B1.5 | SNR-H03MKA40CT005-F02 | TEMPERATOR STATOR CORE NDE MKA25CT002 | [12 empty] | E
| B1.5.36 | B1.5 | SNR-H03MKA40CT005-F03 | TEMPERATOR STATOR CORE NDE MKA25CT003 | [12 empty] | E
| B1.5.37 | B1.5 | SNR-H03MKA40CT005-F04 | TEMPERATOR STATOR CORE DE MKA25CT004 | [12 empty] | E
| B1.5.38 | B1.5 | SNR-H03MKA40CT005-F05 | TEMPERATOR STATOR CORE DE MKA25CT005 | [12 empty] | E
| B1.5.39 | B1.5 | SNR-H03MKA40CT005-F06 | TEMPERATOR STATOR CORE DE MKA25CT006 | [12 empty] | E
| B1.5.40 | B1.5 | SNR-H03MKA40CT006-F02 | TEMPERATOR HOT AIR MKA81CT001 | [12 empty] | E
| B1.5.41 | B1.5 | SNR-H03MKA40CT006-F03 | TEMPERATOR HOT AIR MKA81CT002 | [12 empty] | E
| B1.5.42 | B1.5 | SNR-H03MKA40CT006-F04 | TEMPERATOR HOT AIR MKA81CT003 | [12 empty] | E
| B1.5.43 | B1.5 | SNR-H03MKA40CT006-F05 | TEMPERATOR HOT AIR MKA81CT004 | [12 empty] | E
| B1.5.44 | B1.5 | SNR-H03MKA40CT006-F06 | TEMPERATOR HOT AIR MKA81CT005 | [12 empty] | E
| B1.5.45 | B1.5 | SNR-H03MKA40CT006-F07 | TEMPERATOR HOT AIR MKA81CT006 | [12 empty] | E
| B1.5.46 | B1.5 | SNR-H03MKA40CT006-F08 | TEMPERATOR HOT AIR MKA81CT007 | [12 empty] | E
| B1.5.47 | B1.5 | SNR-H03MKA40CT006-F09 | TEMPERATOR HOT AIR MKA81CT008 | [12 empty] | E
| B1.5.48 | B1.5 | SNR-H03MKA40CT006-F10 | TEMPERATOR HOT AIR MKA81CT009 | [12 empty] | E
| B1.5.49 | B1.5 | SNR-H03MKA40CT006-F11 | TEMPERATOR HOT AIR MKA81CT010 | [12 empty] | E
| B1.5.50 | B1.5 | SNR-H03MKA40CT006-F12 | TEMPERATOR HOT AIR MKA81CT011 | [12 empty] | E
| B1.5.51 | B1.5 | SNR-H03MKA40CT006-F13 | TEMPERATOR HOT AIR MKA81CT012 | [12 empty] | E
| B1.5.52 | B1.5 | SNR-H03MKA40CT007-F02 | TEMPERATOR COLD AIR MKA82CT001 | [12 empty] | E
| B1.5.53 | B1.5 | SNR-H03MKA40CT007-F03 | TEMPERATOR COLD AIR MKA82CT002 | [12 empty] | E
| B1.5.54 | B1.5 | SNR-H03MKA40CT007-F04 | TEMPERATOR COLD AIR MKA82CT003 | [12 empty] | E
| B1.5.55 | B1.5 | SNR-H03MKA40CT007-F05 | TEMPERATOR COLD AIR MKA82CT004 | [12 empty] | E
| B1.5.56 | B1.5 | SNR-H03MKA40CT007-F06 | TEMPERATOR COLD AIR MKA82CT005 | [12 empty] | E
| B1.5.57 | B1.5 | SNR-H03MKA40CT007-F07 | TEMPERATOR COLD AIR MKA82CT006 | [12 empty] | E
| B1.5.58 | B1.5 | SNR-H03MKA40CT007-F08 | TEMPERATOR COLD AIR MKA82CT007 | [12 empty] | E
| B1.5.59 | B1.5 | SNR-H03MKA40CT007-F09 | TEMPERATOR COLD AIR MKA82CT008 | [12 empty] | E
| B1.5.60 | B1.5 | SNR-H03MKA40CT007-F10 | TEMPERATOR COLD AIR MKA82CT009 | [12 empty] | E
| B1.5.61 | B1.5 | SNR-H03MKA40CT007-F11 | TEMPERATOR COLD AIR MKA82CT010 | [12 empty] | E
| B1.5.62 | B1.5 | SNR-H03MKA40CT007-F12 | TEMPERATOR COLD AIR MKA82CT011 | [12 empty] | E
| B1.5.63 | B1.5 | SNR-H03MKA40CT007-F13 | TEMPERATOR COLD AIR MKA82CT012 | [12 empty] | E
| B1.6 | B1 | SNR-H03MKA40 | INSTRUMENT (STATOR DIAL TEMP.) |  | xx | INSTRUMENT (STATOR DIAL TEMP.) | หฟศ-ฟ. | 6 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.6.1 | B1.6 | SNR-H03MKA40CT006-F01 | TEMPERATURE GENERATOR HOT AIR MKA81CT013 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
| B1.6.2 | B1.6 | SNR-H03MKA40CT007-F01 | TEMPERATURE GENERATOR COLD AIR MKA82CT013 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
[5 empty] | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
[5 empty] | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
[5 empty] | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
[5 empty] | 60 | 60 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7 | B1 | SNR-H03MKA41 | INSTRUMENT (AIR COOLER RTD) |  | xx | INSTRUMENT (AIR COOLER RTD) | หฟศ-ฟ. | 42 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7.1 | B1.7 | SNR-H03MKA41AC101-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT001 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
| B1.7.2 | B1.7 | SNR-H03MKA41AC102-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT002 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7.3 | B1.7 | SNR-H03MKA41AC103-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT003 | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7.4 | B1.7 | SNR-H03MKA41AC104-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT004 | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7.5 | B1.7 | SNR-H03MKA41AC105-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT005 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติม 15/7/67 | B1.7.6 | B1.7 | SNR-H03MKA41AC106-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT006 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.7.7 | B1.7 | SNR-H03MKA41AC107-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT007 | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 | [5 empty] | E
| B1.7.8 | B1.7 | SNR-H03MKA41AC108-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT008 | [12 empty] | E
| B1.7.9 | B1.7 | SNR-H03MKA41AC109-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT009 | [12 empty] | E
| B1.7.10 | B1.7 | SNR-H03MKA41AC110-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT010 | [12 empty] | E
| B1.7.11 | B1.7 | SNR-H03MKA41AC111-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT011 | [12 empty] | E
| B1.7.12 | B1.7 | SNR-H03MKA41AC112-F01 | TEMPERATURE COOLING WATER OUTLET from STATOR AIR COOLERS MKA80CT012 | [12 empty] | E
| B1.8 | B1 | SNR-H03MKA50 | INSTRUMENT (LIMIT SWITCH of BRAKE PISTON) |  | xx | INSTRUMENT (LIMIT SWITCH of BRAKE PISTON) | หฟศ-ฟ. | 28 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.1 | B1.8 | SNR-H03MKA50AU201-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU010-S01 | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
| B1.8.2 | B1.8 | SNR-H03MKA50AU202-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU020-S01 | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.3 | B1.8 | SNR-H03MKA50AU203-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU030-S01 | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.4 | B1.8 | SNR-H03MKA50AU204-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU040-S01 | 40 | 40 | TESTING FOR AS FOUND (LIMIT SW.) | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.5 | B1.8 | SNR-H03MKA50AU205-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU050-S01 | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติม 15/7/67 | B1.8.6 | B1.8 | SNR-H03MKA50AU206-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU060-S01 | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.7 | B1.8 | SNR-H03MKA50AU207-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU070-S01 | 70 | 70 | ADJUSTMENT (SW.) | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.8.8 | B1.8 | SNR-H03MKA50AU208-S01 | LIMIT SWITCH BRAKE PISTON ACTIVATED YES/NO MKA90AU080-S01 | [12 empty] | E
| B1.9 | B1 | SNR-H03MKA10HB001-T01 | INSTRUMENT (SHAFT CURRENT TRANSFORMER MKA30CE601) |  | xx | INSTRUMENT (SHAFT CURRENT TRANSFORMER MKA30CE601) | หฟศ-ฟ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.9.1 | B1.9 | SNR-H03MKA10HB001-T01 | INSTRUMENT (SHAFT CURRENT TRANSFORMER MKA30CE601) (หฟศ-ฟ.) | 10 | 10 | ISOLATE EQUIPMENT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKA10HB001-T01 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA10HB001-T01 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA10HB001-T01 |  | 40 | 40 | ASSEMBLY EQUIPMENT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B1.9.2 | B1.9 | SNR-H03MKA10HB001-T01 | INSTRUMENT (SHAFT CURRENT TRANSFORMER MKA30CE601) (หทอฟ-ธ.) | 10 | 10 | ELECTRICAL TEST 1.INSULATION RESISTANCE MEAS. 2.INSULATION PF MEAS. 3.RATIO&POLARITY MEAS. | หทอฟ-ธ. | 2 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
| B1.10 | B1 | SNR-H03MKA42 | INSTRUMENT (SPACE HEATER) |  | xx | INSTRUMENT (SPACE HEATER) | หฟศ-ฟ. | 42 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.10.1 | B1.10 | SNR-H03MKA42AH001 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH001 | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
| B1.10.2 | B1.10 | SNR-H03MKA42AH002 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH002 | 20 | 20 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. | B1.10.3 | B1.10 | SNR-H03MKA42AH003 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH003 | 30 | 30 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.10.4 | B1.10 | SNR-H03MKA42AH004 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH004 | 40 | 40 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติม 15/7/67 | B1.10.5 | B1.10 | SNR-H03MKA42AH005 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH005 | 50 | 50 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. | B1.10.6 | B1.10 | SNR-H03MKA42AH006 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH006 | 60 | 60 | ADJUSTMENT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติมโดย หวปศ-ฟ. | B1.10.7 | B1.10 | SNR-H03MKA42AH007 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH007 | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.10.8 | B1.10 | SNR-H03MKA42AH008 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH008 | [12 empty] | E
| B1.10.9 | B1.10 | SNR-H03MKA42AH009 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH009 | [12 empty] | E
| B1.10.10 | B1.10 | SNR-H03MKA42AH010 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH010 | [12 empty] | E
| B1.10.11 | B1.10 | SNR-H03MKA42AH011 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH011 | [12 empty] | E
| B1.10.12 | B1.10 | SNR-H03MKA42AH012 | HEATER for AIR INSIDE STATOR ANTI CONDENION MKA20AH012 | [12 empty] | E
| B1.11 | B1 | SNR-H03MKA42DT001 | THERMOSTAT STANDSTILL HEATER for ANTI CONDENSATION MKA20DT001 |  | xx | THERMOSTAT STANDSTILL HEATER for ANTI CONDENSATION MKA20DT001 | หฟศ-ฟ. | 3.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
|  |  | SNR-H03MKA42DT001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 60 | 60 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA42DT001 |  | 70 | 70 | FUNCTION TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B1.12 | B1 | SNR-H03MKA80AU001QP01 | DIFF PRESSURE SWITCH of BREAKE DUST EXHAUST MKA93CP001 |  | xx | DIFF PRESSURE SWITCH of BREAKE DUST EXHAUST MKA93CP001 | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA80AU001QP01 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
|  |  | SNR-H03MKA80AU001QP01 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA80AU001QP01 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA80AU001QP01 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA80AU001QP01 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKA80AU001QP01 |  | 60 | 60 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B1.13 | B1 | SNR-H03MKA90AT001-S01 | DIFF PRESSURE SWITCH of CARBON DUST EXHAUST MKA60CP001 |  | xx | DIFF PRESSURE SWITCH of CARBON DUST EXHAUST MKA60CP001 | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 30 | 30 | CLEANING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 40 | 40 | TESTING FOR AS FOUND | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKA90AT001-S01 |  | 60 | 60 | FUNCTION TEST AND FINE SETTING | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B2 | B | SNR-H03BA | HIGH VOLTAGE EQUIPMENT ELECTRICAL TEST |  | xx | HIGH VOLTAGE EQUIPMENT ELECTRICAL TEST | อบฟ.+อขศ. | 144 | 2024-09-03 | 2024-09-09 | [5 empty] | E
| B2.1 | B2 | SNR-H03BAA10GS200 | 13.8 KV. POTENTIAL TRANSFORMER OF GEN. DS. |  | xx | 13.8 KV. POTENTIAL TRANSFORMER OF GEN. DS. | หทอฟ-ธ. | 8 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขตาม MMS 7/8/67 | B2.1.1 | B2.1 | SNR-H03BAA10GS200-T03 | PT1 OF GEN. DS. (SYNCH., GEN.PROT., AVR&GOV.) (หทอฟ-ธ.) |  | xx | PT1 OF GEN. DS. (SYNCH., GEN.PROT., AVR&GOV.) (หทอฟ-ธ.) | หทอฟ-ธ. | 3 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T03 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 50 | 50 | AC. EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 60 | 60 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขตาม MMS 7/8/67 | B2.1.2 | B2.1 | SNR-H03BAA10GS200-T03 | PT1 OF GEN. DS. (SYNCH., GEN.PROT. , AVR&GOV.) (หอตฟ-ธ.) |  | xx | PT1 OF GEN. DS. (SYNCH., GEN.PROT. , AVR&GOV.) (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-T03 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T03 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
แก้ไขตาม MMS 7/8/67 | B2.1.3 | B2.1 | SNR-H03BAA10GS200-T04 | PT2 OF GEN. DS. (GEN.PROT.) (หทอฟ-ธ.) |  | xx | PT2 OF GEN. DS. (GEN.PROT.) (หทอฟ-ธ.) | หทอฟ-ธ. | 3 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T04 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 50 | 50 | AC. EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 60 | 60 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขตาม MMS 7/8/67 | B2.1.4 | B2.1 | SNR-H03BAA10GS200-T04 | PT2 OF GEN. DS. (GEN.PROT.) (หอตฟ-ธ.) |  | xx | PT2 OF GEN. DS. (GEN.PROT.) (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-T04 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T04 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2 | B2 | SNR-H03BAA | 13.8 KV. GEN. CURRENT TRANSFORMER |  | xx | 13.8 KV. GEN. CURRENT TRANSFORMER | หทอฟ-ธ.+หอตฟ-ธ. | 31.5 | 4/9/2024 | 4/9/2024 | [5 empty] | E
| B2.2.1 | B2.2 | SNR-H03BAA11GV100-T05 | CT OF DYNAMIC BRAKING CONTROL (SNR-H03MKY01CE151) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) |  | xx | CT OF DYNAMIC BRAKING CONTROL (SNR-H03MKY01CE151) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T05 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T05 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T05 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T05 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T05 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.2 | B2.2 | SNR-H03BAA11GV100-T05 | CT OF DYNAMIC BRAKING CONTROL (SNR-H03MKY01CE151) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) |  | xx | CT OF DYNAMIC BRAKING CONTROL (SNR-H03MKY01CE151) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA11GV100-T05 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T05 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.3 | B2.2 | SNR-H03BAA11GV100-T04 | CT OF AVR (SNR-H03MKY01CE141) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) |  | xx | CT OF AVR (SNR-H03MKY01CE141) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T04 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T04 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T04 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T04 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T04 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.4 | B2.2 | SNR-H03BAA11GV100-T04 | CT OF AVR (SNR-H03MKY01CE141) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) |  | xx | CT OF AVR (SNR-H03MKY01CE141) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA11GV100-T04 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T04 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.5 | B2.2 | SNR-H03BAA11GV100-T03 | CT OF GEN. PROT, 87G (SNR-H03MKY01CE131) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF GEN. PROT, 87G (SNR-H03MKY01CE131) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T03 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T03 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T03 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T03 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T03 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.6 | B2.2 | SNR-H03BAA11GV100-T03 | CT OF GEN. PROT, 87G (SNR-H03MKY01CE131) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF GEN. PROT, 87G (SNR-H03MKY01CE131) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA11GV100-T03 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T03 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.7 | B2.2 | SNR-H03BAA11GV100-T02 | CT OF METERING, AVR (SNR-H03MKY01CE121) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) |  | xx | CT OF METERING, AVR (SNR-H03MKY01CE121) 7000/5A, CL0.5, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T02 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T02 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T02 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T02 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T02 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.8 | B2.2 | SNR-H03BAA11GV100-T02 | CT OF METERING, AVR (SNR-H03MKY01CE121) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) |  | xx | CT OF METERING, AVR (SNR-H03MKY01CE121) 7000/5A, CL0.5, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA11GV100-T02 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T02 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.9 | B2.2 | SNR-H03BAA11GV100-T01 | CT OF 87MTG1 (SNR-H03MKY01CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03MKY01CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T01 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T01 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GV100-T01 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.10 | B2.2 | SNR-H03BAA11GV100-T01 | CT OF 87MTG1 (SNR-H03MKY01CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03MKY01CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA11GV100-T01 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GV100-T01 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.11 | B2.2 | SNR-H03BAA10GS200-T02 | CT OF 87G (SNR-H03BA-C01CE121) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF 87G (SNR-H03BA-C01CE121) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T02 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T02 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T02 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T02 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T02 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.12 | B2.2 | SNR-H03BAA10GS200-T02 | CT OF 87G (SNR-H03BA-C01CE121) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF 87G (SNR-H03BA-C01CE121) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-T02 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T02 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.13 | B2.2 | SNR-H03BAA10GS200-T01 | CT OF 87MTG1 (SNR-H03BA-C01CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03BA-C01CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T01 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T01 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-T01 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.14 | B2.2 | SNR-H03BAA10GS200-T01 | CT OF 87MTG1 (SNR-H03BA-C01CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03BA-C01CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-T01 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-T01 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.15 | B2.2 | SNR-H03BAA12GH100-T01 | CT OF 51BK (SNR-H03BAC02CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF 51BK (SNR-H03BAC02CE111) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA12GH100-T01 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T01 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T01 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.16 | B2.2 | SNR-H03BAA12GH100-T01 | CT OF 51BK (SNR-H03BAC02CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF 51BK (SNR-H03BAC02CE111) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-T01 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA12GH100-T01 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.2.17 | B2.2 | SNR-H03BAA12GH100-T02 | CT OF 87MTG1 (SNR-H03BAC02CE121) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03BAC02CE121) 7000/5A, 5P20, 40VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T02 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA12GH100-T02 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T02 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T02 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA12GH100-T02 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้ไขโดย หฟศ-ฟ. 17/6/67 | B2.2.18 | B2.2 | SNR-H03BAA12GH100-T02 | CT OF 87MTG1 (SNR-H03BAC02CE121) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) |  | xx | CT OF 87MTG1 (SNR-H03BAC02CE121) 7000/5A, 5P20, 40VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-T02 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA12GH100-T02 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.3 | B2 | SNR-H03BAA10GS200-F01 | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) |  | xx | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) | หทอฟ-ธ. | 3 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.3.1 | B2.3 | SNR-H03BAA10GS200-F01 | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) (หทอฟ-ธ.) |  | xx | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) (หทอฟ-ธ.) | หทอฟ-ธ. | 2 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-F01 |  | 20 | 20 | INSULATION RESISTANCE TEST | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F01 |  | 30 | 30 | INSULATION POWER FACTOR TEST | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F01 |  | 40 | 40 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.3.2 | B2.3 | SNR-H03BAA10GS200-F01 | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) (หอตฟ-ธ.) |  | xx | 13.8 KV. SURGE CAPACITOR (SNR-H03BA-C01GV002) (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-F01 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-F01 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
แก้ไขตาม MMS 7/8/67 | B2.4 | B2 | SNR-H03BAA10GA100 | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts |  | xx | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts | หกฟ-ธ. | 4 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
แก้ไขตาม MMS 7/8/67 | B2.4.1 | B2.4 | SNR-H03BAA10GA100 | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts (หกฟ-ธ.) |  | xx | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts (หกฟ-ธ.) | หกฟ-ธ. | 3 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03BAA10GA100 |  | 10 | 10 | ISOLATE EQUIPMENT | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-E220 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GA100 |  | 20 | 20 | VISUAL INSPECTION | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03BAA10GA100 |  | 30 | 30 | CLEANING | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03BAA10GA100 |  | 40 | 40 | ASSEMBLY EQUIPMENT | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03BAA10GA100 |  | 50 | 50 | CONTACT RESISTANCE MEASUREMENT | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03BAA10GA100 |  | 60 | 60 | FINAL INSPECTION | หกฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E220 |  | E
แก้ไขตาม MMS 7/8/67 | B2.4.2 | B2.4 | SNR-H03BAA10GA100 | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts (หทอฟ-ธ.) |  | xx | 13.8 KV. ISOLATE PHASE BUS DUCT 3 Parts (หทอฟ-ธ.) | หทอฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GA100 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
| B2.5 | B2 | SNR-H03BAA11GT100-T01 | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) |  | xx | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) | หมปฟ-ธ. | 6.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.5.1 | B2.5 | SNR-H03BAA11GT100-T01 | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) (หมปฟ-ธ.) |  | xx | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) (หมปฟ-ธ.) | หมปฟ-ธ. | 3.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 10 | 10 | ISOLATE EQUIPMENT | หมปฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GT100-T01 |  | 20 | 20 | VISUAL INSPECTION | หมปฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 30 | 30 | CLEANING | หมปฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 40 | 40 | RTD INSTRUMENT TEST & CALIBRATION | หมปฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 50 | 50 | FINAL INSPECTION | หมปฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 60 | 60 | ASSEMBLY EQUIPMENT | หมปฟ-ธ. | 1 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.5.2 | B2.5 | SNR-H03BAA11GT100-T01 | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) (หทอฟ-ธ.) |  | xx | NEUTRAL TRANSFORMER NGT. (SNR-H03MKY01CE210) (หทอฟ-ธ.) | หทอฟ-ธ. | 3 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA11GT100-T01 |  | 20 | 20 | EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 30 | 30 | DC. RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 50 | 50 | % IMPEDANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA11GT100-T01 |  | 60 | 60 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 7/9/2024 | 7/9/2024 | [5 empty] | E
| B2.6 | B2 | SNR-H03BAT10GT100 | MAIN TRANS. CURRENT TRANSFORMER |  | xx | MAIN TRANS. CURRENT TRANSFORMER | หทอฟ-ธ. | 17.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.6.1 | B2.6 | SNR-H03BAT10GT100-T05 | CT OF 87MTG1, 51MT (SNR-H03BAY01CE151) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) |  | xx | CT OF 87MTG1, 51MT (SNR-H03BAY01CE151) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T05 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T05 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T05 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T05 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T05 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้้ไขโดย หฟศ-ฟ. 17/6/67 | B2.6.2 | B2.6 | SNR-H03BAT10GT100-T05 | CT OF 87MTG1, 51MT (SNR-H03BAY01CE151) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) |  | xx | CT OF 87MTG1, 51MT (SNR-H03BAY01CE151) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAT10GT100-T05 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T05 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.6.3 | B2.6 | SNR-H03BAT10GT100-T04 | CT OF 51MTN (SNR-H03BAY01CE141) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) |  | xx | CT OF 51MTN (SNR-H03BAY01CE141) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T04 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T04 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T04 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T04 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T04 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้้ไขโดย หฟศ-ฟ. 17/6/67 | B2.6.4 | B2.6 | SNR-H03BAT10GT100-T04 | CT OF 51MTN (SNR-H03BAY01CE141) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) |  | xx | CT OF 51MTN (SNR-H03BAY01CE141) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAT10GT100-T04 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T04 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.6.5 | B2.6 | SNR-H03BAT10GT100-T03 | CT OF 87BB (SNR-H03BAY01CE131) 200016001500/5A, 5P20, 50VA (หทอฟ-ธ.) |  | xx | CT OF 87BB (SNR-H03BAY01CE131) 200016001500/5A, 5P20, 50VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T03 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T03 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T03 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T03 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T03 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 8/9/2024 | 8/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้้ไขโดย หฟศ-ฟ. 17/6/67 | B2.6.6 | B2.6 | SNR-H03BAT10GT100-T03 | CT OF 87BB (SNR-H03BAY01CE131) 200016001500/5A, 5P20, 50VA (หอตฟ-ธ.) |  | xx | CT OF 87BB (SNR-H03BAY01CE131) 200016001500/5A, 5P20, 50VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAT10GT100-T03 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T03 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.6.7 | B2.6 | SNR-H03BAT10GT100-T01 | CT OF 51MT (SNR-H03BAY01CE111) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) |  | xx | CT OF 51MT (SNR-H03BAY01CE111) 600500400/5A, 5P20, 50VA (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T01 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T01 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T01 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้้ไขโดย หฟศ-ฟ. 17/6/67 | B2.6.8 | B2.6 | SNR-H03BAT10GT100-T01 | CT OF 51MT (SNR-H03BAY01CE111) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) |  | xx | CT OF 51MT (SNR-H03BAY01CE111) 600500400/5A, 5P20, 50VA (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAT10GT100-T01 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T01 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.6.9 | B2.6 | SNR-H03BAT10GT100-T02 | CT OF 64REF SNR-H03BAY01CE121 (600500400/5A, 5P20, 50VA) (หทอฟ-ธ.) |  | xx | CT OF 64REF SNR-H03BAY01CE121 (600500400/5A, 5P20, 50VA) (หทอฟ-ธ.) | หทอฟ-ธ. | 2.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T02 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T02 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T02 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T02 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T02 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
แก้้ไขโดย หฟศ-ฟ. 17/6/67 | B2.6.10 | B2.6 | SNR-H03BAT10GT100-T02 | CT OF 64REF SNR-H03BAY01CE121 (600500400/5A, 5P20, 50VA) (หอตฟ-ธ.) |  | xx | CT OF 64REF SNR-H03BAY01CE121 (600500400/5A, 5P20, 50VA) (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAT10GT100-T02 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T02 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 9/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.7 | B2 | SNR-H03BAT10GT100-F01 | LIGHTNING ARRESTER MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) |  | xx | LIGHTNING ARRESTER MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) | หทอฟ-ธ. | 3 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.7.1 | B2.7 | SNR-H03BAT10GT100-F01 | LIGHTNING ARRESTOR MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) (หทอฟ-ธ.) |  | xx | LIGHTNING ARRESTOR MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) (หทอฟ-ธ.) | หทอฟ-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-F01 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-F01 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-F01 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-F01 |  | 40 | 40 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.7.2 | B2.7 | SNR-H03BAT10GT100-F01 | LIGHTNING ARRESTOR MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) (หมปฟ-ธ.) |  | xx | LIGHTNING ARRESTOR MAIN TRANS. 192 KV, 10 KA (SNR-H03BAU01GV001) (หมปฟ-ธ.) | หมปฟ-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100-F01 |  | 10 | 10 | VISUAL INSPECTION | หมปฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-F01 |  | 20 | 20 | CLEANING | หมปฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.8 | B2 | SNR-H03BAA10GS200-F04 | LIGHTNING ARRESTOR GEN. DS. 192 KV, 10KA (SNR-H03BA-C01GV001) |  | xx | LIGHTNING ARRESTOR DS.1311 192 KV, 10KA (SNR-H03BA-C01GV001) | หทอฟ-ธ.+หอตฟ-ธ. | 3 | 3/9/2024 | 3/9/2024 | [5 empty] | E
| B2.8.1 | B2.8 | SNR-H03BAA10GS200-F04 | LIGHTNING ARRESTOR GEN. DS. 192 KV, 10KA (SNR-H03BA-C01GV001) (หทอฟ-ธ.) |  | xx | LIGHTNING ARRESTOR DS.1311 192 KV, 10KA (SNR-H03BA-C01GV001) (หทอฟ-ธ.) | หทอฟ-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F04 |  | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-F04 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F04 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAA10GS200-F04 |  | 40 | 40 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.8.2 | B2.8 | SNR-H03BAA10GS200-F04 | LIGHTINING ARRESTOR GEN. DS. 192 KV, 10KA (SNR-H03BA-C01GV001) (หอตฟ-ธ.) |  | xx | LIGHTINING ARRESTOR DS.1311 192 KV, 10KA (SNR-H03BA-C01GV001) (หอตฟ-ธ.) | หอตฟ-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-F04 |  | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-F04 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.9 | B2 | SNR-H03BAA12GH100-Q01 | DS 57DB |  | xx | DS 57DB | หอตฟ-ธ. | 4 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03BAA12GH100-Q01 |  | 20 | 20 | VISUAL INSPECTION 1.CONTROL PANEL 2.MOVING CONTACT & ACCESSORIES 3.FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 40 | 40 | CLEANING 1. CONTROL PANEL 2. MOVING CONTACT & ACCESSORIES 3. FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 50 | 50 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 60 | 60 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 70 | 70 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA12GH100-Q01 |  | 80 | 80 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 4/9/2024 | 5/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.10 | B2 | SNR-H03BAA10GS200-Q01 | GENERATOR DISCONECTING SWITCHES (1331) |  | xx | GENERATOR DISCONECTING SWITCHES (1311) | หอตฟ-ธ. | 4 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 20 | 20 | VISUAL INSPECTION 1. CONTROL PANEL 2. MOVING CONTACT & ACCESSORIES 3. FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 40 | 40 | CLEANING 1. CONTROL PANEL 2. MOVING CONTACT & ACCESSORIES 3. FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 50 | 50 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 60 | 60 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 70 | 70 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03BAA10GS200-Q01 |  | 80 | 80 | OPERATION TEST | หอตฟ-ธ. | 0.5 | 6/9/2024 | 7/9/2024 |  |  |  | MSP0-E840 |  | E
| B2.11 | B2 | SNR-H03BAT10GT100 | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER |  | xx | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER | หฟศ-ฟ. | 16 | 3/9/2024 | 9/9/2024 |  |  |  | SNR-2E0 |  | E
| B2.11.1 | B2.11 | SNR-H03BAT10GT100 | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หขศ-ฟ.) |  | xx | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หขศ-ฟ.) | หขศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-3D0 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03BAT10GT100 |  | 10 | 10 | SCOFFOLD ASSEMBLY | หขศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 7 | SNR0-3D0 | PTW งานนั่งร้าน : ติดตั้งและแก้ไข, PTW งานนั่งร้าน : รื้อถอน | E
|  |  | SNR-H03BAT10GT100 |  | 20 | 20 | DISASSEMBLY SCAFFOLD | หขศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-3D0 |  | E
| B2.11.2 | B2.11 | SNR-H03BAT10GT100 | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หมปฟ-ธ.) |  | xx | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หมปฟ-ธ.) | หมปฟ-ธ. | 6 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100 |  | 10 | 10 | ISOLATE EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100 |  | 20 | 20 | VISUAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100 |  | 30 | 30 | CLEANING | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100 |  | 40 | 40 | FINAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.11.3 | B2.11 | SNR-H03BAT10GT100 | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หทอฟ-ธ.) |  | xx | 13.8/230 kV OIL IMMERSED TYPE TRANSFORMER (หทอฟ-ธ.) | หทอฟ-ธ. | 8 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100 |  | 20 | 20 | EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 30 | 30 | DC. RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 40 | 40 | TURN RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 50 | 50 | %IMPEDANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 60 | 60 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 70 | 70 | BUSHING MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 80 | 80 | DIELECTRIC BREAKDOWN VOLT. MEASUREMENT OF OIL | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.12 | B2 | SNR-H03BAT10GT100 | MAIN TRANSFORMER OFF-CIRCUIT TAP CHANGER (หทอฟ-ธ.) |  | xx | MAIN TRANSFORMER OFF-CIRCUIT TAP CHANGER (หทอฟ-ธ.) | หทอฟ-ธ. | 7 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 10 | 10 | OIL DIELECTRIC BREAKDOWN VOLTAGE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100 |  | 20 | 20 | OIL INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 30 | 30 | OIL DISSOLVED GAS ANALYSIS | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 40 | 40 | OIL MOISTURE CONTENT MEASUREMENT ( KARL ) | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 50 | 50 | CONTACT TRANSITION TIMING MEASUREMENT / POSITION TAP TEST | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 60 | 60 | CONTACT RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100 |  | 70 | 70 | COOLING FAN CHECK | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B2.13 | B2 | SNR-H00BBT10GT101 | STATION SERVICE TRANSFORMER |  | xx | STATION SERVICE TRANSFORMER | หมปฟ-ธ. | 13 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.13.1 | B2.13 | SNR-H00BBT10GT101 | STATION SERVICE TRANSFORMER (หมปฟ-ธ.) |  | xx | STATION SERVICE TRANSFORMER (หมปฟ-ธ.) | หมปฟ-ธ. | 5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BBT10GT101 |  | 10 | 10 | ISOLATE EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BBT10GT101 |  | 20 | 20 | VISUAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H00BBT10GT101 |  | 30 | 30 | CLEANING | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H00BBT10GT101 |  | 40 | 40 | FINAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H00BBT10GT101 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B2.13.2 | B2.13 | SNR-H00BBT10GT101 | STATION SERVICE TRANSFORMER (หทอฟ-ธ.) |  | xx | STATION SERVICE TRANSFORMER (หทอฟ-ธ.) | หทอฟ-ธ. | 8 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BBT10GT101 |  | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BBT10GT101 |  | 20 | 20 | EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 30 | 30 | DC. RESISTANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 40 | 40 | TURN RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 50 | 50 | %IMPEDANCE MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 60 | 60 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 70 | 70 | BUSHING MEASUREMENT | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H00BBT10GT101 |  | 80 | 80 | DIELECTRIC BREAKDOWN VOLT. MEASUREMENT OF OIL | หทอฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
เพิ่มเติมโดย หฟศ-ฟ. 17/6/67 | B2.14 | B2 | SNR-H03BAT10GT100 | 13.8/230KV.Generator Transformer KG3A |  | xx | 13.8/230KV.Generator Transformer KG3A | หทอฟ-ธ. | 2.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T01 | GEN. TRANS. CT1 | 10 | 10 | BUSHING MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03BAT10GT100-T02 | GEN. TRANS. CT2 | [10 empty] | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T03 | GEN. TRANS. CT3 | [10 empty] | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T04 | GEN. TRANS. CT4 | [10 empty] | MSP0-EA30 |  | E
|  |  | SNR-H03BAT10GT100-T05 | GEN. TRANS. CT5 | [10 empty] | MSP0-EA30 |  | E
| B2.15 | B2 | SNR-H03BAT10GT100 | INTRUMENT (MAIN TRANSFORMER KG3A) |  | xx | INTRUMENT (MAIN TRANSFORMER KG3A) | หมปฟ-ธ. | 21 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100-B01 | HV SIDE WINDING TEMP | 10 | 10 | DISASSEMBLY & REMOVE | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานทั่วไป | E
|  |  | SNR-H03BAT10GT100-B02 | LV SIDE WINDING TEMP | 20 | 20 | ELECTRICAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03BAT10GT100-B03 | OIL TEMP | 30 | 30 | CLEANING | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
[5 empty] | 40 | 40 | TESTING FOR ASFOUND | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
[5 empty] | 50 | 50 | CURRENT FEEDING TEST FOR HEATING COIL | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
[5 empty] | 60 | 60 | CALIBRATION FOR SETTING VALUE | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
[5 empty] | 70 | 70 | ASSEMBLY | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B4 | B | SNR-H03C | PROTECTION SYSTEM |  | xx | PROTECTION SYSTEM | หรวฟ-ธ. | 34 | 3/9/2024 | 9/9/2024 | [5 empty] | E
| B4.1 | B4 | SNR-H03CHA10GH100 | GENERATOR PROTECTION-1 - SYSTEM A / GENERATOR PROTECTION-1 - SYSTEM B | 10 | 10 | ISOLATE EQUIPMENT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CHA10GH100 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH100 |  | 40 | 40 | OPERAT. CHAR. TEST GEN.DIFFERENTIAL PHASE A, B, C(87G) GENERATOR OVER CURRENT PROTECTION(50/51G) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 50 | 50 | OPERAT. CHAR. TEST STATOR EARTH FAULT PROTECTION (64G 100%) STATOR EARTH FAULT PROTECTION (64G 95%) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH100 |  | 60 | 60 | OPERAT. CHAR. TEST BALANCE VOLT.(60P) LOSS OF EXCITE PROTECTION(40) REVERSE POWER PROTECTION(32) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 70 | 70 | OPERAT. CHAR. TEST GEN. UNDER VOLTAGE (27) GEN. OVER VOLTAGE (59) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH100 |  | 80 | 80 | OPERAT. CHAR. TEST GEN. NEG. PHASE SEQ.(46) OVER CURRENT PROTECTION FOR DYNAMIC BRAKING (50/51BK) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 90 | 90 | OPERAT. CHAR. TEST ROTOR EARTH FAULT (64E) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 100 | 100 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 110 | 110 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 120 | 120 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 130 | 130 | FUNCTION TEST | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH100 |  | 140 | 140 | INSPECTION REPORT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.2 | B4 | SNR-H03CHA10GH200 | GENERATOR PROTECTION-2- SYSTEM A / GENERATOR PROTECTION-2 - SYSTEM B | 10 | 10 | ISOLATE EQUIPMENT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CHA10GH200 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH200 |  | 40 | 40 | OPERAT. CHAR. TEST GEN.DIFFERENTIAL PHASE A, B, C(87G) GENERATOR OVER CURRENT PROTECTION(50/51G) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 50 | 50 | OPERAT. CHAR. TEST STATOR EARTH FAULT PROTECTION (64G 100%) STATOR EARTH FAULT PROTECTION (64G 95%) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH200 |  | 60 | 60 | OPERAT. CHAR. TEST BALANCE VOLT.(60P) LOSS OF EXCITE PROTECTION(40) REVERSE POWER PROTECTION(32) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 70 | 70 | OPERAT. CHAR. TEST GEN. UNDER VOLTAGE (27) GEN. OVER VOLTAGE (59) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10GH200 |  | 80 | 80 | OPERAT. CHAR. TEST GEN. NEG. PHASE SEQ.(46) OVER CURRENT PROTECTION FOR DYNAMIC BRAKING(50/51BK) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 90 | 90 | OPERAT. CHAR. TEST ROTOR EARTH FAULT (64E) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 100 | 100 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 110 | 110 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 120 | 120 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 130 | 130 | FUNCTION TEST | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10GH200 |  | 140 | 140 | INSPECTION REPORT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.3 | B4 | SNR-H03CHA10 | MAIN TRANSFORMER PROTECTION -SYSTEM A / MAIN TRANSFORMER PROTECTION -SYSTEM B | 10 | 10 | ISOLATE EQUIPMENT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CHA10 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขโดย หฟศ-ฟ. แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10 |  | 40 | 40 | OPERAT.CHAR.TEST MAIN TRANS.THERMAL PROT(49MT) MAIN TRANS.OVER CURRENT PROT AND EDIT PARA(51MT) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10 |  | 50 | 50 | OPERAT.CHAR.TEST MAIN TRANS.DIFF.PROTECTION(87MTG3) MAIN TRANS.RESTRICTED EARTH FAULT RELAY(64REF) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03CHA10 |  | 60 | 60 | OPERAT.CHAR.TEST MAIN TRANS. NEUTRAL OVER CURRENT PROTECTION(51MTN) BREAKER FAIL PROTECTION (50BF) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 70 | 70 | OPERATING CHARECTERISTIC TEST MAIN TRANSFORMER OVER FLUX PROTECTION (24MT) VT SUPERVISION (60P) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 80 | 80 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 90 | 90 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 100 | 100 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 110 | 110 | FUNCTION TEST | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CHA10 |  | 120 | 120 | INSPECTION REPORT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.4 | B4 | SNR-H00BBT10GT101 | STATION SERVICE TRANSFORMER PROTECTION F111 | 10 | 10 | ISOLATE EQUIPMENT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BBT10GT101 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 40 | 40 | OPERATING CHARECTERISTIC TEST - DIFFERENTIAL RELAY (87ST1) - OVERCURRENT RELAY (87ST1) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 50 | 50 | OPERATING CHARECTERISTIC TEST - GROUND OVERCURRENT RELAY (51STN1) - UNDERVOLTAGE RELAY (27ST1) | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 60 | 60 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 70 | 70 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 80 | 80 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 90 | 90 | FUNCTION TEST | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H00BBT10GT101 |  | 100 | 100 | INSPECTION REPORT | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.5 | B4 | SNR-H03CWF10GK100 | TRANSDUCER (VOLT., AMP., WATT) |  | xx | TRANSDUCER (VOLT., AMP., WATT) | หรวฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 10 | 10 | ISOLATE & DIASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF10GK100 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 40 | 40 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 60 | 60 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.6 | B4 | SNR-H03CWF10GK100 | INDICATION METER (WATT, VAR., VOLT., AMP., BALANCE, SPEED, FREQ.) |  | xx | INDICATION METER (WATT, VAR., VOLT., AMP., BALANCE, SPEED, FREQ.) | หรวฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 10 | 10 | ISOLATE & DIASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF10GK100 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 40 | 40 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 60 | 60 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
| B4.7 | B4 | SNR-H03CWF10GK100 | ENERGY METER (ACTIVE POWER GEN./PUMP) |  | xx | ENERGY METER (ACTIVE POWER GEN./PUMP) | หรวฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 10 | 10 | ISOLATE & DIASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E240 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF10GK100 |  | 20 | 20 | VISUAL INSPECTION | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 30 | 30 | CLEANING | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 40 | 40 | TESTING FOR ASFOUND | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 50 | 50 | CALIBRATE FOR SETTING VALUE | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
|  |  | SNR-H03CWF10GK100 |  | 60 | 60 | ASSEMBLY | หรวฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E240 |  | E
แก้ไขตาม MMS 7/8/67 | B5 | B | SNR-H03MEY10GH100 | GOV. ELECTRICAL CONTROL (SUPPLY MODULE, SENSOR/DETECTOR/FEEDBACK EQUIP, ACTUATOR, AUX/PROTECTION) |  | xx | GOV. ELECTRICAL CONTROL (SUPPLY MODULE, SENSOR/DETECTOR/FEEDBACK EQUIP, ACTUATOR, AUX/PROTECTION) | หคมก-ธ. | 70 | 3/9/2024 | 12/9/2024 | [5 empty] | E
แก้ไข Worklist 11/6/67 |  |  | SNR-H03MEY10GH100 |  | 10 | 10 | VISUAL INSPECTION | หคมก-ธ. | 7 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E920 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MEY10GH100 |  | 20 | 20 | CLEANING ALL COMPONENTS | หคมก-ธ. | 7 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E920 |  | E
|  |  | SNR-H03MEY10GH100 |  | 30 | 30 | CHARACTERISTIC TEST (STATIC TEST) | หคมก-ธ. | 14 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E920 |  | E
|  |  | SNR-H03MEY10GH100 |  | 40 | 40 | SOFT WARE TEST (DIGITAL) | หคมก-ธ. | 14 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E920 |  | E
|  |  | SNR-H03MEY10GH100 |  | 50 | 50 | ADJUSTMENT FOR SETTING VALUE | หคมก-ธ. | 7 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E920 |  | E
|  |  | SNR-H03MEY10GH100 |  | 60 | 60 | DRY TEST WITH MECHANICAL EQUIPMENT (OVER TEST) | หคมก-ธ. | 7 | 10/9/2024 | 10/9/2024 |  |  |  | MSP0-E920 |  | E
|  |  | SNR-H03MEY10GH100 |  | 70 | 70 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หคมก-ธ. | 14 | 11/9/2024 | 12/9/2024 |  |  |  | MSP0-E920 |  | E
| B6 | B | SNR-H03MKC | AUTOMATIC VOLTAGE REGULATOR |  | xx | AUTOMATIC VOLTAGE REGULATOR | หรคฟ-ธ. | 104 | 3/9/2024 | 9/9/2024 | [5 empty] | E
แก้ไขตาม MMS 7/8/67 | B6.1 | B6 | SNR-H03MKC10GH100 | EXCITATION SYSTEM CUBICLE (HIPASECS330, SUPPLY MODULE, SENSOR / DETECTOR EQUIP, AUX/PROTECTION) |  | xx | EXCITATION SYSTEM CUBICLE (HIPASECS330, SUPPLY MODULE, SENSOR / DETECTOR EQUIP, AUX/PROTECTION) | หรคฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 10 | 10 | VISUAL INSPECTION | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E250 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC10GH100 |  | 20 | 20 | CLEANING | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 30 | 30 | THYRISTOR CHECK (LEAKAGE & OUTPUT TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 40 | 40 | CHARACTERISTIC TEST (STATIC TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 50 | 50 | SOFT WARE TEST (DIGITAL) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 60 | 60 | ADJUSTMENT FOR SETTING VALUE | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 70 | 70 | OVER ALL TEST (DRY TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH100 |  | 80 | 80 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หรคฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
| B6.2 | B6 | SNR-H03MKC10GH200 | RECTIFIER 1 CUBICLE |  | xx | RECTIFIER 1 CUBICLE | หรคฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 10 | 10 | VISUAL INSPECTION | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E250 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC10GH200 |  | 20 | 20 | CLEANING | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 30 | 30 | THYRISTOR CHECK (LEAKAGE & OUTPUT TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 40 | 40 | CHARACTERISTIC TEST (STATIC TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 50 | 50 | SOFT WARE TEST (DIGITAL) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 60 | 60 | ADJUSTMENT FOR SETTING VALUE | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 70 | 70 | OVER ALL TEST (DRY TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH200 |  | 80 | 80 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หรคฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
| B6.3 | B6 | SNR-H03MKC10GH300 | RECTIFIER 2 CUBICLE |  | xx | RECTIFIER 2 CUBICLE | หรคฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 10 | 10 | VISUAL INSPECTION | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E250 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC10GH300 |  | 20 | 20 | CLEANING | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 30 | 30 | THYRISTOR CHECK (LEAKAGE & OUTPUT TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 40 | 40 | CHARACTERISTIC TEST (STATIC TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 50 | 50 | SOFT WARE TEST (DIGITAL) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 60 | 60 | ADJUSTMENT FOR SETTING VALUE | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 70 | 70 | OVER ALL TEST (DRY TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC10GH300 |  | 80 | 80 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หรคฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
| B6.4 | B6 | SNR-H03MKC10GH500-Q01 | DC. MAIN FIELD SW.41 |  | xx | DC. MAIN FIELD SW.41 | หอตฟ-ธ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH500-Q01 |  | 20 | 20 | VISUAL INSPECTION 1.MOVING CONTACT&ACCESSORIES 2.FIXED CONTACT&ACCESSORIES 3.INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH500-Q01 |  | 30 | 30 | CLEANING 1.MOVING CONTACT & ACCESSORIES 2.FIXED CONTACT & ACCESSORIES 3.INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 40 | 40 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 50 | 50 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 60 | 60 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 70 | 70 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH500-Q01 |  | 80 | 80 | OPERATION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.5 | B6 | SNR-H03MKC10GH400-Q01 | FILED FLASHING SW. 31 |  | xx | DC. FILED FLASHING SW. 31 | หอตฟ-ธ. | 4 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH400-Q01 |  | 20 | 20 | VISUAL INSPECTION 1.MOVING CONTACT&ACCESSORIES 2.FIXED CONTACT&ACCESSORIES 3.INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH400-Q01 |  | 30 | 30 | CLEANING 1.MOVING CONTACT & ACCESSORIES 2.FIXED CONTACT & ACCESSORIES 3.INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 40 | 40 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 50 | 50 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 60 | 60 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 70 | 70 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH400-Q01 |  | 80 | 80 | OPERATION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.6 | B6 | SNR-H03MKC10GH200-Q01 | EXCITE BREAKER from AUX. SUPPLY EXCITE (41A) |  | xx | EXCITE BREAKER from AUX. SUPPLY EXCITE (41A) | หอตฟ-ธ. | 4.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH200-Q01 |  | 20 | 20 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 40 | 40 | LOOSEN PARTS | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. ALL PARTS ESPECIALLY PORCELAIN COLUMNS 3. INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 60 | 60 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH200-Q01 |  | 90 | 90 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.7 | B6 | SNR-H03MKC10GH300-Q01 | EXCITE BREAKER for BACK to BACK START (41S) |  | xx | EXCITE BREAKER for BACK to BACK START (41S) | หอตฟ-ธ. | 4.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03MKC10GH300-Q01 |  | 20 | 20 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 40 | 40 | LOOSEN PARTS | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. ALL PARTS ESPECIALLY PORCELAIN COLUMNS 3. INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 60 | 60 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC10GH300-Q01 |  | 90 | 90 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.8 | B6 | SNR-H03MKC30 | DYNAMIC BRAKE CUBICLE |  | xx | DYNAMIC BRAKE CUBICLE | หรคฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 10 | 10 | INSPECTION & CLEAN 1. HIPASECS330 2. SUPPLY MODULE 3. SENSOR / DETECTOR EQUIPMENT 4. RECTIFIER | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E250 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC30 |  | 20 | 20 | PROTECTION TEST | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 30 | 30 | THYRISTOR CHECK (LEAKAGE & OUTPUT TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 40 | 40 | CHARACTERISTIC TEST (STATIC TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 50 | 50 | SOFT WARE TEST (DIGITAL) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 60 | 60 | ADJUSTMENT FOR SETTING VALUE | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 70 | 70 | OVER ALL TEST (DRY TEST) | หรคฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03MKC30 |  | 80 | 80 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หรคฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
| B6.9 | B6 | SNR-H03MKC30GH400-Q01 | DYNAMIC BRAKE BREAKER (41DB) |  | xx | DYNAMIC BRAKE BREAKER (41DB) | หอตฟ-ธ. | 4.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 20 | 20 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 40 | 40 | LOOSEN PARTS | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. ALL PARTS ESPECIALLY PORCELAIN COLUMNS 3. INTERRUPTING MODULE | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 60 | 60 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03MKC30GH400-Q01 |  | 90 | 90 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.10 | B6 | SNR-H03MKC20DX102 | SLIP RING AND BRUSH HOLDER |  | xx | SLIP RING AND BRUSH HOLDER | หกฟ-ธ. | 15 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B6.10.1 | B6.10 | SNR-H03MKC20DX102 | SLIP RING AND BRUSH HOLDER (หกฟ-ธ.) | 10 | 10 | DISCONNECT WIRING OR CABLE OR BUS | หกฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E220 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC20DX102 |  | 20 | 20 | VISUAL INSPECTION | หกฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 30 | 30 | CLEANING | หกฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 40 | 40 | RECONDITION | หกฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 50 | 50 | PREADJUSTMENT | หกฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 60 | 60 | CHECK BRUSH HOLDER PRESSURE | หกฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 70 | 70 | CONNECT WIRING OR CABLE OR BUS | หกฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
|  |  | SNR-H03MKC20DX102 |  | 80 | 80 | FINAL INSPECTION & FINAL WORK | หกฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E220 |  | E
| B6.10.2 | B6.10 | SNR-H03MKC20DX102 | SLIP RING AND BRUSH HOLDER (หทอฟ-ธ.) | 10 | 10 | INSULATION RESISTANCE TEST 1 (PRETEST) | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 |  | E
|  |  | SNR-H03MKC20DX102 |  | 20 | 20 | INSULATION RESISTANCE TEST 2 (FINAL TEST) | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.11 | B6 | SNR-H03MKC12GT100 | EXCITATION CURRENT TRANSFORMER |  | xx | EXCITATION CURRENT TRANSFORMER | หทอฟ-ธ. | 10.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.11.1 | B6.11 | SNR-H03MKC12GT100-T02 | CT OF 87ET, 50 ET (SNR-H03MK-C01CE111) 100/5A, 5P20, 40VA (หทอฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T02 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T02 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T02 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T02 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.11.2 | B6.11 | SNR-H03MKC12GT100-T02 | CT OF 87ET, 50 ET (SNR-H03MK-C01CE111) 100/5A, 5P20, 40VA (หอตฟ-ธ.) | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T02 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.11.3 | B6.11 | SNR-H03MKC12GT100-T03 | CT OF 87MTG1 (SNR-H03MK-C01CE121) 100/5A, 5P20, 40VA (หทอฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T03 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T03 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T03 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T03 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.11.4 | B6.11 | SNR-H03MKC12GT100-T03 | CT OF 87MTG1 (SNR-H03MK-C01CE121) 100/5A, 5P20, 40VA (หอตฟ-ธ.) | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T03 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.11.5 | B6.11 | SNR-H03MKC12GT100-T04 | CT OF 87ET (SNR-H03MK-C01CE131) 1500/5A, 5P20, 10VA (หทอฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T04 |  | 20 | 20 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T04 |  | 30 | 30 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T04 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T04 |  | 50 | 50 | ASSEMBLY EQUIPMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.11.6 | B6.11 | SNR-H03MKC12GT100-T04 | CT OF 87ET (SNR-H03MK-C01CE131) 1500/5A, 5P20, 10VA (หอตฟ-ธ.) | 10 | 10 | VISUAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T04 |  | 20 | 20 | CLEANING | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B6.12 | B6 | SNR-H03MKC12GT100-T01 | EXCITATION TRANSFORMER EXTR. |  | xx | EXCITATION TRANSFORMER EXTR. | หมปฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B6.12.1 | B6.12 | SNR-H03MKC12GT100-T01 | EXCITATION TRANSFORMER EXTR. (หมปฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T01 |  | 20 | 20 | VISUAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 30 | 30 | CLEANING | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 40 | 40 | RTD INSTRUMENT TEST & CALIBRATION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 50 | 50 | FINAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 60 | 60 | ASSEMBLY EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B6.12.2 | B6.12 | SNR-H03MKC12GT100-T01 | EXCITATION TRANSFORMER EXTR. (หทอฟ-ธ.) | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC12GT100-T01 |  | 20 | 20 | EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 30 | 30 | DC. RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 50 | 50 | % IMPEDANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC12GT100-T01 |  | 60 | 60 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.13 | B6 | SNR-H03MKC30GH500 | DYNAMIC BRAKE TRANSFORMER |  | xx | DYNAMIC BRAKE TRANSFORMER | หมปฟ-ธ. | 9 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B6.13.1 | B6.13 | SNR-H03MKC30GH500 | DYNAMIC BRAKE TRANSFORMER (หมปฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E830 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC30GH500 |  | 20 | 20 | VISUAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC30GH500 |  | 30 | 30 | CLEANING | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC30GH500 |  | 40 | 40 | RTD INSTRUMENT TEST & CALIBRATION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC30GH500 |  | 50 | 50 | FINAL INSPECTION | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
|  |  | SNR-H03MKC30GH500 |  | 60 | 60 | ASSEMBLY EQUIPMENT | หมปฟ-ธ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E830 |  | E
| B6.13.2 | B6.13 | SNR-H03MKC30GH500 | DYNAMIC BRAKE TRANSFORMER (หทอฟ-ธ.) | 10 | 10 | INSULATION RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-EA30 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03MKC30GH500 |  | 20 | 20 | EXCITING CURRENT MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC30GH500 |  | 30 | 30 | DC. RESISTANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC30GH500 |  | 40 | 40 | RATIO & POLARITY MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC30GH500 |  | 50 | 50 | % IMPEDANCE MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
|  |  | SNR-H03MKC30GH500 |  | 60 | 60 | INSULATION POWER FACTOR MEASUREMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-EA30 |  | E
| B6.14 | B6 | SNR-H03MKC20CT001 | INSTRUMENT (SLIP RING COVER AREA TEMP. MKA05CT001) |  | xx | INSTRUMENT (SLIP RING COVER AREA TEMP. MKA05CT001) | หฟศ-ฟ. | 3.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKC20CT001 |  | 10 | 10 | DISASSEMBLY & REMOVE | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานทั่วไป | E
|  |  | SNR-H03MKC20CT001 |  | 20 | 20 | VISUAL INSPECTION | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKC20CT001 |  | 30 | 30 | RESISTANCE / TEMP. TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKC20CT001 |  | 40 | 40 | CONNECTION TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKC20CT001 |  | 50 | 50 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติม 15/7/67 |  |  | SNR-H03MKC20CT001 |  | 60 | 60 | LOOP TEST | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03MKC20CT001 |  | 70 | 70 | INSPECTION REPORT | หฟศ-ฟ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B7 | B | SNR-H03CWF10GK100-F01 | AUTOMATIC SYNCHRONIZER |  | xx | AUTOMATIC SYNCHRONIZER | หรคฟ-ธ. | 14 | 2024-09-04 | 2024-09-12 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03CWF10GK100-F01 |  | 10 | 10 | VISUAL INSPECTION | หรคฟ-ธ. | 1 | 4/9/2024 | 9/9/2024 |  | 1 | 1 | MSP0-E250 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF10GK100-F01 |  | 20 | 20 | CLEANING | หรคฟ-ธ. | 1 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03CWF10GK100-F01 |  | 30 | 30 | CHARACTERISTIC TEST (STATIC TEST) SPEED MATCHING VOLTAGE MATCHING SYNCHRONIZING COMMAND | หรคฟ-ธ. | 2 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03CWF10GK100-F01 |  | 40 | 40 | SOFT WARE TEST (DIGITAL TYPE) | หรคฟ-ธ. | 2 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03CWF10GK100-F01 |  | 50 | 50 | ADJUSTMENT FOR SETTING VALUE | หรคฟ-ธ. | 1 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E250 |  | E
|  |  | SNR-H03CWF10GK100-F01 |  | 60 | 60 | START UP, OPERATION TEST AND FINE TUNNING (DYNAMIC TEST) | หรคฟ-ธ. | 7 | 11/9/2024 | 12/9/2024 |  |  |  | MSP0-E250 |  | E
| B8 | B | SNR-H03ADA23GS100 | 230 KV. CIRCUIT BREAKER & DISCONNECTING SWITCH |  | xx | 230 KV. CIRCUIT BREAKER & DISCONNECTING SWITCH | อบฟ. | 35.5 | 2024-09-03 | 2024-09-09 | [5 empty] | E
| B8.1 | B8 | SNR-H03ADA23GS100 | BKR. 80032 |  | xx | BKR. 80032 | หอตฟ-ธ. | 15 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B8.1.1 | B8.1 | SNR-H03ADA23GS100 | BKR. 80032 (หอตฟ-ธ.) | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03ADA23GS100 |  | 20 | 20 | VISUAL INSPECTION 1. CONTROL PANEL 2. ALL PART ESPECIALLY PORCELAIN COLUMNS | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 40 | 40 | LOOSEN PART | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. ALL PART ESPECIALLY PORCELAIN COLUMNS | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 60 | 60 | ELECTRICAL TEST 3. GAS PERCENTAGE MEASURMENT 4. GAS DEW POINT MEASUREMENT | หอตฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 70 | 70 | ELECTRICAL TEST 5. CONTACT RESISTANCE MEASUREMENT 6. TIMING MEASUREMENT ( CLOSING / TRIPPING ) | หอตฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 80 | 80 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 90 | 90 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS100 |  | 100 | 100 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B8.1.2 | B8.1 | SNR-H03ADA23GS100 | BKR. 80032 (หทอฟ-ธ.) | 10 | 10 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. INSULATION POWER FACTOR MEASURMENT | หทอฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 | B8.2 | B8 | SNR-H03ADA23GS201 | DS 80036 | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 9.5 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03ADA23GS201 |  | 20 | 20 | VISUAL INSPECTION 1.CONTROL PANEL 2.MOVING CONTACT & ACCESSORIES 3.FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 40 | 40 | LOOSEN PART | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. MOVING CONTACT & ACCESSORIES 3. FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 60 | 60 | ELECTRICAL TEST 1. ISULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 90 | 90 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B8.3 | B8 | SNR-H03ADA23GS201 | DS 80037 | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 11 | 3/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 |  |  | SNR-H03ADA23GS201 |  | 20 | 20 | VISUAL INSPECTION 1.CONTROL PANEL 2.MOVING CONTACT & ACCESSORIES 3.FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 40 | 40 | LOOSEN PART | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 50 | 50 | CLEANING 1. CONTROL PANEL 2. MOVING CONTACT & ACCESSORIES 3. FIXED CONTACT & ACCESSORIES | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 60 | 60 | ELECTRICAL TEST 1. ISULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H03ADA23GS201 |  | 90 | 90 | OPERATION FUNCTION TEST | หอตฟ-ธ. | 2 | 3/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B9 | B | SNR-H00BFA | ACB1-8 |  | xx | ACB1-8 | หอตฟ-ธ. | 4.5 | 2024-09-04 | 2024-09-09 | [5 empty] | E
| B9.1 | B9 | SNR-H00BFA10 | ACB-6 |  | xx | ACB-6 | หอตฟ-ธ. | 4.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 10 | 10 | ISOLATE EQUIPMENT | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  | 2 | 2 | MSP0-E840 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BFA10 |  | 20 | 20 | VISUAL INSPECTION & CLEANING | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 30 | 30 | OPERATING MECHANISM INSPECTION & LUB. | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 40 | 40 | LOOSEN PARTS | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 50 | 50 | CLEANING | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 60 | 60 | ELECTRICAL TEST 1. INSULATION RESISTANCE MEASUREMENT 2. CONTACT RESISTANCE MEASUREMENT | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 70 | 70 | ASSEMBLY | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 80 | 80 | FINAL INSPECTION | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
|  |  | SNR-H00BFA10 |  | 90 | 90 | OPERATION TEST | หอตฟ-ธ. | 0.5 | 4/9/2024 | 9/9/2024 |  |  |  | MSP0-E840 |  | E
| B10 | B | SNR-H03SGJ | FIRE PROTECTION |  | xx | FIRE PROTECTION | หฟศ-ฟ. | 107 | 2024-09-03 | 2024-09-09 | [5 empty] | E
| B10.1 | B10 | SNR-H03SGJ30 | MAIN TRANSFORMER |  | xx | MAIN TRANSFORMER | หฟศ-ฟ. | 12 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B10.1.1 | B10.1 | SNR-H03SGJ30EG001 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.1 | 10 | 10 | INSPECTION & CLEANING | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B10.1.2 | B10.1 | SNR-H03SGJ30EG002 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.2 | 20 | 20 | TESTING FOR ASFOUND | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B10.1.3 | B10.1 | SNR-H03SGJ30EG003 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.3 | [12 empty] | E
| B10.1.4 | B10.1 | SNR-H03SGJ30EG004 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.4 | [12 empty] | E
| B10.1.5 | B10.1 | SNR-H03SGJ30EG005 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.5 | [12 empty] | E
| B10.1.6 | B10.1 | SNR-H03SGJ30EG006 | MAIN TRANSFORMER TEMP HEAT DECTECTOR NO.6 | [12 empty] | E
เพิ่มเติมโดย หฟศ-ฟ. 17/6/67 | B10.2 | B10 | SNR-H03SGJ10 | GENERATOR |  | xx | GENERATOR | หฟศ-ฟ. | 20 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B10.2.1 | B10.2 | SNR-H03SGJ10EG001 | SMOKE DECTECTOR NO.1 | 10 | 10 | TESTING FOR ASFOUND | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B10.2.2 | B10.2 | SNR-H03SGJ10EG002 | SMOKE DECTECTOR NO.2 | 20 | 20 | INSTALL & ASSEMBLY | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B10.2.3 | B10.2 | SNR-H03SGJ10EG003 | SMOKE DECTECTOR NO.3 | [12 empty] | E
| B10.2.4 | B10.2 | SNR-H03SGJ10EG004 | SMOKE DECTECTOR NO.4 | [12 empty] | E
| B10.2.5 | B10.2 | SNR-H03SGJ10EG005 | GENERATOR TEMP HEAT DECTECTOR NO.1 | [12 empty] | E
| B10.2.6 | B10.2 | SNR-H03SGJ10EG006 | GENERATOR TEMP HEAT DECTECTOR NO.2 | [12 empty] | E
| B10.2.7 | B10.2 | SNR-H03SGJ10EG007 | GENERATOR TEMP HEAT DECTECTOR NO.3 | [12 empty] | E
| B10.2.8 | B10.2 | SNR-H03SGJ10EG008 | GENERATOR TEMP HEAT DECTECTOR NO.4 | [12 empty] | E
| B10.2.9 | B10.2 | SNR-H03SGJ10EG009 | GENERATOR TEMP HEAT DECTECTOR NO.5 | [12 empty] | E
| B10.2.10 | B10.2 | SNR-H03SGJ10EG010 | GENERATOR TEMP HEAT DECTECTOR NO.6 | [12 empty] | E
| B10.3 | B10 | SNR-H13SGJ10 | CO2 FIRE FIGHTING UNIT |  | xx | CO2 FIRE FIGHTING UNIT | หฟศ-ฟ. | 72 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B10.3.1 | B10.3 | SNR-H13SGJ10BB001KD01 | CO2 TANK NO.1 | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
แก้ไขตาม MMS 7/8/67 | B10.3.2 | B10.3 | SNR-H13SGJ10BB001KD02 | CO2 TANK NO.2 | 20 | 20 | CLEANING | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B10.3.3 | B10.3 | SNR-H13SGJ10BB001KD03 | CO2 TANK NO.3 | 30 | 30 | TEST & CALIBRATE INSTRUMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B10.3.4 | B10.3 | SNR-H13SGJ10BB001KD04 | CO2 TANK NO.4 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.5 | B10.3 | SNR-H13SGJ10BB001KD05 | CO2 TANK NO.5 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.6 | B10.3 | SNR-H13SGJ10BB001KD06 | CO2 TANK NO.6 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.7 | B10.3 | SNR-H13SGJ10BB001KD07 | CO2 TANK NO.7 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.8 | B10.3 | SNR-H13SGJ10BB001KD08 | CO2 TANK NO.8 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.9 | B10.3 | SNR-H13SGJ10BB001KD09 | CO2 TANK NO.9 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.10 | B10.3 | SNR-H13SGJ10BB001KD10 | CO2 TANK NO.10 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.11 | B10.3 | SNR-H13SGJ10BB001KD11 | CO2 TANK NO.11 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.12 | B10.3 | SNR-H13SGJ10BB001KD12 | CO2 TANK NO.12 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.13 | B10.3 | SNR-H13SGJ10BB001KD13 | CO2 TANK NO.13 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.14 | B10.3 | SNR-H13SGJ10BB001KD14 | CO2 TANK NO.14 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.15 | B10.3 | SNR-H13SGJ10BB001KD15 | CO2 TANK NO.15 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.16 | B10.3 | SNR-H13SGJ10BB001KD16 | CO2 TANK NO.16 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.17 | B10.3 | SNR-H13SGJ10BB001KD17 | CO2 TANK NO.17 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.18 | B10.3 | SNR-H13SGJ10BB001KD18 | CO2 TANK NO.18 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.19 | B10.3 | SNR-H13SGJ10BB001KD19 | CO2 TANK NO.19 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.20 | B10.3 | SNR-H13SGJ10BB001KD20 | CO2 TANK NO.20 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.21 | B10.3 | SNR-H13SGJ10BB001KD21 | CO2 TANK NO.21 | [12 empty] | E
แก้ไขตาม MMS 7/8/67 | B10.3.22 | B10.3 | SNR-H13SGJ10BB001KD22 | CO2 TANK NO.22 | [12 empty] | E
| B10.3.23 | B10.3 | SNR-H13SGJ10EG001 | ADDRESSABLE SMOKE DETECTOR SD1,2,3,4 | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B10.3.24 | B10.3 | SNR-H13SGJ10EG002 | FENWALL HEAT DETECTOR X4UD HD1001/4 | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B10.3.25 | B10.3 | SNR-H13SGJ10EG003 | FENWALL HEAT DETECTOR X4UD HD1005/8 | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 2 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B10.4 | B10 | SNR-H13SGY10EG100 | CO2 PNL. UNIT 1-3 CONTROL PANEL |  | xx | CO2 PNL. UNIT 1-3 CONTROL PANEL | หฟศ-ฟ. | 3 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H13SGY10EG100 |  | 10 | 10 | VISUAL INSPECTION | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 2 | 4 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H13SGY10EG100 |  | 20 | 20 | CLEANING | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H13SGY10EG100 |  | 30 | 30 | TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11 | B | SNR-H03CJA10 | UNIT CONTROL FUNCTION AND SEQUENCE TEST |  | xx | UNIT CONTROL FUNCTION AND SEQUENCE TEST | หฟศ-ฟ. | 116 | 2024-09-03 | 2024-09-12 | [5 empty] | E
| B11.1 | B11 | SNR-H03CJA10 | UNIT CONTROL FUNCTION AND SEQUENCE TEST (หฟศ-ฟ.) | 10 | 10 | AUX. EQUIPMENT FUNCTION TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CJA10 |  | 20 | 20 | AUX. EQUIPMENT OPERATION TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 30 | 30 | CONTROL EQUIPMENT + SIMULATE TEST 1. ANNUNCIATOR 2. PROTECTION | หฟศ-ฟ. | 28 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 40 | 40 | INTERFACING CIRCUIT CHECK | หฟศ-ฟ. | 14 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 50 | 50 | OVERALL SEQUENCE TEST | หฟศ-ฟ. | 3 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 60 | 60 | CLARIFY CONTROL SYSTEM AND PROTECTION EQUIPMENT | หฟศ-ฟ. | 3 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 70 | 70 | TEST PROCEDURE BEFORE UNIT START UP | หฟศ-ฟ. | 7 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10 |  | 80 | 80 | UNIT START UP AND PERFORMANCE TEST | หฟศ-ฟ. | 7 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.2 | B11 | SNR-H03CJA10GH001 | OPC SERVER/CLIENT | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CJA10GH001 |  | 20 | 20 | NETWORK INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.3 | B11 | SNR-H03CJA10GH001 | SEQUENCE OF EVENT SERVER | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CJA10GH001 |  | 20 | 20 | NETWORK INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.4 | B11 | SNR-H03CJA10GH001 | ENGINEERING WORK STATION (EWS) | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CJA10GH001 |  | 20 | 20 | NETWORK INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติมโดย หฟศ-ฟ. 17/6/67 |  |  | SNR-H03CJA10GH001 |  | 30 | 30 | BACKUP PROJECT | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.5 | B11 | SNR-H03CWF20 | EXECUTIVE INFORMATION SYSTEM (EIS) | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF20 |  | 20 | 20 | NETWORK INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.6 | B11 | SNR-H03CJA10GH001 | ALARM AND TRIP CONTROL SIGNAL CHECK FROM ALL THE AUXILIARIES | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B11.7 | B11 | SNR-H03CWF20 | OPERATOR INTERFACE STATION (OIS) : HUMAN MACHINE INTERFACE | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H03CWF20 |  | 20 | 20 | NETWORK INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
เพิ่มเติมโดย หฟศ-ฟ. 17/6/67 |  |  | SNR-H03CWF20 |  | 30 | 30 | BACKUP PROJECT | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.8 | B11 | SNR-H03CJA10GH001 | RECORDING FUNCTION | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B11.9 | B11 | SNR-H03CJA10GH001 | LOCAL CONTROL | 20 | 20 | CHECK OF INDICATION OF ALL ANALOG SIGNALS (TOUCH PANEL AND OPERATOR STATION) | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
|  |  | SNR-H03CJA10GH001 |  | 30 | 30 | FUNCTION TEST OF AUXILIARY SYSTEM | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  |  |  | SNR0-2E0 |  | E
| B11.10 | B11 | SNR-H03CJA10GH001 | REMOTE TERMINAL UNIT (RTU) FUNCTION | 10 | 10 | INSPECTION and TEST | หฟศ-ฟ. | 1 | 3/9/2024 | 10/9/2024 |  | 1 | 3 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B11.11 | B11 | SNR-H03CJA10 | UNIT CONTROL FUNCTION AND SEQUENCE TEST (หวปศ-ฟ.) | 10 | 10 | TEST PROCEDURE BEFORE UNIT START UP | หวปศ-ฟ. | 8 | 11/9/2024 | 12/9/2024 |  | 1 | 2 | SNR0-2P0 | PTW งานทั่วไป | E
|  |  | SNR-H03CJA10 |  | 20 | 20 | UNIT START UP AND PERFORMANCE TEST | หวปศ-ฟ. | 27 | 11/9/2024 | 12/9/2024 |  |  |  | SNR0-2P0 |  | E
ดำเนินการทุก ๆ 4 ปี | B12 | B | SNR-H00B | UPS SYSTEM (INVERTER, CHARGER, BATTERIES) |  | xx | UPS SYSTEM (INVERTER, CHARGER, BATTERIES) | หบฟส-ธ. | 49 | 2024-09-03 | 2024-09-09 | [5 empty] | E
| B12.1 | B12 | SNR-H00BRA10GU100 | INVERTER NO.1 & NO.2 |  | xx | INVERTER NO.1 & NO.2 | หบฟส-ธ. | 14 | 5/9/2024 | 6/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BRA10GU100 |  | 10 | 10 | CLEANING | หบฟส-ธ. | 2 | 5/9/2024 | 5/9/2024 |  | 1 | 2 | MSP0-E940 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BRA10GU100 |  | 20 | 20 | THYRISTOR CHECK ( LEAKAGE & OUTPUT TEST ) | หบฟส-ธ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BRA10GU100 |  | 30 | 30 | CHARACTERISTIC TEST ( STATIC TEST ) | หบฟส-ธ. | 4 | 5/9/2024 | 6/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BRA10GU100 |  | 40 | 40 | ADJUSTMENT FOR SETTING VALUE | หบฟส-ธ. | 2 | 5/9/2024 | 6/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BRA10GU100 |  | 50 | 50 | OPERATION TEST AND FINE TUNNING ( DYNAMIC TEST ) | หบฟส-ธ. | 4 | 5/9/2024 | 6/9/2024 |  |  |  | MSP0-E940 |  | E
| B12.2 | B12 | SNR-H00BTL10GU101 | 125 VDC BATTERY CHARGER NO.1 |  | xx | 125 VDC BATTERY CHARGER NO.1 | หบฟส-ธ. | 7 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU101 |  | 10 | 10 | ELECTRICAL INSPECTION | หบฟส-ธ. | 1 | 3/9/2024 | 3/9/2024 |  | 1 | 2 | MSP0-E940 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BTL10GU101 |  | 20 | 20 | CLEANING | หบฟส-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU101 |  | 30 | 30 | THYRISTOR CHECK ( LEAKAGE & OUTPUT TEST ) | หบฟส-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU101 |  | 40 | 40 | CHARACTERISTIC TEST ( STATIC TEST ) | หบฟส-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU101 |  | 50 | 50 | ADJUSTMENT FOR SETTING VALUE | หบฟส-ธ. | 1 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU101 |  | 60 | 60 | OPERATION TEST AND FINE TUNNING | หบฟส-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-E940 |  | E
| B12.3 | B12 | SNR-H00BTL10GU102 | 125 VDC BATTERY CHARGER NO.2 |  | xx | 125 VDC BATTERY CHARGER NO.2 | หบฟส-ธ. | 7 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU102 |  | 10 | 10 | ELECTRICAL INSPECTION | หบฟส-ธ. | 1 | 4/9/2024 | 4/9/2024 |  | 1 | 2 | MSP0-E940 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BTL10GU102 |  | 20 | 20 | CLEANING | หบฟส-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU102 |  | 30 | 30 | THYRISTOR CHECK ( LEAKAGE & OUTPUT TEST ) | หบฟส-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU102 |  | 40 | 40 | CHARACTERISTIC TEST ( STATIC TEST ) | หบฟส-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU102 |  | 50 | 50 | ADJUSTMENT FOR SETTING VALUE | หบฟส-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTL10GU102 |  | 60 | 60 | OPERATION TEST AND FINE TUNNING | หบฟส-ธ. | 2 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-E940 |  | E
| B12.4 | B12 | SNR-H00BTA10GR101 | BATTERY 125 VDC SET NO. 1 |  | xx | BATTERY 125 VDC SET NO. 1 | หบฟส-ธ. | 10.5 | 7/9/2024 | 8/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR101 |  | 10 | 10 | VISUAL INSPECTION (CONNECTOR , BAR , PLATE AND COVER) | หบฟส-ธ. | 2 | 7/9/2024 | 8/9/2024 |  | 1 | 2 | MSP0-E940 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BTA10GR101 |  | 20 | 20 | LOOSEN, TIGHTEN CONNECTOR | หบฟส-ธ. | 2.5 | 7/9/2024 | 8/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR101 |  | 30 | 30 | VOLT/ CELL , GRAVITATION/ CELL MEASUREMENT | หบฟส-ธ. | 1 | 7/9/2024 | 8/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR101 |  | 40 | 40 | IMPREDANCE / CELL | หบฟส-ธ. | 1 | 7/9/2024 | 8/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR101 |  | 50 | 50 | CAPACITY TEST ( ~ 50% LOAD CERRENT ) | หบฟส-ธ. | 4 | 7/9/2024 | 8/9/2024 |  |  |  | MSP0-E940 |  | E
| B12.5 | B12 | SNR-H00BTA10GR102 | BATTERY 125 VDC SET NO. 2 |  | xx | BATTERY 125 VDC SET NO. 2 | หบฟส-ธ. | 10.5 | 8/9/2024 | 9/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR102 |  | 10 | 10 | VISUAL INSPECTION (CONNECTOR , BAR , PLATE AND COVER) | หบฟส-ธ. | 2 | 8/9/2024 | 9/9/2024 |  | 1 | 2 | MSP0-E940 | PTW งานเกี่ยวกับไฟฟ้า | E
|  |  | SNR-H00BTA10GR102 |  | 20 | 20 | LOOSEN, TIGHTEN CONNECTOR | หบฟส-ธ. | 2.5 | 8/9/2024 | 9/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR102 |  | 30 | 30 | VOLT/ CELL , GRAVITATION/ CELL MEASUREMENT | หบฟส-ธ. | 1 | 8/9/2024 | 9/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR102 |  | 40 | 40 | IMPREDANCE / CELL | หบฟส-ธ. | 1 | 8/9/2024 | 9/9/2024 |  |  |  | MSP0-E940 |  | E
|  |  | SNR-H00BTA10GR102 |  | 50 | 50 | CAPACITY TEST ( ~ 50% LOAD CERRENT ) | หบฟส-ธ. | 4 | 8/9/2024 | 9/9/2024 |  |  |  | MSP0-E940 |  | E
| B13 | B | SNR-H03M | MOTOR |  | xx | MOTOR | หฟศ-ฟ. | 168 | 2024-08-29 | 2024-09-09 | [5 empty] | E
| B13.1 | B13 | SNR-H03M | MOTOR (หฟศ-ฟ.) |  | xx | MOTOR (หฟศ-ฟ.) | หฟศ-ฟ. | 162 | 3/9/2024 | 9/9/2024 | [5 empty] | E
| B13.1.1 | B13.1 | SNR-H13QEA10 | AIR COMPRESSOR MOTOR A | 10 | 10 | OPERATION PRE-TEST ON LOAD & NO LOAD - BEARING TEMP. MEASUREMENT - VOLTAGE & CURRENT MEASUREMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  | 1 | 2 | SNR0-2E0 | PTW งานเกี่ยวกับไฟฟ้า | E
| B13.1.2 | B13.2 | SNR-H13QEA20 | AIR COMPRESSOR MOTOR B | 20 | 20 | ISOLATE EQUIPMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. | B13.1.3 | B13.3 | SNR-H13QEA30 | AIR COMPRESSOR MOTOR C | 30 | 30 | ELECTRICAL TEST 1 - INSULATION RESISTANCE MEASUREMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B13.1.4 | B13.4 | SNR-H03MEX10AP002-M01 | GOVERNOR OIL PUMP MOTOR A | 40 | 40 | VISUAL INSPECTION - FRAME OR CASING - COUPLING - ACCESSORIES - ALIGNEMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B13.1.5 | B13.5 | SNR-H03MEX10AP003-M01 | GOVERNOR OIL PUMP MOTOR B | 50 | 50 | CLEANING | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขโดย หฟศ-ฟ. | B13.1.6 | B13.6 | SNR-H03MEX20AP001-M01 | INLET VALVE OIL PUMP MOTOR | 60 | 60 | ELECTRICAL TEST 2 - INSULATION RESISTANCE MEASUREMENT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B13.1.7 | B13.7 | SNR-H03MEX30AP001 | LEAKED OIL TANK OIL PUMP MOTOR | 70 | 70 | ASSEMBLY | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
แก้ไขตาม MMS 7/8/67 | B13.1.8 | B13.8 | SNR-H03MKY10AP001-M01 | OIL LIFT PUMP MOTOR A | 80 | 80 | OPERATION AND PERFORMANCE TEST -BEARING TEMP. MEAS. -VOLTAGE & CURRENT MEAS. -VIBRATION MEAS. | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B13.1.9 | B13.9 | SNR-H03MKY10AP002-M01 | OIL LIFT PUMP MOTOR B | 90 | 90 | INSPECTION REPORT | หฟศ-ฟ. | 1 | 3/9/2024 | 9/9/2024 |  |  |  | SNR0-2E0 |  | E
| B13.1.10 | B13.10 | SNR-H03MEV10AP001-M01 | TURBINE GUIDE BEARING OIL PUMP MOTOR A | [10 empty] | SNR0-2E0 |  | E
| B13.1.11 | B13.11 | SNR-H03MEV10AP002-M01 | TURBINE GUIDE BEARING OIL PUMP MOTOR B | [10 empty] | SNR0-2E0 |  | E
| B13.1.12 | B13.14 | SNR-H13LSL10AP001-M01 | DRAINAGE PUMP MOTOR A | [10 empty] | SNR0-2E0 |  | E
| B13.1.13 | B13.15 | SNR-H13LSL10AP002-M01 | DRAINAGE PUMP MOTOR B | [10 empty] | SNR0-2E0 |  | E
| B13.1.14 | B13.16 | SNR-H03PAG11AP001 | DRAFT TUBE WATER PUMP MOTOR | [10 empty] | SNR0-2E0 |  | E
| B13.2 | B13 | SNR-H03M | MOTOR (หบศ-ฟ.) |  | xx | MOTOR (หบศ-ฟ.) | หบศ-ฟ. | 7 | 2024-08-29 | 2024-08-30 |  |  |  | SNR0-2M0 |  | E
เพิ่มเติม 15/7/67 |  |  | SNR-H03M |  | 10 | 10 | VIBRATION MEASUREMENT | หบศ-ฟ. | 7 | 2024-08-29 | 2024-08-30 |  | 1 | 3 | SNR0-2M0 | PTW งานทั่วไป | E
| C |  | SNR-H03 | CIVIL WORK |  | xx | CIVIL WORK | อบย. | 16 | 3/9/2024 | 6/9/2024 | [5 empty] | C
| C1 | C | SNR-H03 | อาคาร Power House |  | xx | อาคาร Power House : การประเมินโครงสร้างคอนกรีต | หบฟ3-ธ. | 2 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 2 | 3/9/2024 | 3/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C2 | C | SNR-H03MKA30HA001 | Lower Bracket : ฐานคอนกรีต (Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) |  | xx | Lower Bracket : ฐานคอนกรีต (Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) | หบฟ3-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MKA30HA001 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 0.5 | 3/9/2024 | 3/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C3 | C | SNR-H03MKA40 | Stator : ฐานคอนกรีต (Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) |  | xx | Stator : ฐานคอนกรีต (Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) | หบฟ3-ธ. | 0.5 | 3/9/2024 | 3/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MKA40 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 0.5 | 3/9/2024 | 3/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C4 | C | SNR-H03MEA30 | Turbine Room : ผนังคอนกรีต (RC. Wall) |  | xx | Turbine Room : ผนังคอนกรีต (RC. Wall) | หบฟ3-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MEA30 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 0.5 | 4/9/2024 | 4/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
แก้ไขโดย หบฟ3-ธ. 24/7/67 | C5 | C | SNR-H03MEA40HA004 | Upper Draft Tube : พื้นผิวคอนกรีตภายในท่อ (Abrasion of Concrete Lining) |  | xx | Upper Draft Tube : พื้นผิวคอนกรีตภายในท่อ (Abrasion of Concrete Lining) | หบฟ3-ธ. | 1 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MEA40HA004 |  | 10 | 10 | ตรวจสอบสภาพพื้นผิวคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 1 | 4/9/2024 | 4/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานในที่อับอากาศ | C
| C6 | C | SNR-H03ADA | ตรวจสอบสภาพฐานคอนกรีตรองรับอุปกรณ์ภายใน Switchyard : ฐานรองรับ (Concrete Foundation) |  | xx | Disconnecting Switch : ฐานรองรับ (Concrete Foundation) | หบฟ3-ธ. | 0.5 | 4/9/2024 | 4/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03ADA |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 0.5 | 4/9/2024 | 4/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C7 | C | SNR-H03BAT10GT100 | Transformer : ฐานรองรับ (Concrete Foundation) |  | xx | Transformer : ฐานรองรับ (Concrete Foundation) | หบฟ3-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03BAT10GT100 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 1 | 5/9/2024 | 5/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C8 | C | SNR-H03MEA10HA001 | ตรวจสอบสภาพผนังคอนกรีตหุ้ม Spiral Case |  | xx | ตรวจสอบสภาพผนังคอนกรีตหุ้ม Spiral Case : ผนังคอนกรีต | หบฟ3-ธ. | 2 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MEA10HA001 |  | 10 | 10 | ตรวจสอบสภาพพื้นผิวคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 2 | 5/9/2024 | 5/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C9 | C | SNR-H03MEB10AA001 | Inlet Valve Downsteam : ฐานคอนกรีต(Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) |  | xx | Inlet Valve Downsteam : ฐานคอนกรีต(Concrete Foundation) และเหล็กรองรับฐาน (Base Plate) | หบฟ3-ธ. | 1 | 5/9/2024 | 5/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03MEB10AA001 |  | 10 | 10 | ตรวจสอบสภาพคอนกรีตด้วยสายตา (Visual and Exploratory Investigation) | หบฟ3-ธ. | 1 | 5/9/2024 | 5/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
| C10 | C | SNR-H03 | รวบรวมข้อมูล และจัดทำรายงานเสร็จงาน |  | xx | ตรวจสอบข้อมูลทางวิศวกรรม (Review of Engineering data) | หบฟ3-ธ. | 7 | 3/9/2024 | 6/9/2024 |  |  |  | MSP0-VG80 |  | C
|  |  | SNR-H03 |  | 10 | 10 | จัดทำรายงานการตรวจสอบ (Condition Survey Report) | หบฟ3-ธ. | 4 | 3/9/2024 | 5/9/2024 | 2 | 2 |  | MSP0-VG80 | PTW งานทั่วไป | C
|  |  | SNR-H03 |  | 20 | 20 | ประชุมสรุปผลการตรวจสอบ | หบฟ3-ธ. | 3 | 6/9/2024 | 6/9/2024 |  |  |  | MSP0-VG80 |  | C
Note on A2: "REMARK" - ใช้สำหรับ REMARK
Note on D2: "KKS" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่ข้อมูล KKS
Note on E2: "EQUIPMENT" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ความยาวของข้อมูลห้ามเกิน 100 ตัวอักษร
Note on H2: "TASK" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ความยาวของข้อมูลห้ามเกิน 100 ตัวอักษร
Note on I2: "RESPONSE" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ความยาวของข้อมูลห้ามเกิน 30 ตัวอักษร - ใช้สำหรับใส่ชื่อหน่วยงาน
Note on J2: "DURATION_(HR.)" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่จำนวนชั่วโมงการทำงาน
Note on K2: "START_DATE" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่วันที่เริ่มงาน - รูปแบบวันที่: ดด/วว/ปป เช่น 26/09/2024
Note on L2: "FINISH_DATE" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่วันที่สิ้นสุดงาน - รูปแบบวันที่: ดด/วว/ปป เช่น 26/09/2024
Note on M2: "SUPERVISOR" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่จำนวนผู้ควบคุมงาน (Supervisor)
Note on N2: "FOREMAN" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่จำนวนหัวหน้างาน (Foreman)
Note on O2: "SKILL" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่จำนวน skill
Note on P2: "RESPONSE_CRAFT" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่ข้อมูล Response Craft
Note on Q2: "ประเภทของ_PERMIT_TO_WORK" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่ข้อมูลประเภทของใบอนุญาตทำงาน (PTW)
Note on R2: "TYPE" - คอลัมน์สำคัญ - ห้ามแก้ไขชื่อคอลัมน์ - ใช้สำหรับใส่ข้อมูลประเภทของงาน - รูปแบบ: M : งานเกี่ยวกับเครื่องกล E : งานเกี่ยวกับไฟฟ้า C : งานเกี่ยวกับโยธา
Note on S2: "COMMENT" - คอลัมน์สำคัญ - ใช้สำหรับแจ้งเตือนข้อผิดพลาด