## Sheet1
PMNUM | SITEID | DESCRIPTION | STATUS | LOCATION | WORKTYPE | EGMNTACTTYPE | WOSTATUS | EGPROJECTID | EGWBS | FREQUENCY | FREQUNIT | JPNUM | ROUTE | NEXTDATE | EGCRAFT | RESPONSED BY | PTW | PARENTCHGSSTATUS | LEADTIME | TARGSTARTTIME | PARENT | PMCOUNTER | WOSEQUENCE | MOD | MAIN_SYSTEM | MAIN_SYSTEM_DESC | UNIT_TYPE | TYPE | SUB_SYSTEM | EQUIPMENT | SUB_SYSTEM_DESC | KKS_NEW_DESC | GROUP | FINISH_DATE | FINISH TIME | COMMENT
Group-01-H03MEA-ME-U | SRD0 | Hydraulic Turbine,URD0-6S0,PTW งานทั่วไป, งานในที่อับอากาศ | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 1 | 1 | H03MEA | Hydraulic Turbine | U | ME |  |  |  |  | 1 | 2024-10-15 | 16:00:00
PO-01290-H03MEA30HB001-ME-U | SRD0 | Runner Blade Set | ACTIVE | PMN-H03MEA30HB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01290-H03MEA30HB001-ME-U |  | 2024-10-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-01-H03MEA-ME-U | 0 | 1 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA30 | HB | Runner, Main Shaft | Runner Blade Set | 1 | 2024-10-14 | 16:00:00
PO-01340-H03MEA40HA003-ME-U | SRD0 | Hub Cover (Runner Cap) | ACTIVE | PMN-H03MEA40HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01340-H03MEA40HA003-ME-U |  | 2024-10-15 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-01-H03MEA-ME-U | 0 | 2 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Hub Cover (Runner Cap) | 1 | 2024-10-15 | 16:00:00
PO-01380-H03MEA40HA005-ME-U | SRD0 | Discharge Ring | ACTIVE | PMN-H03MEA40HA005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01380-H03MEA40HA005-ME-U |  | 2024-10-15 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-01-H03MEA-ME-U | 0 | 3 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Discharge Ring | 1 | 2024-10-15 | 16:00:00
Group-02-H03-ME-U | SRD0 | ปากมูล-พลังน้ำ หน่วยที่ 3,SRD0-1M0,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 2 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME |  |  |  |  | 2 | 2024-10-22 | 16:00:00
PO-00040-H03-ME-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00040-H03-ME-U |  | 2024-10-08 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 1 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-08 | 16:00:00
PO-00080-H03-ME-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00080-H03-ME-U |  | 2024-10-19 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 2 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-19 | 16:00:00
PO-02750-H03-ME-U | SRD0 | Final Check | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02750-H03-ME-U |  | 2024-10-19 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 3 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-20 | 16:00:00
PO-02790-H03-ME-U | SRD0 | Prepare Before Kick off Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02790-H03-ME-U |  | 2024-10-20 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 4 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-20 | 16:00:00
PO-02830-H03-ME-U | SRD0 | Kick Off | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02830-H03-ME-U |  | 2024-10-21 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 5 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-21 | 16:00:00
PO-02870-H03-ME-U | SRD0 | Operation Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02870-H03-ME-U |  | 2024-10-21 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-02-H03-ME-U | 0 | 6 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 2 | 2024-10-22 | 16:00:00
Group-03-H03-ME-U | SRD0 | ปากมูล-พลังน้ำ หน่วยที่ 3,MSP0-H010,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 3 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME |  |  |  |  | 3 | 2024-10-22 | 16:00:00
PO-00060-H03-ME-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00060-H03-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 1 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-08 | 16:00:00
PO-00100-H03-ME-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00100-H03-ME-U |  | 2024-10-19 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 2 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-19 | 16:00:00
PO-02770-H03-ME-U | SRD0 | Final Check | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02770-H03-ME-U |  | 2024-10-19 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 3 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-20 | 16:00:00
PO-02810-H03-ME-U | SRD0 | Prepare Before Kick off Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02810-H03-ME-U |  | 2024-10-20 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 4 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-20 | 16:00:00
PO-02850-H03-ME-U | SRD0 | Kick Off | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02850-H03-ME-U |  | 2024-10-21 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 5 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-21 | 16:00:00
PO-02890-H03-ME-U | SRD0 | Operation Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02890-H03-ME-U |  | 2024-10-21 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-03-H03-ME-U | 0 | 6 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | ME | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 3 | 2024-10-22 | 16:00:00
Group-04-H03MKA-ME-U | SRD0 | Generator,MSP0-H010,PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 4 | 0 | H03MKA | Generator | U | ME |  |  |  |  | 4 | 2024-10-16 | 16:00:00
PO-02150-H03MKA30HA001-ME-U | SRD0 | Bulb Noss | ACTIVE | PMN-H03MKA30HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02150-H03MKA30HA001-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-04-H03MKA-ME-U | 0 | 1 | 0 | H03MKA | Generator | U | ME | H03MKA30 | HA | Support Structure & Foundation | Bulb Noss | 4 | 2024-10-16 | 16:00:00
PO-02160-H03MKA30HA002-ME-U | SRD0 | Vertical Bulb Support | ACTIVE | PMN-H03MKA30HA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02160-H03MKA30HA002-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-04-H03MKA-ME-U | 0 | 2 | 0 | H03MKA | Generator | U | ME | H03MKA30 | HA | Support Structure & Foundation | Vertical Bulb Support | 4 | 2024-10-16 | 16:00:00
PO-02170-H03MKA30HA003-ME-U | SRD0 | Lateral Support | ACTIVE | PMN-H03MKA30HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02170-H03MKA30HA003-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-04-H03MKA-ME-U | 0 | 3 | 0 | H03MKA | Generator | U | ME | H03MKA30 | HA | Support Structure & Foundation | Lateral Support | 4 | 2024-10-16 | 16:00:00
Group-05-H03MEA-ME-U | SRD0 | Hydraulic Turbine,MSP0-H010,PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 5 | 1 | H03MEA | Hydraulic Turbine | U | ME |  |  |  |  | 5 | 2024-10-17 | 16:00:00
PO-01160-H03MEA10HA001-ME-U | SRD0 | Up Stream Draft Tube (Bulb Case) | ACTIVE | PMN-H03MEA10HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01160-H03MEA10HA001-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 1 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA10 | HA | Up Stream Draft Tube | Up Stream Draft Tube (Bulb Case) | 5 | 2024-10-16 | 16:00:00
PO-01220-H03MEA20HA003-ME-U | SRD0 | Wicket Gate Set | ACTIVE | PMN-H03MEA20HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01220-H03MEA20HA003-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 2 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA20 | HA | Wicket Gate | Wicket Gate Set | 5 | 2024-10-17 | 16:00:00
PO-01280-H03MEA30HB001-ME-U | SRD0 | Runner Blade Set | ACTIVE | PMN-H03MEA30HB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01280-H03MEA30HB001-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 3 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA30 | HB | Runner, Main Shaft | Runner Blade Set | 5 | 2024-10-17 | 16:00:00
PO-01300-H03MEA30HB005-ME-U | SRD0 | Runner Cone | ACTIVE | PMN-H03MEA30HB005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01300-H03MEA30HB005-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 4 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA30 | HB | Runner, Main Shaft | Runner Cone | 5 | 2024-10-16 | 16:00:00
PO-01310-H03MEA40HA001-ME-U | SRD0 | Inner Cone | ACTIVE | PMN-H03MEA40HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01310-H03MEA40HA001-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 5 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Inner Cone | 5 | 2024-10-16 | 16:00:00
PO-01320-H03MEA40HA002-ME-U | SRD0 | Outer Cone | ACTIVE | PMN-H03MEA40HA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01320-H03MEA40HA002-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 6 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Outer Cone | 5 | 2024-10-16 | 16:00:00
PO-01330-H03MEA40HA003-ME-U | SRD0 | Hub Cover (Runner Cap) | ACTIVE | PMN-H03MEA40HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01330-H03MEA40HA003-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 7 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Hub Cover (Runner Cap) | 5 | 2024-10-16 | 16:00:00
PO-01350-H03MEA40HA004-ME-U | SRD0 | Draft Tube | ACTIVE | PMN-H03MEA40HA004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01350-H03MEA40HA004-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-05-H03MEA-ME-U | 0 | 8 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Draft Tube | 5 | 2024-10-16 | 16:00:00
Group-06-H03SGC-ME-U | SRD0 | Spray deluge System,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 6 | 0 | H03SGC | Spray deluge System | U | ME |  |  |  |  | 6 | 2024-10-18 | 16:00:00
PO-02670-H03SGC10AA001-ME-U | SRD0 | Deluge Valve Station for KG3A | ACTIVE | PMN-H03SGC10AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02670-H03SGC10AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-06-H03SGC-ME-U | 0 | 1 | 0 | H03SGC | Spray deluge System | U | ME | H03SGC10 | AA | Deluge Valve Station for KG3A | Valve for Deluge Valve Station for KG3A | 6 | 2024-10-18 | 16:00:00
PO-02690-H03SGC20BP001-ME-U | SRD0 | Spray Nozzle for Transformer KG3A | ACTIVE | PMN-H03SGC20BP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02690-H03SGC20BP001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-06-H03SGC-ME-U | 0 | 2 | 0 | H03SGC | Spray deluge System | U | ME | H03SGC20 | BP | Spray Nozzle for Transformer KG3A | Spray Nozzle for Transformer KG3A | 6 | 2024-10-18 | 16:00:00
Group-07-H03QEB-ME-U | SRD0 | Compressed Air Distribution System,SRD0-1M0,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-16 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 7 | 1 | H03QEB | Compressed Air Distribution System | U | ME |  |  |  |  | 7 | 2024-10-17 | 16:00:00
PO-02590-H03QEB30AT001-ME-U | SRD0 | Fillter | ACTIVE | PMN-H03QEB30AT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02590-H03QEB30AT001-ME-U |  | 2024-10-16 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-07-H03QEB-ME-U | 0 | 1 | 1 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB30 | AT | Air Supply te Brake Jack (Low) | Fillter | 7 | 2024-10-17 | 16:00:00
PO-02600-H03QEB30BR001-ME-U | SRD0 | Pipe Line | ACTIVE | PMN-H03QEB30BR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02600-H03QEB30BR001-ME-U |  | 2024-10-16 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-07-H03QEB-ME-U | 0 | 2 | 1 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB30 | BR | Air Supply te Brake Jack (Low) | Pipe Line | 7 | 2024-10-17 | 16:00:00
Group-08-H03QEB-ME-U | SRD0 | Compressed Air Distribution System,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-16 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 8 | 0 | H03QEB | Compressed Air Distribution System | U | ME |  |  |  |  | 8 | 2024-10-18 | 16:00:00
PO-02550-H03QEB10BB001-ME-U | SRD0 | Air Pressure Tank (365) | ACTIVE | PMN-H03QEB10BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02550-H03QEB10BB001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-08-H03QEB-ME-U | 0 | 1 | 0 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB10 | BB | Air Pressure Tank ( =3 +BR) | Air Pressure Tank (365) | 8 | 2024-10-18 | 16:00:00
PO-02580-H03QEB30AA001-ME-U | SRD0 | Valve for Air Supply te Brake Jack (Low) | ACTIVE | PMN-H03QEB30AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02580-H03QEB30AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-08-H03QEB-ME-U | 0 | 2 | 0 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB30 | AA | Air Supply te Brake Jack (Low) | Valve for Air Supply te Brake Jack (Low) | 8 | 2024-10-18 | 16:00:00
PO-02620-H03QEB40AA001-ME-U | SRD0 | Valve for Air Supply te Brake Jack (High) | ACTIVE | PMN-H03QEB40AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02620-H03QEB40AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-08-H03QEB-ME-U | 0 | 3 | 0 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB40 | AA | Air Supply te Brake Jack (High) | Valve for Air Supply te Brake Jack (High) | 8 | 2024-10-18 | 16:00:00
PO-02630-H03QEB40BR001-ME-U | SRD0 | Pipe Line | ACTIVE | PMN-H03QEB40BR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02630-H03QEB40BR001-ME-U |  | 2024-10-16 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-08-H03QEB-ME-U | 0 | 4 | 0 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB40 | BR | Air Supply te Brake Jack (High) | Pipe Line | 8 | 2024-10-17 | 16:00:00
PO-02650-H03QEB50AA001-ME-U | SRD0 | Valve for Automatic Air Supply System Unit3 | ACTIVE | PMN-H03QEB50AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02650-H03QEB50AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-08-H03QEB-ME-U | 0 | 5 | 0 | H03QEB | Compressed Air Distribution System | U | ME | H03QEB50 | AA | Automatic Air Supply System Unit 3 | Valve for Automatic Air Supply System Unit3 | 8 | 2024-10-18 | 16:00:00
Group-09-H03PGA-ME-U | SRD0 | Close Cooling Water System,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 9 | 1 | H03PGA | Close Cooling Water System | U | ME |  |  |  |  | 9 | 2024-10-08 | 16:00:00
PO-02460-H03PGA10AP001-ME-U | SRD0 | Cooling Water Pump Generator No.1 | ACTIVE | PMN-H03PGA10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02460-H03PGA10AP001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-09-H03PGA-ME-U | 0 | 1 | 1 | H03PGA | Close Cooling Water System | U | ME | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Generator No.1 | 9 | 2024-10-08 | 16:00:00
PO-02480-H03PGA10AP002-ME-U | SRD0 | Cooling Water Pump Generator No.2 | ACTIVE | PMN-H03PGA10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02480-H03PGA10AP002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-09-H03PGA-ME-U | 0 | 2 | 1 | H03PGA | Close Cooling Water System | U | ME | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Generator No.2 | 9 | 2024-10-08 | 16:00:00
PO-02500-H03PGA10AP003-ME-U | SRD0 | Cooling Water Pump Bearing No.1 | ACTIVE | PMN-H03PGA10AP003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02500-H03PGA10AP003-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-09-H03PGA-ME-U | 0 | 3 | 1 | H03PGA | Close Cooling Water System | U | ME | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Bearing No.1 | 9 | 2024-10-08 | 16:00:00
PO-02520-H03PGA10AP004-ME-U | SRD0 | Cooling Water Pump Bearing No.2 | ACTIVE | PMN-H03PGA10AP004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02520-H03PGA10AP004-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-09-H03PGA-ME-U | 0 | 4 | 1 | H03PGA | Close Cooling Water System | U | ME | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Bearing No.2 | 9 | 2024-10-08 | 16:00:00
PO-02540-H03PGA10BB001-ME-U | SRD0 | Expansion Tank ( DN 20 ) ( R3/4 ) | ACTIVE | PMN-H03PGA10BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02540-H03PGA10BB001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-09-H03PGA-ME-U | 0 | 5 | 1 | H03PGA | Close Cooling Water System | U | ME | H03PGA10 | BB | Close Cooling Water System | Expansion Tank ( DN 20 ) ( R3/4 ) | 9 | 2024-10-08 | 16:00:00
Group-10-H03MKA-ME-U | SRD0 | Generator,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 10 | 0 | H03MKA | Generator | U | ME |  |  |  |  | 10 | 2024-10-18 | 16:00:00
PO-02120-H03MKA20CG001-ME-U | SRD0 | Position Rotor Locking Bolt GB-S10 | ACTIVE | PMN-H03MKA20CG001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02120-H03MKA20CG001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-10-H03MKA-ME-U | 0 | 1 | 0 | H03MKA | Generator | U | ME | H03MKA20 | CG | Generator Rotor | Position Rotor Locking Bolt GB-S10 | 10 | 2024-10-08 | 16:00:00
PO-02320-H03MKA60AU001-ME-U | SRD0 | Brake Jack (Set) | ACTIVE | PMN-H03MKA60AU001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02320-H03MKA60AU001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-10-H03MKA-ME-U | 0 | 2 | 0 | H03MKA | Generator | U | ME | H03MKA60 | AU | Generator Friction Brake | Brake Jack | 10 | 2024-10-18 | 16:00:00
Group-11-H03MEX-ME-U | SRD0 | Hydraulic Turbine,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 11 | 1 | H03MEX | Hydraulic Turbine | U | ME |  |  |  |  | 11 | 2024-10-17 | 16:00:00
PO-01710-H03MEX10AC001-ME-U | SRD0 | Gov. Oil Cooler (2902) | ACTIVE | PMN-H03MEX10AC001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01710-H03MEX10AC001-ME-U |  | 2024-10-14 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 1 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX10 | AC | Governor Oil Sump. Tank | Gov. Oil Cooler (2902) | 11 | 2024-10-15 | 16:00:00
PO-01730-H03MEX10AP001-ME-U | SRD0 | Governor Oil Pump No.1 (210/1) | ACTIVE | PMN-H03MEX10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01730-H03MEX10AP001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 2 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/1) | 11 | 2024-10-08 | 16:00:00
PO-01760-H03MEX10AP002-ME-U | SRD0 | Governor Oil Pump No.2 (210/2) | ACTIVE | PMN-H03MEX10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01760-H03MEX10AP002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 3 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/2) | 11 | 2024-10-08 | 16:00:00
PO-01780-H03MEX10AP003-ME-U | SRD0 | Governor Oil Curculation Pump (2901) | ACTIVE | PMN-H03MEX10AP003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01780-H03MEX10AP003-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 4 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Curculation Pump (2901) | 11 | 2024-10-08 | 16:00:00
PO-01800-H03MEX10BB001-ME-U | SRD0 | Sump Tank | ACTIVE | PMN-H03MEX10BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01800-H03MEX10BB001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 5 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX10 | BB | Governor Oil Sump. Tank | Sump Tank | 11 | 2024-10-11 | 16:00:00
PO-01830-H03MEX20BB001-ME-U | SRD0 | Pressure Tank (240) | ACTIVE | PMN-H03MEX20BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01830-H03MEX20BB001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 6 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX20 | BB | Governor Oil Pressure Tank (240) | Pressure Tank (240) | 11 | 2024-10-10 | 16:00:00
PO-01860-H03MEX30AP001-ME-U | SRD0 | Leakage Oil Pump No.1 (7701) | ACTIVE | PMN-H03MEX30AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01860-H03MEX30AP001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 7 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX30 | AP | Leakage Oil Sump Tank | Leakage Oil Pump No.1 (7701) | 11 | 2024-10-08 | 16:00:00
PO-01880-H03MEX30AP002-ME-U | SRD0 | Leakage Oil Pump No.2 (7702) | ACTIVE | PMN-H03MEX30AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01880-H03MEX30AP002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 8 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX30 | AP | Leakage Oil Sump Tank | Leakage Oil Pump No.2 (7702) | 11 | 2024-10-08 | 16:00:00
PO-01900-H03MEX30BB001-ME-U | SRD0 | Leakage Oil Tank (7700) | ACTIVE | PMN-H03MEX30BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01900-H03MEX30BB001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 9 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX30 | BB | Leakage Oil Sump Tank | Leakage Oil Tank (7700) | 11 | 2024-10-10 | 16:00:00
PO-01930-H03MEX40BB001-ME-U | SRD0 | Runner Hub Oil Tank (7750) | ACTIVE | PMN-H03MEX40BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01930-H03MEX40BB001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 10 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX40 | BB | Runner Hub Oil Tank | Runner Hub Oil Tank (7750) | 11 | 2024-10-14 | 16:00:00
PO-01950-H03MEX50AU001-ME-U | SRD0 | Runner Servo Motor | ACTIVE | PMN-H03MEX50AU001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01950-H03MEX50AU001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 11 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX50 | AU | Oil Head & Runner Servo Motor | Runner Servo Motor | 11 | 2024-10-17 | 16:00:00
PO-01960-H03MEX50BR001-ME-U | SRD0 | Oil Head (8500) | ACTIVE | PMN-H03MEX50BR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01960-H03MEX50BR001-ME-U |  | 2024-10-13 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 12 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX50 | BR | Oil Head & Runner Servo Motor | Oil Head (8500) | 11 | 2024-10-13 | 16:00:00
PO-01990-H03MEX60AA001-ME-U | SRD0 | Overspeed Pendulum Valve 1200 | ACTIVE | PMN-H03MEX60AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01990-H03MEX60AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 13 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX60 | AA | Overspeed Pendulum (1200) | Overspeed Pendulum Valve 1200 | 11 | 2024-10-17 | 16:00:00
PO-02020-H03MEX70AA001-ME-U | SRD0 | Turbine Control Device | ACTIVE | PMN-H03MEX70AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02020-H03MEX70AA001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 14 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX70 | AA | Turbine Control | Turbine Control Device | 11 | 2024-10-17 | 16:00:00
PO-02030-H03MEX70AA002-ME-U | SRD0 | Wicket Gate Control Device | ACTIVE | PMN-H03MEX70AA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02030-H03MEX70AA002-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 15 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX70 | AA | Turbine Control | Wicket Gate Control Device | 11 | 2024-10-17 | 16:00:00
PO-02040-H03MEX70AA003-ME-U | SRD0 | Runner Blade Control Device | ACTIVE | PMN-H03MEX70AA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02040-H03MEX70AA003-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 16 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX70 | AA | Turbine Control | Runner Blade Control Device | 11 | 2024-10-17 | 16:00:00
PO-02060-H03MEX90AU001-ME-U | SRD0 | Servo Motor (79000/1) | ACTIVE | PMN-H03MEX90AU001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02060-H03MEX90AU001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 17 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX90 | AU | Servo Motor | Servo Motor (79000/1) | 11 | 2024-10-17 | 16:00:00
PO-02070-H03MEX90AU002-ME-U | SRD0 | Servo Motor (79000/2) | ACTIVE | PMN-H03MEX90AU002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02070-H03MEX90AU002-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 18 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX90 | AU | Servo Motor | Servo Motor (79000/2) | 11 | 2024-10-17 | 16:00:00
PO-02080-H03MEX90CW001-ME-U | SRD0 | Closing Weight (79010) | ACTIVE | PMN-H03MEX90CW001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02080-H03MEX90CW001-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-11-H03MEX-ME-U | 0 | 19 | 1 | H03MEX | Hydraulic Turbine | U | ME | H03MEX90 | CW | Servo Motor | Closing Weight (79010) | 11 | 2024-10-17 | 16:00:00
Group-12-H03MEV-ME-U | SRD0 | Lubrication Oil System,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 12 | 0 | H03MEV | Lubrication Oil System | U | ME |  |  |  |  | 12 | 2024-10-15 | 16:00:00
PO-01450-H03MEV10AP001-ME-U | SRD0 | Filling Oil Pump No.1 (DN 80 ) | ACTIVE | PMN-H03MEV10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01450-H03MEV10AP001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 1 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV10 | AP | Lower Oil Tank | Filling Oil Pump No.1( DN 80 ) | 12 | 2024-10-08 | 16:00:00
PO-01470-H03MEV10AP002-ME-U | SRD0 | Filling Oil Pump No.2 (DN 80 ) | ACTIVE | PMN-H03MEV10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01470-H03MEV10AP002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 2 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV10 | AP | Lower Oil Tank | Filling Oil Pump No.2( DN 80 ) | 12 | 2024-10-08 | 16:00:00
PO-01480-H03MEV10AT001-ME-U | SRD0 | Tank | ACTIVE | PMN-H03MEV10AT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01480-H03MEV10AT001-ME-U |  | 2024-10-12 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 3 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV10 | AT | Lower Oil Tank | Tank | 12 | 2024-10-15 | 16:00:00
PO-01520-H03MEV20AN001-ME-U | SRD0 | Exhaust Fan | ACTIVE | PMN-H03MEV20AN001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01520-H03MEV20AN001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 4 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV20 | AN | Oil Vapour Exhaust Fan | Exhaust Fan | 12 | 2024-10-08 | 16:00:00
PO-01530-H03MEV30AC001-ME-U | SRD0 | Oil Cooler No.1 | ACTIVE | PMN-H03MEV30AC001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01530-H03MEV30AC001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 5 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV30 | AC | Oil Cooler | Oil Cooler No.1 | 12 | 2024-10-08 | 16:00:00
PO-01540-H03MEV30AC002-ME-U | SRD0 | Oil Cooler No.2 | ACTIVE | PMN-H03MEV30AC002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01540-H03MEV30AC002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 6 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV30 | AC | Oil Cooler | Oil Cooler No.2 | 12 | 2024-10-08 | 16:00:00
PO-01580-H03MEV50AT001-ME-U | SRD0 | Tank | ACTIVE | PMN-H03MEV50AT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01580-H03MEV50AT001-ME-U |  | 2024-10-12 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 7 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV50 | AT | High Oil Tank | Tank | 12 | 2024-10-14 | 16:00:00
PO-01610-H03MEV60AA001-ME-U | SRD0 | Main Bearing Oil Valve (Overhaul Oil Valve) | ACTIVE | PMN-H03MEV60AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01610-H03MEV60AA001-ME-U |  | 2024-10-14 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 8 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV60 | AA | Bearing Oil Valve | Main Bearing Oil Valve | 12 | 2024-10-15 | 16:00:00
PO-01640-H03MEV70BN001-ME-U | SRD0 | High Pressure Oil Pump ( DC ) & ( AC ) | ACTIVE | PMN-H03MEV70BN001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01640-H03MEV70BN001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 9 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pump ( DC ) & ( AC ) | 12 | 2024-10-08 | 16:00:00
PO-01660-H03MEV70BN002-ME-U | SRD0 | High Pressure Oil for Main Thrust Brg. | ACTIVE | PMN-H03MEV70BN002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01660-H03MEV70BN002-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 10 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe For Thrust Bearing | 12 | 2024-10-08 | 16:00:00
PO-01680-H03MEV70BN003-ME-U | SRD0 | High Pressure Oil for Gen. Guide Brg. | ACTIVE | PMN-H03MEV70BN003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01680-H03MEV70BN003-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 11 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe for Gen. Guide Brg. | 12 | 2024-10-08 | 16:00:00
PO-01700-H03MEV70BN004-ME-U | SRD0 | High Pressure Oil for Turbine Guide Brg. | ACTIVE | PMN-H03MEV70BN004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01700-H03MEV70BN004-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-12-H03MEV-ME-U | 0 | 12 | 0 | H03MEV | Lubrication Oil System | U | ME | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe for Turbine Guide Brg. | 12 | 2024-10-08 | 16:00:00
Group-13-H03MEA-ME-U | SRD0 | Hydraulic Turbine,MSP0-H010,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 13 | 1 | H03MEA | Hydraulic Turbine | U | ME |  |  |  |  | 13 | 2024-10-17 | 16:00:00
PO-01230-H03MEA20HA004-ME-U | SRD0 | Arm Lever Wicket Gate Set | ACTIVE | PMN-H03MEA20HA004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01230-H03MEA20HA004-ME-U |  | 2024-10-17 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-13-H03MEA-ME-U | 0 | 1 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA20 | HA | Wicket Gate | Arm Lever Wicket Gate Set | 13 | 2024-10-17 | 16:00:00
PO-01240-H03MEA20HA006-ME-U | SRD0 | Wicket Gate Link Set | ACTIVE | PMN-H03MEA20HA006 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01240-H03MEA20HA006-ME-U |  | 2024-10-09 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-13-H03MEA-ME-U | 0 | 2 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA20 | HA | Wicket Gate | Wicket Gate Link Set | 13 | 2024-10-17 | 16:00:00
PO-01250-H03MEA30AU001-ME-U | SRD0 | Coupling Bolts | ACTIVE | PMN-H03MEA30AU001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01250-H03MEA30AU001-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-13-H03MEA-ME-U | 0 | 3 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA30 | AU | Runner, Main Shaft | Coupling Bolts | 13 | 2024-10-08 | 16:00:00
PO-01390-H03MEA40HA006-ME-U | SRD0 | Turbine Shaft Seal (No Replace Seal) | ACTIVE | PMN-H03MEA40HA006 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01390-H03MEA40HA006-ME-U |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-13-H03MEA-ME-U | 0 | 4 | 1 | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Turbine Shaft Seal | 13 | 2024-10-09 | 16:00:00
Group-14-H03LSL-ME-U | SRD0 | Drain Unit Systems,SRD0-1M0,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 14 | 0 | H03LSL | Drain Unit Systems | U | ME |  |  |  |  | 14 | 2024-10-10 | 16:00:00
PO-01140-H03LSL10AA001-ME-U | SRD0 | Drain Valve | ACTIVE | PMN-H03LSL10AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01140-H03LSL10AA001-ME-U |  | 2024-10-08 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-14-H03LSL-ME-U | 0 | 1 | 0 | H03LSL | Drain Unit Systems | U | ME | H03LSL10 | AA | Drain Unit 3 | Drain Valve | 14 | 2024-10-10 | 16:00:00
PO-01150-H03LSL10BR001-ME-U | SRD0 | Pipe Line | ACTIVE | PMN-H03LSL10BR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01150-H03LSL10BR001-ME-U |  | 2024-10-08 | SRD0-1M0 | หคธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-14-H03LSL-ME-U | 0 | 2 | 0 | H03LSL | Drain Unit Systems | U | ME | H03LSL10 | BR | Drain Unit 3 | Pipe Line | 14 | 2024-10-10 | 16:00:00
Group-15-H00SAB-ME-C | SRD0 | Air-Conditioning System,MSP0-H010,PTW งานทั่วไป | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 15 | 1 | H00SAB | Air-Conditioning System | C | ME |  |  |  |  | 15 | 2024-10-08 | 16:00:00
PO-00760-H00SAB20AP001-ME-C | SRD0 | Chiller Water Pump No.1 | ACTIVE | PMN-H00SAB20AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00760-H00SAB20AP001-ME-C |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-15-H00SAB-ME-C | 0 | 1 | 1 | H00SAB | Air-Conditioning System | C | ME | H00SAB20 | AP | Chiller Water Pump System | Chiller Water Pump No.1 | 15 | 2024-10-08 | 16:00:00
PO-00780-H00SAB20AP002-ME-C | SRD0 | Chiller Water Pump No.2 | ACTIVE | PMN-H00SAB20AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00780-H00SAB20AP002-ME-C |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-15-H00SAB-ME-C | 0 | 2 | 1 | H00SAB | Air-Conditioning System | C | ME | H00SAB20 | AP | Chiller Water Pump System | Chiller Water Pump No.2 | 15 | 2024-10-08 | 16:00:00
PO-01370-H03MEA40HA005-ME-U | SRD0 | Discharge Ring | ACTIVE | PMN-H03MEA40HA005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01370-H03MEA40HA005-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานในที่อับอากาศ//งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 16 |  | H03MEA | Hydraulic Turbine | U | ME | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Discharge Ring |  | 2024-10-16 | 16:00:00
PO-01970-H03MEX50BR004-ME-U | SRD0 | Pipe Line | ACTIVE | PMN-H03MEX50BR004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01970-H03MEX50BR004-ME-U |  | 2024-10-13 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 17 |  | H03MEX | Hydraulic Turbine | U | ME | H03MEX50 | BR | Oil Head & Runner Servo Motor | Pipe Line |  | 2024-10-13 | 16:00:00
PO-01200-H03MEA20HA001-ME-U | SRD0 | Operating Ring | ACTIVE | PMN-H03MEA20HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01200-H03MEA20HA001-ME-U |  | 2024-09-03 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป, งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 18 |  | H03MEA | Hydraulic Turbine | U | ME | H03MEA20 | HA | Wicket Gate | Operating Ring |  | 2024-10-17 | 16:00:00
PO-02440-H03PCD20CL001-ME-U | SRD0 | Internal Oil Cooler (Main Tr. Oil Cooler) | ACTIVE | PMN-H03PCD20CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02440-H03PCD20CL001-ME-U |  | 2024-10-14 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 19 |  | H03PCD | Open Loop Cooling System | U | ME | H03PCD20 | CL | Water Supply to Main Transformer KG3A | Internal Water Cooler |  | 2024-10-15 | 16:00:00
PO-01420-H03MES10AA001-ME-U | SRD0 | Water Supply Valve for Shaft Seal (Solenoid Valve) | ACTIVE | PMN-H03MES10AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01420-H03MES10AA001-ME-U |  | 2024-10-14 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 20 |  | H03MES | Water Supply for Shaft Seal Unit 3 | U | ME | H03MES10 | AA | Water Supply for Shaft Seal Unit3 | Water Supply Valve for Shaft Seal |  | 2024-10-15 | 16:00:00
PO-00660-H00GHA10AP001-ME-C | SRD0 | Service Water Pump | ACTIVE | PMN-H00GHA10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00660-H00GHA10AP001-ME-C |  | 2024-10-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 21 |  | H00GHA | Service Water | C | ME | H00GHA10 | AP | Service Water Treatment Plant | Service Water Pump |  | 2024-10-08 | 16:00:00
Group-16-H03SGY-EE-U | SRD0 | Control & Protection,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 22 | 0 | H03SGY | Control & Protection | U | EE |  |  |  |  | 16 | 2024-10-18 | 16:00:00
PO-02710-H03SGY10CH001-EE-U | SRD0 | Alarm Pressure Sensor | ACTIVE | PMN-H03SGY10CH001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02710-H03SGY10CH001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H03SGY-EE-U | 0 | 1 | 0 | H03SGY | Control & Protection | U | EE | H03SGY10 | CH | Fire Alarm Control | Alarm Pressure Sensor | 16 | 2024-10-18 | 16:00:00
PO-02720-H03SGY10CP001-EE-U | SRD0 | Alarm Pressure Sw. | ACTIVE | PMN-H03SGY10CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02720-H03SGY10CP001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H03SGY-EE-U | 0 | 2 | 0 | H03SGY | Control & Protection | U | EE | H03SGY10 | CP | Fire Alarm Control | Alarm Pressure Sw. | 16 | 2024-10-18 | 16:00:00
PO-02730-H03SGY10DR001-EE-U | SRD0 | Heat Detecters | ACTIVE | PMN-H03SGY10DR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02730-H03SGY10DR001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H03SGY-EE-U | 0 | 3 | 0 | H03SGY | Control & Protection | U | EE | H03SGY10 | DR | Fire Alarm Control | Heat Detecters | 16 | 2024-10-18 | 16:00:00
Group-17-H03SGC-EE-U | SRD0 | Spray deluge System,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 23 | 1 | H03SGC | Spray deluge System | U | EE |  |  |  |  | 17 | 2024-10-18 | 16:00:00
PO-02660-H03SGC10AA001-EE-U | SRD0 | Deluge Valve Station for KG3A | ACTIVE | PMN-H03SGC10AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02660-H03SGC10AA001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-17-H03SGC-EE-U | 0 | 1 | 1 | H03SGC | Spray deluge System | U | EE | H03SGC10 | AA | Deluge Valve Station for KG3A | Valve for Deluge Valve Station for KG3A | 17 | 2024-10-18 | 16:00:00
PO-02680-H03SGC20BP001-EE-U | SRD0 | Spray Nozzle for Transformer KG3A | ACTIVE | PMN-H03SGC20BP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02680-H03SGC20BP001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-17-H03SGC-EE-U | 0 | 2 | 1 | H03SGC | Spray deluge System | U | EE | H03SGC20 | BP | Spray Nozzle for Transformer KG3A | Spray Nozzle for Transformer KG3A | 17 | 2024-10-18 | 16:00:00
Group-18-H03MKD-EE-U | SRD0 | Generator Bearing,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 24 | 0 | H03MKD | Generator Bearing | U | EE |  |  |  |  | 18 | 2024-10-13 | 16:00:00
PO-02400-H03MKD10CT001-EE-U | SRD0 | Temp. Main Thrust Brg. Pad Set | ACTIVE | PMN-H03MKD10CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02400-H03MKD10CT001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H03MKD-EE-U | 0 | 1 | 0 | H03MKD | Generator Bearing | U | EE | H03MKD10 | CT | Gen Main Thrust Bearing Set | Temp. Main Thrust Brg. Pad Set | 18 | 2024-10-13 | 16:00:00
PO-02410-H03MKD10HD002-EE-U | SRD0 | Thrust Bearng Set | ACTIVE | PMN-H03MKD10HD002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02410-H03MKD10HD002-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H03MKD-EE-U | 0 | 2 | 0 | H03MKD | Generator Bearing | U | EE | H03MKD10 | HD | Gen Main Thrust Bearing Set | Thrust Bearing Set | 18 | 2024-10-13 | 16:00:00
PO-02420-H03MKD20CT001-EE-U | SRD0 | Temp. Counter Thrust Brg. Pad Set | ACTIVE | PMN-H03MKD20CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02420-H03MKD20CT001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H03MKD-EE-U | 0 | 3 | 0 | H03MKD | Generator Bearing | U | EE | H03MKD20 | CT | Counter Thrust Bearing Shell Set | Temp. Counter Thrust Brg. Pad Set | 18 | 2024-10-13 | 16:00:00
Group-19-H03MKC-EE-U | SRD0 | Exciter Set,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 25 | 1 | H03MKC | Exciter Set | U | EE |  |  |  |  | 19 | 2024-10-14 | 16:00:00
PO-02350-H03MKC10GW001-EE-U | SRD0 | Automatic Voltage Regulator Cabinet (+EC1) | ACTIVE | PMN-H03MKC10GW001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02350-H03MKC10GW001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H03MKC-EE-U | 0 | 1 | 1 | H03MKC | Exciter Set | U | EE | H03MKC10 | GW | Exciter Set | Automatic Voltage Regulator Cabinet (+EC1) | 19 | 2024-10-14 | 16:00:00
PO-02360-H03MKC10GW002-EE-U | SRD0 | Rectifier Cabinet (+EC2) | ACTIVE | PMN-H03MKC10GW002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02360-H03MKC10GW002-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H03MKC-EE-U | 0 | 2 | 1 | H03MKC | Exciter Set | U | EE | H03MKC10 | GW | Exciter Set | Rectifier Cabinet (+EC2) | 19 | 2024-10-14 | 16:00:00
PO-02370-H03MKC10GW003-EE-U | SRD0 | Field Circuit Cubicle (+EC3) | ACTIVE | PMN-H03MKC10GW003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02370-H03MKC10GW003-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H03MKC-EE-U | 0 | 3 | 1 | H03MKC | Exciter Set | U | EE | H03MKC10 | GW | Exciter Set | Field Breaker Cabinet (+EC3) | 19 | 2024-10-14 | 16:00:00
PO-02380-H03MKC20GS001-EE-U | SRD0 | DS Excitation Transf. Cubicle (+MV3) | ACTIVE | PMN-H03MKC20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02380-H03MKC20GS001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H03MKC-EE-U | 0 | 4 | 1 | H03MKC | Exciter Set | U | EE | H03MKC20 | GS | DS Excitation Transf. Cubicle (=3+MV3) | DS Excitation Transf. Cubicle (=3+MV3) | 19 | 2024-10-14 | 16:00:00
PO-02390-H03MKC30-EE-U | SRD0 | Excitation Transformer Cubicle (=3+ET) | ACTIVE | PMN-H03MKC30 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02390-H03MKC30-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H03MKC-EE-U | 0 | 5 | 1 | H03MKC | Exciter Set | U | EE | H03MKC30 |  | Excitation Transformer Cubicle (=3+ET) | Excitation Transformer Cubicle (=3+ET) | 19 | 2024-10-10 | 16:00:00
Group-20-H03MKA-EE-U | SRD0 | Generator,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 26 | 0 | H03MKA | Generator | U | EE |  |  |  |  | 20 | 2024-10-19 | 16:00:00
PO-02090-H03MKA20-EE-U | SRD0 | Generator Rotor | ACTIVE | PMN-H03MKA20 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02090-H03MKA20-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 1 | 0 | H03MKA | Generator | U | EE | H03MKA20 |  | Generator Rotor | Generator Rotor | 20 | 2024-10-19 | 16:00:00
PO-02100-H03MKA20AE001-EE-U | SRD0 | Motor for Coal Exaust GB-M07 | ACTIVE | PMN-H03MKA20AE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02100-H03MKA20AE001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 2 | 0 | H03MKA | Generator | U | EE | H03MKA20 | AE | Generator Rotor | Motor for Coal Exaust GB-M07 | 20 | 2024-10-15 | 16:00:00
PO-02110-H03MKA20CG001-EE-U | SRD0 | Position Rotor Locking Bolt GB-S10 | ACTIVE | PMN-H03MKA20CG001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02110-H03MKA20CG001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 3 | 0 | H03MKA | Generator | U | EE | H03MKA20 | CG | Generator Rotor | Position Rotor Locking Bolt GB-S10 | 20 | 2024-10-15 | 16:00:00
PO-02130-H03MKA20CT001-EE-U | SRD0 | Thermostat Air Slip Ring Room GB-S21 | ACTIVE | PMN-H03MKA20CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02130-H03MKA20CT001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 4 | 0 | H03MKA | Generator | U | EE | H03MKA20 | CT | Generator Rotor | Thermostat Air Slip Ring Room GB-S21 | 20 | 2024-10-15 | 16:00:00
PO-02190-H03MKA40CT001-EE-U | SRD0 | Temp. Stator Winding | ACTIVE | PMN-H03MKA40CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02190-H03MKA40CT001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 5 | 0 | H03MKA | Generator | U | EE | H03MKA40 | CT | Stator | Temp. Stator Winding | 20 | 2024-10-19 | 16:00:00
PO-02200-H03MKA40CT002-EE-U | SRD0 | Temp. Stator Core | ACTIVE | PMN-H03MKA40CT002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02200-H03MKA40CT002-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 6 | 0 | H03MKA | Generator | U | EE | H03MKA40 | CT | Stator | Temp. Stator Core | 20 | 2024-10-19 | 16:00:00
PO-02210-H03MKA40CT003-EE-U | SRD0 | Thermostat Stand Still Heating | ACTIVE | PMN-H03MKA40CT003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02210-H03MKA40CT003-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 7 | 0 | H03MKA | Generator | U | EE | H03MKA40 | CT | Stator | Thermostat Stand Still Heating | 20 | 2024-10-19 | 16:00:00
PO-02220-H03MKA40HA001-EE-U | SRD0 | Gen. Stator Frame | ACTIVE | PMN-H03MKA40HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02220-H03MKA40HA001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 8 | 0 | H03MKA | Generator | U | EE | H03MKA40 | HA | Stator | Gen. Stator Frame | 20 | 2024-10-19 | 16:00:00
PO-02230-H03MKA40HA002-EE-U | SRD0 | Gen. Stator Core | ACTIVE | PMN-H03MKA40HA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02230-H03MKA40HA002-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 9 | 0 | H03MKA | Generator | U | EE | H03MKA40 | HA | Stator | Gen. Stator Core | 20 | 2024-10-19 | 16:00:00
PO-02240-H03MKA40HA003-EE-U | SRD0 | Gen. Stator Winding | ACTIVE | PMN-H03MKA40HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02240-H03MKA40HA003-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 10 | 0 | H03MKA | Generator | U | EE | H03MKA40 | HA | Stator | Gen. Stator Winding | 20 | 2024-10-19 | 16:00:00
PO-02250-H03MKA50AC001-EE-U | SRD0 | Gen. Cooling Air Fan No.01 | ACTIVE | PMN-H03MKA50AC001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02250-H03MKA50AC001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 11 | 0 | H03MKA | Generator | U | EE | H03MKA50 | AC | Gen. Air Fan | Gen. Cooling Air Fan No.01 | 20 | 2024-10-15 | 16:00:00
PO-02260-H03MKA50AC002-EE-U | SRD0 | Gen. Cooling Air Fan No.02 | ACTIVE | PMN-H03MKA50AC002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02260-H03MKA50AC002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 12 | 0 | H03MKA | Generator | U | EE | H03MKA50 | AC | Gen. Air Fan | Gen. Cooling Air Fan No.02 | 20 | 2024-10-15 | 16:00:00
PO-02270-H03MKA50AC003-EE-U | SRD0 | Gen. Cooling Air Fan No.03 | ACTIVE | PMN-H03MKA50AC003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02270-H03MKA50AC003-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 13 | 0 | H03MKA | Generator | U | EE | H03MKA50 | AC | Gen. Air Fan | Gen. Cooling Air Fan No.03 | 20 | 2024-10-15 | 16:00:00
PO-02280-H03MKA50AC004-EE-U | SRD0 | Gen. Cooling Air Fan No.04 | ACTIVE | PMN-H03MKA50AC004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02280-H03MKA50AC004-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 14 | 0 | H03MKA | Generator | U | EE | H03MKA50 | AC | Gen. Air Fan | Gen. Cooling Air Fan No.04 | 20 | 2024-10-15 | 16:00:00
PO-02290-H03MKA50AC005-EE-U | SRD0 | Air Dehumidditier | ACTIVE | PMN-H03MKA50AC005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02290-H03MKA50AC005-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 15 | 0 | H03MKA | Generator | U | EE | H03MKA50 | AC | Gen. Air Fan | Air Dehumidditier | 20 | 2024-10-15 | 16:00:00
PO-02300-H03MKA50CP001-EE-U | SRD0 | Cooling Air Circulat.Pressure Sw. | ACTIVE | PMN-H03MKA50CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02300-H03MKA50CP001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 16 | 0 | H03MKA | Generator | U | EE | H03MKA50 | CP | Gen. Air Fan | Cooling Air Circulat.Pressure Sw. | 20 | 2024-10-15 | 16:00:00
PO-02310-H03MKA50CT001-EE-U | SRD0 | Temp. Gen. Air Fan | ACTIVE | PMN-H03MKA50CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02310-H03MKA50CT001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H03MKA-EE-U | 0 | 17 | 0 | H03MKA | Generator | U | EE | H03MKA50 | CT | Gen. Air Fan | Temp. Gen. Air Fan | 20 | 2024-10-15 | 16:00:00
Group-21-H03CHA-EE-U | SRD0 | Cab.Generator And Transformer Protection,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 27 | 1 | H03CHA | Cab.Generator And Transformer Protection | U | EE |  |  |  |  | 21 | 2024-10-13 | 16:00:00
PO-01110-H03CHA10EY001-EE-U | SRD0 | Unit3 Protection Cubicle (=3+PU1) | ACTIVE | PMN-H03CHA10EY001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01110-H03CHA10EY001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H03CHA-EE-U | 0 | 1 | 1 | H03CHA | Cab.Generator And Transformer Protection | U | EE | H03CHA10 | EY | Unit3 Protection (=3+PU1) | Unit3 Protection Cubicle (=3+PU1) | 21 | 2024-10-10 | 16:00:00
PO-01120-H03CHA20EY001-EE-U | SRD0 | Unit3 Transformer Protection Cubicle (=3+PU2) | ACTIVE | PMN-H03CHA20EY001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01120-H03CHA20EY001-EE-U |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H03CHA-EE-U | 0 | 2 | 1 | H03CHA | Cab.Generator And Transformer Protection | U | EE | H03CHA20 | EY | Unit3 Transformer Protection (=3+PU2) | Unit3 Transformer Protection Cubicle (=3+PU2) | 21 | 2024-10-13 | 16:00:00
Group-22-H03CFA-EE-U | SRD0 | Cabinets for Measurement,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 28 | 0 | H03CFA | Cabinets for Measurement | U | EE |  |  |  |  | 22 | 2024-10-17 | 16:00:00
PO-01080-H03CFA10FE001-EE-U | SRD0 | Metering | ACTIVE | PMN-H03CFA10FE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01080-H03CFA10FE001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H03CFA-EE-U | 0 | 1 | 0 | H03CFA | Cabinets for Measurement | U | EE | H03CFA10 | FE | Metering | Metering | 22 | 2024-10-15 | 16:00:00
PO-01090-H03CFA20FE001-EE-U | SRD0 | Recorder | ACTIVE | PMN-H03CFA20FE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01090-H03CFA20FE001-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H03CFA-EE-U | 0 | 2 | 0 | H03CFA | Cabinets for Measurement | U | EE | H03CFA20 | FE | Recorder | Recorder | 22 | 2024-10-16 | 16:00:00
PO-01100-H03CFA30FE001-EE-U | SRD0 | Energy Meter | ACTIVE | PMN-H03CFA30FE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01100-H03CFA30FE001-EE-U |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H03CFA-EE-U | 0 | 3 | 0 | H03CFA | Cabinets for Measurement | U | EE | H03CFA30 | FE | Energy Meter | Energy Meter | 22 | 2024-10-17 | 16:00:00
Group-23-H03CDA-EE-U | SRD0 | Cabinets for Drive Control Interface,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 29 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE |  |  |  |  | 23 | 2024-10-17 | 16:00:00
PO-01000-H03CDA10GH001-EE-U | SRD0 | Unit Control Cubicle =3+CU1 | ACTIVE | PMN-H03CDA10GH001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01000-H03CDA10GH001-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 1 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA10 | GH | Unit Control Cubicle | Unit Control Cubicle =3+CU1 | 23 | 2024-10-17 | 16:00:00
PO-01010-H03CDA10GH002-EE-U | SRD0 | Unit Control Cubicle =3+CU2 | ACTIVE | PMN-H03CDA10GH002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01010-H03CDA10GH002-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 2 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA10 | GH | Unit Control Cubicle | Unit Control Cubicle =3+CU2 | 23 | 2024-10-17 | 16:00:00
PO-01020-H03CDA10GH003-EE-U | SRD0 | Unit Control Cubicle =3+CU3 | ACTIVE | PMN-H03CDA10GH003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01020-H03CDA10GH003-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 3 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA10 | GH | Unit Control Cubicle | Unit Control Cubicle =3+CU3 | 23 | 2024-10-17 | 16:00:00
PO-01030-H03CDA10GH004-EE-U | SRD0 | Unit Control Cubicle =3+CU4 | ACTIVE | PMN-H03CDA10GH004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01030-H03CDA10GH004-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 4 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA10 | GH | Unit Control Cubicle | Unit Control Cubicle =3+CU4 | 23 | 2024-10-17 | 16:00:00
PO-01040-H03CDA10GH005-EE-U | SRD0 | Unit Control Cubicle =3+CU5 | ACTIVE | PMN-H03CDA10GH005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01040-H03CDA10GH005-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 5 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA10 | GH | Unit Control Cubicle | Unit Control Cubicle =3+CU5 | 23 | 2024-10-17 | 16:00:00
PO-01050-H03CDA20GH001-EE-U | SRD0 | Leakage Oil Control Cubicle | ACTIVE | PMN-H03CDA20GH001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01050-H03CDA20GH001-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 6 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA20 | GH | Local Control Box | Leakage Oil Control Cubicle | 23 | 2024-10-17 | 16:00:00
PO-01060-H03CDA20GH002-EE-U | SRD0 | Governor Oil Supply Control Cubicle | ACTIVE | PMN-H03CDA20GH002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01060-H03CDA20GH002-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 7 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA20 | GH | Local Control Box | Governor Oil Supply Control Cubicle | 23 | 2024-10-17 | 16:00:00
PO-01070-H03CDA20GH003-EE-U | SRD0 | Turbine terminal Box | ACTIVE | PMN-H03CDA20GH003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01070-H03CDA20GH003-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H03CDA-EE-U | 0 | 8 | 1 | H03CDA | Cabinets for Drive Control Interface | U | EE | H03CDA20 | GH | Local Control Box | Turbine terminal Box | 23 | 2024-10-17 | 16:00:00
Group-24-H03BAT-EE-U | SRD0 | Generator Transformers,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 30 | 0 | H03BAT | Generator Transformers | U | EE |  |  |  |  | 24 | 2024-10-09 | 16:00:00
PO-00970-H03BAT10GT001-EE-U | SRD0 | 6/115kV.Generator Transformer KG3A | ACTIVE | PMN-H03BAT10GT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00970-H03BAT10GT001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H03BAT-EE-U | 0 | 1 | 0 | H03BAT | Generator Transformers | U | EE | H03BAT10 | GT | Generator Transformers | 6/115kV.Generator Transformer KG3A | 24 | 2024-10-09 | 16:00:00
PO-00980-H03BAT10CT001-EE-U | SRD0 | Instru. for Main Transformer KG3A | ACTIVE | PMN-H03BAT10CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00980-H03BAT10CT001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H03BAT-EE-U | 0 | 2 | 0 | H03BAT | Generator Transformers | U | EE | H03BAT10 | CT | Generator Transformers | Instru. for Main Transformer KG3A | 24 | 2024-10-09 | 16:00:00
Group-25-H03BAC-EE-U | SRD0 | Generator Circuit Breaker&Disconnecting,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 31 | 1 | H03BAC | Generator Circuit Breaker&Disconnecting | U | EE |  |  |  |  | 25 | 2024-10-13 | 16:00:00
PO-00950-H03BAC10GS001-EE-U | SRD0 | Unit3 Generator Unit Breaker 632 | ACTIVE | PMN-H03BAC10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00950-H03BAC10GS001-EE-U |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H03BAC-EE-U | 0 | 1 | 1 | H03BAC | Generator Circuit Breaker&Disconnecting | U | EE | H03BAC10 | GS | Unit3 Generator Unit Breaker | Unit3 Generator Unit Breaker 632 | 25 | 2024-10-13 | 16:00:00
PO-00960-H03BAC20GS002-EE-U | SRD0 | Unit3 Generator Disconnecting Sw.(634) | ACTIVE | PMN-H03BAC20GS002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00960-H03BAC20GS002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H03BAC-EE-U | 0 | 2 | 1 | H03BAC | Generator Circuit Breaker&Disconnecting | U | EE | H03BAC20 | GS | Generator Disconnecting Sw.(=3+GDS) | Unit3 Generator Disconnecting Sw.(634) | 25 | 2024-10-09 | 16:00:00
Group-26-H03BAA-EE-U | SRD0 | Generator Leads,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 32 | 0 | H03BAA | Generator Leads | U | EE |  |  |  |  | 26 | 2024-10-12 | 16:00:00
PO-00790-H03BAA10CE001-EE-U | SRD0 | PT VW3B1 | ACTIVE | PMN-H03BAA10CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00790-H03BAA10CE001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 1 | 0 | H03BAA | Generator Leads | U | EE | H03BAA10 | CE | Dynamic Brake (=3+MV1) | PT VW1B2 | 26 | 2024-10-10 | 16:00:00
PO-00800-H03BAA10CE002-EE-U | SRD0 | PT Fuse (VW3B2 ) | ACTIVE | PMN-H03BAA10CE002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00800-H03BAA10CE002-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 2 | 0 | H03BAA | Generator Leads | U | EE | H03BAA10 | CE | Dynamic Brake (=3+MV1) | PT Fuse (-F4 ) | 26 | 2024-10-10 | 16:00:00
PO-00810-H03BAA10GS001-EE-U | SRD0 | DS Dynamic Brake 632C | ACTIVE | PMN-H03BAA10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00810-H03BAA10GS001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 3 | 0 | H03BAA | Generator Leads | U | EE | H03BAA10 | GS | Dynamic Brake (=3+MV1) | DS Dynamic Brake 632C | 26 | 2024-10-10 | 16:00:00
PO-00820-H03BAA20CE001-EE-U | SRD0 | CT QW3B1 Gen. Trans. Diff. Rly (87T) | ACTIVE | PMN-H03BAA20CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00820-H03BAA20CE001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 4 | 0 | H03BAA | Generator Leads | U | EE | H03BAA20 | CE | Gen. Ground DS. (=3+MV2) | CT QW1B1 Gen. Trans. Diff. Rly (87T) | 26 | 2024-10-11 | 16:00:00
PO-00830-H03BAA20CE002-EE-U | SRD0 | CT QW3B1 Gen. Diff. Rly (87G) | ACTIVE | PMN-H03BAA20CE002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00830-H03BAA20CE002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 5 | 0 | H03BAA | Generator Leads | U | EE | H03BAA20 | CE | Gen. Ground DS. (=3+MV2) | CT QW1B1 Gen. Diff. Rly (87G) | 26 | 2024-10-11 | 16:00:00
PO-00840-H03BAA20CE003-EE-U | SRD0 | CT QW3B2 Gen. Over Cur. Rly. (50/51) | ACTIVE | PMN-H03BAA20CE003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00840-H03BAA20CE003-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 6 | 0 | H03BAA | Generator Leads | U | EE | H03BAA20 | CE | Gen. Ground DS. (=3+MV2) | CT QW1B2 Gen. Over Cur. Rly. (50/51) | 26 | 2024-10-11 | 16:00:00
PO-00850-H03BAA20CE004-EE-U | SRD0 | CT QW3B2 Gen. Metering | ACTIVE | PMN-H03BAA20CE004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00850-H03BAA20CE004-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 7 | 0 | H03BAA | Generator Leads | U | EE | H03BAA20 | CE | Gen. Ground DS. (=3+MV2) | CT QW1B2 Gen. Metering | 26 | 2024-10-11 | 16:00:00
PO-00860-H03BAA20GS001-EE-U | SRD0 | DS 634GB | ACTIVE | PMN-H03BAA20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00860-H03BAA20GS001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 8 | 0 | H03BAA | Generator Leads | U | EE | H03BAA20 | GS | Gen. Ground DS. (=3+MV2) | DS 634GB | 26 | 2024-10-11 | 16:00:00
PO-00870-H03BAA30GS001-EE-U | SRD0 | DS 634GA | ACTIVE | PMN-H03BAA30GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00870-H03BAA30GS001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 9 | 0 | H03BAA | Generator Leads | U | EE | H03BAA30 | GS | Gen. Ground DS & Surge Arres.(=3+MV3) | DS 634GA | 26 | 2024-10-12 | 16:00:00
PO-00880-H03BAA30GV002-EE-U | SRD0 | Surge Arrester 7.2kV | ACTIVE | PMN-H03BAA30GV002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00880-H03BAA30GV002-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 10 | 0 | H03BAA | Generator Leads | U | EE | H03BAA30 | GV | Gen. Ground DS & Surge Arres.(=3+MV3) | Surge Arrester 7.2kV | 26 | 2024-10-12 | 16:00:00
PO-00890-H03BAA40CE001-EE-U | SRD0 | CT. Gen. Stator Earth 50/51N (-F12) | ACTIVE | PMN-H03BAA40CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00890-H03BAA40CE001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 11 | 0 | H03BAA | Generator Leads | U | EE | H03BAA40 | CE | Generator Neutral Grounding (=3+MV4) | CT. Gen. Stator Earth 50/51N (-F12) | 26 | 2024-10-10 | 16:00:00
PO-00900-H03BAA40GH002-EE-U | SRD0 | Neutral Grounding | ACTIVE | PMN-H03BAA40GH002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00900-H03BAA40GH002-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 12 | 0 | H03BAA | Generator Leads | U | EE | H03BAA40 | GH | Generator Neutral Grounding (=3+MV4) | Neutral Grounding | 26 | 2024-10-10 | 16:00:00
PO-00910-H03BAA50CE001-EE-U | SRD0 | CT Gen. Impedance Rly. 21G | ACTIVE | PMN-H03BAA50CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00910-H03BAA50CE001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 13 | 0 | H03BAA | Generator Leads | U | EE | H03BAA50 | CE | Generator Star Point (=3+GB) | CT Gen. Impedance Rly. 21G | 26 | 2024-10-10 | 16:00:00
PO-00920-H03BAA50CE002-EE-U | SRD0 | CT Gen. Diffential Rly. 87 | ACTIVE | PMN-H03BAA50CE002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00920-H03BAA50CE002-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 14 | 0 | H03BAA | Generator Leads | U | EE | H03BAA50 | CE | Generator Star Point (=3+GB) | CT Gen. Diffential Rly. 87 | 26 | 2024-10-10 | 16:00:00
PO-00930-H03BAA50GE001-EE-U | SRD0 | Star Point Connecting | ACTIVE | PMN-H03BAA50GE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00930-H03BAA50GE001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 15 | 0 | H03BAA | Generator Leads | U | EE | H03BAA50 | GE | Generator Star Point (=3+GB) | Star Point Connecting | 26 | 2024-10-10 | 16:00:00
PO-00940-H03BAA60GA001-EE-U | SRD0 | Power Cable 115 kV | ACTIVE | PMN-H03BAA60GA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00940-H03BAA60GA001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H03BAA-EE-U | 0 | 16 | 0 | H03BAA | Generator Leads | U | EE | H03BAA60 | GA | 115 kV. Cable | Power Cable 115 kV | 26 | 2024-10-09 | 16:00:00
Group-27-H03-EE-U | SRD0 | ปากมูล-พลังน้ำ หน่วยที่ 3,SRD0-1E0,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 33 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE |  |  |  |  | 27 | 2024-10-22 | 16:00:00
PO-00010-H03-EE-U | SRD0 | Switching Order | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00010-H03-EE-U |  | 2024-10-16 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 1 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-16 | 16:00:00
PO-00020-H03-EE-U | SRD0 | Switching Order | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00020-H03-EE-U |  | 2024-10-22 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 2 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-22 | 16:00:00
PO-00030-H03-EE-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00030-H03-EE-U |  | 2024-10-08 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 3 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-08 | 16:00:00
PO-00070-H03-EE-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00070-H03-EE-U |  | 2024-10-19 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 4 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-19 | 16:00:00
PO-02740-H03-EE-U | SRD0 | Final Check | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02740-H03-EE-U |  | 2024-10-19 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 5 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-20 | 16:00:00
PO-02780-H03-EE-U | SRD0 | Prepare Before Kick off Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02780-H03-EE-U |  | 2024-10-20 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 6 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-20 | 16:00:00
PO-02820-H03-EE-U | SRD0 | Kick Off | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02820-H03-EE-U |  | 2024-10-21 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 7 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-21 | 16:00:00
PO-02860-H03-EE-U | SRD0 | Operation Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02860-H03-EE-U |  | 2024-10-21 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H03-EE-U | 0 | 8 | 1 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 27 | 2024-10-22 | 16:00:00
Group-28-H03-EE-U | SRD0 | ปากมูล-พลังน้ำ หน่วยที่ 3,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 34 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE |  |  |  |  | 28 | 2024-10-22 | 16:00:00
PO-00050-H03-EE-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00050-H03-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 1 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-08 | 16:00:00
PO-00090-H03-EE-U | SRD0 | Protection Systems | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00090-H03-EE-U |  | 2024-10-19 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 2 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-19 | 16:00:00
PO-02760-H03-EE-U | SRD0 | Final Check | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02760-H03-EE-U |  | 2024-10-19 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 3 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-20 | 16:00:00
PO-02800-H03-EE-U | SRD0 | Prepare Before Kick off Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02800-H03-EE-U |  | 2024-10-20 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 4 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-20 | 16:00:00
PO-02840-H03-EE-U | SRD0 | Kick Off | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02840-H03-EE-U |  | 2024-10-21 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 5 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-21 | 16:00:00
PO-02880-H03-EE-U | SRD0 | Operation Test | ACTIVE | PMN-H03 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02880-H03-EE-U |  | 2024-10-21 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H03-EE-U | 0 | 6 | 0 | H03 | ปากมูล-พลังน้ำ หน่วยที่ 3 | U | EE | H03 |  | ปากมูล-พลังน้ำ หน่วยที่ 3 | ปากมูล-พลังน้ำ หน่วยที่ 3 | 28 | 2024-10-22 | 16:00:00
Group-29-H03QEB-EE-U | SRD0 | Compressed Air Distribution System,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 35 | 1 | H03QEB | Compressed Air Distribution System | U | EE |  |  |  |  | 29 | 2024-10-17 | 16:00:00
PO-02560-H03QEB10CT001-EE-U | SRD0 | Manometer (3552) | ACTIVE | PMN-H03QEB10CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02560-H03QEB10CT001-EE-U |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-29-H03QEB-EE-U | 0 | 1 | 1 | H03QEB | Compressed Air Distribution System | U | EE | H03QEB10 | CT | Air Pressure Tank ( =3 +BR) | Manometer (3552) | 29 | 2024-10-17 | 16:00:00
PO-02570-H03QEB30AA001-EE-U | SRD0 | Valve for Air Supply te Brake Jack (Low) | ACTIVE | PMN-H03QEB30AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02570-H03QEB30AA001-EE-U |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-29-H03QEB-EE-U | 0 | 2 | 1 | H03QEB | Compressed Air Distribution System | U | EE | H03QEB30 | AA | Air Supply te Brake Jack (Low) | Valve for Air Supply te Brake Jack (Low) | 29 | 2024-10-17 | 16:00:00
PO-02610-H03QEB30CP001-EE-U | SRD0 | Pressure Measurment for Air Supply to Brake Jack (Low) | ACTIVE | PMN-H03QEB30CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02610-H03QEB30CP001-EE-U |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-29-H03QEB-EE-U | 0 | 3 | 1 | H03QEB | Compressed Air Distribution System | U | EE | H03QEB30 | CP | Air Supply te Brake Jack (Low) | Pressure Measurment for Air Supply te Brake Jack | 29 | 2024-10-17 | 16:00:00
PO-02640-H03QEB40CP001-EE-U | SRD0 | Pressure Switch (BR-S02) | ACTIVE | PMN-H03QEB40CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02640-H03QEB40CP001-EE-U |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-29-H03QEB-EE-U | 0 | 4 | 1 | H03QEB | Compressed Air Distribution System | U | EE | H03QEB40 | CP | Air Supply te Brake Jack (High) | Pressure Switch (BR-S02) | 29 | 2024-10-17 | 16:00:00
Group-30-H03PGA-EE-U | SRD0 | Close Cooling Water System,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 36 | 0 | H03PGA | Close Cooling Water System | U | EE |  |  |  |  | 30 | 2024-10-17 | 16:00:00
PO-02450-H03PGA10AP001-EE-U | SRD0 | Cooling Water Pump Generator No.1 | ACTIVE | PMN-H03PGA10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02450-H03PGA10AP001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-30-H03PGA-EE-U | 0 | 1 | 0 | H03PGA | Close Cooling Water System | U | EE | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Generator No.1 | 30 | 2024-10-17 | 16:00:00
PO-02470-H03PGA10AP002-EE-U | SRD0 | Cooling Water Pump Generator No.2 | ACTIVE | PMN-H03PGA10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02470-H03PGA10AP002-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-30-H03PGA-EE-U | 0 | 2 | 0 | H03PGA | Close Cooling Water System | U | EE | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Generator No.2 | 30 | 2024-10-17 | 16:00:00
PO-02490-H03PGA10AP003-EE-U | SRD0 | Cooling Water Pump Bearing No.1 | ACTIVE | PMN-H03PGA10AP003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02490-H03PGA10AP003-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-30-H03PGA-EE-U | 0 | 3 | 0 | H03PGA | Close Cooling Water System | U | EE | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Bearing No.1 | 30 | 2024-10-17 | 16:00:00
PO-02510-H03PGA10AP004-EE-U | SRD0 | Cooling Water Pump Bearing No.2 | ACTIVE | PMN-H03PGA10AP004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02510-H03PGA10AP004-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-30-H03PGA-EE-U | 0 | 4 | 0 | H03PGA | Close Cooling Water System | U | EE | H03PGA10 | AP | Close Cooling Water System | Cooling Water Pump Bearing No.2 | 30 | 2024-10-17 | 16:00:00
PO-02530-H03PGA10BB001-EE-U | SRD0 | Expansion Tank ( DN 20 ) ( R3/4 ) | ACTIVE | PMN-H03PGA10BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02530-H03PGA10BB001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-30-H03PGA-EE-U | 0 | 5 | 0 | H03PGA | Close Cooling Water System | U | EE | H03PGA10 | BB | Close Cooling Water System | Expansion Tank ( DN 20 ) ( R3/4 ) | 30 | 2024-10-17 | 16:00:00
Group-31-H03MKA-EE-U | SRD0 | Generator,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 37 | 1 | H03MKA | Generator | U | EE |  |  |  |  | 31 | 2024-10-16 | 16:00:00
PO-02140-H03MKA30CL001-EE-U | SRD0 | Water Level Drainage Line GB-S09 | ACTIVE | PMN-H03MKA30CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02140-H03MKA30CL001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-31-H03MKA-EE-U | 0 | 1 | 1 | H03MKA | Generator | U | EE | H03MKA30 | CL | Support Structure & Foundation | Water Level Drainage Line GB-S09 | 31 | 2024-10-16 | 16:00:00
PO-02330-H03MKA60CG001-EE-U | SRD0 | Position of Braking Jack (Limit Switch) | ACTIVE | PMN-H03MKA60CG001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02330-H03MKA60CG001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-31-H03MKA-EE-U | 0 | 2 | 1 | H03MKA | Generator | U | EE | H03MKA60 | CG | Generator Friction Brake | Position of Braking Jack | 31 | 2024-10-16 | 16:00:00
PO-02340-H03MKA60CP001-EE-U | SRD0 | Low Pressure Air (Pressure Switch) | ACTIVE | PMN-H03MKA60CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02340-H03MKA60CP001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-31-H03MKA-EE-U | 0 | 3 | 1 | H03MKA | Generator | U | EE | H03MKA60 | CP | Generator Friction Brake | Low Pressure Air | 31 | 2024-10-16 | 16:00:00
Group-32-H03MEX-EE-U | SRD0 | Hydraulic Turbine,SRD0-1E0,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-12 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 38 | 0 | H03MEX | Hydraulic Turbine | U | EE |  |  |  |  | 32 | 2024-10-14 | 16:00:00
PO-01720-H03MEX10AP001-EE-U | SRD0 | Governor Oil Pump No.1 (210/1) | ACTIVE | PMN-H03MEX10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01720-H03MEX10AP001-EE-U |  | 2024-10-12 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-32-H03MEX-EE-U | 0 | 1 | 0 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/1) | 32 | 2024-10-14 | 16:00:00
PO-01750-H03MEX10AP002-EE-U | SRD0 | Governor Oil Pump No.2 (210/2) | ACTIVE | PMN-H03MEX10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01750-H03MEX10AP002-EE-U |  | 2024-10-12 | SRD0-1E0 | หฟธอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-32-H03MEX-EE-U | 0 | 2 | 0 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/2) | 32 | 2024-10-14 | 16:00:00
Group-33-H03MEX-EE-U | SRD0 | Hydraulic Turbine,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 39 | 1 | H03MEX | Hydraulic Turbine | U | EE |  |  |  |  | 33 | 2024-10-16 | 16:00:00
PO-01740-H03MEX10AP001-EE-U | SRD0 | Governor Oil Pump No.1 (210/1) | ACTIVE | PMN-H03MEX10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01740-H03MEX10AP001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 1 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/1) | 33 | 2024-10-14 | 16:00:00
PO-01770-H03MEX10AP002-EE-U | SRD0 | Governor Oil Pump No.2 (210/2) | ACTIVE | PMN-H03MEX10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01770-H03MEX10AP002-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 2 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Pump No.1 (210/2) | 33 | 2024-10-14 | 16:00:00
PO-01790-H03MEX10AP003-EE-U | SRD0 | Governor Oil Curculation Pump (2901) | ACTIVE | PMN-H03MEX10AP003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01790-H03MEX10AP003-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 3 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | AP | Governor Oil Sump. Tank | Governor Oil Curculation Pump (2901) | 33 | 2024-10-14 | 16:00:00
PO-01810-H03MEX10CL001-EE-U | SRD0 | Oil Level Gauge | ACTIVE | PMN-H03MEX10CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01810-H03MEX10CL001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 4 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | CL | Governor Oil Sump. Tank | Oil Level Gauge | 33 | 2024-10-14 | 16:00:00
PO-01820-H03MEX10CT001-EE-U | SRD0 | Thermometer for Oil Outlet Temp.(2905) | ACTIVE | PMN-H03MEX10CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01820-H03MEX10CT001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 5 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX10 | CT | Governor Oil Sump. Tank | Thermometer for Oil Outlet Temp.(2905) | 33 | 2024-10-14 | 16:00:00
PO-01840-H03MEX20CL001-EE-U | SRD0 | Instrument (Oil Level) for Governor Oil Pressure Tank | ACTIVE | PMN-H03MEX20CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01840-H03MEX20CL001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 6 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX20 | CL | Governor Oil Pressure Tank (240) | Instrument ( Oil Level ) for Governor Oil Pressure Tank | 33 | 2024-10-14 | 16:00:00
PO-01850-H03MEX20CP001-EE-U | SRD0 | Pressure Guage for Pressure Tank (2407) | ACTIVE | PMN-H03MEX20CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01850-H03MEX20CP001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 7 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX20 | CP | Governor Oil Pressure Tank (240) | Pressure Guage for Pressure Tank (2407) | 33 | 2024-10-12 | 16:00:00
PO-01870-H03MEX30AP001-EE-U | SRD0 | Leakage Oil Pump No.1 (7701) | ACTIVE | PMN-H03MEX30AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01870-H03MEX30AP001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 8 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX30 | AP | Leakage Oil Sump Tank | Leakage Oil Pump No.1 (7701) | 33 | 2024-10-14 | 16:00:00
PO-01890-H03MEX30AP002-EE-U | SRD0 | Leakage Oil Pump No.2 (7702) | ACTIVE | PMN-H03MEX30AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01890-H03MEX30AP002-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 9 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX30 | AP | Leakage Oil Sump Tank | Leakage Oil Pump No.2 (7702) | 33 | 2024-10-14 | 16:00:00
PO-01910-H03MEX30CL001-EE-U | SRD0 | Instrument ( Oil Level ) for Leaked Oil Sump Tank | ACTIVE | PMN-H03MEX30CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01910-H03MEX30CL001-EE-U |  | 2024-10-13 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 10 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX30 | CL | Leakage Oil Sump Tank | Instrument ( Oil Level ) for Leaked Oil Sump Tank | 33 | 2024-10-15 | 16:00:00
PO-01920-H03MEX30CP001-EE-U | SRD0 | Differential Pressure Switch (S02) | ACTIVE | PMN-H03MEX30CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01920-H03MEX30CP001-EE-U |  | 2024-10-13 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 11 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX30 | CP | Leakage Oil Sump Tank | Differential Pressure Switch (S02) | 33 | 2024-10-15 | 16:00:00
PO-01940-H03MEX40CL001-EE-U | SRD0 | Instrument ( Oil Level ) for Runner Hub Oil Tank | ACTIVE | PMN-H03MEX40CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01940-H03MEX40CL001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 12 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX40 | CL | Runner Hub Oil Tank | Instrument ( Oil Level ) for Runner Hub Oil Tank | 33 | 2024-10-12 | 16:00:00
PO-02000-H03MEX60AU001-EE-U | SRD0 | Pendulum | ACTIVE | PMN-H03MEX60AU001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02000-H03MEX60AU001-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 13 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX60 | AU | Overspeed Pendulum (1200) | Pendulum | 33 | 2024-10-16 | 16:00:00
PO-02010-H03MEX60CS001-EE-U | SRD0 | Limit Sw. Overspeed Device | ACTIVE | PMN-H03MEX60CS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02010-H03MEX60CS001-EE-U |  | 2024-10-15 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 14 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX60 | CS | Overspeed Pendulum (1200) | Limit Sw. Overspeed Device | 33 | 2024-10-16 | 16:00:00
PO-02050-H03MEX70CP001-EE-U | SRD0 | Turbine Control ( Pressure Sw. ) | ACTIVE | PMN-H03MEX70CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02050-H03MEX70CP001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-33-H03MEX-EE-U | 0 | 15 | 1 | H03MEX | Hydraulic Turbine | U | EE | H03MEX70 | CP | Turbine Control | Turbine Control ( Pressure Sw. ) | 33 | 2024-10-14 | 16:00:00
Group-34-H03MEV-EE-U | SRD0 | Lubrication Oil System,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 40 | 0 | H03MEV | Lubrication Oil System | U | EE |  |  |  |  | 34 | 2024-10-16 | 16:00:00
PO-01440-H03MEV10AP001-EE-U | SRD0 | Filling Oil Pump No.1 (DN 80 ) | ACTIVE | PMN-H03MEV10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01440-H03MEV10AP001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 1 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV10 | AP | Lower Oil Tank | Filling Oil Pump No.1( DN 80 ) | 34 | 2024-10-11 | 16:00:00
PO-01460-H03MEV10AP002-EE-U | SRD0 | Filling Oil Pump No.2 (DN 80 ) | ACTIVE | PMN-H03MEV10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01460-H03MEV10AP002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 2 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV10 | AP | Lower Oil Tank | Filling Oil Pump No.2( DN 80 ) | 34 | 2024-10-11 | 16:00:00
PO-01490-H03MEV10CE001-EE-U | SRD0 | Instrument (Oil Level) for Lower Oil Tank | ACTIVE | PMN-H03MEV10CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01490-H03MEV10CE001-EE-U |  | 2024-10-13 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 3 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV10 | CE | Lower Oil Tank | Instrument (Oil Level) for Lower Oil Tank | 34 | 2024-10-14 | 16:00:00
PO-01500-H03MEV10CP001-EE-U | SRD0 | Instrument (Temp.) for Lower Oil Tank | ACTIVE | PMN-H03MEV10CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01500-H03MEV10CP001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 4 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV10 | CP | Lower Oil Tank | Instrument (Temp.) for Lower Oil Tank | 34 | 2024-10-15 | 16:00:00
PO-01550-H03MEV30AC003-EE-U | SRD0 | Inlet Scrw.Thermometer (DN 15)(R1/2) | ACTIVE | PMN-H03MEV30AC003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01550-H03MEV30AC003-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 5 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV30 | AC | Oil Cooler | Inlet Scrw.Thermometer (DN 15)(R1/2) | 34 | 2024-10-16 | 16:00:00
PO-01560-H03MEV30AC004-EE-U | SRD0 | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | ACTIVE | PMN-H03MEV30AC004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01560-H03MEV30AC004-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 6 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV30 | AC | Oil Cooler | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | 34 | 2024-10-16 | 16:00:00
PO-01570-H03MEV40CP001-EE-U | SRD0 | Diff. Pressure Switch (Oil Filter) | ACTIVE | PMN-H03MEV40CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01570-H03MEV40CP001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 7 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV40 | CP | Double Oil Filter (DN80 ) | Diff. Pressure Switch (Oil Filter) | 34 | 2024-10-16 | 16:00:00
PO-01590-H03MEV50CE001-EE-U | SRD0 | Instrument ( Oil Level ) for High Oil Tank | ACTIVE | PMN-H03MEV50CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01590-H03MEV50CE001-EE-U |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 8 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV50 | CE | High Oil Tank | Instrument ( Oil Level ) for High Oil Tank | 34 | 2024-10-14 | 16:00:00
PO-01600-H03MEV50CT001-EE-U | SRD0 | Instrument ( Temp. ) for High Oil Tank | ACTIVE | PMN-H03MEV50CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01600-H03MEV50CT001-EE-U |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 9 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV50 | CT | High Oil Tank | Instrument ( Temp. ) for High Oil Tank | 34 | 2024-10-14 | 16:00:00
PO-01620-H03MEV60AA001-EE-U | SRD0 | Main Bearing Oil Valve (Overhaul Oil Valve) | ACTIVE | PMN-H03MEV60AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01620-H03MEV60AA001-EE-U |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 10 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV60 | AA | Bearing Oil Valve | Main Bearing Oil Valve | 34 | 2024-10-14 | 16:00:00
PO-01630-H03MEV70BN001-EE-U | SRD0 | High Pressure Oil Pump ( DC ) & ( AC ) | ACTIVE | PMN-H03MEV70BN001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01630-H03MEV70BN001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 11 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pump ( DC ) & ( AC ) | 34 | 2024-10-15 | 16:00:00
PO-01650-H03MEV70BN002-EE-U | SRD0 | High Pressure Oil for Main Thrust Brg. | ACTIVE | PMN-H03MEV70BN002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01650-H03MEV70BN002-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 12 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe For Thrust Bearing | 34 | 2024-10-15 | 16:00:00
PO-01670-H03MEV70BN003-EE-U | SRD0 | High Pressure Oil for Gen. Guide Brg. | ACTIVE | PMN-H03MEV70BN003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01670-H03MEV70BN003-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 13 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe for Gen. Guide Brg. | 34 | 2024-10-15 | 16:00:00
PO-01690-H03MEV70BN004-EE-U | SRD0 | High Pressure Oil for Turbine Guide Brg. | ACTIVE | PMN-H03MEV70BN004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01690-H03MEV70BN004-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-34-H03MEV-EE-U | 0 | 14 | 0 | H03MEV | Lubrication Oil System | U | EE | H03MEV70 | BN | High Pressure Oil Pump ( DC ) & ( AC ) | High Pressure Oil Pipe for Turbine Guide Brg. | 34 | 2024-10-15 | 16:00:00
Group-35-H03MES-EE-U | SRD0 | Water Supply for Shaft Seal Unit 3,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 41 | 1 | H03MES | Water Supply for Shaft Seal Unit 3 | U | EE |  |  |  |  | 35 | 2024-10-12 | 16:00:00
PO-01410-H03MES10AA001-EE-U | SRD0 | Water Supply Valve for Shaft Seal (Solenoid Valve) | ACTIVE | PMN-H03MES10AA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01410-H03MES10AA001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-35-H03MES-EE-U | 0 | 1 | 1 | H03MES | Water Supply for Shaft Seal Unit 3 | U | EE | H03MES10 | AA | Water Supply for Shaft Seal Unit3 | Water Supply Valve for Shaft Seal | 35 | 2024-10-12 | 16:00:00
PO-01430-H03MES10CF001-EE-U | SRD0 | Flow Indicator (1+TB-S20) | ACTIVE | PMN-H03MES10CF001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01430-H03MES10CF001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-35-H03MES-EE-U | 0 | 2 | 1 | H03MES | Water Supply for Shaft Seal Unit 3 | U | EE | H03MES10 | CF | Water Supply for Shaft Seal Unit3 | Flow Indicator (1+TB-S20) | 35 | 2024-10-12 | 16:00:00
Group-36-H03MEA-EE-U | SRD0 | Hydraulic Turbine,MSP0-H020,PTW งานทั่วไป | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 42 | 0 | H03MEA | Hydraulic Turbine | U | EE |  |  |  |  | 36 | 2024-10-15 | 16:00:00
PO-01180-H03MEA20CG001-EE-U | SRD0 | Limit Sw. - W/G At Closed Posi.(S01) | ACTIVE | PMN-H03MEA20CG001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01180-H03MEA20CG001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-36-H03MEA-EE-U | 0 | 1 | 0 | H03MEA | Hydraulic Turbine | U | EE | H03MEA20 | CG | Wicket Gate | Limit Sw. - W/G At Closed Posi.(S01) | 36 | 2024-10-15 | 16:00:00
PO-01190-H03MEA20CG002-EE-U | SRD0 | W/G Position FeedBack Transducer -B01 | ACTIVE | PMN-H03MEA20CG002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01190-H03MEA20CG002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-36-H03MEA-EE-U | 0 | 2 | 0 | H03MEA | Hydraulic Turbine | U | EE | H03MEA20 | CG | Wicket Gate | W/G Position FeedBack TransdUCer -B01 | 36 | 2024-10-15 | 16:00:00
PO-01210-H03MEA20HA002-EE-U | SRD0 | Limit Sw. Set (G/V safety link) | ACTIVE | PMN-H03MEA20HA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01210-H03MEA20HA002-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-36-H03MEA-EE-U | 0 | 3 | 0 | H03MEA | Hydraulic Turbine | U | EE | H03MEA20 | HA | Wicket Gate | Limit Sw. Set (G/V safety link) | 36 | 2024-10-15 | 16:00:00
PO-01260-H03MEA30CS001-EE-U | SRD0 | Speed Senser | ACTIVE | PMN-H03MEA30CS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01260-H03MEA30CS001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-36-H03MEA-EE-U | 0 | 4 | 0 | H03MEA | Hydraulic Turbine | U | EE | H03MEA30 | CS | Runner, Main Shaft | Speed Senser | 36 | 2024-10-12 | 16:00:00
PO-01270-H03MEA30CY001-EE-U | SRD0 | Turbine Vibration | ACTIVE | PMN-H03MEA30CY001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01270-H03MEA30CY001-EE-U |  | 2024-10-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-36-H03MEA-EE-U | 0 | 5 | 0 | H03MEA | Hydraulic Turbine | U | EE | H03MEA30 | CY | Runner, Main Shaft | Turbine Vibration | 36 | 2024-10-13 | 16:00:00
Group-37-H00CKN-EE-C | SRD0 | Process Computer System,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 43 | 1 | H00CKN | Process Computer System | C | EE |  |  |  |  | 37 | 2024-10-14 | 16:00:00
PO-00590-H00CKN10EM001-EE-C | SRD0 | Drop No.5 (Spillway) | ACTIVE | PMN-H00CKN10EM001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00590-H00CKN10EM001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 1 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Drop No.5 (Spillway) | 37 | 2024-10-14 | 16:00:00
PO-00600-H00CKN10EM002-EE-C | SRD0 | Drop No.6 (GIS) | ACTIVE | PMN-H00CKN10EM002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00600-H00CKN10EM002-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 2 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Drop No.6 (GIS) | 37 | 2024-10-14 | 16:00:00
PO-00610-H00CKN10EM003-EE-C | SRD0 | Drop No.7 (Common) | ACTIVE | PMN-H00CKN10EM003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00610-H00CKN10EM003-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 3 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Drop No.7 (Common) | 37 | 2024-10-14 | 16:00:00
PO-00620-H00CKN10EM004-EE-C | SRD0 | Drop No.8 (Spare) | ACTIVE | PMN-H00CKN10EM004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00620-H00CKN10EM004-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 4 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Drop No.8 (Spare) | 37 | 2024-10-14 | 16:00:00
PO-00630-H00CKN10EM005-EE-C | SRD0 | Highway Interface Node No.60 | ACTIVE | PMN-H00CKN10EM005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00630-H00CKN10EM005-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 5 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Highway Interface Node No.60 | 37 | 2024-10-14 | 16:00:00
PO-00640-H00CKN10EM006-EE-C | SRD0 | Highway Interface Node No.62 | ACTIVE | PMN-H00CKN10EM006 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00640-H00CKN10EM006-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H00CKN-EE-C | 0 | 6 | 1 | H00CKN | Process Computer System | C | EE | H00CKN10 | EM | Ovation Control Systems | Highway Interface Node No.62 | 37 | 2024-10-14 | 16:00:00
Group-38-H00BUB-EE-C | SRD0 | DC.Distribution Boards,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 44 | 0 | H00BUB | DC.Distribution Boards | C | EE |  |  |  |  | 38 | 2024-10-11 | 16:00:00
PO-00570-H00BUB10GS001-EE-C | SRD0 | 125V Battery System 1 | ACTIVE | PMN-H00BUB10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00570-H00BUB10GS001-EE-C |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H00BUB-EE-C | 0 | 1 | 0 | H00BUB | DC.Distribution Boards | C | EE | H00BUB10 | GS | 125V Battery System | 125V Battery System 1 | 38 | 2024-10-11 | 16:00:00
PO-00580-H00BUB20GS001-EE-C | SRD0 | 125V Battery System 2 | ACTIVE | PMN-H00BUB20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00580-H00BUB20GS001-EE-C |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H00BUB-EE-C | 0 | 2 | 0 | H00BUB | DC.Distribution Boards | C | EE | H00BUB20 | GS | 125V Battery System | 125V Battery System 2 | 38 | 2024-10-11 | 16:00:00
Group-39-H00BTM-EE-C | SRD0 | Battery Chargers,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 45 | 1 | H00BTM | Battery Chargers | C | EE |  |  |  |  | 39 | 2024-10-12 | 16:00:00
PO-00550-H00BTM10GR001-EE-C | SRD0 | 125V Battery Charger 1(=22+DC11) | ACTIVE | PMN-H00BTM10GR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00550-H00BTM10GR001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H00BTM-EE-C | 0 | 1 | 1 | H00BTM | Battery Chargers | C | EE | H00BTM10 | GR | Battery Chargers | 125V Battery Charger 1(=22+DC11) | 39 | 2024-10-12 | 16:00:00
PO-00560-H00BTM10GR002-EE-C | SRD0 | 125V Battery Charger 2(=22+DC17) | ACTIVE | PMN-H00BTM10GR002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00560-H00BTM10GR002-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H00BTM-EE-C | 0 | 2 | 1 | H00BTM | Battery Chargers | C | EE | H00BTM10 | GR | Battery Chargers | 125V Battery Charger 2(=22+DC17) | 39 | 2024-10-12 | 16:00:00
Group-40-H00BTB-EE-C | SRD0 | 125V Battery,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 46 | 0 | H00BTB | 125V Battery | C | EE |  |  |  |  | 40 | 2024-10-10 | 16:00:00
PO-00530-H00BTB10GR001-EE-C | SRD0 | 125V Battery Rack No.1 | ACTIVE | PMN-H00BTB10GR001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00530-H00BTB10GR001-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H00BTB-EE-C | 0 | 1 | 0 | H00BTB | 125V Battery | C | EE | H00BTB10 | GR | 125V Battery | 125V Battery Rack No.1 | 40 | 2024-10-10 | 16:00:00
PO-00540-H00BTB10GR002-EE-C | SRD0 | 125V Battery Rack No.2 | ACTIVE | PMN-H00BTB10GR002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00540-H00BTB10GR002-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H00BTB-EE-C | 0 | 2 | 0 | H00BTB | 125V Battery | C | EE | H00BTB10 | GR | 125V Battery | 125V Battery Rack No.2 | 40 | 2024-10-10 | 16:00:00
Group-41-H00BRU-EE-C | SRD0 | Safe AC Inverter,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 47 | 1 | H00BRU | Safe AC Inverter | C | EE |  |  |  |  | 41 | 2024-10-11 | 16:00:00
PO-00500-H00BRU10GS001-EE-C | SRD0 | Safe AC Inverter Cubicle1=21+SA1 | ACTIVE | PMN-H00BRU10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00500-H00BRU10GS001-EE-C |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H00BRU-EE-C | 0 | 1 | 1 | H00BRU | Safe AC Inverter | C | EE | H00BRU10 | GS | Safe AC Inverter | Safe AC Inverter Cubicle1=21+SA1 | 41 | 2024-10-11 | 16:00:00
PO-00510-H00BRU10GS002-EE-C | SRD0 | Safe AC Inverter Cubicle1=21+SA2 | ACTIVE | PMN-H00BRU10GS002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00510-H00BRU10GS002-EE-C |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H00BRU-EE-C | 0 | 2 | 1 | H00BRU | Safe AC Inverter | C | EE | H00BRU10 | GS | Safe AC Inverter | Safe AC Inverter Cubicle1=21+SA2 | 41 | 2024-10-11 | 16:00:00
PO-00520-H00BRU20GS003-EE-C | SRD0 | Inverter Volt Distribution 230 V 50Hz | ACTIVE | PMN-H00BRU20GS003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00520-H00BRU20GS003-EE-C |  | 2024-10-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H00BRU-EE-C | 0 | 3 | 1 | H00BRU | Safe AC Inverter | C | EE | H00BRU20 | GS | Inverter Volt Distribution 230 V 50Hz | Inverter Volt Distribution 230 V 50Hz | 41 | 2024-10-11 | 16:00:00
Group-42-H00BFY-EE-C | SRD0 | Control And Protection,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 48 | 0 | H00BFY | Control And Protection | C | EE |  |  |  |  | 42 | 2024-10-13 | 16:00:00
PO-00470-H00BFY20EY001-EE-C | SRD0 | Controller Transformer STR-2 | ACTIVE | PMN-H00BFY20EY001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00470-H00BFY20EY001-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-42-H00BFY-EE-C | 0 | 1 | 0 | H00BFY | Control And Protection | C | EE | H00BFY20 | EY | Auxiliary Protection AT2 | Controller Transformer STR-2 | 42 | 2024-10-13 | 16:00:00
PO-00480-H00BFY20EY002-EE-C | SRD0 | DC Distribution Board | ACTIVE | PMN-H00BFY20EY002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00480-H00BFY20EY002-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-42-H00BFY-EE-C | 0 | 2 | 0 | H00BFY | Control And Protection | C | EE | H00BFY20 | EY | Auxiliary Protection AT2 | Safe DC Source 2 | 42 | 2024-10-13 | 16:00:00
Group-43-H00BFT-EE-C | SRD0 | Low Voltage Auxiliary Transformer,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 49 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE |  |  |  |  | 43 | 2024-10-15 | 16:00:00
PO-00420-H00BFT20CE001-EE-C | SRD0 | CT QW2C 200/1A (=20+MV6 -T1-3) | ACTIVE | PMN-H00BFT20CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00420-H00BFT20CE001-EE-C |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-43-H00BFT-EE-C | 0 | 1 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE | H00BFT20 | CE | Low Voltage Aux. Transformer KW2B Sys. | CT QW2C 200/1A (=20+MV6 -T1-3) | 43 | 2024-10-15 | 16:00:00
PO-00430-H00BFT20GS001-EE-C | SRD0 | 6 kV Breaker 622A (=20+MV6) | ACTIVE | PMN-H00BFT20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00430-H00BFT20GS001-EE-C |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-43-H00BFT-EE-C | 0 | 2 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE | H00BFT20 | GS | Low Voltage Aux. Transformer KW2B Sys. | 6 kV Breaker 622A (=20+MV6) | 43 | 2024-10-15 | 16:00:00
PO-00440-H00BFT20GS002-EE-C | SRD0 | DS 615B (=20+MV3) | ACTIVE | PMN-H00BFT20GS002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00440-H00BFT20GS002-EE-C |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-43-H00BFT-EE-C | 0 | 3 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE | H00BFT20 | GS | Low Voltage Aux. Transformer KW2B Sys. | DS 615B (=20+MV3) | 43 | 2024-10-15 | 16:00:00
PO-00450-H00BFT20GS004-EE-C | SRD0 | DS 624GC | ACTIVE | PMN-H00BFT20GS004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00450-H00BFT20GS004-EE-C |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-43-H00BFT-EE-C | 0 | 4 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE | H00BFT20 | GS | Low Voltage Aux. Transformer KW2B Sys. | DS 624GC | 43 | 2024-10-15 | 16:00:00
PO-00460-H00BFT20GT001-EE-C | SRD0 | Station Service Transformer KW2B | ACTIVE | PMN-H00BFT20GT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00460-H00BFT20GT001-EE-C |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-43-H00BFT-EE-C | 0 | 5 | 1 | H00BFT | Low Voltage Auxiliary Transformer | C | EE | H00BFT20 | GT | Low Voltage Aux. Transformer KW2B Sys. | Station Service Transformer KW2B | 43 | 2024-10-15 | 16:00:00
Group-44-H00BFB-EE-C | SRD0 | LV.Distribution Board,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 50 | 0 | H00BFB | LV.Distribution Board | C | EE |  |  |  |  | 44 | 2024-10-13 | 16:00:00
PO-00360-H00BFB10GS001-EE-C | SRD0 | 416V General Service Board | ACTIVE | PMN-H00BFB10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00360-H00BFB10GS001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 1 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB10 | GS | General Service Board | 416V General Service Board | 44 | 2024-10-13 | 16:00:00
PO-00370-H00BFB20GS001-EE-C | SRD0 | Power House Drainage Board | ACTIVE | PMN-H00BFB20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00370-H00BFB20GS001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 2 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB20 | GS | Power House Drainage Board | Power House Drainage Board | 44 | 2024-10-13 | 16:00:00
PO-00380-H00BFB30GS001-EE-C | SRD0 | De-Watering Sys. Board | ACTIVE | PMN-H00BFB30GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00380-H00BFB30GS001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 3 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB30 | GS | De-Watering Sys. Board | De-Watering Sys. Board | 44 | 2024-10-13 | 16:00:00
PO-00390-H00BFB40GS001-EE-C | SRD0 | Spillway Drainage Board | ACTIVE | PMN-H00BFB40GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00390-H00BFB40GS001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 4 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB40 | GS | Spillway Drainage Board | Spillway Drainage Board | 44 | 2024-10-13 | 16:00:00
PO-00400-H00BFB70GH001-EE-C | SRD0 | Lighting & Socket Supply Board& Panel | ACTIVE | PMN-H00BFB70GH001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00400-H00BFB70GH001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 5 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB70 | GH | Lighting & Socket Systems | Lighting & Socket Supply Board& Panel | 44 | 2024-10-13 | 16:00:00
PO-00410-H00BFB70GT001-EE-C | SRD0 | Lighting & Socket Transformer | ACTIVE | PMN-H00BFB70GT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00410-H00BFB70GT001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-44-H00BFB-EE-C | 0 | 6 | 0 | H00BFB | LV.Distribution Board | C | EE | H00BFB70 | GT | Lighting & Socket Systems | Lighting & Socket Transformer | 44 | 2024-10-13 | 16:00:00
Group-45-H00BFA-EE-C | SRD0 | LV.Distribution Board,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 51 | 1 | H00BFA | LV.Distribution Board | C | EE |  |  |  |  | 45 | 2024-10-13 | 16:00:00
PO-00330-H00BFA20CE001-EE-C | SRD0 | CT T11-T13 2500/1A (=21+MD22) | ACTIVE | PMN-H00BFA20CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00330-H00BFA20CE001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-45-H00BFA-EE-C | 0 | 1 | 1 | H00BFA | LV.Distribution Board | C | EE | H00BFA20 | CE | Main Distribution Board 2 | CT T11-T13 2500/1A (=21+MD22) | 45 | 2024-10-13 | 16:00:00
PO-00340-H00BFA20CE002-EE-C | SRD0 | PT 440/110V | ACTIVE | PMN-H00BFA20CE002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00340-H00BFA20CE002-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-45-H00BFA-EE-C | 0 | 2 | 1 | H00BFA | LV.Distribution Board | C | EE | H00BFA20 | CE | Main Distribution Board 2 | PT 440/110V | 45 | 2024-10-13 | 16:00:00
PO-00350-H00BFA20GS001-EE-C | SRD0 | 400 V Main Distribution Board Bus B | ACTIVE | PMN-H00BFA20GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00350-H00BFA20GS001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-45-H00BFA-EE-C | 0 | 3 | 1 | H00BFA | LV.Distribution Board | C | EE | H00BFA20 | GS | Main Distribution Board 2 | 400 V Main Distribution Board Bus B | 45 | 2024-10-13 | 16:00:00
Group-46-H00AEA-EE-C | SRD0 | GIS 115 kV,MSP0-H020,PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 52 | 0 | H00AEA | GIS 115 kV | C | EE |  |  |  |  | 46 | 2024-10-18 | 16:00:00
PO-00110-H00AEA40CE001-EE-C | SRD0 | CT QY5B 600/1A | ACTIVE | PMN-H00AEA40CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00110-H00AEA40CE001-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 1 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | CE | Bay5 115 kV Unit Feeder 3 | CT QY5B 600/1A | 46 | 2024-10-18 | 16:00:00
PO-00120-H00AEA40GS001-EE-C | SRD0 | Breaker 7052 | ACTIVE | PMN-H00AEA40GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00120-H00AEA40GS001-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 2 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | Breaker 7052 | 46 | 2024-10-18 | 16:00:00
PO-00130-H00AEA40GS002-EE-C | SRD0 | DS 7056 | ACTIVE | PMN-H00AEA40GS002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00130-H00AEA40GS002-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 3 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7056 | 46 | 2024-10-18 | 16:00:00
PO-00140-H00AEA40GS003-EE-C | SRD0 | DS 7054 | ACTIVE | PMN-H00AEA40GS003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00140-H00AEA40GS003-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 4 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7054 | 46 | 2024-10-18 | 16:00:00
PO-00150-H00AEA40GS004-EE-C | SRD0 | DS 7057 | ACTIVE | PMN-H00AEA40GS004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00150-H00AEA40GS004-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 5 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7057 | 46 | 2024-10-18 | 16:00:00
PO-00160-H00AEA40GS005-EE-C | SRD0 | DS 7054GA | ACTIVE | PMN-H00AEA40GS005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00160-H00AEA40GS005-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 6 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7054GA | 46 | 2024-10-18 | 16:00:00
PO-00170-H00AEA40GS006-EE-C | SRD0 | DS 7054GB | ACTIVE | PMN-H00AEA40GS006 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00170-H00AEA40GS006-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 7 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7054GB | 46 | 2024-10-18 | 16:00:00
PO-00180-H00AEA40GS007-EE-C | SRD0 | DS 7054GC | ACTIVE | PMN-H00AEA40GS007 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00180-H00AEA40GS007-EE-C |  | 2024-10-18 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 8 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA40 | GS | Bay5 115 kV Unit Feeder 3 | DS 7054GC | 46 | 2024-10-18 | 16:00:00
PO-00190-H00AEA60CE001-EE-C | SRD0 | CT QY2B 600/1A | ACTIVE | PMN-H00AEA60CE001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00190-H00AEA60CE001-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 9 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | CE | Bay2 115 kV Line 1 | CT QY2B 600/1A | 46 | 2024-10-16 | 16:00:00
PO-00200-H00AEA60CE002-EE-C | SRD0 | CT QY2A | ACTIVE | PMN-H00AEA60CE002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00200-H00AEA60CE002-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 10 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | CE | Bay2 115 kV Line 1 | CT QY2A | 46 | 2024-10-16 | 16:00:00
PO-00210-H00AEA60CE003-EE-C | SRD0 | PT VY2A | ACTIVE | PMN-H00AEA60CE003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00210-H00AEA60CE003-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 11 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | CE | Bay2 115 kV Line 1 | PT VY2A | 46 | 2024-10-16 | 16:00:00
PO-00220-H00AEA60GS001-EE-C | SRD0 | Breaker 7022 | ACTIVE | PMN-H00AEA60GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00220-H00AEA60GS001-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 12 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | Breaker 7022 | 46 | 2024-10-17 | 16:00:00
PO-00230-H00AEA60GS002-EE-C | SRD0 | DS 7026 | ACTIVE | PMN-H00AEA60GS002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00230-H00AEA60GS002-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 13 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7026 | 46 | 2024-10-17 | 16:00:00
PO-00240-H00AEA60GS003-EE-C | SRD0 | DS 7024 | ACTIVE | PMN-H00AEA60GS003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00240-H00AEA60GS003-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 14 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7024 | 46 | 2024-10-17 | 16:00:00
PO-00250-H00AEA60GS004-EE-C | SRD0 | DS 7025 | ACTIVE | PMN-H00AEA60GS004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00250-H00AEA60GS004-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 15 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7025 | 46 | 2024-10-17 | 16:00:00
PO-00260-H00AEA60GS005-EE-C | SRD0 | DS 7023 | ACTIVE | PMN-H00AEA60GS005 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00260-H00AEA60GS005-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 16 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7023 | 46 | 2024-10-17 | 16:00:00
PO-00270-H00AEA60GS007-EE-C | SRD0 | DS 7024GA | ACTIVE | PMN-H00AEA60GS007 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00270-H00AEA60GS007-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 17 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7024GA | 46 | 2024-10-17 | 16:00:00
PO-00280-H00AEA60GS008-EE-C | SRD0 | DS 7024GB | ACTIVE | PMN-H00AEA60GS008 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00280-H00AEA60GS008-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 18 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7024GB | 46 | 2024-10-17 | 16:00:00
PO-00290-H00AEA60GS009-EE-C | SRD0 | DS 7024GC | ACTIVE | PMN-H00AEA60GS009 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00290-H00AEA60GS009-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 19 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7024GC | 46 | 2024-10-17 | 16:00:00
PO-00300-H00AEA60GS010-EE-C | SRD0 | DS 7024GD | ACTIVE | PMN-H00AEA60GS010 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00300-H00AEA60GS010-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 20 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GS | Bay2 115 kV Line 1 | DS 7024GD | 46 | 2024-10-17 | 16:00:00
PO-00310-H00AEA60GV001-EE-C | SRD0 | Lightning Arester | ACTIVE | PMN-H00AEA60GV001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00310-H00AEA60GV001-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 21 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GV | Bay2 115 kV Line 1 | Lightning Arester | 46 | 2024-10-17 | 16:00:00
PO-00320-H00AEA60GY001-EE-C | SRD0 | Wave Trap Phase A,C | ACTIVE | PMN-H00AEA60GY001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00320-H00AEA60GY001-EE-C |  | 2024-10-16 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-46-H00AEA-EE-C | 0 | 22 | 0 | H00AEA | GIS 115 kV | C | EE | H00AEA60 | GY | Bay2 115 kV Line 1 | Wave Trap Phase A | 46 | 2024-10-17 | 16:00:00
Group-47-H00SAB-EE-C | SRD0 | Air-Conditioning System,MSP0-H020,PTW งานทั่วไป | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 53 | 1 | H00SAB | Air-Conditioning System | C | EE |  |  |  |  | 47 | 2024-10-10 | 16:00:00
PO-00750-H00SAB20AP001-EE-C | SRD0 | Chiller Water Pump No.1 | ACTIVE | PMN-H00SAB20AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00750-H00SAB20AP001-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H00SAB-EE-C | 0 | 1 | 1 | H00SAB | Air-Conditioning System | C | EE | H00SAB20 | AP | Chiller Water Pump System | Chiller Water Pump No.1 | 47 | 2024-10-10 | 16:00:00
PO-00770-H00SAB20AP002-EE-C | SRD0 | Chiller Water Pump No.2 | ACTIVE | PMN-H00SAB20AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00770-H00SAB20AP002-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H00SAB-EE-C | 0 | 2 | 1 | H00SAB | Air-Conditioning System | C | EE | H00SAB20 | AP | Chiller Water Pump System | Chiller Water Pump No.2 | 47 | 2024-10-10 | 16:00:00
Group-48-H00PCD-EE-C | SRD0 | Outfall Cooling System,MSP0-H020,PTW งานทั่วไป | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 54 | 0 | H00PCD | Outfall Cooling System | C | EE |  |  |  |  | 48 | 2024-10-14 | 16:00:00
PO-00730-H00PCD10AP001-EE-C | SRD0 | Cooling Pump for Chiller No.1 | ACTIVE | PMN-H00PCD10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00730-H00PCD10AP001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H00PCD-EE-C | 0 | 1 | 0 | H00PCD | Outfall Cooling System | C | EE | H00PCD10 | AP | Water Cooling for Chiller No.1,2 | Cooling Pump for Chiller No.1 | 48 | 2024-10-14 | 16:00:00
PO-00740-H00PCD10AP002-EE-C | SRD0 | Cooling Pump for Chiller No.2 | ACTIVE | PMN-H00PCD10AP002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00740-H00PCD10AP002-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H00PCD-EE-C | 0 | 2 | 0 | H00PCD | Outfall Cooling System | C | EE | H00PCD10 | AP | Water Cooling for Chiller No.1,2 | Cooling Pump for Chiller No.2 | 48 | 2024-10-14 | 16:00:00
Group-49-H00LSL-EE-C | SRD0 | De-Watoring & Drainage Systems,MSP0-H020,PTW งานทั่วไป | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 55 | 1 | H00LSL | De-Watoring & Drainage Systems | C | EE |  |  |  |  | 49 | 2024-10-12 | 16:00:00
PO-00690-H00LSL20CL001-EE-C | SRD0 | Float Switch Set | ACTIVE | PMN-H00LSL20CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00690-H00LSL20CL001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-49-H00LSL-EE-C | 0 | 1 | 1 | H00LSL | De-Watoring & Drainage Systems | C | EE | H00LSL20 | CL | Spillway Drainage (55DP) | Float Switch Set | 49 | 2024-10-12 | 16:00:00
PO-00720-H00LSL30CL001-EE-C | SRD0 | Float Switch Set | ACTIVE | PMN-H00LSL30CL001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00720-H00LSL30CL001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-49-H00LSL-EE-C | 0 | 2 | 1 | H00LSL | De-Watoring & Drainage Systems | C | EE | H00LSL30 | CL | De-Watering Drainage (56DP) | Float Switch Set | 49 | 2024-10-12 | 16:00:00
PO-01980-H03MEX50CP001-EE-U | SRD0 | Indicator Position | ACTIVE | PMN-H03MEX50CP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01980-H03MEX50CP001-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 56 |  | H03MEX | Hydraulic Turbine | U | EE | H03MEX50 | CP | Oil Head & Runner Servo Motor | Indicator Position |  | 2024-10-14 | 16:00:00
PO-02700-H03SGJ10BB001-EE-U | SRD0 | Co2 Fire - Fighting | ACTIVE | PMN-H03SGJ10BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02700-H03SGJ10BB001-EE-U |  | 2024-10-17 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 57 |  | H03SGJ | Co2 Fire - Fighting System | U | EE | H03SGJ10 | BB | Co2 Fire - Fighting System | Co2 Fire - Fighting |  | 2024-10-18 | 16:00:00
PO-02430-H03PCD20AA002-EE-U | SRD0 | Motor Operated Valve (4381) | ACTIVE | PMN-H03PCD20AA002 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02430-H03PCD20AA002-EE-U |  | 2024-10-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 58 |  | H03PCD | Open Loop Cooling System | U | EE | H03PCD20 | AA | Water Supply to Main Transformer KG3A | Motor Operated Valve (4381) |  | 2024-10-14 | 16:00:00
PO-01510-H03MEV20AN001-EE-U | SRD0 | Exhaust Fan | ACTIVE | PMN-H03MEV20AN001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01510-H03MEV20AN001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 59 |  | H03MEV | Lubrication Oil System | U | EE | H03MEV20 | AN | Oil Vapour Exhaust Fan | Exhaust Fan |  | 2024-10-10 | 16:00:00
PO-01130-H03CKN10EM001-EE-U | SRD0 | Drop No.3/53 (Unit#3) | ACTIVE | PMN-H03CKN10EM001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01130-H03CKN10EM001-EE-U |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 60 |  | H03CKN | Process ComPuter System | U | EE | H03CKN10 | EM | Ovation Control Systems | Drop No.3/53 (Unit#3) |  | 2024-10-14 | 16:00:00
PO-00990-H03BFB10GS001-EE-U | SRD0 | Unit3 Auxiliary Board | ACTIVE | PMN-H03BFB10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00990-H03BFB10GS001-EE-U |  | 2024-10-14 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 61 |  | H03BFB | LV.Distribution Board | U | EE | H03BFB10 | GS | Unit Auxiliary Board | Unit3 Auxiliary Board |  | 2024-10-16 | 16:00:00
PO-01400-H03MED10CT001-EE-U | SRD0 | Temp. Turbine Brg. Instrument | ACTIVE | PMN-H03MED10CT001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01400-H03MED10CT001-EE-U |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 62 |  | H03MED | Turbine Guide Bearing | U | EE | H03MED10 | CT | Turbine Guide Bearing | Temp. Turbine Brg. Shell |  | 2024-10-12 | 16:00:00
PO-00650-H00GHA10AP001-EE-C | SRD0 | Service Water Pump | ACTIVE | PMN-H00GHA10AP001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00650-H00GHA10AP001-EE-C |  | 2024-10-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 63 |  | H00GHA | Service Water | C | EE | H00GHA10 | AP | Service Water Treatment Plant | Service Water Pump |  | 2024-10-14 | 16:00:00
PO-00490-H00BMA10GS001-EE-C | SRD0 | Diesel Generator Breaker | ACTIVE | PMN-H00BMA10GS001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00490-H00BMA10GS001-EE-C |  | 2024-10-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป, งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 64 |  | H00BMA | Low Voltage Emer. Distribution Board | C | EE | H00BMA10 | GS | Diesel Generator Board | Diesel Generator Breaker |  | 2024-10-09 | 16:00:00
Group-50-H03MEA-CV-U | SRD0 | Hydraulic Turbine,URD0-3D0,PTW งานทั่วไป, งานในที่อับอากาศ | ACTIVE | SRD-H04 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 65 | 0 | H03MEA | Hydraulic Turbine | U | CV |  |  |  |  | 50 | 2024-10-10 | 16:00:00
PO-01170-H03MEA10HA001-CV-U | SRD0 | Up Stream Draft Tube (Bulb Case) | ACTIVE | PMN-H03MEA10HA001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01170-H03MEA10HA001-CV-U |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-50-H03MEA-CV-U | 0 | 1 | 0 | H03MEA | Hydraulic Turbine | U | CV | H03MEA10 | HA | Up Stream Draft Tube | Up Stream Draft Tube (Bulb Case) | 50 | 2024-10-10 | 16:00:00
PO-01360-H03MEA40HA004-CV-U | SRD0 | Draft Tube | ACTIVE | PMN-H03MEA40HA004 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-01360-H03MEA40HA004-CV-U |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-50-H03MEA-CV-U | 0 | 2 | 0 | H03MEA | Hydraulic Turbine | U | CV | H03MEA40 | HA | Cover, Draft Tube, Shaft Seal | Draft Tube | 50 | 2024-10-10 | 16:00:00
Group-51-H00LSL-CV-C | SRD0 | De-Watoring & Drainage Systems,URD0-3D0,PTW งานทั่วไป, งานในที่อับอากาศ | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 66 | 1 | H00LSL | De-Watoring & Drainage Systems | C | CV |  |  |  |  | 51 | 2024-10-10 | 16:00:00
PO-00680-H00LSL20BB001-CV-C | SRD0 | Drainage Pit | ACTIVE | PMN-H00LSL20BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00680-H00LSL20BB001-CV-C |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-51-H00LSL-CV-C | 0 | 1 | 1 | H00LSL | De-Watoring & Drainage Systems | C | CV | H00LSL20 | BB | Spillway Drainage (55DP) | Drainage Pit | 51 | 2024-10-10 | 16:00:00
PO-00710-H00LSL30BB001-CV-C | SRD0 | Drainage Pit | ACTIVE | PMN-H00LSL30BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00710-H00LSL30BB001-CV-C |  | 2024-10-10 | URD0-3D0 | หขอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-51-H00LSL-CV-C | 0 | 2 | 1 | H00LSL | De-Watoring & Drainage Systems | C | CV | H00LSL30 | BB | De-Watering Drainage (56DP) | Drainage Pit | 51 | 2024-10-10 | 16:00:00
Group-52-H00LSL-CV-C | SRD0 | De-Watoring & Drainage Systems,SRD0-1C0,PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | ACTIVE | PMN-H00 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS |  |  | 2024-10-08 | SRD0-1C0 | หยธอ-ฟ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 67 | 0 | H00LSL | De-Watoring & Drainage Systems | C | CV |  |  |  |  | 52 | 2024-10-13 | 16:00:00
PO-00670-H00LSL20BB001-CV-C | SRD0 | Drainage Pit | ACTIVE | PMN-H00LSL20BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00670-H00LSL20BB001-CV-C |  | 2024-10-08 | SRD0-1C0 | หยธอ-ฟ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-52-H00LSL-CV-C | 0 | 1 | 0 | H00LSL | De-Watoring & Drainage Systems | C | CV | H00LSL20 | BB | Spillway Drainage (55DP) | Drainage Pit | 52 | 2024-10-13 | 16:00:00
PO-00700-H00LSL30BB001-CV-C | SRD0 | Drainage Pit | ACTIVE | PMN-H00LSL30BB001 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-00700-H00LSL30BB001-CV-C |  | 2024-10-08 | SRD0-1C0 | หยธอ-ฟ. | PTW งานทั่วไป, งานนั่งร้าน, งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-52-H00LSL-CV-C | 0 | 2 | 0 | H00LSL | De-Watoring & Drainage Systems | C | CV | H00LSL30 | BB | De-Watering Drainage (56DP) | Drainage Pit | 52 | 2024-10-13 | 16:00:00
PO-02180-H03MKA30HA003-CV-U | SRD0 | Lateral Support | ACTIVE | PMN-H03MKA30HA003 | APOO | AO2 | WSCH | O-SRD0H04-67MI | O-SRD0H04-67MI-WO | 4 | YEARS | JP-02180-H03MKA30HA003-CV-U |  | 2024-10-08 | SRD0-1C0 | หยธอ-ฟ. | PTW งานทั่วไป, งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 68 |  | H03MKA | Generator | U | CV | H03MKA30 | HA | Support Structure & Foundation | Lateral Support |  | 2024-10-16 | 16:00:00