## Sheet1
JOB_NUM | ORGID | SITEID | PLUSCREVNUM | STATUS | EQUIPMENT | DURATION_TOTAL | TASK_ORDER_NEW | PLUSCJPREVNUM | DURATION_(HR.) | TASK_NEW | START_DATE | FINISH_DATE | GROUP | MOD | COMMENT
JP-00010-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Switching Order | 3 | 10 | 0 | 3 | DE-ENERGIZE KG3A | 2024-10-16 | 2024-10-16 | 1 | 1
JP-00020-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Switching Order | 3 | 10 | 0 | 3 | ENERGIZE KG3A | 2024-10-22 | 2024-10-22 | 2 | 0
JP-00030-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | BLOCKING | 2024-10-08 | 2024-10-08 | 3 | 1
JP-00040-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | BLOCKING | 2024-10-08 | 2024-10-08 | 4 | 0
JP-00050-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | BLOCKING | 2024-10-08 | 2024-10-08 | 5 | 1
JP-00060-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | BLOCKING | 2024-10-08 | 2024-10-08 | 6 | 0
JP-00070-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | UNBLOCKING | 2024-10-19 | 2024-10-19 | 7 | 1
JP-00080-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | UNBLOCKING | 2024-10-19 | 2024-10-19 | 8 | 0
JP-00090-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | UNBLOCKING | 2024-10-19 | 2024-10-19 | 9 | 1
JP-00100-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Protection Systems | 4 | 10 | 0 | 4 | UNBLOCKING | 2024-10-19 | 2024-10-19 | 10 | 0
JP-00110-H00AEA40CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QY5B 600/1A | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 11 | 1
JP-00120-H00AEA40GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Breaker 7052 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 12 | 0
JP-00130-H00AEA40GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7056 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 13 | 1
JP-00140-H00AEA40GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7054 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 14 | 0
JP-00150-H00AEA40GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7057 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 15 | 1
JP-00160-H00AEA40GS005-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7054GA | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 16 | 0
JP-00170-H00AEA40GS006-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7054GB | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 17 | 1
JP-00180-H00AEA40GS007-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7054GC | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-18 | 2024-10-18 | 18 | 0
JP-00190-H00AEA60CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QY2B 600/1A | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-16 | 19 | 1
JP-00200-H00AEA60CE002-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QY2A | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-16 | 20 | 0
JP-00210-H00AEA60CE003-EE-C | EGAT | KBI0 | 0 | ACTIVE | PT VY2A | 4 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-16 | 21 | 1
JP-00210-H00AEA60CE003-EE-C | EGAT | KBI0 | 0 | ACTIVE | PT VY2A | 4 | 20 | 0 | 2 | ELECTRICAL TEST | 2024-10-16 | 2024-10-16 | 21 | 1
JP-00220-H00AEA60GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Breaker 7022 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 22 | 0
JP-00230-H00AEA60GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7026 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 23 | 1
JP-00240-H00AEA60GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7024 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 24 | 0
JP-00250-H00AEA60GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7025 | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 25 | 1
JP-00260-H00AEA60GS005-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7023 | 4 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 26 | 0
JP-00260-H00AEA60GS005-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7023 | 4 | 20 | 0 | 2 | ELECTRICAL TEST | 2024-10-16 | 2024-10-17 | 26 | 0
JP-00270-H00AEA60GS007-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7024GA | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 27 | 1
JP-00280-H00AEA60GS008-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7024GB | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 28 | 0
JP-00290-H00AEA60GS009-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7024GC | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 29 | 1
JP-00300-H00AEA60GS010-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 7024GD | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 30 | 0
JP-00310-H00AEA60GV001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lightning Arester | 4 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 31 | 1
JP-00310-H00AEA60GV001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lightning Arester | 4 | 20 | 0 | 2 | ELECTRICAL TEST | 2024-10-16 | 2024-10-17 | 31 | 1
JP-00320-H00AEA60GY001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Wave Trap Phase A,C | 2 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 32 | 0
JP-00330-H00BFA20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT T11-T13 2500/1A (=21+MD22) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 33 | 1
JP-00330-H00BFA20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT T11-T13 2500/1A (=21+MD22) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 33 | 1
JP-00330-H00BFA20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT T11-T13 2500/1A (=21+MD22) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 33 | 1
JP-00340-H00BFA20CE002-EE-C | EGAT | KBI0 | 0 | ACTIVE | PT 440/110V | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 34 | 0
JP-00340-H00BFA20CE002-EE-C | EGAT | KBI0 | 0 | ACTIVE | PT 440/110V | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 34 | 0
JP-00340-H00BFA20CE002-EE-C | EGAT | KBI0 | 0 | ACTIVE | PT 440/110V | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 34 | 0
JP-00350-H00BFA20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 400 V Main Distribution Board Bus B | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 35 | 1
JP-00350-H00BFA20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 400 V Main Distribution Board Bus B | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 35 | 1
JP-00350-H00BFA20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 400 V Main Distribution Board Bus B | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 35 | 1
JP-00360-H00BFB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 416V General Service Board | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 36 | 0
JP-00360-H00BFB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 416V General Service Board | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 36 | 0
JP-00360-H00BFB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 416V General Service Board | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 36 | 0
JP-00370-H00BFB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Power House Drainage Board | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 37 | 1
JP-00370-H00BFB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Power House Drainage Board | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 37 | 1
JP-00370-H00BFB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Power House Drainage Board | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 37 | 1
JP-00380-H00BFB30GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | De-Watering Sys. Board | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 38 | 0
JP-00380-H00BFB30GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | De-Watering Sys. Board | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 38 | 0
JP-00380-H00BFB30GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | De-Watering Sys. Board | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 38 | 0
JP-00390-H00BFB40GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Spillway Drainage Board | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 39 | 1
JP-00390-H00BFB40GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Spillway Drainage Board | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 39 | 1
JP-00390-H00BFB40GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Spillway Drainage Board | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 39 | 1
JP-00400-H00BFB70GH001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Supply Board& Panel | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 40 | 0
JP-00400-H00BFB70GH001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Supply Board& Panel | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 40 | 0
JP-00400-H00BFB70GH001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Supply Board& Panel | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 40 | 0
JP-00410-H00BFB70GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Transformer | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 41 | 1
JP-00410-H00BFB70GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Transformer | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 41 | 1
JP-00410-H00BFB70GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Lighting & Socket Transformer | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-13 | 41 | 1
JP-00420-H00BFT20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QW2C 200/1A (=20+MV6 -T1-3) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 42 | 0
JP-00420-H00BFT20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QW2C 200/1A (=20+MV6 -T1-3) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 42 | 0
JP-00420-H00BFT20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QW2C 200/1A (=20+MV6 -T1-3) | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-15 | 42 | 0
JP-00420-H00BFT20CE001-EE-C | EGAT | KBI0 | 0 | ACTIVE | CT QW2C 200/1A (=20+MV6 -T1-3) | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 42 | 0
JP-00430-H00BFT20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 6 kV Breaker 622A (=20+MV6) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 43 | 1
JP-00430-H00BFT20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 6 kV Breaker 622A (=20+MV6) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 43 | 1
JP-00430-H00BFT20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 6 kV Breaker 622A (=20+MV6) | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-15 | 43 | 1
JP-00430-H00BFT20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 6 kV Breaker 622A (=20+MV6) | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 43 | 1
JP-00440-H00BFT20GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 615B (=20+MV3) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 44 | 0
JP-00440-H00BFT20GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 615B (=20+MV3) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 44 | 0
JP-00440-H00BFT20GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 615B (=20+MV3) | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-15 | 44 | 0
JP-00440-H00BFT20GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 615B (=20+MV3) | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 44 | 0
JP-00450-H00BFT20GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 624GC | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 45 | 1
JP-00450-H00BFT20GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 624GC | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 45 | 1
JP-00450-H00BFT20GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 624GC | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-15 | 45 | 1
JP-00450-H00BFT20GS004-EE-C | EGAT | KBI0 | 0 | ACTIVE | DS 624GC | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 45 | 1
JP-00460-H00BFT20GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Station Service Transformer KW2B | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 46 | 0
JP-00460-H00BFT20GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Station Service Transformer KW2B | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 46 | 0
JP-00460-H00BFT20GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Station Service Transformer KW2B | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-15 | 46 | 0
JP-00460-H00BFT20GT001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Station Service Transformer KW2B | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 46 | 0
JP-00470-H00BFY20EY001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Controller Transformer STR-2 | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-13 | 47 | 1
JP-00470-H00BFY20EY001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Controller Transformer STR-2 | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-13 | 47 | 1
JP-00470-H00BFY20EY001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Controller Transformer STR-2 | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-13 | 47 | 1
JP-00470-H00BFY20EY001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Controller Transformer STR-2 | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-13 | 47 | 1
JP-00480-H00BFY20EY002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DC Distribution Board | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-13 | 48 | 0
JP-00480-H00BFY20EY002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DC Distribution Board | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-13 | 48 | 0
JP-00480-H00BFY20EY002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DC Distribution Board | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-13 | 48 | 0
JP-00480-H00BFY20EY002-EE-C | EGAT | KBI0 | 0 | ACTIVE | DC Distribution Board | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-13 | 48 | 0
JP-00490-H00BMA10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Diesel Generator Breaker | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-09 | 49 | 1
JP-00490-H00BMA10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Diesel Generator Breaker | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-09 | 49 | 1
JP-00490-H00BMA10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Diesel Generator Breaker | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-09 | 49 | 1
JP-00490-H00BMA10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Diesel Generator Breaker | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-09 | 49 | 1
JP-00500-H00BRU10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA1 | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 50 | 0
JP-00500-H00BRU10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA1 | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-11 | 50 | 0
JP-00500-H00BRU10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA1 | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-11 | 50 | 0
JP-00500-H00BRU10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA1 | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-10 | 2024-10-11 | 50 | 0
JP-00510-H00BRU10GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA2 | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 51 | 1
JP-00510-H00BRU10GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA2 | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-11 | 51 | 1
JP-00510-H00BRU10GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA2 | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-11 | 51 | 1
JP-00510-H00BRU10GS002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Safe AC Inverter Cubicle1=21+SA2 | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-10 | 2024-10-11 | 51 | 1
JP-00520-H00BRU20GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Inverter Volt Distribution 230 V 50Hz | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 52 | 0
JP-00520-H00BRU20GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Inverter Volt Distribution 230 V 50Hz | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-11 | 52 | 0
JP-00520-H00BRU20GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Inverter Volt Distribution 230 V 50Hz | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-11 | 52 | 0
JP-00520-H00BRU20GS003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Inverter Volt Distribution 230 V 50Hz | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-10 | 2024-10-11 | 52 | 0
JP-00530-H00BTB10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.1 | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-09 | 2024-10-10 | 53 | 1
JP-00530-H00BTB10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.1 | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-10 | 53 | 1
JP-00530-H00BTB10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.1 | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-09 | 2024-10-10 | 53 | 1
JP-00530-H00BTB10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.1 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-10 | 53 | 1
JP-00530-H00BTB10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.1 | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-09 | 2024-10-10 | 53 | 1
JP-00540-H00BTB10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.2 | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-09 | 2024-10-10 | 54 | 0
JP-00540-H00BTB10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.2 | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-10 | 54 | 0
JP-00540-H00BTB10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.2 | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-09 | 2024-10-10 | 54 | 0
JP-00540-H00BTB10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.2 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-10 | 54 | 0
JP-00540-H00BTB10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Rack No.2 | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-09 | 2024-10-10 | 54 | 0
JP-00550-H00BTM10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 1(=22+DC11) | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-11 | 2024-10-12 | 55 | 1
JP-00550-H00BTM10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 1(=22+DC11) | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-12 | 55 | 1
JP-00550-H00BTM10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 1(=22+DC11) | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-11 | 2024-10-12 | 55 | 1
JP-00550-H00BTM10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 1(=22+DC11) | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-11 | 2024-10-12 | 55 | 1
JP-00550-H00BTM10GR001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 1(=22+DC11) | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-11 | 2024-10-12 | 55 | 1
JP-00560-H00BTM10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 2(=22+DC17) | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-11 | 2024-10-12 | 56 | 0
JP-00560-H00BTM10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 2(=22+DC17) | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-12 | 56 | 0
JP-00560-H00BTM10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 2(=22+DC17) | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-11 | 2024-10-12 | 56 | 0
JP-00560-H00BTM10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 2(=22+DC17) | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-11 | 2024-10-12 | 56 | 0
JP-00560-H00BTM10GR002-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery Charger 2(=22+DC17) | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-11 | 2024-10-12 | 56 | 0
JP-00570-H00BUB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 1 | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-10 | 2024-10-11 | 57 | 1
JP-00570-H00BUB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 1 | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 57 | 1
JP-00570-H00BUB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 1 | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-10 | 2024-10-11 | 57 | 1
JP-00570-H00BUB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 1 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-11 | 57 | 1
JP-00570-H00BUB10GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 1 | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-10 | 2024-10-11 | 57 | 1
JP-00580-H00BUB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 2 | 4.5 | 10 | 0 | 1 | ISOLATE EQUIPMENT | 2024-10-10 | 2024-10-11 | 58 | 0
JP-00580-H00BUB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 2 | 4.5 | 20 | 0 | 0.5 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 58 | 0
JP-00580-H00BUB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 2 | 4.5 | 30 | 0 | 1 | CLEANING | 2024-10-10 | 2024-10-11 | 58 | 0
JP-00580-H00BUB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 2 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-11 | 58 | 0
JP-00580-H00BUB20GS001-EE-C | EGAT | KBI0 | 0 | ACTIVE | 125V Battery System 2 | 4.5 | 50 | 0 | 1 | ASSEMBLY EQUIPMENT | 2024-10-10 | 2024-10-11 | 58 | 0
JP-00590-H00CKN10EM001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.5 (Spillway) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 59 | 1
JP-00590-H00CKN10EM001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.5 (Spillway) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 59 | 1
JP-00590-H00CKN10EM001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.5 (Spillway) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 59 | 1
JP-00600-H00CKN10EM002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.6 (GIS) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 60 | 0
JP-00600-H00CKN10EM002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.6 (GIS) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 60 | 0
JP-00600-H00CKN10EM002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.6 (GIS) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 60 | 0
JP-00610-H00CKN10EM003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.7 (Common) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 61 | 1
JP-00610-H00CKN10EM003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.7 (Common) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 61 | 1
JP-00610-H00CKN10EM003-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.7 (Common) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 61 | 1
JP-00620-H00CKN10EM004-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.8 (Spare) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 62 | 0
JP-00620-H00CKN10EM004-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.8 (Spare) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 62 | 0
JP-00620-H00CKN10EM004-EE-C | EGAT | KBI0 | 0 | ACTIVE | Drop No.8 (Spare) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 62 | 0
JP-00630-H00CKN10EM005-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.60 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 63 | 1
JP-00630-H00CKN10EM005-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.60 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 63 | 1
JP-00630-H00CKN10EM005-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.60 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 63 | 1
JP-00640-H00CKN10EM006-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.62 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 64 | 0
JP-00640-H00CKN10EM006-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.62 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 64 | 0
JP-00640-H00CKN10EM006-EE-C | EGAT | KBI0 | 0 | ACTIVE | Highway Interface Node No.62 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 64 | 0
JP-00650-H00GHA10AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Service Water Pump | 1 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 65 | 1
JP-00660-H00GHA10AP001-ME-C | EGAT | KBI0 | 0 | ACTIVE | Service Water Pump | 1.2 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 66 | 0
JP-00660-H00GHA10AP001-ME-C | EGAT | KBI0 | 0 | ACTIVE | Service Water Pump | 1.2 | 20 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 66 | 0
JP-00670-H00LSL20BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 2 | 10 | 0 | 1 | ตั้งนั่งร้าน | 2024-10-08 | 2024-10-08 | 67 | 1
JP-00670-H00LSL20BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 2 | 20 | 0 | 1 | รื้อนั่งร้าน | 2024-10-13 | 2024-10-13 | 67 | 1
JP-00680-H00LSL20BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 1 | 10 | 0 | 1 | CIVIL INSPECTION | 2024-10-10 | 2024-10-10 | 68 | 0
JP-00690-H00LSL20CL001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Float Switch Set | 1 | 10 | 0 | 1 | FUNCTION & OPERATION TEST | 2024-10-11 | 2024-10-12 | 69 | 1
JP-00700-H00LSL30BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 2 | 10 | 0 | 1 | ตั้งนั่งร้าน | 2024-10-08 | 2024-10-12 | 70 | 0
JP-00700-H00LSL30BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 2 | 20 | 0 | 1 | รื้อนั่งร้าน | 2024-10-13 | 2024-10-13 | 70 | 0
JP-00710-H00LSL30BB001-CV-C | EGAT | KBI0 | 0 | ACTIVE | Drainage Pit | 1 | 10 | 0 | 1 | CIVIL INSPECTION | 2024-10-10 | 2024-10-10 | 71 | 1
JP-00720-H00LSL30CL001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Float Switch Set | 1 | 10 | 0 | 1 | FUNCTION & OPERATION TEST | 2024-10-11 | 2024-10-12 | 72 | 0
JP-00730-H00PCD10AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.1 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 73 | 1
JP-00730-H00PCD10AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.1 | 2.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-11 | 2024-10-14 | 73 | 1
JP-00730-H00PCD10AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.1 | 2.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-11 | 2024-10-14 | 73 | 1
JP-00740-H00PCD10AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.2 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 74 | 0
JP-00740-H00PCD10AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.2 | 2.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-11 | 2024-10-14 | 74 | 0
JP-00740-H00PCD10AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Cooling Pump for Chiller No.2 | 2.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-11 | 2024-10-14 | 74 | 0
JP-00750-H00SAB20AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.1 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-10 | 75 | 1
JP-00750-H00SAB20AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.1 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-10 | 75 | 1
JP-00750-H00SAB20AP001-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-09 | 2024-10-10 | 75 | 1
JP-00760-H00SAB20AP001-ME-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.1 | 1.2 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 76 | 0
JP-00760-H00SAB20AP001-ME-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.1 | 1.2 | 20 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 76 | 0
JP-00770-H00SAB20AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.2 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-10 | 77 | 1
JP-00770-H00SAB20AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.2 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-10 | 77 | 1
JP-00770-H00SAB20AP002-EE-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-09 | 2024-10-10 | 77 | 1
JP-00780-H00SAB20AP002-ME-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.2 | 1.2 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 78 | 0
JP-00780-H00SAB20AP002-ME-C | EGAT | KBI0 | 0 | ACTIVE | Chiller Water Pump No.2 | 1.2 | 20 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 78 | 0
JP-00790-H03BAA10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT VW3B1 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 79 | 1
JP-00790-H03BAA10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT VW3B1 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 79 | 1
JP-00790-H03BAA10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT VW3B1 | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 79 | 1
JP-00800-H03BAA10CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT Fuse (VW3B2 ) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 80 | 0
JP-00800-H03BAA10CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT Fuse (VW3B2 ) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 80 | 0
JP-00800-H03BAA10CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | PT Fuse (VW3B2 ) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 80 | 0
JP-00810-H03BAA10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Dynamic Brake 632C | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 81 | 1
JP-00810-H03BAA10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Dynamic Brake 632C | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 81 | 1
JP-00810-H03BAA10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Dynamic Brake 632C | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 81 | 1
JP-00810-H03BAA10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Dynamic Brake 632C | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-08 | 2024-10-10 | 81 | 1
JP-00820-H03BAA20CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Trans. Diff. Rly (87T) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 82 | 0
JP-00820-H03BAA20CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Trans. Diff. Rly (87T) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-11 | 82 | 0
JP-00820-H03BAA20CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Trans. Diff. Rly (87T) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 82 | 0
JP-00830-H03BAA20CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Diff. Rly (87G) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 83 | 1
JP-00830-H03BAA20CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Diff. Rly (87G) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-11 | 83 | 1
JP-00830-H03BAA20CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B1 Gen. Diff. Rly (87G) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 83 | 1
JP-00840-H03BAA20CE003-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Over Cur. Rly. (50/51) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 84 | 0
JP-00840-H03BAA20CE003-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Over Cur. Rly. (50/51) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-11 | 84 | 0
JP-00840-H03BAA20CE003-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Over Cur. Rly. (50/51) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 84 | 0
JP-00850-H03BAA20CE004-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Metering | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 85 | 1
JP-00850-H03BAA20CE004-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Metering | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-11 | 85 | 1
JP-00850-H03BAA20CE004-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT QW3B2 Gen. Metering | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 85 | 1
JP-00860-H03BAA20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GB | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 86 | 0
JP-00860-H03BAA20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GB | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-11 | 86 | 0
JP-00860-H03BAA20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GB | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-11 | 86 | 0
JP-00870-H03BAA30GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GA | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-12 | 87 | 1
JP-00870-H03BAA30GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GA | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-12 | 87 | 1
JP-00870-H03BAA30GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS 634GA | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-10 | 2024-10-12 | 87 | 1
JP-00880-H03BAA30GV002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Surge Arrester 7.2kV | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-12 | 88 | 0
JP-00880-H03BAA30GV002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Surge Arrester 7.2kV | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-12 | 88 | 0
JP-00880-H03BAA30GV002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Surge Arrester 7.2kV | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-12 | 88 | 0
JP-00890-H03BAA40CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT. Gen. Stator Earth 50/51N (-F12) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 89 | 1
JP-00890-H03BAA40CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT. Gen. Stator Earth 50/51N (-F12) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 89 | 1
JP-00890-H03BAA40CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT. Gen. Stator Earth 50/51N (-F12) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 89 | 1
JP-00900-H03BAA40GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Neutral Grounding | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 90 | 0
JP-00900-H03BAA40GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Neutral Grounding | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 90 | 0
JP-00900-H03BAA40GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Neutral Grounding | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 90 | 0
JP-00910-H03BAA50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Impedance Rly. 21G | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 91 | 1
JP-00910-H03BAA50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Impedance Rly. 21G | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 91 | 1
JP-00910-H03BAA50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Impedance Rly. 21G | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 91 | 1
JP-00920-H03BAA50CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Diffential Rly. 87 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 92 | 0
JP-00920-H03BAA50CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Diffential Rly. 87 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 92 | 0
JP-00920-H03BAA50CE002-EE-U | EGAT | KBI0 | 0 | ACTIVE | CT Gen. Diffential Rly. 87 | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 92 | 0
JP-00930-H03BAA50GE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Star Point Connecting | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 93 | 1
JP-00930-H03BAA50GE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Star Point Connecting | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 93 | 1
JP-00930-H03BAA50GE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Star Point Connecting | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-08 | 2024-10-10 | 93 | 1
JP-00940-H03BAA60GA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Power Cable 115 kV | 1.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-09 | 94 | 0
JP-00940-H03BAA60GA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Power Cable 115 kV | 1.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-09 | 2024-10-09 | 94 | 0
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 40 | 0 | 1 | MECHANISM INSPECTION | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 50 | 0 | 1 | GAS SF6 TESTING | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00950-H03BAC10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Unit Breaker 632 | 5.5 | 60 | 0 | 1 | FUNCTION TEST | 2024-10-11 | 2024-10-13 | 95 | 1
JP-00960-H03BAC20GS002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Disconnecting Sw.(634) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-09 | 96 | 0
JP-00960-H03BAC20GS002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Disconnecting Sw.(634) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-09 | 96 | 0
JP-00960-H03BAC20GS002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Disconnecting Sw.(634) | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-09 | 2024-10-09 | 96 | 0
JP-00960-H03BAC20GS002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Generator Disconnecting Sw.(634) | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-09 | 96 | 0
JP-00970-H03BAT10GT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | 6/115kV.Generator Transformer KG3A | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-09 | 97 | 1
JP-00970-H03BAT10GT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | 6/115kV.Generator Transformer KG3A | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-09 | 97 | 1
JP-00970-H03BAT10GT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | 6/115kV.Generator Transformer KG3A | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-09 | 2024-10-09 | 97 | 1
JP-00980-H03BAT10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instru. for Main Transformer KG3A | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-09 | 98 | 0
JP-00980-H03BAT10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instru. for Main Transformer KG3A | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-09 | 98 | 0
JP-00980-H03BAT10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instru. for Main Transformer KG3A | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-09 | 98 | 0
JP-00990-H03BFB10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Auxiliary Board | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 99 | 1
JP-00990-H03BFB10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Auxiliary Board | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 99 | 1
JP-00990-H03BFB10GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Auxiliary Board | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-14 | 2024-10-16 | 99 | 1
JP-01000-H03CDA10GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU1 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 100 | 0
JP-01000-H03CDA10GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU1 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 100 | 0
JP-01000-H03CDA10GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU1 | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 100 | 0
JP-01010-H03CDA10GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU2 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 101 | 1
JP-01010-H03CDA10GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU2 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 101 | 1
JP-01010-H03CDA10GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU2 | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 101 | 1
JP-01020-H03CDA10GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU3 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 102 | 0
JP-01020-H03CDA10GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU3 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 102 | 0
JP-01020-H03CDA10GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU3 | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 102 | 0
JP-01030-H03CDA10GH004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU4 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 103 | 1
JP-01030-H03CDA10GH004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU4 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 103 | 1
JP-01030-H03CDA10GH004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU4 | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 103 | 1
JP-01040-H03CDA10GH005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU5 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 104 | 0
JP-01040-H03CDA10GH005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU5 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 104 | 0
JP-01040-H03CDA10GH005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit Control Cubicle =3+CU5 | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 104 | 0
JP-01050-H03CDA20GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Control Cubicle | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 105 | 1
JP-01050-H03CDA20GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Control Cubicle | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 105 | 1
JP-01050-H03CDA20GH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Control Cubicle | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 105 | 1
JP-01060-H03CDA20GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Supply Control Cubicle | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 106 | 0
JP-01060-H03CDA20GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Supply Control Cubicle | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 106 | 0
JP-01060-H03CDA20GH002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Supply Control Cubicle | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 106 | 0
JP-01070-H03CDA20GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine terminal Box | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-17 | 107 | 1
JP-01070-H03CDA20GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine terminal Box | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-17 | 107 | 1
JP-01070-H03CDA20GH003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine terminal Box | 2.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-17 | 107 | 1
JP-01080-H03CFA10FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Metering | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 108 | 0
JP-01080-H03CFA10FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Metering | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 108 | 0
JP-01080-H03CFA10FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Metering | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-14 | 2024-10-15 | 108 | 0
JP-01080-H03CFA10FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Metering | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-14 | 2024-10-15 | 108 | 0
JP-01090-H03CFA20FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Recorder | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-16 | 109 | 1
JP-01090-H03CFA20FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Recorder | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-16 | 109 | 1
JP-01090-H03CFA20FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Recorder | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-15 | 2024-10-16 | 109 | 1
JP-01090-H03CFA20FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Recorder | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-16 | 109 | 1
JP-01100-H03CFA30FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Energy Meter | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 110 | 0
JP-01100-H03CFA30FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Energy Meter | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-16 | 2024-10-17 | 110 | 0
JP-01100-H03CFA30FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Energy Meter | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-16 | 2024-10-17 | 110 | 0
JP-01100-H03CFA30FE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Energy Meter | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-16 | 2024-10-17 | 110 | 0
JP-01110-H03CHA10EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Protection Cubicle (=3+PU1) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-10 | 111 | 1
JP-01110-H03CHA10EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Protection Cubicle (=3+PU1) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-10 | 111 | 1
JP-01110-H03CHA10EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Protection Cubicle (=3+PU1) | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-08 | 2024-10-10 | 111 | 1
JP-01110-H03CHA10EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Protection Cubicle (=3+PU1) | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-10 | 111 | 1
JP-01120-H03CHA20EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Transformer Protection Cubicle (=3+PU2) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-13 | 112 | 0
JP-01120-H03CHA20EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Transformer Protection Cubicle (=3+PU2) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-13 | 112 | 0
JP-01120-H03CHA20EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Transformer Protection Cubicle (=3+PU2) | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-11 | 2024-10-13 | 112 | 0
JP-01120-H03CHA20EY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Unit3 Transformer Protection Cubicle (=3+PU2) | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-11 | 2024-10-13 | 112 | 0
JP-01130-H03CKN10EM001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Drop No.3/53 (Unit#3) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 113 | 1
JP-01130-H03CKN10EM001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Drop No.3/53 (Unit#3) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 113 | 1
JP-01130-H03CKN10EM001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Drop No.3/53 (Unit#3) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 113 | 1
JP-01140-H03LSL10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Drain Valve | 3.5 | 10 | 0 | 1 | CLEANING | 2024-10-08 | 2024-10-10 | 114 | 0
JP-01140-H03LSL10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Drain Valve | 3.5 | 20 | 0 | 0.5 | OPERATION TEST | 2024-10-08 | 2024-10-10 | 114 | 0
JP-01140-H03LSL10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Drain Valve | 3.5 | 30 | 0 | 1 | MECHANICAL INSPECTION | 2024-10-08 | 2024-10-10 | 114 | 0
JP-01140-H03LSL10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Drain Valve | 3.5 | 40 | 0 | 1 | LEAKAGE TEST | 2024-10-08 | 2024-10-10 | 114 | 0
JP-01150-H03LSL10BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 2.5 | 10 | 0 | 1 | CLEANING | 2024-10-08 | 2024-10-10 | 115 | 1
JP-01150-H03LSL10BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 2.5 | 20 | 0 | 0.5 | MECHANICAL INSPECTION | 2024-10-08 | 2024-10-10 | 115 | 1
JP-01150-H03LSL10BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 2.5 | 30 | 0 | 1 | LEAKAGE CHECK | 2024-10-08 | 2024-10-10 | 115 | 1
JP-01160-H03MEA10HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Up Stream Draft Tube (Bulb Case) | 38 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 116 | 0
JP-01160-H03MEA10HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Up Stream Draft Tube (Bulb Case) | 38 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 116 | 0
JP-01160-H03MEA10HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Up Stream Draft Tube (Bulb Case) | 38 | 30 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 116 | 0
JP-01170-H03MEA10HA001-CV-U | EGAT | KBI0 | 0 | ACTIVE | Up Stream Draft Tube (Bulb Case) | 1 | 10 | 0 | 1 | VISUAL INSPECTION สภาพผิวคอนกรีต,การรั่วซึมของน้ำ,รอยต่อเหล็กและคอนกรีต | 2024-10-10 | 2024-10-10 | 117 | 1
JP-01180-H03MEA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. - W/G At Closed Posi.(S01) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 118 | 0
JP-01180-H03MEA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. - W/G At Closed Posi.(S01) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 118 | 0
JP-01180-H03MEA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. - W/G At Closed Posi.(S01) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-09 | 2024-10-15 | 118 | 0
JP-01180-H03MEA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. - W/G At Closed Posi.(S01) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-09 | 2024-10-15 | 118 | 0
JP-01190-H03MEA20CG002-EE-U | EGAT | KBI0 | 0 | ACTIVE | W/G Position FeedBack Transducer -B01 | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 119 | 1
JP-01190-H03MEA20CG002-EE-U | EGAT | KBI0 | 0 | ACTIVE | W/G Position FeedBack Transducer -B01 | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 119 | 1
JP-01190-H03MEA20CG002-EE-U | EGAT | KBI0 | 0 | ACTIVE | W/G Position FeedBack Transducer -B01 | 3.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-15 | 119 | 1
JP-01190-H03MEA20CG002-EE-U | EGAT | KBI0 | 0 | ACTIVE | W/G Position FeedBack Transducer -B01 | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-09 | 2024-10-15 | 119 | 1
JP-01200-H03MEA20HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operating Ring | 33 | 10 | 0 | 7 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 120 | 0
JP-01200-H03MEA20HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operating Ring | 33 | 20 | 0 | 3 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 120 | 0
JP-01200-H03MEA20HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operating Ring | 33 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-11 | 2024-10-12 | 120 | 0
JP-01200-H03MEA20HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operating Ring | 33 | 40 | 0 | 20 | GUIDE STRIP INSPECTION & REPLACE | 2024-10-11 | 2024-10-12 | 120 | 0
JP-01200-H03MEA20HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operating Ring | 33 | 50 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 120 | 0
JP-01210-H03MEA20HA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Set (G/V safety link) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 121 | 1
JP-01210-H03MEA20HA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Set (G/V safety link) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 121 | 1
JP-01210-H03MEA20HA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Set (G/V safety link) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-09 | 2024-10-15 | 121 | 1
JP-01210-H03MEA20HA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Set (G/V safety link) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-09 | 2024-10-15 | 121 | 1
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 122 | 0
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 122 | 0
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 122 | 0
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 40 | 0 | 3 | GUIDE VANE GAP CHECK & ADJUST | 2024-10-15 | 2024-10-15 | 122 | 0
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 50 | 0 | 5 | PAINTING INSPECTION & REPAIR | 2024-10-15 | 2024-10-15 | 122 | 0
JP-01220-H03MEA20HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Set | 48 | 60 | 0 | 1 | TRAVELING TIME CHECK | 2024-10-17 | 2024-10-17 | 122 | 0
JP-01230-H03MEA20HA004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Arm Lever Wicket Gate Set | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 123 | 1
JP-01240-H03MEA20HA006-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Link Set | 11 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 124 | 0
JP-01240-H03MEA20HA006-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Link Set | 11 | 20 | 0 | 10 | BUSH SAMPLING INSPECTION | 2024-10-09 | 2024-10-10 | 124 | 0
JP-01250-H03MEA30AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Coupling Bolts | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 125 | 1
JP-01260-H03MEA30CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Speed Senser | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-12 | 126 | 0
JP-01260-H03MEA30CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Speed Senser | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-12 | 126 | 0
JP-01260-H03MEA30CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Speed Senser | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-08 | 2024-10-12 | 126 | 0
JP-01270-H03MEA30CY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Vibration | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-13 | 127 | 1
JP-01270-H03MEA30CY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Vibration | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-12 | 2024-10-13 | 127 | 1
JP-01270-H03MEA30CY001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Vibration | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-12 | 2024-10-13 | 127 | 1
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 40 | 0 | 2 | OPERATION TEST | 2024-10-14 | 2024-10-17 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 50 | 0 | 1 | TRAVELING TIME CHECK | 2024-10-17 | 2024-10-17 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 60 | 0 | 60 | SEAL INSPECTION & REPLACE | 2024-10-08 | 2024-10-14 | 128 | 0
JP-01280-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 107 | 70 | 0 | 5 | PAINTING INSPECTION & REPAIR | 2024-10-15 | 2024-10-15 | 128 | 0
JP-01290-H03MEA30HB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Set | 1 | 10 | 0 | 1 | SURFACE INSPECTION & REPAIR | 2024-10-08 | 2024-10-14 | 129 | 1
JP-01300-H03MEA30HB005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Cone | 43 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 130 | 0
JP-01300-H03MEA30HB005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Cone | 43 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 130 | 0
JP-01300-H03MEA30HB005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Cone | 43 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-14 | 130 | 0
JP-01300-H03MEA30HB005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Cone | 43 | 40 | 0 | 4 | PAINTING INSPECTION & REPAIR | 2024-10-08 | 2024-10-14 | 130 | 0
JP-01310-H03MEA40HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Inner Cone | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 131 | 1
JP-01310-H03MEA40HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Inner Cone | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 131 | 1
JP-01310-H03MEA40HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Inner Cone | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 131 | 1
JP-01320-H03MEA40HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Outer Cone | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 132 | 0
JP-01320-H03MEA40HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Outer Cone | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 132 | 0
JP-01320-H03MEA40HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Outer Cone | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-14 | 132 | 0
JP-01330-H03MEA40HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Hub Cover (Runner Cap) | 44 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 133 | 1
JP-01330-H03MEA40HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Hub Cover (Runner Cap) | 44 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 133 | 1
JP-01330-H03MEA40HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Hub Cover (Runner Cap) | 44 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 133 | 1
JP-01330-H03MEA40HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Hub Cover (Runner Cap) | 44 | 40 | 0 | 5 | PAINTING INSPECTION & REPAIR (หปคนม-ธ.) | 2024-10-15 | 2024-10-15 | 133 | 1
JP-01340-H03MEA40HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Hub Cover (Runner Cap) | 5 | 10 | 0 | 5 | PAINTING INSPECTION & REPAIR (children work order หรงอ-ฟ.) | 2024-10-15 | 2024-10-15 | 134 | 0
JP-01350-H03MEA40HA004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Draft Tube | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 135 | 1
JP-01350-H03MEA40HA004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Draft Tube | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 135 | 1
JP-01350-H03MEA40HA004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Draft Tube | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-14 | 135 | 1
JP-01360-H03MEA40HA004-CV-U | EGAT | KBI0 | 0 | ACTIVE | Draft Tube | 1 | 10 | 0 | 1 | VISUAL INSPECTION | 2024-10-10 | 2024-10-10 | 136 | 0
JP-01370-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 48 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 137 | 1
JP-01370-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 48 | 20 | 0 | 4 | SEAL INSPECTION | 2024-10-08 | 2024-10-09 | 137 | 1
JP-01370-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 48 | 30 | 0 | 5 | PAINTING INSPECTION & REPAIR (หปคนม-ธ.) | 2024-10-15 | 2024-10-15 | 137 | 1
JP-01370-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 48 | 40 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 137 | 1
JP-01370-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 48 | 50 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 137 | 1
JP-01380-H03MEA40HA005-ME-U | EGAT | KBI0 | 0 | ACTIVE | Discharge Ring | 5 | 10 | 0 | 5 | PAINTING INSPECTION & REPAIR (children work order หรงอ-ฟ.) | 2024-10-15 | 2024-10-15 | 138 | 0
JP-01390-H03MEA40HA006-ME-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Shaft Seal (No Replace Seal) | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 139 | 1
JP-01400-H03MED10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Turbine Brg. Instrument | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-12 | 140 | 0
JP-01400-H03MED10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Turbine Brg. Instrument | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-12 | 140 | 0
JP-01400-H03MED10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Turbine Brg. Instrument | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-12 | 140 | 0
JP-01400-H03MED10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Turbine Brg. Instrument | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-12 | 140 | 0
JP-01410-H03MES10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Supply Valve for Shaft Seal (Solenoid Valve) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-12 | 141 | 1
JP-01410-H03MES10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Supply Valve for Shaft Seal (Solenoid Valve) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-12 | 141 | 1
JP-01410-H03MES10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Supply Valve for Shaft Seal (Solenoid Valve) | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-12 | 141 | 1
JP-01410-H03MES10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Supply Valve for Shaft Seal (Solenoid Valve) | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-12 | 141 | 1
JP-01420-H03MES10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Water Supply Valve for Shaft Seal (Solenoid Valve) | 4 | 10 | 0 | 4 | MECHANICAL INSPECTION & CLEANING | 2024-10-14 | 2024-10-15 | 142 | 0
JP-01430-H03MES10CF001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Flow Indicator (1+TB-S20) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-12 | 143 | 1
JP-01430-H03MES10CF001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Flow Indicator (1+TB-S20) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-12 | 143 | 1
JP-01430-H03MES10CF001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Flow Indicator (1+TB-S20) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-09 | 2024-10-12 | 143 | 1
JP-01430-H03MES10CF001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Flow Indicator (1+TB-S20) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-09 | 2024-10-12 | 143 | 1
JP-01440-H03MEV10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 144 | 0
JP-01440-H03MEV10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 3.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 144 | 0
JP-01440-H03MEV10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 3.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-09 | 2024-10-11 | 144 | 0
JP-01440-H03MEV10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 3.5 | 40 | 0 | 1 | BEARING REPLACE (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-09 | 2024-10-11 | 144 | 0
JP-01450-H03MEV10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 1.4 | 10 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 145 | 1
JP-01450-H03MEV10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 1.4 | 20 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 145 | 1
JP-01450-H03MEV10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.1 (DN 80 ) | 1.4 | 30 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 145 | 1
JP-01460-H03MEV10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-11 | 146 | 0
JP-01460-H03MEV10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 3.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-09 | 2024-10-11 | 146 | 0
JP-01460-H03MEV10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 3.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-09 | 2024-10-11 | 146 | 0
JP-01460-H03MEV10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 3.5 | 40 | 0 | 1 | BEARING REPLACE (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-09 | 2024-10-11 | 146 | 0
JP-01470-H03MEV10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 1.4 | 10 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 147 | 1
JP-01470-H03MEV10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 1.4 | 20 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 147 | 1
JP-01470-H03MEV10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Filling Oil Pump No.2 (DN 80 ) | 1.4 | 30 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 147 | 1
JP-01480-H03MEV10AT001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Tank | 41 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-13 | 2024-10-14 | 148 | 0
JP-01480-H03MEV10AT001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Tank | 41 | 20 | 0 | 40 | OIL PURIFY | 2024-10-12 | 2024-10-15 | 148 | 0
JP-01490-H03MEV10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Lower Oil Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-13 | 2024-10-14 | 149 | 1
JP-01490-H03MEV10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Lower Oil Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-13 | 2024-10-14 | 149 | 1
JP-01490-H03MEV10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Lower Oil Tank | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-13 | 2024-10-14 | 149 | 1
JP-01490-H03MEV10CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Lower Oil Tank | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-13 | 2024-10-14 | 149 | 1
JP-01500-H03MEV10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Temp.) for Lower Oil Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-15 | 150 | 0
JP-01500-H03MEV10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Temp.) for Lower Oil Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-15 | 150 | 0
JP-01500-H03MEV10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Temp.) for Lower Oil Tank | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 150 | 0
JP-01500-H03MEV10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Temp.) for Lower Oil Tank | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-14 | 2024-10-15 | 150 | 0
JP-01510-H03MEV20AN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-10 | 151 | 1
JP-01510-H03MEV20AN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 3.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-09 | 2024-10-10 | 151 | 1
JP-01510-H03MEV20AN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 3.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-09 | 2024-10-10 | 151 | 1
JP-01510-H03MEV20AN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 3.5 | 40 | 0 | 1 | BEARING REPLACE (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-09 | 2024-10-10 | 151 | 1
JP-01520-H03MEV20AN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 1.4 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 152 | 0
JP-01520-H03MEV20AN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 1.4 | 20 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 152 | 0
JP-01520-H03MEV20AN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Exhaust Fan | 1.4 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 152 | 0
JP-01530-H03MEV30AC001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Oil Cooler No.1 | 0.5 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 153 | 1
JP-01540-H03MEV30AC002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Oil Cooler No.2 | 0.5 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 154 | 0
JP-01550-H03MEV30AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Inlet Scrw.Thermometer (DN 15)(R1/2) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 155 | 1
JP-01550-H03MEV30AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Inlet Scrw.Thermometer (DN 15)(R1/2) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 155 | 1
JP-01550-H03MEV30AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Inlet Scrw.Thermometer (DN 15)(R1/2) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-14 | 2024-10-16 | 155 | 1
JP-01550-H03MEV30AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Inlet Scrw.Thermometer (DN 15)(R1/2) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-14 | 2024-10-16 | 155 | 1
JP-01560-H03MEV30AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 156 | 0
JP-01560-H03MEV30AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 156 | 0
JP-01560-H03MEV30AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-14 | 2024-10-16 | 156 | 0
JP-01560-H03MEV30AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Outlet Scrw.Thermometer (DN 15)(R1/2 ) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-14 | 2024-10-16 | 156 | 0
JP-01570-H03MEV40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Diff. Pressure Switch (Oil Filter) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 157 | 1
JP-01570-H03MEV40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Diff. Pressure Switch (Oil Filter) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 157 | 1
JP-01570-H03MEV40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Diff. Pressure Switch (Oil Filter) | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-16 | 157 | 1
JP-01570-H03MEV40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Diff. Pressure Switch (Oil Filter) | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-14 | 2024-10-16 | 157 | 1
JP-01580-H03MEV50AT001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Tank | 5 | 10 | 0 | 3 | MECHANICAL INSPECTION & CLEANING | 2024-10-13 | 2024-10-14 | 158 | 0
JP-01580-H03MEV50AT001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Tank | 5 | 20 | 0 | 2 | OIL DRAIN | 2024-10-12 | 2024-10-12 | 158 | 0
JP-01590-H03MEV50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for High Oil Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 159 | 1
JP-01590-H03MEV50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for High Oil Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 159 | 1
JP-01590-H03MEV50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for High Oil Tank | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 159 | 1
JP-01590-H03MEV50CE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for High Oil Tank | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-11 | 2024-10-14 | 159 | 1
JP-01600-H03MEV50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Temp. ) for High Oil Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-11 | 2024-10-14 | 160 | 0
JP-01600-H03MEV50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Temp. ) for High Oil Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-14 | 160 | 0
JP-01600-H03MEV50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Temp. ) for High Oil Tank | 3.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-11 | 2024-10-14 | 160 | 0
JP-01600-H03MEV50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Temp. ) for High Oil Tank | 3.5 | 40 | 0 | 1 | CALIBRATION TEST | 2024-10-11 | 2024-10-14 | 160 | 0
JP-01610-H03MEV60AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Main Bearing Oil Valve (Overhaul Oil Valve) | 11 | 10 | 0 | 10 | MECHANICAL INSPECTION & CLEANING | 2024-10-14 | 2024-10-15 | 161 | 1
JP-01610-H03MEV60AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Main Bearing Oil Valve (Overhaul Oil Valve) | 11 | 20 | 0 | 1 | OPERATION TEST | 2024-10-14 | 2024-10-15 | 161 | 1
JP-01620-H03MEV60AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Main Bearing Oil Valve (Overhaul Oil Valve) | 4 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-14 | 162 | 0
JP-01620-H03MEV60AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Main Bearing Oil Valve (Overhaul Oil Valve) | 4 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-14 | 162 | 0
JP-01620-H03MEV60AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Main Bearing Oil Valve (Overhaul Oil Valve) | 4 | 30 | 0 | 2 | MOTOR BEARING REPLACE (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-10 | 2024-10-14 | 162 | 0
JP-01630-H03MEV70BN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 6 | 10 | 0 | 2 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-15 | 163 | 1
JP-01630-H03MEV70BN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 6 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-15 | 163 | 1
JP-01630-H03MEV70BN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 6 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-15 | 163 | 1
JP-01630-H03MEV70BN001-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 6 | 40 | 0 | 2 | BEARING REPLACE | 2024-10-12 | 2024-10-15 | 163 | 1
JP-01640-H03MEV70BN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 1.4 | 10 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 164 | 0
JP-01640-H03MEV70BN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 1.4 | 20 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 164 | 0
JP-01640-H03MEV70BN001-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil Pump ( DC ) & ( AC ) | 1.4 | 30 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 164 | 0
JP-01650-H03MEV70BN002-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Main Thrust Brg. | 1 | 10 | 0 | 1 | CALIBRATION TEST | 2024-10-12 | 2024-10-15 | 165 | 1
JP-01660-H03MEV70BN002-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Main Thrust Brg. | 2 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 166 | 0
JP-01670-H03MEV70BN003-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Gen. Guide Brg. | 1 | 10 | 0 | 1 | CALIBRATION TEST | 2024-10-12 | 2024-10-15 | 167 | 1
JP-01680-H03MEV70BN003-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Gen. Guide Brg. | 2 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 168 | 0
JP-01690-H03MEV70BN004-EE-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Turbine Guide Brg. | 1 | 10 | 0 | 1 | CALIBRATION TEST | 2024-10-12 | 2024-10-15 | 169 | 1
JP-01700-H03MEV70BN004-ME-U | EGAT | KBI0 | 0 | ACTIVE | High Pressure Oil for Turbine Guide Brg. | 2 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 170 | 0
JP-01710-H03MEX10AC001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Gov. Oil Cooler (2902) | 4 | 10 | 0 | 1 | HYDROSTATIC TEST | 2024-10-14 | 2024-10-15 | 171 | 1
JP-01710-H03MEX10AC001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Gov. Oil Cooler (2902) | 4 | 20 | 0 | 3 | MECHANICAL INSPECTION & CLEANING | 2024-10-14 | 2024-10-15 | 171 | 1
JP-01720-H03MEX10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 2 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-14 | 172 | 0
JP-01720-H03MEX10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 2 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-14 | 172 | 0
JP-01730-H03MEX10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 1.9 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 173 | 1
JP-01730-H03MEX10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 1.9 | 20 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 173 | 1
JP-01730-H03MEX10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 1.9 | 30 | 0 | 0.5 | CAPACITY TEST | 2024-10-08 | 2024-10-08 | 173 | 1
JP-01730-H03MEX10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 1.9 | 40 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 173 | 1
JP-01740-H03MEX10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.1 (210/1) | 1 | 10 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-14 | 174 | 0
JP-01750-H03MEX10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 2 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-14 | 175 | 1
JP-01750-H03MEX10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 2 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-14 | 175 | 1
JP-01760-H03MEX10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 1.9 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 176 | 0
JP-01760-H03MEX10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 1.9 | 20 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 176 | 0
JP-01760-H03MEX10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 1.9 | 40 | 0 | 0.5 | CAPACITY TEST | 2024-10-08 | 2024-10-08 | 176 | 0
JP-01760-H03MEX10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 1.9 | 50 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 176 | 0
JP-01770-H03MEX10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Pump No.2 (210/2) | 1 | 10 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-14 | 177 | 1
JP-01780-H03MEX10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 1.4 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 178 | 0
JP-01780-H03MEX10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 1.4 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 178 | 0
JP-01780-H03MEX10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 1.4 | 40 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 178 | 0
JP-01790-H03MEX10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-14 | 179 | 1
JP-01790-H03MEX10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 5 | 20 | 0 | 2 | ELECTRICAL TEST | 2024-10-12 | 2024-10-14 | 179 | 1
JP-01790-H03MEX10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 5 | 30 | 0 | 1 | BEARING REPLACE | 2024-10-12 | 2024-10-14 | 179 | 1
JP-01790-H03MEX10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Governor Oil Curculation Pump (2901) | 5 | 40 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-14 | 179 | 1
JP-01800-H03MEX10BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Sump Tank | 45 | 10 | 0 | 5 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-11 | 180 | 0
JP-01800-H03MEX10BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Sump Tank | 45 | 30 | 0 | 40 | OIL PURIFY | 2024-10-08 | 2024-10-11 | 180 | 0
JP-01810-H03MEX10CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Oil Level Gauge | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 181 | 1
JP-01810-H03MEX10CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Oil Level Gauge | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-14 | 181 | 1
JP-01810-H03MEX10CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Oil Level Gauge | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-14 | 181 | 1
JP-01810-H03MEX10CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Oil Level Gauge | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-08 | 2024-10-14 | 181 | 1
JP-01820-H03MEX10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermometer for Oil Outlet Temp.(2905) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 182 | 0
JP-01820-H03MEX10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermometer for Oil Outlet Temp.(2905) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-14 | 182 | 0
JP-01820-H03MEX10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermometer for Oil Outlet Temp.(2905) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-14 | 182 | 0
JP-01820-H03MEX10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermometer for Oil Outlet Temp.(2905) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-08 | 2024-10-14 | 182 | 0
JP-01830-H03MEX20BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Tank (240) | 6 | 10 | 0 | 5 | MECHANICAL INSPECTION & CLEANING | 2024-10-09 | 2024-10-10 | 183 | 1
JP-01830-H03MEX20BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Tank (240) | 6 | 20 | 0 | 1 | OIL DRAIN | 2024-10-08 | 2024-10-08 | 183 | 1
JP-01840-H03MEX20CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Governor Oil Pressure Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-10 | 184 | 0
JP-01840-H03MEX20CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Governor Oil Pressure Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-11 | 2024-10-11 | 184 | 0
JP-01840-H03MEX20CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Governor Oil Pressure Tank | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-11 | 2024-10-12 | 184 | 0
JP-01840-H03MEX20CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument (Oil Level) for Governor Oil Pressure Tank | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-13 | 2024-10-14 | 184 | 0
JP-01850-H03MEX20CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Guage for Pressure Tank (2407) | 2 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-11 | 185 | 1
JP-01850-H03MEX20CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Guage for Pressure Tank (2407) | 2 | 20 | 0 | 1 | CALIBRATION TEST | 2024-10-11 | 2024-10-12 | 185 | 1
JP-01860-H03MEX30AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 1.9 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 186 | 0
JP-01860-H03MEX30AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 1.9 | 20 | 0 | 0.5 | CAPACITY TEST | 2024-10-08 | 2024-10-08 | 186 | 0
JP-01860-H03MEX30AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 1.9 | 30 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 186 | 0
JP-01860-H03MEX30AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 1.9 | 40 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 186 | 0
JP-01870-H03MEX30AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-14 | 187 | 1
JP-01870-H03MEX30AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 2.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-12 | 2024-10-14 | 187 | 1
JP-01870-H03MEX30AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.1 (7701) | 2.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-14 | 187 | 1
JP-01880-H03MEX30AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 1.9 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 188 | 0
JP-01880-H03MEX30AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 1.9 | 20 | 0 | 0.5 | CAPACITY TEST | 2024-10-08 | 2024-10-08 | 188 | 0
JP-01880-H03MEX30AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 1.9 | 30 | 0 | 1 | VIBRATION TEST & ALIGNMENT IF NECESSARY | 2024-10-08 | 2024-10-08 | 188 | 0
JP-01880-H03MEX30AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 1.9 | 40 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 188 | 0
JP-01890-H03MEX30AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-14 | 189 | 1
JP-01890-H03MEX30AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 2.5 | 20 | 0 | 0.5 | ELECTRICAL TEST | 2024-10-12 | 2024-10-14 | 189 | 1
JP-01890-H03MEX30AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Pump No.2 (7702) | 2.5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-14 | 189 | 1
JP-01900-H03MEX30BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Tank (7700) | 4 | 10 | 0 | 3 | MECHANICAL INSPECTION & CLEANING | 2024-10-09 | 2024-10-10 | 190 | 0
JP-01900-H03MEX30BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Leakage Oil Tank (7700) | 4 | 20 | 0 | 1 | OIL DRAIN | 2024-10-08 | 2024-10-08 | 190 | 0
JP-01910-H03MEX30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Leaked Oil Sump Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-13 | 2024-10-15 | 191 | 1
JP-01910-H03MEX30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Leaked Oil Sump Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-13 | 2024-10-15 | 191 | 1
JP-01910-H03MEX30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Leaked Oil Sump Tank | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-13 | 2024-10-15 | 191 | 1
JP-01910-H03MEX30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Leaked Oil Sump Tank | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-13 | 2024-10-15 | 191 | 1
JP-01920-H03MEX30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Differential Pressure Switch (S02) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-13 | 2024-10-15 | 192 | 0
JP-01920-H03MEX30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Differential Pressure Switch (S02) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-13 | 2024-10-15 | 192 | 0
JP-01920-H03MEX30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Differential Pressure Switch (S02) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-13 | 2024-10-15 | 192 | 0
JP-01920-H03MEX30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Differential Pressure Switch (S02) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-13 | 2024-10-15 | 192 | 0
JP-01930-H03MEX40BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Hub Oil Tank (7750) | 4 | 10 | 0 | 3 | MECHANICAL INSPECTION & CLEANING | 2024-10-09 | 2024-10-14 | 193 | 1
JP-01930-H03MEX40BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Hub Oil Tank (7750) | 4 | 20 | 0 | 1 | OIL DRAIN | 2024-10-08 | 2024-10-08 | 193 | 1
JP-01940-H03MEX40CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Runner Hub Oil Tank | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-12 | 194 | 0
JP-01940-H03MEX40CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Runner Hub Oil Tank | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-12 | 194 | 0
JP-01940-H03MEX40CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Runner Hub Oil Tank | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-12 | 194 | 0
JP-01940-H03MEX40CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Instrument ( Oil Level ) for Runner Hub Oil Tank | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-08 | 2024-10-12 | 194 | 0
JP-01950-H03MEX50AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Servo Motor | 1 | 10 | 0 | 1 | TRAVELING TIME CHECK | 2024-10-17 | 2024-10-17 | 195 | 1
JP-01960-H03MEX50BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Oil Head (8500) | 3 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-13 | 2024-10-13 | 196 | 0
JP-01960-H03MEX50BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Oil Head (8500) | 3 | 20 | 0 | 2 | DOWEL REPLACE | 2024-10-13 | 2024-10-13 | 196 | 0
JP-01970-H03MEX50BR004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 6 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-13 | 2024-10-13 | 197 | 1
JP-01970-H03MEX50BR004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 6 | 20 | 0 | 5 | FLEXIBLE HOST REPLACE (CONTROL & LUBE) | 2024-10-13 | 2024-10-13 | 197 | 1
JP-01980-H03MEX50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Indicator Position | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 198 | 0
JP-01980-H03MEX50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Indicator Position | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-14 | 198 | 0
JP-01980-H03MEX50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Indicator Position | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-14 | 198 | 0
JP-01980-H03MEX50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Indicator Position | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-08 | 2024-10-14 | 198 | 0
JP-01990-H03MEX60AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Overspeed Pendulum Valve 1200 | 1 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 199 | 1
JP-01990-H03MEX60AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Overspeed Pendulum Valve 1200 | 1 | 20 | 0 | 0.5 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 199 | 1
JP-02000-H03MEX60AU001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pendulum | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-16 | 200 | 0
JP-02000-H03MEX60AU001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pendulum | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-16 | 200 | 0
JP-02000-H03MEX60AU001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pendulum | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-16 | 200 | 0
JP-02000-H03MEX60AU001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pendulum | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-15 | 2024-10-16 | 200 | 0
JP-02010-H03MEX60CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Overspeed Device | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-15 | 2024-10-16 | 201 | 1
JP-02010-H03MEX60CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Overspeed Device | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-15 | 2024-10-16 | 201 | 1
JP-02010-H03MEX60CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Overspeed Device | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-15 | 2024-10-16 | 201 | 1
JP-02010-H03MEX60CS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Limit Sw. Overspeed Device | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-15 | 2024-10-16 | 201 | 1
JP-02020-H03MEX70AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Control Device | 1 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 202 | 0
JP-02020-H03MEX70AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Control Device | 1 | 20 | 0 | 0.5 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 202 | 0
JP-02030-H03MEX70AA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Control Device | 1 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 203 | 1
JP-02030-H03MEX70AA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Wicket Gate Control Device | 1 | 20 | 0 | 0.5 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 203 | 1
JP-02040-H03MEX70AA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Control Device | 1 | 10 | 0 | 0.5 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 204 | 0
JP-02040-H03MEX70AA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Runner Blade Control Device | 1 | 20 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 204 | 0
JP-02050-H03MEX70CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Control ( Pressure Sw. ) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 205 | 1
JP-02050-H03MEX70CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Control ( Pressure Sw. ) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-14 | 205 | 1
JP-02050-H03MEX70CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Turbine Control ( Pressure Sw. ) | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-08 | 2024-10-14 | 205 | 1
JP-02060-H03MEX90AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Servo Motor (79000/1) | 3.5 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 206 | 0
JP-02060-H03MEX90AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Servo Motor (79000/1) | 3.5 | 20 | 0 | 3 | SQUEEZE CHECK & ADJUST IF NECESSARY | 2024-10-17 | 2024-10-17 | 206 | 0
JP-02070-H03MEX90AU002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Servo Motor (79000/2) | 3.5 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 207 | 1
JP-02070-H03MEX90AU002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Servo Motor (79000/2) | 3.5 | 20 | 0 | 3 | SQUEEZE CHECK & ADJUST IF NECESSARY | 2024-10-17 | 2024-10-17 | 207 | 1
JP-02080-H03MEX90CW001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Closing Weight (79010) | 4 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-17 | 208 | 0
JP-02080-H03MEX90CW001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Closing Weight (79010) | 4 | 20 | 0 | 3 | OPERATION TEST | 2024-10-17 | 2024-10-17 | 208 | 0
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 10 | 0 | 2 | REMOVE ROTOR LEAD | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 20 | 0 | 0.5 | VISUAL INSPECTION | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 30 | 0 | 1 | ELECTRICAL TEST(PRE-TEST) | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 40 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 50 | 0 | 4 | DRYING OUT | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 60 | 0 | 1 | ELECTRICAL TEST(FINAL-TEST) | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 70 | 0 | 1 | FINAL INSPECTION | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 80 | 0 | 1 | SPRAY RED VARNISH (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02090-H03MKA20-EE-U | EGAT | KBI0 | 0 | ACTIVE | Generator Rotor | 13 | 90 | 0 | 2 | ASSEMBLY AND RE-INSULATION | 2024-10-10 | 2024-10-19 | 209 | 1
JP-02100-H03MKA20AE001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Motor for Coal Exaust GB-M07 | 1 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-15 | 210 | 0
JP-02110-H03MKA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Position Rotor Locking Bolt GB-S10 | 2 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-15 | 211 | 1
JP-02110-H03MKA20CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Position Rotor Locking Bolt GB-S10 | 2 | 20 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-08 | 2024-10-15 | 211 | 1
JP-02120-H03MKA20CG001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Position Rotor Locking Bolt GB-S10 | 1 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 212 | 0
JP-02120-H03MKA20CG001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Position Rotor Locking Bolt GB-S10 | 1 | 20 | 0 | 0.5 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 212 | 0
JP-02130-H03MKA20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Air Slip Ring Room GB-S21 | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-15 | 213 | 1
JP-02130-H03MKA20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Air Slip Ring Room GB-S21 | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-15 | 213 | 1
JP-02130-H03MKA20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Air Slip Ring Room GB-S21 | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-08 | 2024-10-15 | 213 | 1
JP-02130-H03MKA20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Air Slip Ring Room GB-S21 | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-08 | 2024-10-15 | 213 | 1
JP-02140-H03MKA30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Level Drainage Line GB-S09 | 2 | 10 | 0 | 1 | CALIBRATION TEST | 2024-10-08 | 2024-10-16 | 214 | 0
JP-02140-H03MKA30CL001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Water Level Drainage Line GB-S09 | 2 | 20 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-08 | 2024-10-16 | 214 | 0
JP-02150-H03MKA30HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Bulb Noss | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 215 | 1
JP-02150-H03MKA30HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Bulb Noss | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 215 | 1
JP-02150-H03MKA30HA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Bulb Noss | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-16 | 215 | 1
JP-02160-H03MKA30HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Vertical Bulb Support | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 216 | 0
JP-02160-H03MKA30HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Vertical Bulb Support | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 216 | 0
JP-02160-H03MKA30HA002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Vertical Bulb Support | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 216 | 0
JP-02170-H03MKA30HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Lateral Support | 39 | 10 | 0 | 30 | INSTALL SCAFFOLDING | 2024-09-03 | 2024-09-12 | 217 | 1
JP-02170-H03MKA30HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Lateral Support | 39 | 20 | 0 | 7 | REMOVE SCAFFOLDING | 2024-10-16 | 2024-10-16 | 217 | 1
JP-02170-H03MKA30HA003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Lateral Support | 39 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-09 | 217 | 1
JP-02180-H03MKA30HA003-CV-U | EGAT | KBI0 | 0 | ACTIVE | Lateral Support | 2 | 10 | 0 | 2 | CIVIL INSPECTION | 2024-10-08 | 2024-10-16 | 218 | 0
JP-02190-H03MKA40CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Winding | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-19 | 219 | 1
JP-02190-H03MKA40CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Winding | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-19 | 219 | 1
JP-02190-H03MKA40CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Winding | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-10 | 2024-10-19 | 219 | 1
JP-02190-H03MKA40CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Winding | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-10 | 2024-10-19 | 219 | 1
JP-02200-H03MKA40CT002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Core | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-19 | 220 | 0
JP-02200-H03MKA40CT002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Core | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-19 | 220 | 0
JP-02200-H03MKA40CT002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Core | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-10 | 2024-10-19 | 220 | 0
JP-02200-H03MKA40CT002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Stator Core | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-10 | 2024-10-19 | 220 | 0
JP-02210-H03MKA40CT003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Stand Still Heating | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-19 | 221 | 1
JP-02210-H03MKA40CT003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Stand Still Heating | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-19 | 221 | 1
JP-02210-H03MKA40CT003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Stand Still Heating | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-10 | 2024-10-19 | 221 | 1
JP-02210-H03MKA40CT003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thermostat Stand Still Heating | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-10 | 2024-10-19 | 221 | 1
JP-02220-H03MKA40HA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Frame | 0.5 | 10 | 0 | 0.5 | VISUAL INSPECTION | 2024-10-10 | 2024-10-19 | 222 | 0
JP-02230-H03MKA40HA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Core | 0.5 | 10 | 0 | 0.5 | VISUAL INSPECTION | 2024-10-10 | 2024-10-19 | 223 | 1
JP-02240-H03MKA40HA003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Winding | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-19 | 224 | 0
JP-02240-H03MKA40HA003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Winding | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-19 | 224 | 0
JP-02240-H03MKA40HA003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Winding | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-19 | 224 | 0
JP-02240-H03MKA40HA003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Stator Winding | 3.5 | 40 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-10 | 2024-10-19 | 224 | 0
JP-02250-H03MKA50AC001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.01 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 225 | 1
JP-02250-H03MKA50AC001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.01 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 225 | 1
JP-02250-H03MKA50AC001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.01 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-15 | 225 | 1
JP-02260-H03MKA50AC002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.02 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 226 | 0
JP-02260-H03MKA50AC002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.02 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 226 | 0
JP-02260-H03MKA50AC002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.02 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-15 | 226 | 0
JP-02270-H03MKA50AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.03 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 227 | 1
JP-02270-H03MKA50AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.03 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 227 | 1
JP-02270-H03MKA50AC003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.03 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-15 | 227 | 1
JP-02280-H03MKA50AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.04 | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 228 | 0
JP-02280-H03MKA50AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.04 | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 228 | 0
JP-02280-H03MKA50AC004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Gen. Cooling Air Fan No.04 | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-09 | 2024-10-15 | 228 | 0
JP-02290-H03MKA50AC005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Air Dehumidditier | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 229 | 1
JP-02290-H03MKA50AC005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Air Dehumidditier | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 229 | 1
JP-02290-H03MKA50AC005-EE-U | EGAT | KBI0 | 0 | ACTIVE | Air Dehumidditier | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST (ADD MEGGER TEST) | 2024-10-09 | 2024-10-15 | 229 | 1
JP-02300-H03MKA50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Air Circulat.Pressure Sw. | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 230 | 0
JP-02300-H03MKA50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Air Circulat.Pressure Sw. | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 230 | 0
JP-02300-H03MKA50CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Air Circulat.Pressure Sw. | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-15 | 230 | 0
JP-02310-H03MKA50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Gen. Air Fan | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-09 | 2024-10-15 | 231 | 1
JP-02310-H03MKA50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Gen. Air Fan | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-09 | 2024-10-15 | 231 | 1
JP-02310-H03MKA50CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Gen. Air Fan | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-09 | 2024-10-15 | 231 | 1
JP-02320-H03MKA60AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Brake Jack (Set) | 5 | 10 | 0 | 4 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 232 | 0
JP-02320-H03MKA60AU001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Brake Jack (Set) | 5 | 20 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 232 | 0
JP-02330-H03MKA60CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Position of Braking Jack (Limit Switch) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 233 | 1
JP-02330-H03MKA60CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Position of Braking Jack (Limit Switch) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 233 | 1
JP-02330-H03MKA60CG001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Position of Braking Jack (Limit Switch) | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-14 | 2024-10-16 | 233 | 1
JP-02340-H03MKA60CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Low Pressure Air (Pressure Switch) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-14 | 2024-10-16 | 234 | 0
JP-02340-H03MKA60CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Low Pressure Air (Pressure Switch) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-14 | 2024-10-16 | 234 | 0
JP-02340-H03MKA60CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Low Pressure Air (Pressure Switch) | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-14 | 2024-10-16 | 234 | 0
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 235 | 1
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-11 | 235 | 1
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 30 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-09 | 2024-10-11 | 235 | 1
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 40 | 0 | 1 | OVER ALL TEST ( DRY TEST ) | 2024-10-12 | 2024-10-13 | 235 | 1
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 50 | 0 | 1 | OPERATION TEST AND FINE TUNNING | 2024-10-12 | 2024-10-13 | 235 | 1
JP-02350-H03MKC10GW001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Automatic Voltage Regulator Cabinet (+EC1) | 5.5 | 60 | 0 | 1 | CHARACTERISTIC TEST | 2024-10-13 | 2024-10-14 | 235 | 1
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 236 | 0
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-11 | 236 | 0
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 30 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-09 | 2024-10-11 | 236 | 0
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 40 | 0 | 1 | OVER ALL TEST ( DRY TEST ) | 2024-10-12 | 2024-10-13 | 236 | 0
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 50 | 0 | 1 | OPERATION TEST AND FINE TUNNING | 2024-10-12 | 2024-10-13 | 236 | 0
JP-02360-H03MKC10GW002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Rectifier Cabinet (+EC2) | 5.5 | 60 | 0 | 1 | CHARACTERISTIC TEST | 2024-10-13 | 2024-10-14 | 236 | 0
JP-02370-H03MKC10GW003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Field Circuit Cubicle (+EC3) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-11 | 237 | 1
JP-02370-H03MKC10GW003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Field Circuit Cubicle (+EC3) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-12 | 2024-10-13 | 237 | 1
JP-02370-H03MKC10GW003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Field Circuit Cubicle (+EC3) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-13 | 2024-10-14 | 237 | 1
JP-02380-H03MKC20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Excitation Transf. Cubicle (+MV3) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-11 | 238 | 0
JP-02380-H03MKC20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Excitation Transf. Cubicle (+MV3) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-12 | 2024-10-13 | 238 | 0
JP-02380-H03MKC20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Excitation Transf. Cubicle (+MV3) | 3.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-13 | 238 | 0
JP-02380-H03MKC20GS001-EE-U | EGAT | KBI0 | 0 | ACTIVE | DS Excitation Transf. Cubicle (+MV3) | 3.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-13 | 2024-10-14 | 238 | 0
JP-02390-H03MKC30-EE-U | EGAT | KBI0 | 0 | ACTIVE | Excitation Transformer Cubicle (=3+ET) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-10 | 239 | 1
JP-02390-H03MKC30-EE-U | EGAT | KBI0 | 0 | ACTIVE | Excitation Transformer Cubicle (=3+ET) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-10 | 239 | 1
JP-02390-H03MKC30-EE-U | EGAT | KBI0 | 0 | ACTIVE | Excitation Transformer Cubicle (=3+ET) | 2.5 | 30 | 0 | 1 | ELECTRICAL TEST | 2024-10-10 | 2024-10-10 | 239 | 1
JP-02400-H03MKD10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Main Thrust Brg. Pad Set | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-13 | 240 | 0
JP-02400-H03MKD10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Main Thrust Brg. Pad Set | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-13 | 240 | 0
JP-02400-H03MKD10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Main Thrust Brg. Pad Set | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-10 | 2024-10-13 | 240 | 0
JP-02410-H03MKD10HD002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thrust Bearng Set | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-13 | 241 | 1
JP-02410-H03MKD10HD002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thrust Bearng Set | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-13 | 241 | 1
JP-02410-H03MKD10HD002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Thrust Bearng Set | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-10 | 2024-10-13 | 241 | 1
JP-02420-H03MKD20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Counter Thrust Brg. Pad Set | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-10 | 2024-10-13 | 242 | 0
JP-02420-H03MKD20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Counter Thrust Brg. Pad Set | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-10 | 2024-10-13 | 242 | 0
JP-02420-H03MKD20CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Temp. Counter Thrust Brg. Pad Set | 2.5 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-10 | 2024-10-13 | 242 | 0
JP-02430-H03PCD20AA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Motor Operated Valve (4381) | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-08 | 2024-10-14 | 243 | 1
JP-02430-H03PCD20AA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Motor Operated Valve (4381) | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-08 | 2024-10-14 | 243 | 1
JP-02430-H03PCD20AA002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Motor Operated Valve (4381) | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-08 | 2024-10-14 | 243 | 1
JP-02440-H03PCD20CL001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Internal Oil Cooler (Main Tr. Oil Cooler) | 6 | 10 | 0 | 4 | MECHANICAL INSPECTION & CLEANING | 2024-10-14 | 2024-10-15 | 244 | 0
JP-02440-H03PCD20CL001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Internal Oil Cooler (Main Tr. Oil Cooler) | 6 | 20 | 0 | 2 | HYDROSTATIC TEST | 2024-10-14 | 2024-10-15 | 244 | 0
JP-02450-H03PGA10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-17 | 245 | 1
JP-02450-H03PGA10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-17 | 245 | 1
JP-02450-H03PGA10AP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-17 | 245 | 1
JP-02460-H03PGA10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 0.6 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 246 | 0
JP-02460-H03PGA10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 0.6 | 20 | 0 | 0.2 | VIBRATION TEST | 2024-10-08 | 2024-10-08 | 246 | 0
JP-02460-H03PGA10AP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.1 | 0.6 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 246 | 0
JP-02470-H03PGA10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-17 | 247 | 1
JP-02470-H03PGA10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-17 | 247 | 1
JP-02470-H03PGA10AP002-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-17 | 247 | 1
JP-02480-H03PGA10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 0.6 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 248 | 0
JP-02480-H03PGA10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 0.6 | 20 | 0 | 0.2 | VIBRATION TEST | 2024-10-08 | 2024-10-08 | 248 | 0
JP-02480-H03PGA10AP002-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Generator No.2 | 0.6 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 248 | 0
JP-02490-H03PGA10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-17 | 249 | 1
JP-02490-H03PGA10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-17 | 249 | 1
JP-02490-H03PGA10AP003-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-17 | 249 | 1
JP-02500-H03PGA10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 0.6 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 250 | 0
JP-02500-H03PGA10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 0.6 | 20 | 0 | 0.2 | VIBRATION TEST | 2024-10-08 | 2024-10-08 | 250 | 0
JP-02500-H03PGA10AP003-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.1 | 0.6 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 250 | 0
JP-02510-H03PGA10AP004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 3 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-12 | 2024-10-17 | 251 | 1
JP-02510-H03PGA10AP004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 3 | 20 | 0 | 1 | ELECTRICAL TEST | 2024-10-12 | 2024-10-17 | 251 | 1
JP-02510-H03PGA10AP004-EE-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-12 | 2024-10-17 | 251 | 1
JP-02520-H03PGA10AP004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 0.6 | 10 | 0 | 0.2 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 252 | 0
JP-02520-H03PGA10AP004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 0.6 | 20 | 0 | 0.2 | VIBRATION TEST | 2024-10-08 | 2024-10-08 | 252 | 0
JP-02520-H03PGA10AP004-ME-U | EGAT | KBI0 | 0 | ACTIVE | Cooling Water Pump Bearing No.2 | 0.6 | 30 | 0 | 0.2 | OPERATION TEST | 2024-10-08 | 2024-10-08 | 252 | 0
JP-02530-H03PGA10BB001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Expansion Tank ( DN 20 ) ( R3/4 ) | 2 | 10 | 0 | 1 | CALIBRATION TEST | 2024-10-12 | 2024-10-17 | 253 | 1
JP-02530-H03PGA10BB001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Expansion Tank ( DN 20 ) ( R3/4 ) | 2 | 20 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-12 | 2024-10-17 | 253 | 1
JP-02540-H03PGA10BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Expansion Tank ( DN 20 ) ( R3/4 ) | 0.5 | 10 | 0 | 0.5 | MECHANICAL INSPECTION & CLEANING | 2024-10-08 | 2024-10-08 | 254 | 0
JP-02550-H03QEB10BB001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Air Pressure Tank (365) | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 255 | 1
JP-02560-H03QEB10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Manometer (3552) | 3.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-16 | 2024-10-17 | 256 | 0
JP-02560-H03QEB10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Manometer (3552) | 3.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-16 | 2024-10-17 | 256 | 0
JP-02560-H03QEB10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Manometer (3552) | 3.5 | 30 | 0 | 1 | TESTING FOR AS FOUND | 2024-10-16 | 2024-10-17 | 256 | 0
JP-02560-H03QEB10CT001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Manometer (3552) | 3.5 | 40 | 0 | 1 | ADJUSTMENT FOR SETTING VALUE | 2024-10-16 | 2024-10-17 | 256 | 0
JP-02570-H03QEB30AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Air Supply te Brake Jack (Low) | 3 | 10 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-16 | 2024-10-17 | 257 | 1
JP-02570-H03QEB30AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Air Supply te Brake Jack (Low) | 3 | 20 | 0 | 1 | OPERATION TEST | 2024-10-16 | 2024-10-17 | 257 | 1
JP-02570-H03QEB30AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Air Supply te Brake Jack (Low) | 3 | 30 | 0 | 1 | CALIBRATION TEST | 2024-10-16 | 2024-10-17 | 257 | 1
JP-02580-H03QEB30AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Air Supply te Brake Jack (Low) | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 258 | 0
JP-02590-H03QEB30AT001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Fillter | 2 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-16 | 2024-10-17 | 259 | 1
JP-02600-H03QEB30BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 3 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-16 | 2024-10-17 | 260 | 0
JP-02600-H03QEB30BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 3 | 20 | 0 | 1 | LEAKAGE CHECK | 2024-10-16 | 2024-10-17 | 260 | 0
JP-02610-H03QEB30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Measurment for Air Supply to Brake Jack (Low) | 3 | 10 | 0 | 1 | OPERATION TEST | 2024-10-16 | 2024-10-17 | 261 | 1
JP-02610-H03QEB30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Measurment for Air Supply to Brake Jack (Low) | 3 | 20 | 0 | 1 | CALIBRATION TEST | 2024-10-16 | 2024-10-17 | 261 | 1
JP-02610-H03QEB30CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Measurment for Air Supply to Brake Jack (Low) | 3 | 30 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-16 | 2024-10-17 | 261 | 1
JP-02620-H03QEB40AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Air Supply te Brake Jack (High) | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 262 | 0
JP-02630-H03QEB40BR001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Pipe Line | 2 | 10 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-16 | 2024-10-17 | 263 | 1
JP-02640-H03QEB40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Switch (BR-S02) | 3 | 10 | 0 | 1 | OPERATION TEST | 2024-10-16 | 2024-10-17 | 264 | 0
JP-02640-H03QEB40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Switch (BR-S02) | 3 | 20 | 0 | 1 | CALIBRATION TEST | 2024-10-16 | 2024-10-17 | 264 | 0
JP-02640-H03QEB40CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Pressure Switch (BR-S02) | 3 | 30 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-16 | 2024-10-17 | 264 | 0
JP-02650-H03QEB50AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Valve for Automatic Air Supply System Unit3 | 1 | 10 | 0 | 1 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 265 | 1
JP-02660-H03SGC10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-17 | 2024-10-18 | 266 | 0
JP-02660-H03SGC10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 5 | 20 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 266 | 0
JP-02660-H03SGC10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 5 | 30 | 0 | 1 | FUNCTION TEST | 2024-10-17 | 2024-10-18 | 266 | 0
JP-02660-H03SGC10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 5 | 40 | 0 | 1 | CALIBRATION TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 266 | 0
JP-02660-H03SGC10AA001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 5 | 50 | 0 | 1 | INSTRUMENT INSPECTION (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 266 | 0
JP-02670-H03SGC10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 4 | 10 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 267 | 1
JP-02670-H03SGC10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 4 | 20 | 0 | 1 | FUNCTION TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 267 | 1
JP-02670-H03SGC10AA001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Deluge Valve Station for KG3A | 4 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 267 | 1
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 10 | 0 | 1 | INSTRUMENT INSPECTION | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 20 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 30 | 0 | 1 | FUNCTION TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 40 | 0 | 1 | CALIBRATION TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 50 | 0 | 1 | INSTRUMENT INSPECTION (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02680-H03SGC20BP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 6 | 60 | 0 | 1 | ELECTRICAL INSPECTION (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 268 | 0
JP-02690-H03SGC20BP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 4 | 10 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 269 | 1
JP-02690-H03SGC20BP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 4 | 20 | 0 | 1 | FUNCTION TEST (ดำเนินการในงานPMแล้ว/ดำเนินการร่วมกับtaskงานอื่น) | 2024-10-17 | 2024-10-18 | 269 | 1
JP-02690-H03SGC20BP001-ME-U | EGAT | KBI0 | 0 | ACTIVE | Spray Nozzle for Transformer KG3A | 4 | 30 | 0 | 2 | MECHANICAL INSPECTION & CLEANING | 2024-10-17 | 2024-10-18 | 269 | 1
JP-02700-H03SGJ10BB001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Co2 Fire - Fighting | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-17 | 2024-10-18 | 270 | 0
JP-02700-H03SGJ10BB001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Co2 Fire - Fighting | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-17 | 2024-10-18 | 270 | 0
JP-02700-H03SGJ10BB001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Co2 Fire - Fighting | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 270 | 0
JP-02710-H03SGY10CH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sensor | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-17 | 2024-10-18 | 271 | 1
JP-02710-H03SGY10CH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sensor | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-17 | 2024-10-18 | 271 | 1
JP-02710-H03SGY10CH001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sensor | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 271 | 1
JP-02720-H03SGY10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sw. | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-17 | 2024-10-18 | 272 | 0
JP-02720-H03SGY10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sw. | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-17 | 2024-10-18 | 272 | 0
JP-02720-H03SGY10CP001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Alarm Pressure Sw. | 2.5 | 30 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 272 | 0
JP-02730-H03SGY10DR001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Heat Detecters | 2.5 | 10 | 0 | 1 | ELECTRICAL INSPECTION | 2024-10-17 | 2024-10-18 | 273 | 1
JP-02730-H03SGY10DR001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Heat Detecters | 2.5 | 20 | 0 | 0.5 | CLEANING | 2024-10-17 | 2024-10-18 | 273 | 1
JP-02730-H03SGY10DR001-EE-U | EGAT | KBI0 | 0 | ACTIVE | Heat Detecters | 2.5 | 40 | 0 | 1 | OPERATION TEST | 2024-10-17 | 2024-10-18 | 273 | 1
JP-02740-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Final Check | 12 | 10 | 0 | 12 | FINAL CHECK | 2024-10-19 | 2024-10-20 | 274 | 0
JP-02750-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Final Check | 12 | 10 | 0 | 12 | FINAL CHECK | 2024-10-19 | 2024-10-20 | 275 | 1
JP-02760-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Final Check | 12 | 10 | 0 | 12 | FINAL CHECK | 2024-10-19 | 2024-10-20 | 276 | 0
JP-02770-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Final Check | 12 | 10 | 0 | 12 | FINAL CHECK | 2024-10-19 | 2024-10-20 | 277 | 1
JP-02780-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Prepare Before Kick off Test | 4 | 10 | 0 | 4 | CHECK | 2024-10-20 | 2024-10-20 | 278 | 0
JP-02790-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Prepare Before Kick off Test | 4 | 10 | 0 | 4 | CHECK | 2024-10-20 | 2024-10-20 | 279 | 1
JP-02800-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Prepare Before Kick off Test | 4 | 10 | 0 | 4 | CHECK | 2024-10-20 | 2024-10-20 | 280 | 0
JP-02810-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Prepare Before Kick off Test | 4 | 10 | 0 | 4 | CHECK | 2024-10-20 | 2024-10-20 | 281 | 1
JP-02820-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Kick Off | 4 | 10 | 0 | 4 | KICK OFF | 2024-10-21 | 2024-10-21 | 282 | 0
JP-02830-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Kick Off | 4 | 10 | 0 | 4 | KICK OFF | 2024-10-21 | 2024-10-21 | 283 | 1
JP-02840-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Kick Off | 4 | 10 | 0 | 4 | KICK OFF | 2024-10-21 | 2024-10-21 | 284 | 0
JP-02850-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Kick Off | 4 | 10 | 0 | 4 | KICK OFF | 2024-10-21 | 2024-10-21 | 285 | 1
JP-02860-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Operation Test | 6 | 10 | 0 | 6 | STEP LOAD TEST, TRIP TEST, LOAD TEST | 2024-10-21 | 2024-10-22 | 286 | 0
JP-02870-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operation Test | 6 | 10 | 0 | 6 | STEP LOAD TEST, TRIP TEST, LOAD TEST | 2024-10-21 | 2024-10-22 | 287 | 1
JP-02880-H03-EE-U | EGAT | KBI0 | 0 | ACTIVE | Operation Test | 6 | 10 | 0 | 6 | STEP LOAD TEST, TRIP TEST, LOAD TEST | 2024-10-21 | 2024-10-22 | 288 | 0
JP-02890-H03-ME-U | EGAT | KBI0 | 0 | ACTIVE | Operation Test | 6 | 10 | 0 | 6 | STEP LOAD TEST, TRIP TEST, LOAD TEST | 2024-10-21 | 2024-10-22 | 289 | 1