## Sheet1
PMNUM | SITEID | DESCRIPTION | STATUS | LOCATION | WORKTYPE | EGMNTACTTYPE | WOSTATUS | EGPROJECTID | EGWBS | FREQUENCY | FREQUNIT | JPNUM | ROUTE | NEXTDATE | EGCRAFT | RESPONSED BY | PTW | PARENTCHGSSTATUS | LEADTIME | TARGSTARTTIME | PARENT | PMCOUNTER | WOSEQUENCE | MOD | MAIN_SYSTEM | MAIN_SYSTEM_DESC | UNIT_TYPE | TYPE | SUB_SYSTEM | EQUIPMENT | SUB_SYSTEM_DESC | KKS_NEW_DESC | GROUP | FINISH_DATE | FINISH TIME | COMMENT
Group-01-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,URD0-6S0,PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 0 | 7 | 08:00:00 |  | 0 | 1 | 1 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 1 | 2024-11-11 | 16:00:00
PO-00380-H04MFA10HA001-ME-U | LTK0 | SPIRAL CASE | ACTIVE | LTK-H04MFA10HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00380-H04MFA10HA001-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 1 | 7 | 08:00:00 | Group-01-H04MFA-ME-U | 0 | 1 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA10 | HA | SPIRAL CASE | SPIRAL CASE | 1 | 2024-11-11 | 16:00:00
PO-02240-H04MFA30HB200-ME-U | LTK0 | RUNNER | ACTIVE | LTK-H04MFA30HB200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02240-H04MFA30HB200-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 1 | 7 | 08:00:00 | Group-01-H04MFA-ME-U | 0 | 2 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | HB | RUNNER & TURBINE SHAFT | RUNNER | 1 | 2024-11-11 | 16:00:00
PO-02250-H04MFA60HA001-ME-U | LTK0 | DRAFT TUBE | ACTIVE | LTK-H04MFA60HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02250-H04MFA60HA001-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 1 | 7 | 08:00:00 | Group-01-H04MFA-ME-U | 0 | 3 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | HA | DRAFT TUBE SYSTEM | DRAFT TUBE | 1 | 2024-11-11 | 16:00:00
PO-02260-H04MFA60HA011-ME-U | LTK0 | DISCHARGE RING | ACTIVE | LTK-H04MFA60HA011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02260-H04MFA60HA011-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 1 | 7 | 08:00:00 | Group-01-H04MFA-ME-U | 0 | 4 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | HA | DRAFT TUBE SYSTEM | DISCHARGE RING | 1 | 2024-11-11 | 16:00:00
Group-02-H04MFX-ME-U | LTK0 | FLUID SUPPLY SYSTEM,MSP0-H010,PTW งานในที่อับอากาศ | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 2 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME |  |  |  |  | 2 | 2024-11-11 | 16:00:00
PO-00660-H04MFX60BB520-ME-U | LTK0 | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.1 | ACTIVE | LTK-H04MFX60BB520 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00660-H04MFX60BB520-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-02-H04MFX-ME-U | 0 | 1 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | BB | FLUID SUPPLY SYSTEM for MIV | Oil & Air Pressure Tank (Volume : 9500L) | 2 | 2024-11-07 | 16:00:00
PO-00670-H04MFX60BB530-ME-U | LTK0 | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.2 | ACTIVE | LTK-H04MFX60BB530 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00670-H04MFX60BB530-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-02-H04MFX-ME-U | 0 | 2 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | BB | FLUID SUPPLY SYSTEM for MIV | Air Pressure Tank (Volume : 9500L ) | 2 | 2024-11-07 | 16:00:00
PO-00700-H04MFX60BB010-ME-U | LTK0 | INLET VALVE OIL SUMP TANK | ACTIVE | LTK-H04MFX60BB010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00700-H04MFX60BB010-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-02-H04MFX-ME-U | 0 | 3 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | BB | FLUID SUPPLY SYSTEM for MIV | MIV Oil Sump Tank (Total volume : 16000 | 2 | 2024-11-07 | 16:00:00
PO-00820-H04MFX10BB610-ME-U | LTK0 | GOVERNOR OIL SUMP TANK | ACTIVE | LTK-H04MFX10BB610 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00820-H04MFX10BB610-ME-U |  | 2024-11-10 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-02-H04MFX-ME-U | 0 | 4 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | BB | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | Gov. Oil Sump Tank (Total volume:2800L) | 2 | 2024-11-11 | 16:00:00
PO-00830-H04MFX10BB520-ME-U | LTK0 | GOVERNOR OIL PRESSURE TANK | ACTIVE | LTK-H04MFX10BB520 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00830-H04MFX10BB520-ME-U |  | 2024-11-10 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-02-H04MFX-ME-U | 0 | 5 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | BB | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | Gov. Oil Pressure Tank (Volume:3000L) | 2 | 2024-11-11 | 16:00:00
Group-03-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,MSP0-H010,PTW งานในที่อับอากาศ | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 3 | 1 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 3 | 2024-11-07 | 16:00:00
PO-00480-H04MFA20-ME-U | LTK0 | GUIDE VANE (ROUTE) | ACTIVE | LTK-H04MFA20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00480-H04MFA20-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-03-H04MFA-ME-U | 0 | 1 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 |  | GUIDE VANE | GUIDE VANE | 3 | 2024-11-07 | 16:00:00
PO-00520-H04MFA60HA021-ME-U | LTK0 | BOTTOM COVER | ACTIVE | LTK-H04MFA60HA021 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00520-H04MFA60HA021-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-03-H04MFA-ME-U | 0 | 2 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | HA | DRAFT TUBE SYSTEM | BOTTOM RING | 3 | 2024-11-07 | 16:00:00
PO-00530-H04MFA60HA011-ME-U | LTK0 | DISCHARGE RING | ACTIVE | LTK-H04MFA60HA011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00530-H04MFA60HA011-ME-U |  | 2024-11-07 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-03-H04MFA-ME-U | 0 | 3 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | HA | DRAFT TUBE SYSTEM | DISCHARGE RING | 3 | 2024-11-07 | 16:00:00
Group-04-H04SGC-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 4 | 0 | H04SGC | No_kks_found | U | ME |  |  |  |  | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10AA001-ME-U | LTK0 | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.1 | ACTIVE | LTK-H04SGC10AA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10AA001-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 1 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | AA | No_kks_found | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.1 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10AA002-ME-U | LTK0 | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.2 | ACTIVE | LTK-H04SGC10AA002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10AA002-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 2 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | AA | No_kks_found | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.2 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10CP001-ME-U | LTK0 | KG4A FIRE EXTINGUISGER WATER SUPPLY LINE PRESSURE GAUGE - CP001 | ACTIVE | LTK-H04SGC10CP001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10CP001-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 3 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | CP | No_kks_found | KG4A FIRE EXTINGUISGER WATER SUPPLY LINE PRESSURE GAUGE - CP001 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10CP002-ME-U | LTK0 | KG4A FIRE EXTINGUISGER WATER SUPPLY DELUGE PRESSURE GAUGE - CP002 | ACTIVE | LTK-H04SGC10CP002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10CP002-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 4 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | CP | No_kks_found | KG4A FIRE EXTINGUISGER WATER SUPPLY DELUGE PRESSURE GAUGE - CP002 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10CP003-ME-U | LTK0 | KG4A FIRE EXTINGUISGER WATER DISCHARGE PRESSURE SWITCH - CP003 | ACTIVE | LTK-H04SGC10CP003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10CP003-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 5 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | CP | No_kks_found | KG4A FIRE EXTINGUISGER WATER DISCHARGE PRESSURE SWITCH - CP003 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD001-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | ACTIVE | LTK-H04SGC10HD001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD001-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 6 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD002-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | ACTIVE | LTK-H04SGC10HD002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD002-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 7 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD003-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | ACTIVE | LTK-H04SGC10HD003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD003-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 8 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD004-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | ACTIVE | LTK-H04SGC10HD004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD004-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 9 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD005-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | ACTIVE | LTK-H04SGC10HD005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD005-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 10 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD006-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | ACTIVE | LTK-H04SGC10HD006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD006-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 11 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD007-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.7 | ACTIVE | LTK-H04SGC10HD007 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD007-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 12 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.7 | 4 | 2024-11-08 | 16:00:00
PO-02120-H04SGC10HD008-ME-U | LTK0 | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.8 | ACTIVE | LTK-H04SGC10HD008 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H04SGC10HD008-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-04-H04SGC-ME-U | 0 | 13 | 0 | H04SGC | No_kks_found | U | ME | H04SGC10 | HD | No_kks_found | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.8 | 4 | 2024-11-08 | 16:00:00
Group-05-H04QFB-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 5 | 1 | H04QFB | No_kks_found | U | ME |  |  |  |  | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP010-ME-U | LTK0 | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | ACTIVE | LTK-H04QFB30CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP010-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 1 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP110-ME-U | LTK0 | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | ACTIVE | LTK-H04QFB30CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP110-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 2 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP120-ME-U | LTK0 | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | ACTIVE | LTK-H04QFB30CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP120-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 3 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP130-ME-U | LTK0 | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | ACTIVE | LTK-H04QFB30CP130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP130-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 4 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP140-ME-U | LTK0 | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | ACTIVE | LTK-H04QFB30CP140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP140-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 5 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 5 | 2024-11-12 | 16:00:00
PO-01210-H04QFB30CP150-ME-U | LTK0 | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | ACTIVE | LTK-H04QFB30CP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01210-H04QFB30CP150-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 6 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 5 | 2024-11-12 | 16:00:00
PO-01220-H04QFB30CP020-ME-U | LTK0 | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | ACTIVE | LTK-H04QFB30CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01220-H04QFB30CP020-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 7 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 5 | 2024-11-12 | 16:00:00
PO-01220-H04QFB30CP160-ME-U | LTK0 | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | ACTIVE | LTK-H04QFB30CP160 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01220-H04QFB30CP160-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 8 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 5 | 2024-11-12 | 16:00:00
PO-01220-H04QFB30CP170-ME-U | LTK0 | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | ACTIVE | LTK-H04QFB30CP170 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01220-H04QFB30CP170-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 9 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 5 | 2024-11-12 | 16:00:00
PO-01230-H04QFB31CP010-ME-U | LTK0 | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | ACTIVE | LTK-H04QFB31CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01230-H04QFB31CP010-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 10 | 1 | H04QFB | No_kks_found | U | ME | H04QFB31 | CP | AIR Pressure System 2 | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 5 | 2024-11-12 | 16:00:00
PO-01230-H04QFB31CP110-ME-U | LTK0 | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | ACTIVE | LTK-H04QFB31CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01230-H04QFB31CP110-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 11 | 1 | H04QFB | No_kks_found | U | ME | H04QFB31 | CP | AIR Pressure System 2 | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 5 | 2024-11-12 | 16:00:00
PO-01230-H04QFB31CP120-ME-U | LTK0 | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | ACTIVE | LTK-H04QFB31CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01230-H04QFB31CP120-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 12 | 1 | H04QFB | No_kks_found | U | ME | H04QFB31 | CP | AIR Pressure System 2 | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 5 | 2024-11-12 | 16:00:00
PO-01240-H04QFB32CP010-ME-U | LTK0 | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | ACTIVE | LTK-H04QFB32CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01240-H04QFB32CP010-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 13 | 1 | H04QFB | No_kks_found | U | ME | H04QFB32 | CP | AIR Pressure System 3 | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 5 | 2024-11-12 | 16:00:00
PO-01240-H04QFB32CP110-ME-U | LTK0 | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | ACTIVE | LTK-H04QFB32CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01240-H04QFB32CP110-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 14 | 1 | H04QFB | No_kks_found | U | ME | H04QFB32 | CP | AIR Pressure System 3 | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 5 | 2024-11-12 | 16:00:00
PO-01240-H04QFB32CP120-ME-U | LTK0 | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | ACTIVE | LTK-H04QFB32CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01240-H04QFB32CP120-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 15 | 1 | H04QFB | No_kks_found | U | ME | H04QFB32 | CP | AIR Pressure System 3 | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 5 | 2024-11-12 | 16:00:00
PO-01250-H04QFB33CP010-ME-U | LTK0 | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | ACTIVE | LTK-H04QFB33CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01250-H04QFB33CP010-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 16 | 1 | H04QFB | No_kks_found | U | ME | H04QFB33 | CP | AIR Pressure System 4 | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 5 | 2024-11-12 | 16:00:00
PO-01250-H04QFB33CP110-ME-U | LTK0 | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | ACTIVE | LTK-H04QFB33CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01250-H04QFB33CP110-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 17 | 1 | H04QFB | No_kks_found | U | ME | H04QFB33 | CP | AIR Pressure System 4 | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 5 | 2024-11-12 | 16:00:00
PO-01250-H04QFB33CP120-ME-U | LTK0 | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | ACTIVE | LTK-H04QFB33CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01250-H04QFB33CP120-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-05-H04QFB-ME-U | 0 | 18 | 1 | H04QFB | No_kks_found | U | ME | H04QFB33 | CP | AIR Pressure System 4 | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 5 | 2024-11-12 | 16:00:00
Group-06-H04PCM-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 6 | 0 | H04PCM | No_kks_found | U | ME |  |  |  |  | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT001-ME-U | LTK0 | 1# AIR COOLER INLET RTD | ACTIVE | LTK-H04PCM30CT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT001-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 1 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 1# AIR COOLER INLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT002-ME-U | LTK0 | 2# AIR COOLER INLET RTD | ACTIVE | LTK-H04PCM30CT002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT002-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 2 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 2# AIR COOLER INLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT003-ME-U | LTK0 | 3# AIR COOLER INLET RTD | ACTIVE | LTK-H04PCM30CT003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT003-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 3 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 3# AIR COOLER INLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT004-ME-U | LTK0 | 4# AIR COOLER INLET RTD | ACTIVE | LTK-H04PCM30CT004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT004-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 4 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 4# AIR COOLER INLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT011-ME-U | LTK0 | 1# AIR COOLER OUTLET RTD | ACTIVE | LTK-H04PCM30CT011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT011-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 5 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 1# AIR COOLER OUTLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT012-ME-U | LTK0 | 2# AIR COOLER OUTLET RTD | ACTIVE | LTK-H04PCM30CT012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT012-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 6 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 2# AIR COOLER OUTLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT013-ME-U | LTK0 | 3# AIR COOLER OUTLET RTD | ACTIVE | LTK-H04PCM30CT013 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT013-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 7 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 3# AIR COOLER OUTLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT014-ME-U | LTK0 | 4# AIR COOLER OUTLET RTD | ACTIVE | LTK-H04PCM30CT014 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT014-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 8 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | 4# AIR COOLER OUTLET RTD | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT100-ME-U | LTK0 | RTD FOR GENERATOR COOLING WATER INLET | ACTIVE | LTK-H04PCM30CT100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT100-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 9 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | RTD FOR GENERATOR COOLING WATER INLET | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT101-ME-U | LTK0 | RTD FOR GENERATOR COOLING WATER OUTLET | ACTIVE | LTK-H04PCM30CT101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 10 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | RTD FOR GENERATOR COOLING WATER OUTLET | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT200-ME-U | LTK0 | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | ACTIVE | LTK-H04PCM30CT200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT200-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 11 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 6 | 2024-11-12 | 16:00:00
PO-00080-H04PCM30CT201-ME-U | LTK0 | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | ACTIVE | LTK-H04PCM30CT201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00080-H04PCM30CT201-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-06-H04PCM-ME-U | 0 | 12 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CT | COOLING WATER SUPPLY FOR GEN AIR COOLER | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 6 | 2024-11-12 | 16:00:00
Group-07-H04PAC-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 7 | 1 | H04PAC | No_kks_found | U | ME |  |  |  |  | 7 | 2024-11-05 | 16:00:00
PO-00910-H04PAC10AP110-M01-ME-U | LTK0 | MOTOR FOR MAIN COOLING WATER SUPPLY | ACTIVE | LTK-H04PAC10AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00910-H04PAC10AP110-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 1 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MOTOR FOR MAIN COOLING WATER SUPPLY | 7 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00920-H04PAC10AP120-M01-ME-U | LTK0 | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | ACTIVE | LTK-H04PAC10AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00920-H04PAC10AP120-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 2 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 7 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00920-H04PAC10AP130-M01-ME-U | LTK0 | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | ACTIVE | LTK-H04PAC10AP130-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00920-H04PAC10AP130-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 3 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 7 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00980-H04PAC10CP010-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | ACTIVE | LTK-H04PAC10CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAC10CP010-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 4 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 2024-11-05 | 16:00:00
PO-00980-H04PAC10CP020-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | ACTIVE | LTK-H04PAC10CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAC10CP020-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 5 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 2024-11-05 | 16:00:00
PO-00980-H04PAC10CP030-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | ACTIVE | LTK-H04PAC10CP030 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAC10CP030-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-07-H04PAC-ME-U | 0 | 6 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 2024-11-05 | 16:00:00
Group-08-H04PAB-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 8 | 0 | H04PAB | No_kks_found | U | ME |  |  |  |  | 8 | 2024-11-07 | 16:00:00
PO-00930-H04PAB10AT110-M01-ME-U | LTK0 | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | ACTIVE | LTK-H04PAB10AT110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00930-H04PAB10AT110-M01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 1 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 8 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00930-H04PAB10AT110-M02-ME-U | LTK0 | MOV FOR MAIN COOLING AUTOMATIC STRAINER | ACTIVE | LTK-H04PAB10AT110-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00930-H04PAB10AT110-M02-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 2 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 8 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00930-H04PAB10AT110-N01-ME-U | LTK0 | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | ACTIVE | LTK-H04PAB10AT110-N01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00930-H04PAB10AT110-N01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 3 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 8 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00940-H04PAB10AT120-M01-ME-U | LTK0 | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00940-H04PAB10AT120-M01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 4 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00940-H04PAB10AT120-M02-ME-U | LTK0 | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT120-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00940-H04PAB10AT120-M02-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 5 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00940-H04PAB10AT120-N01-ME-U | LTK0 | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT120-N01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00940-H04PAB10AT120-N01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 6 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00950-H04PAB10AT130-M01-ME-U | LTK0 | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT130-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00950-H04PAB10AT130-M01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 7 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00950-H04PAB10AT130-M02-ME-U | LTK0 | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT130-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00950-H04PAB10AT130-M02-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 8 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00950-H04PAB10AT130-N01-ME-U | LTK0 | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT130-N01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00950-H04PAB10AT130-N01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 9 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 8 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00980-H04PAB10CP116-ME-U | LTK0 | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | ACTIVE | LTK-H04PAB10CP116 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAB10CP116-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 10 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 8 | 2024-11-05 | 16:00:00
PO-00980-H04PAB10CP117-ME-U | LTK0 | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | ACTIVE | LTK-H04PAB10CP117 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAB10CP117-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 11 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 8 | 2024-11-05 | 16:00:00
PO-00980-H04PAB10CP126-ME-U | LTK0 | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | ACTIVE | LTK-H04PAB10CP126 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAB10CP126-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 12 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 8 | 2024-11-05 | 16:00:00
PO-00980-H04PAB10CP136-ME-U | LTK0 | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | ACTIVE | LTK-H04PAB10CP136 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAB10CP136-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 13 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 8 | 2024-11-05 | 16:00:00
PO-00980-H04PAB10CT010-ME-U | LTK0 | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | ACTIVE | LTK-H04PAB10CT010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00980-H04PAB10CT010-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-08-H04PAB-ME-U | 0 | 14 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | CT | COOLING WATER PIPING AND CULVERT SYSTEM | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 8 | 2024-11-05 | 16:00:00
Group-09-H04PAB-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 9 | 1 | H04PAB | No_kks_found | U | ME |  |  |  |  | 9 | 2024-11-07 | 16:00:00
PO-00960-H04PAB10AT150-M01-ME-U | LTK0 | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT150-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00960-H04PAB10AT150-M01-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 1 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00960-H04PAB10AT150-M02-ME-U | LTK0 | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT150-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00960-H04PAB10AT150-M02-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 2 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00960-H04PAB10AT150-N01-ME-U | LTK0 | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT150-N01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00960-H04PAB10AT150-N01-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 3 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00970-H04PAB10AT155-M01-ME-U | LTK0 | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT155-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00970-H04PAB10AT155-M01-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 4 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00970-H04PAB10AT155-M02-ME-U | LTK0 | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT155-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00970-H04PAB10AT155-M02-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 5 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00970-H04PAB10AT155-N01-ME-U | LTK0 | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT155-N01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00970-H04PAB10AT155-N01-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-09-H04PAB-ME-U | 0 | 6 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 9 | 2024-11-07 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-10-H04MLV-ME-U | LTK0 | BEARINGS SUPPLY SYSTEM,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 10 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME |  |  |  |  | 10 | 2024-11-10 | 16:00:00
PO-00050-H04MLV20AP110-M01-ME-U | LTK0 | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | ACTIVE | LTK-H04MLV20AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00050-H04MLV20AP110-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 1 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AP | UGB SUPPLY SYSTEM | MOTOR FOR UGB OIL PUMP NO.1 | 10 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00050-H04MLV20AP120-M01-ME-U | LTK0 | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | ACTIVE | LTK-H04MLV20AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00050-H04MLV20AP120-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 2 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AP | UGB SUPPLY SYSTEM | MOTOR FOR UGB OIL PUMP NO.2 | 10 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00060-H04MLV20CF100-ME-U | LTK0 | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04MLV20CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLV20CF100-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 3 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CF | UGB SUPPLY SYSTEM | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 10 | 2024-11-06 | 16:00:00
PO-00060-H04MLV20CP100-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | ACTIVE | LTK-H04MLV20CP100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLV20CP100-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 4 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 10 | 2024-11-06 | 16:00:00
PO-00060-H04MLV20CP101-ME-U | LTK0 | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MLV20CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLV20CP101-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 5 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 10 | 2024-11-06 | 16:00:00
PO-00060-H04MLV20CP102-ME-U | LTK0 | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | ACTIVE | LTK-H04MLV20CP102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLV20CP102-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 6 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 10 | 2024-11-06 | 16:00:00
PO-00100-H04MLV10AP110-M01-ME-U | LTK0 | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | ACTIVE | LTK-H04MLV10AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00100-H04MLV10AP110-M01-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 7 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AP | CGB SUPPLY SYSTEM | MOTOR FOR CGB OIL PUMP NO.1 | 10 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00100-H04MLV10AP120-M01-ME-U | LTK0 | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | ACTIVE | LTK-H04MLV10AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00100-H04MLV10AP120-M01-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 8 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AP | CGB SUPPLY SYSTEM | MOTOR FOR CGB OIL PUMP NO.2 | 10 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00120-H04MLV10CF100-ME-U | LTK0 | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04MLV10CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLV10CF100-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 9 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CF | CGB SUPPLY SYSTEM | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 10 | 2024-11-10 | 16:00:00
PO-00120-H04MLV10CP100-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | ACTIVE | LTK-H04MLV10CP100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLV10CP100-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 10 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 10 | 2024-11-10 | 16:00:00
PO-00120-H04MLV10CP101-ME-U | LTK0 | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MLV10CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLV10CP101-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 11 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 10 | 2024-11-10 | 16:00:00
PO-00120-H04MLV10CP102-ME-U | LTK0 | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | ACTIVE | LTK-H04MLV10CP102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLV10CP102-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 12 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 10 | 2024-11-10 | 16:00:00
PO-00140-H04MLV40AP110-M01-ME-U | LTK0 | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | ACTIVE | LTK-H04MLV40AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00140-H04MLV40AP110-M01-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 13 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | AP | HIGH PRESSURE PUMP SUPPLY SYSTEM | MOTOR FOR HPO PUMP NO.1 | 10 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00140-H04MLV40AP120-M01-ME-U | LTK0 | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | ACTIVE | LTK-H04MLV40AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00140-H04MLV40AP120-M01-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 14 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | AP | HIGH PRESSURE PUMP SUPPLY SYSTEM | MOTOR FOR HPO PUMP NO.2 | 10 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00150-H04MLV40CF100-ME-U | LTK0 | HPOS FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04MLV40CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00150-H04MLV40CF100-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 15 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CF | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 10 | 2024-11-05 | 16:00:00
PO-00150-H04MLV40CP100-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | ACTIVE | LTK-H04MLV40CP100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00150-H04MLV40CP100-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 16 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 10 | 2024-11-05 | 16:00:00
PO-00150-H04MLV40CP101-ME-U | LTK0 | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MLV40CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00150-H04MLV40CP101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 17 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 10 | 2024-11-05 | 16:00:00
PO-00150-H04MLV40CP111-ME-U | LTK0 | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | ACTIVE | LTK-H04MLV40CP111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00150-H04MLV40CP111-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 18 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 10 | 2024-11-05 | 16:00:00
PO-00200-H04MLV70AP010-M01-ME-U | LTK0 | MOTOR FOR CGB OIL MIST EXHAUST - MLV70AP010 | ACTIVE | LTK-H04MLV70AP010-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00200-H04MLV70AP010-M01-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-10-H04MLV-ME-U | 0 | 19 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV70 | AP | CGB OIL MIST EXHAUST | MOTOR FOR CGB OIL MIST EXHAUST | 10 | 2024-11-09 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-11-H04MLV-ME-U | LTK0 | BEARINGS SUPPLY SYSTEM,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 11 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME |  |  |  |  | 11 | 2024-11-11 | 16:00:00
PO-02560-H04MLV40CP101-ME-U | LTK0 | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MLV40CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02560-H04MLV40CP101-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-11-H04MLV-ME-U | 0 | 1 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 11 | 2024-11-11 | 16:00:00
PO-02560-H04MLV40CP111-ME-U | LTK0 | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | ACTIVE | LTK-H04MLV40CP111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02560-H04MLV40CP111-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-11-H04MLV-ME-U | 0 | 2 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 11 | 2024-11-11 | 16:00:00
Group-12-H04MLD-ME-U | LTK0 | CGB. BEARINGS,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 12 | 0 | H04MLD | CGB. BEARINGS | U | ME |  |  |  |  | 12 | 2024-11-10 | 16:00:00
PO-00060-H04MLD20CL010-ME-U | LTK0 | UGB OIL PAN LEVEL TRANSMITTER - CL010 | ACTIVE | LTK-H04MLD20CL010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CL010-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 1 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CL | Upper Guide Bearing(UGB) | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CL310-ME-U | LTK0 | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | ACTIVE | LTK-H04MLD20CL310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CL310-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 2 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CL | Upper Guide Bearing(UGB) | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CM105-ME-U | LTK0 | UGB WATER IN OIL RELAY | ACTIVE | LTK-H04MLD20CM105 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CM105-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 3 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CM | Upper Guide Bearing(UGB) | UGB WATER IN OIL RELAY | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT001-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.1 | ACTIVE | LTK-H04MLD20CT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT001-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 4 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.1 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT002-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.2 | ACTIVE | LTK-H04MLD20CT002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT002-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 5 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.2 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT003-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.3 | ACTIVE | LTK-H04MLD20CT003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT003-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 6 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.3 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT004-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.4 | ACTIVE | LTK-H04MLD20CT004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT004-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 7 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.4 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT005-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.5 | ACTIVE | LTK-H04MLD20CT005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT005-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 8 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.5 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT006-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.6 | ACTIVE | LTK-H04MLD20CT006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT006-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 9 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.6 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT007-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.7 | ACTIVE | LTK-H04MLD20CT007 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT007-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 10 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.7 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT008-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.8 | ACTIVE | LTK-H04MLD20CT008 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT008-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 11 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.8 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT010-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.10 | ACTIVE | LTK-H04MLD20CT010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT010-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 12 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.10 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT011-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.11 | ACTIVE | LTK-H04MLD20CT011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT011-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 13 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.11 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT012-ME-U | LTK0 | UGB PAD TEMPERATURE RTD NO.12 | ACTIVE | LTK-H04MLD20CT012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT012-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 14 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | UGB PAD TEMPERATURE RTD NO.12 | 12 | 2024-11-06 | 16:00:00
PO-00060-H04MLD20CT100-ME-U | LTK0 | DIAL THERMOMETER FOR UGB PAD - CT100 | ACTIVE | LTK-H04MLD20CT100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00060-H04MLD20CT100-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 15 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | CT | Upper Guide Bearing(UGB) | DIAL THERMOMETER FOR UGB PAD - CT100 | 12 | 2024-11-06 | 16:00:00
PO-00120-H04MLD10CL010-ME-U | LTK0 | CGB OIL PAN LEVEL TRANSMITTER - CL010 | ACTIVE | LTK-H04MLD10CL010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CL010-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 16 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CL | Combined Guide Bearing(CGB) | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CL310-ME-U | LTK0 | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | ACTIVE | LTK-H04MLD10CL310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CL310-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 17 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CL | Combined Guide Bearing(CGB) | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CM105-ME-U | LTK0 | CGB WATER IN OIL RELAY | ACTIVE | LTK-H04MLD10CM105 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CM105-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 18 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CM | Combined Guide Bearing(CGB) | CGB WATER IN OIL RELAY | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT001-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.1 | ACTIVE | LTK-H04MLD10CT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT001-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 19 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.1 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT002-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.3 | ACTIVE | LTK-H04MLD10CT002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT002-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 20 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.3 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT003-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.5 | ACTIVE | LTK-H04MLD10CT003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT003-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 21 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.5 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT004-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.7 | ACTIVE | LTK-H04MLD10CT004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT004-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 22 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.7 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT005-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.9 | ACTIVE | LTK-H04MLD10CT005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT005-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 23 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.9 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT006-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.11 | ACTIVE | LTK-H04MLD10CT006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT006-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 24 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.11 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT007-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.13 | ACTIVE | LTK-H04MLD10CT007 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT007-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 25 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.13 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT008-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.15 | ACTIVE | LTK-H04MLD10CT008 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT008-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 26 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.15 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT009-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.17 | ACTIVE | LTK-H04MLD10CT009 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT009-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 27 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.17 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT010-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.19 | ACTIVE | LTK-H04MLD10CT010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT010-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 28 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.19 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT011-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.21 | ACTIVE | LTK-H04MLD10CT011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT011-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 29 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.21 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT012-ME-U | LTK0 | LGB PAD TEMPERATURE RTD NO.23 | ACTIVE | LTK-H04MLD10CT012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT012-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 30 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | LGB PAD TEMPERATURE RTD NO.23 | 12 | 2024-11-10 | 16:00:00
PO-00120-H04MLD10CT110-ME-U | LTK0 | DIAL THERMOMETER FOR LGB PAD - CT110 | ACTIVE | LTK-H04MLD10CT110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00120-H04MLD10CT110-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-12-H04MLD-ME-U | 0 | 31 | 0 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | CT | Combined Guide Bearing(CGB) | DIAL THERMOMETER FOR LGB PAD - CT110 | 12 | 2024-11-10 | 16:00:00
Group-13-H04MLC-ME-U | LTK0 | EXCITATION,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 13 | 1 | H04MLC | EXCITATION | U | ME |  |  |  |  | 13 | 2024-11-07 | 16:00:00
PO-01920-H04MLC10GT001-ME-U | LTK0 | EXCITATION TRANSFORMER (หปฟนม-ธ.) | ACTIVE | LTK-H04MLC10GT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01920-H04MLC10GT001-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-13-H04MLC-ME-U | 0 | 1 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GT | EXCITER SETS | EXCITATION TRANSFORMER | 13 | 2024-11-07 | 16:00:00
PO-01940-H04MLC10CE110-ME-U | LTK0 | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | ACTIVE | LTK-H04MLC10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01940-H04MLC10CE110-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-13-H04MLC-ME-U | 0 | 2 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | CE | EXCITER SETS | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION | 13 | 2024-11-07 | 16:00:00
PO-01960-H04MLC10CE120-ME-U | LTK0 | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | ACTIVE | LTK-H04MLC10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01960-H04MLC10CE120-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-13-H04MLC-ME-U | 0 | 3 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | CE | EXCITER SETS | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION | 13 | 2024-11-07 | 16:00:00
Group-14-H04MLC-ME-U | LTK0 | EXCITATION,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 14 | 0 | H04MLC | EXCITATION | U | ME |  |  |  |  | 14 | 2024-11-08 | 16:00:00
PO-01930-H04MLC10GT001-ME-U | LTK0 | EXCITATION TRANSFORMER (หทอฟ-ธ.) | ACTIVE | LTK-H04MLC10GT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01930-H04MLC10GT001-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-14-H04MLC-ME-U | 0 | 1 | 0 | H04MLC | EXCITATION | U | ME | H04MLC10 | GT | EXCITER SETS | EXCITATION TRANSFORMER | 14 | 2024-11-08 | 16:00:00
PO-01950-H04MLC10CE110-ME-U | LTK0 | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION (หทอฟ-ธ.) | ACTIVE | LTK-H04MLC10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01950-H04MLC10CE110-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-14-H04MLC-ME-U | 0 | 2 | 0 | H04MLC | EXCITATION | U | ME | H04MLC10 | CE | EXCITER SETS | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION | 14 | 2024-11-08 | 16:00:00
PO-01970-H04MLC10CE120-ME-U | LTK0 | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION (หทอฟ-ธ.) | ACTIVE | LTK-H04MLC10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01970-H04MLC10CE120-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-14-H04MLC-ME-U | 0 | 3 | 0 | H04MLC | EXCITATION | U | ME | H04MLC10 | CE | EXCITER SETS | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION | 14 | 2024-11-08 | 16:00:00
Group-15-H04MLC-ME-U | LTK0 | EXCITATION,MSP0-E250,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 15 | 1 | H04MLC | EXCITATION | U | ME |  |  |  |  | 15 | 2024-11-12 | 16:00:00
PO-02000-H04MLC10GH100-ME-U | LTK0 | EXCITATION CONTROLLER CUBICLE (หรคฟ-ธ.) | ACTIVE | LTK-H04MLC10GH100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02000-H04MLC10GH100-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 1 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GH | EXCITER SETS | EXCITATION CONTROLLER CUBICLE | 15 | 2024-11-12 | 16:00:00
PO-02010-H04MLC10DE100-ME-U | LTK0 | EXCITATION CONTROL (AVR) | ACTIVE | LTK-H04MLC10DE100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02010-H04MLC10DE100-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 2 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | DE | EXCITER SETS | EXCITAION CONTROL (AVR) | 15 | 2024-11-12 | 16:00:00
PO-02020-H04MLC10GS100-ME-U | LTK0 | EXCITATION INCOMING BUS CUBICLE | ACTIVE | LTK-H04MLC10GS100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02020-H04MLC10GS100-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 3 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GS | EXCITER SETS | EXCITATION INCOMING BUS CUBICLE | 15 | 2024-11-12 | 16:00:00
PO-02030-H04MLC10GH200-ME-U | LTK0 | EXCITATION POWER CONVERTER 1 CUBICLE | ACTIVE | LTK-H04MLC10GH200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02030-H04MLC10GH200-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 4 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GH | EXCITER SETS | EXCITATION POWER CONVERTER 1 CUBICLE | 15 | 2024-11-12 | 16:00:00
PO-02040-H04MLC10GH201-ME-U | LTK0 | EXCITATION POWER CONVERTER 2 CUBICLE | ACTIVE | LTK-H04MLC10GH201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02040-H04MLC10GH201-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 5 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GH | EXCITER SETS | EXCITATION POWER CONVERTER 2 CUBICLE | 15 | 2024-11-12 | 16:00:00
PO-02050-H04MLC10GS200-ME-U | LTK0 | EXCITATION FIELD BREAKER (41E) CUBICLE | ACTIVE | LTK-H04MLC10GS200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02050-H04MLC10GS200-ME-U |  | 2024-11-05 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-15-H04MLC-ME-U | 0 | 6 | 1 | H04MLC | EXCITATION | U | ME | H04MLC10 | GS | EXCITER SETS | EXCITATION FIELD BREAKER (41E) CUBICLE | 15 | 2024-11-12 | 16:00:00
Group-16-H04MLA-ME-U | LTK0 | STATOR,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 16 | 0 | H04MLA | STATOR | U | ME |  |  |  |  | 16 | 2024-11-12 | 16:00:00
PO-00170-H04MLA50AP010-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.1 (G) | ACTIVE | LTK-H04MLA50AP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP010-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 1 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.1 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP011-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.2 (G) | ACTIVE | LTK-H04MLA50AP011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP011-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 2 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.2 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP012-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.3 (G) | ACTIVE | LTK-H04MLA50AP012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP012-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 3 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.3 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP013-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.4 (G) | ACTIVE | LTK-H04MLA50AP013 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP013-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 4 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.4 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP014-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.5 (G) | ACTIVE | LTK-H04MLA50AP014 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP014-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 5 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.5 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP015-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.6 (G) | ACTIVE | LTK-H04MLA50AP015 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP015-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 6 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.6 (G) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP016-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.1 (M) | ACTIVE | LTK-H04MLA50AP016 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP016-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 7 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.1 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP017-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.2 (M) | ACTIVE | LTK-H04MLA50AP017 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP017-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 8 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.2 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP018-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.3 (M) | ACTIVE | LTK-H04MLA50AP018 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP018-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 9 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.3 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP019-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.4 (M) | ACTIVE | LTK-H04MLA50AP019 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP019-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 10 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.4 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP020-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.5 (M) | ACTIVE | LTK-H04MLA50AP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP020-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 11 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.5 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50AP021-ME-U | LTK0 | BRAKING DUS COLLECTOR NO.6 (M) | ACTIVE | LTK-H04MLA50AP021 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50AP021-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 12 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | AP | MECHANICAL BRAKE SYSTEM | BRAKING DUS COLLECTOR NO.6 (M) | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG201-ME-U | LTK0 | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG201-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 13 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG202-ME-U | LTK0 | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG202 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG202-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 14 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG203-ME-U | LTK0 | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG203 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG203-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 15 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG204-ME-U | LTK0 | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG204 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG204-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 16 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG205-ME-U | LTK0 | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG205 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG205-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 17 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG206-ME-U | LTK0 | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | ACTIVE | LTK-H04MLA50CG206 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG206-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 18 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG211-ME-U | LTK0 | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG211 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG211-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 19 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG212-ME-U | LTK0 | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG212 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG212-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 20 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG213-ME-U | LTK0 | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG213 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG213-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 21 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG214-ME-U | LTK0 | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG214 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG214-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 22 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG215-ME-U | LTK0 | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG215 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG215-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 23 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CG216-ME-U | LTK0 | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | ACTIVE | LTK-H04MLA50CG216 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CG216-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 24 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CG | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CP101-ME-U | LTK0 | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MLA50CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CP101-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 25 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CP | MECHANICAL BRAKE SYSTEM | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 16 | 2024-11-10 | 16:00:00
PO-00170-H04MLA50CP102-ME-U | LTK0 | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | ACTIVE | LTK-H04MLA50CP102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00170-H04MLA50CP102-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 26 | 0 | H04MLA | STATOR | U | ME | H04MLA50 | CP | MECHANICAL BRAKE SYSTEM | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 16 | 2024-11-10 | 16:00:00
PO-00190-H04MLA60AP110-M01-ME-U | LTK0 | MOTOR FOR UGB OIL MIST EXHAUST - MLA60AP110 | ACTIVE | LTK-H04MLA60AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00190-H04MLA60AP110-M01-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 27 | 0 | H04MLA | STATOR | U | ME | H04MLA60 | AP | UGB Oil Mist Exhaust | MOTOR FOR UGB OIL MIST EXHAUST | 16 | 2024-11-09 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01350-H04MLA20CT201-ME-U | LTK0 | RTD FOR SLIP RING ROOM NO.1 | ACTIVE | LTK-H04MLA20CT201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01350-H04MLA20CT201-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 28 | 0 | H04MLA | STATOR | U | ME | H04MLA20 | CT | SLIP RING AND CARBON BRUSH | RTD FOR SLIP RING ROOM NO.1 | 16 | 2024-11-12 | 16:00:00
PO-01350-H04MLA20CT202-ME-U | LTK0 | RTD FOR SLIP RING ROOM NO.2 | ACTIVE | LTK-H04MLA20CT202 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01350-H04MLA20CT202-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 29 | 0 | H04MLA | STATOR | U | ME | H04MLA20 | CT | SLIP RING AND CARBON BRUSH | RTD FOR SLIP RING ROOM NO.2 | 16 | 2024-11-12 | 16:00:00
PO-01360-H04MLA20AP010-ME-U | LTK0 | CARBON DUST EXHAUST NO.1 | ACTIVE | LTK-H04MLA20AP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01360-H04MLA20AP010-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 30 | 0 | H04MLA | STATOR | U | ME | H04MLA20 | AP | SLIP RING AND CARBON BRUSH | CARBON DUST EXHAUST NO.1 | 16 | 2024-11-12 | 16:00:00
PO-01360-H04MLA20AP011-ME-U | LTK0 | CARBON DUST EXHAUST NO.2 | ACTIVE | LTK-H04MLA20AP011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01360-H04MLA20AP011-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 31 | 0 | H04MLA | STATOR | U | ME | H04MLA20 | AP | SLIP RING AND CARBON BRUSH | CARBON DUST EXHAUST NO.2 | 16 | 2024-11-12 | 16:00:00
PO-01990-H04MLA20-ME-U | LTK0 | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | ACTIVE | LTK-H04MLA20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01990-H04MLA20-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-16-H04MLA-ME-U | 0 | 32 | 0 | H04MLA | STATOR | U | ME | H04MLA20 |  | SLIP RING AND CARBON BRUSH | SLIP RING AND CARBON BRUSH | 16 | 2024-11-12 | 16:00:00
Group-17-H04MLA-ME-U | LTK0 | STATOR,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 17 | 1 | H04MLA | STATOR | U | ME |  |  |  |  | 17 | 2024-11-08 | 16:00:00
PO-01320-H04MLA10-ME-U | LTK0 | GENERATOR STATOR (หทอฟ-ธ.) | ACTIVE | LTK-H04MLA10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01320-H04MLA10-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-17-H04MLA-ME-U | 0 | 1 | 1 | H04MLA | STATOR | U | ME | H04MLA10 |  | STATOR | STATOR | 17 | 2024-11-08 | 16:00:00
PO-01340-H04MLA30-ME-U | LTK0 | GEN. ROTOR (หทอฟ-ธ.) | ACTIVE | LTK-H04MLA30 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01340-H04MLA30-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-17-H04MLA-ME-U | 0 | 2 | 1 | H04MLA | STATOR | U | ME | H04MLA30 |  | ROTOR | ROTOR | 17 | 2024-11-08 | 16:00:00
Group-18-H04MLA-ME-U | LTK0 | STATOR,MSP0-E220,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-E220 | หกฟ-ธ._หกฟ-ธ | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 18 | 0 | H04MLA | STATOR | U | ME |  |  |  |  | 18 | 2024-11-12 | 16:00:00
PO-01310-H04MLA10-ME-U | LTK0 | GENERATOR STATOR (หกฟ-ธ.) | ACTIVE | LTK-H04MLA10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01310-H04MLA10-ME-U |  | 2024-11-05 | MSP0-E220 | หกฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H04MLA-ME-U | 0 | 1 | 0 | H04MLA | STATOR | U | ME | H04MLA10 |  | STATOR | STATOR | 18 | 2024-11-12 | 16:00:00
PO-01330-H04MLA30-ME-U | LTK0 | GEN. ROTOR (หกฟ-ธ.) | ACTIVE | LTK-H04MLA30 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01330-H04MLA30-ME-U |  | 2024-11-05 | MSP0-E220 | หกฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H04MLA-ME-U | 0 | 2 | 0 | H04MLA | STATOR | U | ME | H04MLA30 |  | ROTOR | ROTOR | 18 | 2024-11-12 | 16:00:00
PO-01980-H04MLA20-ME-U | LTK0 | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | ACTIVE | LTK-H04MLA20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01980-H04MLA20-ME-U |  | 2024-11-05 | MSP0-E220 | หกฟ-ธ | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-18-H04MLA-ME-U | 0 | 3 | 0 | H04MLA | STATOR | U | ME | H04MLA20 |  | SLIP RING AND CARBON BRUSH | SLIP RING AND CARBON BRUSH | 18 | 2024-11-12 | 16:00:00
Group-19-H04MFX-ME-U | LTK0 | FLUID SUPPLY SYSTEM,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 19 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME |  |  |  |  | 19 | 2024-11-10 | 16:00:00
PO-00690-H04MFX60AP110-M01-ME-U | LTK0 | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | ACTIVE | LTK-H04MFX60AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00690-H04MFX60AP110-M01-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 1 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | AP | FLUID SUPPLY SYSTEM for MIV | ELECTRICAL MOTOR MIV PUMP NO.1 | 19 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00690-H04MFX60AP111-M02-ME-U | LTK0 | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | ACTIVE | LTK-H04MFX60AP111-M02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00690-H04MFX60AP111-M02-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 2 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | AP | FLUID SUPPLY SYSTEM for MIV | ELECTRICAL MOTOR MIV PUMP NO.2 | 19 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00730-H04MFX60CL010-ME-U | LTK0 | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | ACTIVE | LTK-H04MFX60CL010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL010-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 3 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL020-ME-U | LTK0 | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | ACTIVE | LTK-H04MFX60CL020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL020-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 4 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL111-ME-U | LTK0 | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | ACTIVE | LTK-H04MFX60CL111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL111-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 5 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL112-ME-U | LTK0 | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | ACTIVE | LTK-H04MFX60CL112 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL112-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 6 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL113-ME-U | LTK0 | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | ACTIVE | LTK-H04MFX60CL113 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL113-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 7 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL120-ME-U | LTK0 | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | ACTIVE | LTK-H04MFX60CL120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL120-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 8 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL121-ME-U | LTK0 | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | ACTIVE | LTK-H04MFX60CL121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL121-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 9 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL122-ME-U | LTK0 | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | ACTIVE | LTK-H04MFX60CL122 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL122-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 10 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL123-ME-U | LTK0 | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | ACTIVE | LTK-H04MFX60CL123 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL123-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 11 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL310-ME-U | LTK0 | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | ACTIVE | LTK-H04MFX60CL310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL310-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 12 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CL320-ME-U | LTK0 | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | ACTIVE | LTK-H04MFX60CL320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CL320-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 13 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CL | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CM110-ME-U | LTK0 | MIV SUMP TANK WATER IN OIL RELAY | ACTIVE | LTK-H04MFX60CM110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CM110-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 14 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CM | FLUID SUPPLY SYSTEM for MIV | MIV SUMP TANK WATER IN OIL RELAY | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CP001-ME-U | LTK0 | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | ACTIVE | LTK-H04MFX60CP001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CP001-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 15 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CP101-ME-U | LTK0 | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | ACTIVE | LTK-H04MFX60CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CP101-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 16 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CP102-ME-U | LTK0 | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | ACTIVE | LTK-H04MFX60CP102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CP102-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 17 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 19 | 2024-11-07 | 16:00:00
PO-00730-H04MFX60CP150-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | ACTIVE | LTK-H04MFX60CP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00730-H04MFX60CP150-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 18 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV HPU Oil Filter | 19 | 2024-11-07 | 16:00:00
PO-00770-H04MFX10AP110-M01-ME-U | LTK0 | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | ACTIVE | LTK-H04MFX10AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00770-H04MFX10AP110-M01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 19 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | MOTOR FOR GOVERNOR OIL PUMP NO.1 | 19 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00770-H04MFX10AP111-M01-ME-U | LTK0 | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | ACTIVE | LTK-H04MFX10AP111-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00770-H04MFX10AP111-M01-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 20 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | MOTOR FOR GOVERNOR OIL PUMP NO.2 | 19 | 2024-11-06 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00780-H04MFX10CL010-ME-U | LTK0 | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | ACTIVE | LTK-H04MFX10CL010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL010-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 21 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL020-ME-U | LTK0 | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | ACTIVE | LTK-H04MFX10CL020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL020-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 22 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL111-ME-U | LTK0 | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | ACTIVE | LTK-H04MFX10CL111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL111-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 23 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL112-ME-U | LTK0 | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | ACTIVE | LTK-H04MFX10CL112 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL112-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 24 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL113-ME-U | LTK0 | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | ACTIVE | LTK-H04MFX10CL113 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL113-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 25 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL120-ME-U | LTK0 | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | ACTIVE | LTK-H04MFX10CL120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL120-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 26 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL121-ME-U | LTK0 | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | ACTIVE | LTK-H04MFX10CL121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL121-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 27 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL122-ME-U | LTK0 | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | ACTIVE | LTK-H04MFX10CL122 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL122-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 28 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL123-ME-U | LTK0 | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | ACTIVE | LTK-H04MFX10CL123 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL123-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 29 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL310-ME-U | LTK0 | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | ACTIVE | LTK-H04MFX10CL310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL310-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 30 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CL320-ME-U | LTK0 | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | ACTIVE | LTK-H04MFX10CL320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CL320-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 31 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CM110-ME-U | LTK0 | GOV SUMP TANK WATER IN OIL RELAY | ACTIVE | LTK-H04MFX10CM110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CM110-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 32 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CM | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK WATER IN OIL RELAY | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CP021-ME-U | LTK0 | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | ACTIVE | LTK-H04MFX10CP021 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CP021-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 33 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CP110-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | ACTIVE | LTK-H04MFX10CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CP110-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 34 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CP120-ME-U | LTK0 | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | ACTIVE | LTK-H04MFX10CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CP120-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 35 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CP121-ME-U | LTK0 | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | ACTIVE | LTK-H04MFX10CP121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CP121-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 36 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CT010-ME-U | LTK0 | GOV SUMP TANK TEMPERATURE RTD | ACTIVE | LTK-H04MFX10CT010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CT010-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 37 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CT | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK TEMPERATURE RTD | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX10CT110-ME-U | LTK0 | GOV SUMP TANK TEMPERATURE SWITCH | ACTIVE | LTK-H04MFX10CT110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX10CT110-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 38 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CT | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV SUMP TANK TEMPERATURE SWITCH | 19 | 2024-11-10 | 16:00:00
PO-00780-H04MFX20CP101-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | ACTIVE | LTK-H04MFX20CP101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00780-H04MFX20CP101-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 39 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX20 | CP | FLUID SUPPLY SYSTEM 2 (GOVERNOR) | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 19 | 2024-11-10 | 16:00:00
PO-00800-H04MFX10AP330-M01-ME-U | LTK0 | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | ACTIVE | LTK-H04MFX10AP330-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00800-H04MFX10AP330-M01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 40 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | MOTOR FOR RETURN OIL LEAK PUMP | 19 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-00810-H04MFX10CL131-ME-U | LTK0 | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | ACTIVE | LTK-H04MFX10CL131 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00810-H04MFX10CL131-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 41 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 19 | 2024-11-10 | 16:00:00
PO-00810-H04MFX10CL132-ME-U | LTK0 | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | ACTIVE | LTK-H04MFX10CL132 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00810-H04MFX10CL132-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 42 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 19 | 2024-11-10 | 16:00:00
PO-00810-H04MFX10CL133-ME-U | LTK0 | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | ACTIVE | LTK-H04MFX10CL133 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00810-H04MFX10CL133-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 43 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CL | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 19 | 2024-11-10 | 16:00:00
PO-00810-H04MFX10CM130-ME-U | LTK0 | OIL LEAKAGE WATER IN OIL RELAY | ACTIVE | LTK-H04MFX10CM130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00810-H04MFX10CM130-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-19-H04MFX-ME-U | 0 | 44 | 1 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CM | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | OIL LEAKAGE WATER IN OIL RELAY | 19 | 2024-11-10 | 16:00:00
Group-20-H04MFX-ME-U | LTK0 | FLUID SUPPLY SYSTEM,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 20 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME |  |  |  |  | 20 | 2024-11-11 | 16:00:00
PO-00750-H04MFX60CP310-ME-U | LTK0 | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MFX60CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFX60CP310-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 1 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 20 | 2024-11-07 | 16:00:00
PO-00750-H04MFX60CP320-ME-U | LTK0 | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04MFX60CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFX60CP320-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 2 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 20 | 2024-11-07 | 16:00:00
PO-00750-H04MFX60CP321-ME-U | LTK0 | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | ACTIVE | LTK-H04MFX60CP321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFX60CP321-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 3 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 20 | 2024-11-07 | 16:00:00
PO-00750-H04MFX60CP322-ME-U | LTK0 | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | ACTIVE | LTK-H04MFX60CP322 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFX60CP322-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 4 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | CP | FLUID SUPPLY SYSTEM for MIV | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 20 | 2024-11-07 | 16:00:00
PO-00790-H04MFX10CP310-ME-U | LTK0 | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MFX10CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00790-H04MFX10CP310-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 5 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 20 | 2024-11-11 | 16:00:00
PO-00790-H04MFX10CP320-ME-U | LTK0 | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04MFX10CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00790-H04MFX10CP320-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 6 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 20 | 2024-11-11 | 16:00:00
PO-00790-H04MFX10CP321-ME-U | LTK0 | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | ACTIVE | LTK-H04MFX10CP321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00790-H04MFX10CP321-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 7 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | CP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 20 | 2024-11-11 | 16:00:00
PO-00790-H04MFX20CP301-ME-U | LTK0 | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MFX20CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00790-H04MFX20CP301-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-20-H04MFX-ME-U | 0 | 8 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX20 | CP | FLUID SUPPLY SYSTEM 2 (GOVERNOR) | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 20 | 2024-11-11 | 16:00:00
Group-21-H04MFW-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 21 | 1 | H04MFW | No_kks_found | U | ME |  |  |  |  | 21 | 2024-11-10 | 16:00:00
PO-00460-H04MFW40CP100-ME-U | LTK0 | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | ACTIVE | LTK-H04MFW40CP100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00460-H04MFW40CP100-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H04MFW-ME-U | 0 | 1 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 21 | 2024-11-10 | 16:00:00
PO-00460-H04MFW40CP110-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | ACTIVE | LTK-H04MFW40CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00460-H04MFW40CP110-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H04MFW-ME-U | 0 | 2 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 21 | 2024-11-10 | 16:00:00
PO-00460-H04MFW40CP120-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | ACTIVE | LTK-H04MFW40CP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00460-H04MFW40CP120-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H04MFW-ME-U | 0 | 3 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 21 | 2024-11-10 | 16:00:00
PO-00460-H04MFW40CT010-ME-U | LTK0 | SHAFT SEAL TEMPERATURE RTD NO.1 | ACTIVE | LTK-H04MFW40CT010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00460-H04MFW40CT010-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H04MFW-ME-U | 0 | 4 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CT | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL TEMPERATURE RTD NO.1 | 21 | 2024-11-10 | 16:00:00
PO-00460-H04MFW40CT020-ME-U | LTK0 | SHAFT SEAL TEMPERATURE RTD NO.2 | ACTIVE | LTK-H04MFW40CT020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00460-H04MFW40CT020-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-21-H04MFW-ME-U | 0 | 5 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CT | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL TEMPERATURE RTD NO.2 | 21 | 2024-11-10 | 16:00:00
Group-22-H04MFV-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 22 | 0 | H04MFV | No_kks_found | U | ME |  |  |  |  | 22 | 2024-11-13 | 16:00:00
PO-00440-H04MFV20CF110-ME-U | LTK0 | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | ACTIVE | LTK-H04MFV20CF110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFV20CF110-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H04MFV-ME-U | 0 | 1 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | CF | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 22 | 2024-11-13 | 16:00:00
PO-00440-H04MFV20CP110-ME-U | LTK0 | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | ACTIVE | LTK-H04MFV20CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFV20CP110-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H04MFV-ME-U | 0 | 2 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 22 | 2024-11-13 | 16:00:00
PO-00440-H04MFV20CP151-ME-U | LTK0 | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | ACTIVE | LTK-H04MFV20CP151 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFV20CP151-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H04MFV-ME-U | 0 | 3 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 22 | 2024-11-13 | 16:00:00
PO-00440-H04MFV20CP152-ME-U | LTK0 | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | ACTIVE | LTK-H04MFV20CP152 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFV20CP152-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-22-H04MFV-ME-U | 0 | 4 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 22 | 2024-11-13 | 16:00:00
Group-23-H04MFP-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 23 | 1 | H04MFP | No_kks_found | U | ME |  |  |  |  | 23 | 2024-11-07 | 16:00:00
PO-02110-H04MFP14AA001-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SOLINOID DRIVE DELUGE VALVE | ACTIVE | LTK-H04MFP14AA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H04MFP14AA001-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H04MFP-ME-U | 0 | 1 | 1 | H04MFP | No_kks_found | U | ME | H04MFP14 | AA | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SOLINOID DRIVE DELUGE VALVE | 23 | 2024-11-07 | 16:00:00
PO-02110-H04MFP14CP001-ME-U | LTK0 | G/M FIRE EXTINGUISHER WATER DISCHARGE PRESSURE SWITCH - CP001 | ACTIVE | LTK-H04MFP14CP001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H04MFP14CP001-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H04MFP-ME-U | 0 | 2 | 1 | H04MFP | No_kks_found | U | ME | H04MFP14 | CP | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER WATER DISCHARGE PRESSURE SWITCH - CP001 | 23 | 2024-11-07 | 16:00:00
PO-02110-H04MFP14GH001-ME-U | LTK0 | G/M FIRE EXTINGUISHER - MODULE BOX | ACTIVE | LTK-H04MFP14GH001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H04MFP14GH001-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-23-H04MFP-ME-U | 0 | 3 | 1 | H04MFP | No_kks_found | U | ME | H04MFP14 | GH | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - MODULE BOX | 23 | 2024-11-07 | 16:00:00
Group-24-H04MFD-ME-U | LTK0 | TURBINE GUIDE BEARING,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 24 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME |  |  |  |  | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL020-ME-U | LTK0 | TGB OIL PAN LEVEL TRANSMITTER - CL020 | ACTIVE | LTK-H04MFD20CL020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL020-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 1 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL120-ME-U | LTK0 | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | ACTIVE | LTK-H04MFD20CL120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL120-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 2 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL121-ME-U | LTK0 | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | ACTIVE | LTK-H04MFD20CL121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL121-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 3 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL122-ME-U | LTK0 | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | ACTIVE | LTK-H04MFD20CL122 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL122-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 4 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL123-ME-U | LTK0 | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | ACTIVE | LTK-H04MFD20CL123 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL123-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 5 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CL320-ME-U | LTK0 | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | ACTIVE | LTK-H04MFD20CL320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CL320-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 6 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CL | TURBINE GUIDE BEARING | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CM115-ME-U | LTK0 | TGB WATER IN OIL RELAY | ACTIVE | LTK-H04MFD20CM115 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CM115-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 7 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CM | TURBINE GUIDE BEARING | TGB WATER IN OIL RELAY | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT011-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.1 | ACTIVE | LTK-H04MFD20CT011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT011-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 8 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.1 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT012-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.2 | ACTIVE | LTK-H04MFD20CT012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT012-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 9 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.2 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT013-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.3 | ACTIVE | LTK-H04MFD20CT013 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT013-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 10 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.3 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT014-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.4 | ACTIVE | LTK-H04MFD20CT014 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT014-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 11 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.4 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT015-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.5 | ACTIVE | LTK-H04MFD20CT015 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT015-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 12 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.5 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT016-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.6 | ACTIVE | LTK-H04MFD20CT016 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT016-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 13 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.6 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT017-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.7 | ACTIVE | LTK-H04MFD20CT017 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT017-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 14 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.7 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT018-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.8 | ACTIVE | LTK-H04MFD20CT018 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT018-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 15 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.8 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT019-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.9 | ACTIVE | LTK-H04MFD20CT019 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT019-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 16 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.9 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT020-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.10 | ACTIVE | LTK-H04MFD20CT020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT020-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 17 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.10 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT021-ME-U | LTK0 | TGB PAD TEMPERATURE RTD NO.11 | ACTIVE | LTK-H04MFD20CT021 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT021-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 18 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | TGB PAD TEMPERATURE RTD NO.11 | 24 | 2024-11-13 | 16:00:00
PO-00440-H04MFD20CT101-ME-U | LTK0 | DIAL THERMOMETER FOR TGB PAD - CT101 | ACTIVE | LTK-H04MFD20CT101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00440-H04MFD20CT101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-24-H04MFD-ME-U | 0 | 19 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | CT | TURBINE GUIDE BEARING | DIAL THERMOMETER FOR TGB PAD - CT101 | 24 | 2024-11-13 | 16:00:00
Group-25-H04MFB-ME-U | LTK0 | MAIN INLET VALVE,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 25 | 1 | H04MFB | MAIN INLET VALVE | U | ME |  |  |  |  | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG114-ME-U | LTK0 | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | ACTIVE | LTK-H04MFB10CG114 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG114-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 1 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG115-ME-U | LTK0 | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | ACTIVE | LTK-H04MFB10CG115 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG115-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 2 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG140-ME-U | LTK0 | MIV POSITION - PROXIMITY SENSOR NO.1 | ACTIVE | LTK-H04MFB10CG140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG140-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 3 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG141-ME-U | LTK0 | MIV POSITION - PROXIMITY SENSOR NO.2 | ACTIVE | LTK-H04MFB10CG141 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG141-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 4 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG150-ME-U | LTK0 | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | ACTIVE | LTK-H04MFB10CG150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG150-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 5 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG151-ME-U | LTK0 | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | ACTIVE | LTK-H04MFB10CG151 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG151-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 6 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CG152-ME-U | LTK0 | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | ACTIVE | LTK-H04MFB10CG152 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CG152-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 7 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP010-ME-U | LTK0 | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | ACTIVE | LTK-H04MFB10CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP010-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 8 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP011-ME-U | LTK0 | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | ACTIVE | LTK-H04MFB10CP011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP011-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 9 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP015-ME-U | LTK0 | SV INLET PRESSURE - PRESSURE TRANSMITTER | ACTIVE | LTK-H04MFB10CP015 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP015-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 10 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP020-ME-U | LTK0 | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | ACTIVE | LTK-H04MFB10CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP020-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 11 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP110-ME-U | LTK0 | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | ACTIVE | LTK-H04MFB10CP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP110-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 12 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 25 | 2024-11-08 | 16:00:00
PO-00710-H04MFB10CP150-ME-U | LTK0 | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | ACTIVE | LTK-H04MFB10CP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00710-H04MFB10CP150-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-25-H04MFB-ME-U | 0 | 13 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CP | INLET VALVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 25 | 2024-11-08 | 16:00:00
Group-26-H04MFB-ME-U | LTK0 | MAIN INLET VALVE,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 26 | 0 | H04MFB | MAIN INLET VALVE | U | ME |  |  |  |  | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG120-ME-U | LTK0 | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | ACTIVE | LTK-H04MFB10CG120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG120-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 1 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG121-ME-U | LTK0 | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | ACTIVE | LTK-H04MFB10CG121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG121-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 2 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG122-ME-U | LTK0 | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | ACTIVE | LTK-H04MFB10CG122 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG122-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 3 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG130-ME-U | LTK0 | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | ACTIVE | LTK-H04MFB10CG130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG130-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 4 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG131-ME-U | LTK0 | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | ACTIVE | LTK-H04MFB10CG131 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG131-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 5 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 26 | 2024-11-07 | 16:00:00
PO-00750-H04MFB10CG132-ME-U | LTK0 | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | ACTIVE | LTK-H04MFB10CG132 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00750-H04MFB10CG132-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-26-H04MFB-ME-U | 0 | 6 | 0 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | CG | INLET VALVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 26 | 2024-11-07 | 16:00:00
Group-27-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 27 | 1 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA10CP020-ME-U | LTK0 | SC INLET PRESSURE TRANSDUCER - CP020 | ACTIVE | LTK-H04MFA10CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA10CP020-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 1 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA10 | CP | SPIRAL CASE | SC INLET PRESSURE TRANSDUCER - CP020 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA20CP010-ME-U | LTK0 | VANELESS AREA PRESSURE TRANSDUCER - CP010 | ACTIVE | LTK-H04MFA20CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA20CP010-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 2 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA20CP020-ME-U | LTK0 | BOTTOM RING PRESSURE TRANSDUCER - CP020 | ACTIVE | LTK-H04MFA20CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA20CP020-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 3 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA20CP105-ME-U | LTK0 | VANELESS AREA PRESSURE SWITCH - CP105 | ACTIVE | LTK-H04MFA20CP105 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA20CP105-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 4 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | VANELESS AREA PRESSURE SWITCH - CP105 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA30CP010-ME-U | LTK0 | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | ACTIVE | LTK-H04MFA30CP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA30CP010-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 5 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | CP | RUNNER & TURBINE SHAFT | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA30CP020-ME-U | LTK0 | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | ACTIVE | LTK-H04MFA30CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA30CP020-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 6 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | CP | RUNNER & TURBINE SHAFT | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA30CP301-ME-U | LTK0 | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | ACTIVE | LTK-H04MFA30CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA30CP301-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 7 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | CP | RUNNER & TURBINE SHAFT | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA30CP311-ME-U | LTK0 | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | ACTIVE | LTK-H04MFA30CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA30CP311-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 8 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | CP | RUNNER & TURBINE SHAFT | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA60CP020-ME-U | LTK0 | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | ACTIVE | LTK-H04MFA60CP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA60CP020-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 9 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 27 | 2024-11-14 | 16:00:00
PO-00390-H04MFA60CP030-ME-U | LTK0 | DT OUTLET PRESSURE TRANSDUCER - CP030 | ACTIVE | LTK-H04MFA60CP030 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00390-H04MFA60CP030-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 10 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | DT OUTLET PRESSURE TRANSDUCER - CP030 | 27 | 2024-11-14 | 16:00:00
PO-00410-H04MFA20CG001-ME-U | LTK0 | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | ACTIVE | LTK-H04MFA20CG001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG001-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 11 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG002-ME-U | LTK0 | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | ACTIVE | LTK-H04MFA20CG002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG002-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 12 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG121-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | ACTIVE | LTK-H04MFA20CG121 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG121-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 13 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG122-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | ACTIVE | LTK-H04MFA20CG122 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG122-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 14 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG123-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | ACTIVE | LTK-H04MFA20CG123 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG123-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 15 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG124-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | ACTIVE | LTK-H04MFA20CG124 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG124-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 16 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG131-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | ACTIVE | LTK-H04MFA20CG131 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG131-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 17 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG132-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | ACTIVE | LTK-H04MFA20CG132 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG132-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 18 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG141-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | ACTIVE | LTK-H04MFA20CG141 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG141-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 19 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG142-ME-U | LTK0 | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | ACTIVE | LTK-H04MFA20CG142 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG142-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 20 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B1-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.1 | ACTIVE | LTK-H04MFA20CG910-B1 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B1-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 21 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | Gate Opening Limit switch/Proximity switch No.1 | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B2-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.2 | ACTIVE | LTK-H04MFA20CG910-B2 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B2-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 22 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | No_kks_found | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B3-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.3 | ACTIVE | LTK-H04MFA20CG910-B3 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B3-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 23 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | No_kks_found | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B4-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.4 | ACTIVE | LTK-H04MFA20CG910-B4 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B4-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 24 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | No_kks_found | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B5-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.5 | ACTIVE | LTK-H04MFA20CG910-B5 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B5-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 25 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | No_kks_found | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-B6-ME-U | LTK0 | GUIDE VANE POSITION SWITCH NO.6 | ACTIVE | LTK-H04MFA20CG910-B6 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-B6-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 26 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | Gate Opening Limit switch/Proximity switch No.2 | 27 | 2024-11-08 | 16:00:00
PO-00410-H04MFA20CG910-ME-U | LTK0 | LVDT FOR GUIDE VANE POSITION | ACTIVE | LTK-H04MFA20CG910 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00410-H04MFA20CG910-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-27-H04MFA-ME-U | 0 | 27 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CG | GUIDE VANE | LVDT FOR GUIDE VANE POSITION | 27 | 2024-11-08 | 16:00:00
Group-28-H04CKA-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 28 | 0 | H04CKA | No_kks_found | U | ME |  |  |  |  | 28 | 2024-11-12 | 16:00:00
PO-01690-H04CKA20GH100-ME-U | LTK0 | VIBRATION MONITORING SYSTEM (MMS) | ACTIVE | LTK-H04CKA20GH100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01690-H04CKA20GH100-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 1 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | GH | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | VIBRATION MONITORING SYSTEM (MMS) | 28 | 2024-11-11 | 16:00:00
PO-01700-H04CKA20CY001-ME-U | LTK0 | UPPER GUIDE BEARING - SHAFT RUNOUT X | ACTIVE | LTK-H04CKA20CY001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY001-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 2 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | UPPER GUIDE BEARING - SHAFT RUNOUT X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY002-ME-U | LTK0 | UPPER GUIDE BEARING - SHAFT RUNOUT Y | ACTIVE | LTK-H04CKA20CY002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY002-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 3 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | UPPER GUIDE BEARING - SHAFT RUNOUT Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY003-ME-U | LTK0 | UPPER GUIDE BEARING - VIBRATION X | ACTIVE | LTK-H04CKA20CY003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY003-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 4 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | UPPER GUIDE BEARING - VIBRATION X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY004-ME-U | LTK0 | UPPER GUIDE BEARING - VIBRATION Y | ACTIVE | LTK-H04CKA20CY004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY004-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 5 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | UPPER GUIDE BEARING - VIBRATION Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY005-ME-U | LTK0 | LOWER GUIDE BEARING - SHAFT RUNOUT X | ACTIVE | LTK-H04CKA20CY005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY005-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 6 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | LOWER GUIDE BEARING - SHAFT RUNOUT X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY006-ME-U | LTK0 | LOWER GUIDE BEARING - SHAFT RUNOUT Y | ACTIVE | LTK-H04CKA20CY006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY006-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 7 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | LOWER GUIDE BEARING - SHAFT RUNOUT Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY007-ME-U | LTK0 | LOWER GUIDE BEARING - VIBRATION X | ACTIVE | LTK-H04CKA20CY007 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY007-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 8 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | LOWER GUIDE BEARING - VIBRATION X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY008-ME-U | LTK0 | LOWER GUIDE BEARING - VIBRATION Y | ACTIVE | LTK-H04CKA20CY008 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY008-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 9 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | LOWER GUIDE BEARING - VIBRATION Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY009-ME-U | LTK0 | STATOR FRAME - VIBRATION X | ACTIVE | LTK-H04CKA20CY009 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY009-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 10 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | STATOR FRAME - VIBRATION X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY010-ME-U | LTK0 | STATOR FRAME - VIBRATION Y | ACTIVE | LTK-H04CKA20CY010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY010-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 11 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | STATOR FRAME - VIBRATION Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY011-ME-U | LTK0 | TURBINE GUIDE BEARING - VIBRATION X | ACTIVE | LTK-H04CKA20CY011 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY011-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 12 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | TURBINE GUIDE BEARING - VIBRATION X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY012-ME-U | LTK0 | TURBINE GUIDE BEARING - VIBRATION Y | ACTIVE | LTK-H04CKA20CY012 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY012-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 13 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | TURBINE GUIDE BEARING - VIBRATION Y | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY013-ME-U | LTK0 | TURBINE GUIDE BEARING - SHAFT RUNOUT X | ACTIVE | LTK-H04CKA20CY013 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY013-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 14 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | TURBINE GUIDE BEARING - SHAFT RUNOUT X | 28 | 2024-11-12 | 16:00:00
PO-01700-H04CKA20CY014-ME-U | LTK0 | TURBINE GUIDE BEARING - SHAFT RUNOUT Y | ACTIVE | LTK-H04CKA20CY014 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01700-H04CKA20CY014-ME-U |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-28-H04CKA-ME-U | 0 | 15 | 0 | H04CKA | No_kks_found | U | ME | H04CKA20 | CY | INSTRUMENTS FOR VIBRATION MONITORING SYSTEM (MMS) | TURBINE GUIDE BEARING - SHAFT RUNOUT Y | 28 | 2024-11-12 | 16:00:00
Group-29-H04CJA-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 29 | 1 | H04CJA | No_kks_found | U | ME |  |  |  |  | 29 | 2024-11-10 | 16:00:00
PO-01630-H04CJA10GH101-ME-U | LTK0 | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | ACTIVE | LTK-H04CJA10GH101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01630-H04CJA10GH101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 1 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 29 | 2024-11-05 | 16:00:00
PO-01640-H04CJA10GH102-ME-U | LTK0 | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | ACTIVE | LTK-H04CJA10GH102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01640-H04CJA10GH102-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 2 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 29 | 2024-11-06 | 16:00:00
PO-01650-H04CJA10GH103-ME-U | LTK0 | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | ACTIVE | LTK-H04CJA10GH103 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01650-H04CJA10GH103-ME-U |  | 2024-11-07 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 3 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 29 | 2024-11-07 | 16:00:00
PO-01660-H04CJA10GH104-ME-U | LTK0 | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | ACTIVE | LTK-H04CJA10GH104 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01660-H04CJA10GH104-ME-U |  | 2024-11-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 4 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | 29 | 2024-11-08 | 16:00:00
PO-01670-H04CJA10GH105-ME-U | LTK0 | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | ACTIVE | LTK-H04CJA10GH105 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01670-H04CJA10GH105-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 5 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 29 | 2024-11-09 | 16:00:00
PO-01680-H04CJA10GH106-ME-U | LTK0 | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | ACTIVE | LTK-H04CJA10GH106 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01680-H04CJA10GH106-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-29-H04CJA-ME-U | 0 | 6 | 1 | H04CJA | No_kks_found | U | ME | H04CJA10 | GH | UNIT CONTROL SYSTEM | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 29 | 2024-11-10 | 16:00:00
Group-30-H04CHB-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 30 | 0 | H04CHB | No_kks_found | U | ME |  |  |  |  | 30 | 2024-11-13 | 16:00:00
PO-01800-H04CHB10GH101-ME-U | LTK0 | TRANSFORMER PROTECTION SYSTEM A CUBICLE | ACTIVE | LTK-H04CHB10GH101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01800-H04CHB10GH101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 1 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | TRANSFORMER PROTECTION SYSTEM A CUBICLE | 30 | 2024-11-13 | 16:00:00
PO-01810-H04CHB10GH101-U01-ME-U | LTK0 | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | ACTIVE | LTK-H04CHB10GH101-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01810-H04CHB10GH101-U01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 2 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01820-H04CHB10GH101-U02-ME-U | LTK0 | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | ACTIVE | LTK-H04CHB10GH101-U02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01820-H04CHB10GH101-U02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 3 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01830-H04CHB10GH101-K01-ME-U | LTK0 | LOCKOUT RELAY 86-T (SYSTEM A) | ACTIVE | LTK-H04CHB10GH101-K01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01830-H04CHB10GH101-K01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 4 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | LOCKOUT RELAY 86-T (SYSTEM A) | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01840-H04CHB10GH102-ME-U | LTK0 | TRANSFORMER PROTECTION SYSTEM B CUBICLE | ACTIVE | LTK-H04CHB10GH102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01840-H04CHB10GH102-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 5 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | TRANSFORMER PROTECTION SYSTEM B CUBICLE | 30 | 2024-11-13 | 16:00:00
PO-01850-H04CHB10GH102-U01-ME-U | LTK0 | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | ACTIVE | LTK-H04CHB10GH102-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01850-H04CHB10GH102-U01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 6 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01860-H04CHB10GH102-U02-ME-U | LTK0 | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | ACTIVE | LTK-H04CHB10GH102-U02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01860-H04CHB10GH102-U02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 7 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01870-H04CHB10GH102-U03-ME-U | LTK0 | MAIN TRANSFORMER MECHNICAL PROTECTION RELAY | ACTIVE | LTK-H04CHB10GH102-U03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01870-H04CHB10GH102-U03-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 8 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | MAIN TRANSFORMER MECHANICAL PROTECTION RELAY | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01880-H04CHB10GH102-K02-ME-U | LTK0 | LOCKOUT RELAY 86-T (SYSTEM B) | ACTIVE | LTK-H04CHB10GH102-K02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01880-H04CHB10GH102-K02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-30-H04CHB-ME-U | 0 | 9 | 0 | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | LOCKOUT RELAY 86-T (SYSTEM B) | 30 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-31-H04CHA-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 31 | 1 | H04CHA | No_kks_found | U | ME |  |  |  |  | 31 | 2024-11-13 | 16:00:00
PO-01710-H04CHA10GH101-ME-U | LTK0 | GENERATOR PROTECTION SYSTEM A CUBICLE | ACTIVE | LTK-H04CHA10GH101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01710-H04CHA10GH101-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 1 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | GENERATOR PROTECTION SYSTEM A CUBICLE | 31 | 2024-11-13 | 16:00:00
PO-01720-H04CHA10GH101-U01-ME-U | LTK0 | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | ACTIVE | LTK-H04CHA10GH101-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01720-H04CHA10GH101-U01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 2 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01730-H04CHA10GH101-U02-ME-U | LTK0 | SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04CHA10GH101-U02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01730-H04CHA10GH101-U02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 3 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | SPLIT PHASE PROTECTION RELAY | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01740-H04CHA10GH101-K01-ME-U | LTK0 | LOCKOUT RELAY 86-1 (SYSTEM A) | ACTIVE | LTK-H04CHA10GH101-K01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01740-H04CHA10GH101-K01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 4 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | LOCKOUT RELAY 86-1 (SYSTEM A) | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01750-H04CHA10GH102-ME-U | LTK0 | GENERATOR PROTECTION SYSTEM B CUBICLE | ACTIVE | LTK-H04CHA10GH102 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01750-H04CHA10GH102-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 5 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | GENERATOR PROTECTION SYSTEM B CUBICLE | 31 | 2024-11-13 | 16:00:00
PO-01760-H04CHA10GH102-U01-ME-U | LTK0 | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | ACTIVE | LTK-H04CHA10GH102-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01760-H04CHA10GH102-U01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 6 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01770-H04CHA10GH102-U02-ME-U | LTK0 | G/M MECHANICAL PROTECTION RELAY | ACTIVE | LTK-H04CHA10GH102-U02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01770-H04CHA10GH102-U02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 7 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | G/M MECHANICAL PROTECTION RELAY | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01780-H04CHA10GH102-K02-ME-U | LTK0 | LOCKOUT RELAY 86-1 (SYSTEM B) | ACTIVE | LTK-H04CHA10GH102-K02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01780-H04CHA10GH102-K02-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 8 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | LOCK OUT RELAY 86-1 (SYSTEM B) | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01790-H04CHA10GH102-K01-ME-U | LTK0 | LOCKOUT RELAY 86-2 | ACTIVE | LTK-H04CHA10GH102-K01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01790-H04CHA10GH102-K01-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-31-H04CHA-ME-U | 0 | 9 | 1 | H04CHA | No_kks_found | U | ME | H04CHA10 | GH | CABINETS FOR GENERATOR PROTECTION | LOCK OUT RELAY 86-2 | 31 | 2024-11-13 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-32-H04BAU-ME-U | LTK0 | No_kks_found,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 32 | 0 | H04BAU | No_kks_found | U | ME |  |  |  |  | 32 | 2024-11-05 | 16:00:00
PO-01380-H04BAU10CE110-ME-U | LTK0 | NGR CURRENT TRANSFORMER - CE110 | ACTIVE | LTK-H04BAU10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01380-H04BAU10CE110-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-32-H04BAU-ME-U | 0 | 1 | 0 | H04BAU | No_kks_found | U | ME | H04BAU10 | CE | EARTHING AND LIGHTNING PROTECTION SYSTEM | NGR CURRENT TRANSFORMER - CE110 | 32 | 2024-11-05 | 16:00:00
PO-01380-H04BAU10CE210-ME-U | LTK0 | NGR POTENTIAL TRANSFORMER - CE210 | ACTIVE | LTK-H04BAU10CE210 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01380-H04BAU10CE210-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-32-H04BAU-ME-U | 0 | 2 | 0 | H04BAU | No_kks_found | U | ME | H04BAU10 | CE | EARTHING AND LIGHTNING PROTECTION SYSTEM | NGR POTENTIAL TRANSFORMER - CE210 | 32 | 2024-11-05 | 16:00:00
Group-33-H04BAT-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 33 | 1 | H04BAT | No_kks_found | U | ME |  |  |  |  | 33 | 2024-11-11 | 16:00:00
PO-01520-H04BAT01GT001-ME-U | LTK0 | MAIN TRANSFORMER KG4A | ACTIVE | LTK-H04BAT01GT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01520-H04BAT01GT001-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 1 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GT | GENERATOR TRANSFORMERS | MAIN TRANSFORMER KG4A | 33 | 2024-11-11 | 16:00:00
PO-01530-H04BAT01CD001-ME-U | LTK0 | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | ACTIVE | LTK-H04BAT01CD001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01530-H04BAT01CD001-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 2 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CD | GENERATOR TRANSFORMERS | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | 33 | 2024-11-11 | 16:00:00
PO-01540-H04BAT01GH001-ME-U | LTK0 | GENERATOR TRANSFORMER CONTROL CABINET - GH001 | ACTIVE | LTK-H04BAT01GH001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01540-H04BAT01GH001-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 3 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GH | GENERATOR TRANSFORMERS | GENERATOR TRANSFORMER CONTROL CABINET - GH001 | 33 | 2024-11-11 | 16:00:00
PO-01540-H04BAT01GH002-ME-U | LTK0 | GENERATOR TRANSFORMER CONTROL CABINET - GH002 | ACTIVE | LTK-H04BAT01GH002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01540-H04BAT01GH002-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 4 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GH | GENERATOR TRANSFORMERS | GENERATOR TRANSFORMER CONTROL CABINET - GH002 | 33 | 2024-11-11 | 16:00:00
PO-01560-H04BAT10GV100-ME-U | LTK0 | SURGE ARRESTER 192kV, 10kA (หปฟนม-ธ.) | ACTIVE | LTK-H04BAT10GV100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01560-H04BAT10GV100-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 5 | 1 | H04BAT | No_kks_found | U | ME | H04BAT10 | GV | No_kks_found | SURGE ARRESTER 192kV, 10kA | 33 | 2024-11-11 | 16:00:00
PO-01570-H04BAT01GH004-ME-U | LTK0 | ONLOAD TAP CHANGER (หปฟนม-ธ.) | ACTIVE | LTK-H04BAT01GH004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01570-H04BAT01GH004-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 6 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GH | GENERATOR TRANSFORMERS | OLTC | 33 | 2024-11-11 | 16:00:00
PO-01580-H04BAT01AP110-M01-ME-U | LTK0 | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | ACTIVE | LTK-H04BAT01AP110-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01580-H04BAT01AP110-M01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 7 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01590-H04BAT01AP120-M01-ME-U | LTK0 | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | ACTIVE | LTK-H04BAT01AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01590-H04BAT01AP120-M01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 8 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01600-H04BAT01AP120-M01-ME-U | LTK0 | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | ACTIVE | LTK-H04BAT01AP120-M01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01600-H04BAT01AP120-M01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 9 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT001XQ01-ME-U | LTK0 | A PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT001XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT001XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 10 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | A PHASE OIL TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT002XQ01-ME-U | LTK0 | B PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT002XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT002XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 11 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE OIL TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT003XQ01-ME-U | LTK0 | C PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT003XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT003XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 12 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | C PHASE OIL TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT004XQ01-ME-U | LTK0 | B PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT004XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT004XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 13 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE WINDING TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT005XQ01-ME-U | LTK0 | A PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT005XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT005XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 14 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | A PHASE WINDING TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT006XQ01-ME-U | LTK0 | b PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT006XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT006XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 15 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE WINDING TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01610-H04BAT01CT007XQ01-ME-U | LTK0 | C PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT007XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01610-H04BAT01CT007XQ01-ME-U |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-33-H04BAT-ME-U | 0 | 16 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | C PHASE WINDING TEMPERATURE | 33 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-34-H04BAT-ME-U | LTK0 | No_kks_found,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 34 | 0 | H04BAT | No_kks_found | U | ME |  |  |  |  | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE110-ME-U | LTK0 | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | ACTIVE | LTK-H04BAT01CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE110-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 1 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE120-ME-U | LTK0 | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | ACTIVE | LTK-H04BAT01CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE120-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 2 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE130-ME-U | LTK0 | CT: 230kV, 1000A/5A - MTR PROTECTION RELAY (NEUTRAL) | ACTIVE | LTK-H04BAT01CE130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE130-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 3 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1000A/5A - MTR PROTECTION RELAY (NEUTRAL) | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE150-ME-U | LTK0 | CT: 230kV, 1000A/5A - AVR OF OLTC | ACTIVE | LTK-H04BAT01CE150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE150-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 4 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1000A/5A - AVR OF OLTC | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE160-ME-U | LTK0 | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | ACTIVE | LTK-H04BAT01CE160 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE160-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 5 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE170-ME-U | LTK0 | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | ACTIVE | LTK-H04BAT01CE170 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE170-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 6 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | 34 | 2024-11-11 | 16:00:00
PO-01550-H04BAT01CE180-ME-U | LTK0 | CT: 16.5kV, 26000A/5A - WINDING TEMP. TRANSMITTER | ACTIVE | LTK-H04BAT01CE180 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01550-H04BAT01CE180-ME-U |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-34-H04BAT-ME-U | 0 | 7 | 0 | H04BAT | No_kks_found | U | ME | H04BAT01 | CE | GENERATOR TRANSFORMERS | CT: 16.5kV, 26000A/5A - WINDING TEMP. TRANSMITTER | 34 | 2024-11-11 | 16:00:00
Group-35-H04BAT-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 35 | 1 | H04BAT | No_kks_found | U | ME |  |  |  |  | 35 | 2024-11-10 | 16:00:00
PO-02130-H04BAT01GH003-ME-U | LTK0 | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | ACTIVE | LTK-H04BAT01GH003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02130-H04BAT01GH003-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 1 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GH | GENERATOR TRANSFORMERS | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 35 | 2024-11-08 | 16:00:00
PO-02140-H04BAT01GH003-ME-U | LTK0 | KW3B TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | ACTIVE | LTK-H04BAT01GH003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02140-H04BAT01GH003-ME-U |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 2 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | GH | GENERATOR TRANSFORMERS | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 35 | 2024-11-08 | 16:00:00
PO-02550-H04BAT01CT001XQ01-ME-U | LTK0 | A PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT001XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT001XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 3 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | A PHASE OIL TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT002XQ01-ME-U | LTK0 | B PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT002XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT002XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 4 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE OIL TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT003XQ01-ME-U | LTK0 | C PHASE OIL TEMPERATURE | ACTIVE | LTK-H04BAT01CT003XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT003XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 5 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | C PHASE OIL TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT004XQ01-ME-U | LTK0 | B PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT004XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT004XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 6 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE WINDING TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT005XQ01-ME-U | LTK0 | A PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT005XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT005XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 7 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | A PHASE WINDING TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT006XQ01-ME-U | LTK0 | b PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT006XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT006XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 8 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | B PHASE WINDING TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02550-H04BAT01CT007XQ01-ME-U | LTK0 | C PHASE WINDING TEMPERATURE | ACTIVE | LTK-H04BAT01CT007XQ01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02550-H04BAT01CT007XQ01-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-35-H04BAT-ME-U | 0 | 9 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | CT | GENERATOR TRANSFORMERS | C PHASE WINDING TEMPERATURE | 35 | 2024-11-10 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-36-H04BAB-ME-U | LTK0 | NEUTRAL STAR POINT BUS,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 36 | 0 | H04BAB | NEUTRAL STAR POINT BUS | U | ME |  |  |  |  | 36 | 2024-11-05 | 16:00:00
PO-01390-H04BAB10CE110-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAB10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAB10CE110-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-36-H04BAB-ME-U | 0 | 1 | 0 | H04BAB | NEUTRAL STAR POINT BUS | U | ME | H04BAB10 | CE | No_kks_found | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 36 | 2024-11-05 | 16:00:00
PO-01390-H04BAB10CE120-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAB10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAB10CE120-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-36-H04BAB-ME-U | 0 | 2 | 0 | H04BAB | NEUTRAL STAR POINT BUS | U | ME | H04BAB10 | CE | No_kks_found | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 36 | 2024-11-05 | 16:00:00
Group-37-H04BAB-ME-U | LTK0 | NEUTRAL STAR POINT BUS,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 37 | 1 | H04BAB | NEUTRAL STAR POINT BUS | U | ME |  |  |  |  | 37 | 2024-11-05 | 16:00:00
PO-01400-H04BAB10CE110-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAB10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAB10CE110-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H04BAB-ME-U | 0 | 1 | 1 | H04BAB | NEUTRAL STAR POINT BUS | U | ME | H04BAB10 | CE | No_kks_found | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 37 | 2024-11-05 | 16:00:00
PO-01400-H04BAB10CE120-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAB10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAB10CE120-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-37-H04BAB-ME-U | 0 | 2 | 1 | H04BAB | NEUTRAL STAR POINT BUS | U | ME | H04BAB10 | CE | No_kks_found | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 37 | 2024-11-05 | 16:00:00
Group-38-H04BAA-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 38 | 0 | H04BAA | No_kks_found | U | ME |  |  |  |  | 38 | 2024-11-10 | 16:00:00
PO-01390-H04BAA10CE130-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE130-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 1 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE140-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE140-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 2 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE151-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | ACTIVE | LTK-H04BAA10CE151 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE151-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 3 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE152-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | ACTIVE | LTK-H04BAA10CE152 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE152-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 4 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE161-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE161 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE161-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 5 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE162-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE162 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE162-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 6 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 38 | 2024-11-05 | 16:00:00
PO-01390-H04BAA10CE163-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE163 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01390-H04BAA10CE163-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 7 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 38 | 2024-11-05 | 16:00:00
PO-01410-H04BAA10GS600-ME-U | LTK0 | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | ACTIVE | LTK-H04BAA10GS600 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01410-H04BAA10GS600-ME-U |  | 2024-11-09 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 8 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 38 | 2024-11-09 | 16:00:00
PO-01420-H04BAA10GS270-ME-U | LTK0 | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | ACTIVE | LTK-H04BAA10GS270 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01420-H04BAA10GS270-ME-U |  | 2024-11-10 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 9 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | SFC DISCONNECTING SWITCH - 89SB4 | 38 | 2024-11-10 | 16:00:00
PO-01490-H04BAA10GS200-ME-U | LTK0 | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | ACTIVE | LTK-H04BAA10GS200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01490-H04BAA10GS200-ME-U |  | 2024-11-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 10 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 38 | 2024-11-08 | 16:00:00
PO-01500-H04BAA10GS630-ME-U | LTK0 | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | ACTIVE | LTK-H04BAA10GS630 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01500-H04BAA10GS630-ME-U |  | 2024-11-08 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 11 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 38 | 2024-11-08 | 16:00:00
PO-01910-H04BAA10GS290-ME-U | LTK0 | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | ACTIVE | LTK-H04BAA10GS290 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01910-H04BAA10GS290-ME-U |  | 2024-11-06 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-38-H04BAA-ME-U | 0 | 12 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 38 | 2024-11-06 | 16:00:00
Group-39-H04BAA-ME-U | LTK0 | No_kks_found,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 39 | 1 | H04BAA | No_kks_found | U | ME |  |  |  |  | 39 | 2024-11-10 | 16:00:00
PO-01400-H04BAA10CE130-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE130-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 1 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE140-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE140-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 2 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE151-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | ACTIVE | LTK-H04BAA10CE151 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE151-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 3 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE152-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | ACTIVE | LTK-H04BAA10CE152 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE152-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 4 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE161-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE161 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE161-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 5 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE162-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE162 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE162-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 6 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 39 | 2024-11-05 | 16:00:00
PO-01400-H04BAA10CE163-ME-U | LTK0 | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE163 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01400-H04BAA10CE163-ME-U |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 7 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 39 | 2024-11-05 | 16:00:00
PO-01430-H04BAACE210-ME-U | LTK0 | PT: 16.5/√3kV:115/√3,1.2, 200VA - SYNC & METERING | ACTIVE | LTK-H04BAACE210 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01430-H04BAACE210-ME-U |  | 2024-11-10 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 8 | 1 | H04BAA | No_kks_found | U | ME | H04BAACE | 21 | No_kks_found | No_kks_found | 39 | 2024-11-10 | 16:00:00
PO-01430-H04BAACE220-ME-U | LTK0 | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION & G/M PROTECTION RELAY | ACTIVE | LTK-H04BAACE220 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01430-H04BAACE220-ME-U |  | 2024-11-10 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 9 | 1 | H04BAA | No_kks_found | U | ME | H04BAACE | 22 | No_kks_found | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION & G/M PROTECTION RELAY | 39 | 2024-11-10 | 16:00:00
PO-01430-H04BAACE230-ME-U | LTK0 | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION, GOVERNOR & G/M PROTECTION RELAY | ACTIVE | LTK-H04BAACE230 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01430-H04BAACE230-ME-U |  | 2024-11-10 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 10 | 1 | H04BAA | No_kks_found | U | ME | H04BAACE | 23 | No_kks_found | No_kks_found | 39 | 2024-11-10 | 16:00:00
PO-01470-H04BAA10GV100-ME-U | LTK0 | GENERATOR CIRCUIT BREAKER SURGE CAPACITOR | ACTIVE | LTK-H04BAA10GV100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01470-H04BAA10GV100-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 11 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | GV | GENERATOR LEADS | No_kks_found | 39 | 2024-11-08 | 16:00:00
PO-01480-H04BAA10CE120-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01480-H04BAA10CE120-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 12 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 39 | 2024-11-08 | 16:00:00
PO-01480-H04BAA10CE130-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01480-H04BAA10CE130-ME-U |  | 2024-11-08 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-39-H04BAA-ME-U | 0 | 13 | 1 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 39 | 2024-11-08 | 16:00:00
Group-40-H04BAA-ME-U | LTK0 | No_kks_found,MSP0-E840,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 40 | 0 | H04BAA | No_kks_found | U | ME |  |  |  |  | 40 | 2024-11-08 | 16:00:00
PO-01440-H04BAA10GS100-ME-U | LTK0 | GENERATOR CIRCUIT BREAKER (52G) | ACTIVE | LTK-H04BAA10GS100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01440-H04BAA10GS100-ME-U |  | 2024-11-05 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 1 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | GENERATOR CIRCUIT BREAKER (52G) | 40 | 2024-11-08 | 16:00:00
PO-01450-H04BAA10GS610-ME-U | LTK0 | GCB EARTH SWITCH (MKGG) | ACTIVE | LTK-H04BAA10GS610 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01450-H04BAA10GS610-ME-U |  | 2024-11-08 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 2 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | GCB EARTH SWITCH (MKGG) | 40 | 2024-11-08 | 16:00:00
PO-01450-H04BAA10GS620-ME-U | LTK0 | GCB EARTH SWITCH (MKGT) | ACTIVE | LTK-H04BAA10GS620 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01450-H04BAA10GS620-ME-U |  | 2024-11-08 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 3 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GS | GENERATOR LEADS | GCB EARTH SWITCH (MKGT) | 40 | 2024-11-08 | 16:00:00
PO-01460-H04BAA10CE120-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01460-H04BAA10CE120-ME-U |  | 2024-11-08 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 4 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 12000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 40 | 2024-11-08 | 16:00:00
PO-01460-H04BAA10CE130-ME-U | LTK0 | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | ACTIVE | LTK-H04BAA10CE130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01460-H04BAA10CE130-ME-U |  | 2024-11-08 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 5 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | CE | GENERATOR LEADS | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 40 | 2024-11-08 | 16:00:00
PO-01460-H04BAA10GV100-ME-U | LTK0 | GENERATOR CIRCUIT BREAKER SURGE CAPACITOR | ACTIVE | LTK-H04BAA10GV100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01460-H04BAA10GV100-ME-U |  | 2024-11-08 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-40-H04BAA-ME-U | 0 | 6 | 0 | H04BAA | No_kks_found | U | ME | H04BAA10 | GV | GENERATOR LEADS | No_kks_found | 40 | 2024-11-08 | 16:00:00
Group-41-H03MFP-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 41 | 1 | H03MFP | No_kks_found | U | ME |  |  |  |  | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14GH002-ME-U | LTK0 | G/M FIRE EXTINGUISHER - CONTROL PANEL | ACTIVE | LTK-H03MFP14GH002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14GH002-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 1 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | GH | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - CONTROL PANEL | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD001-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | ACTIVE | LTK-H03MFP14HD001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD001-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 2 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD002-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | ACTIVE | LTK-H03MFP14HD002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD002-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 3 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD003-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | ACTIVE | LTK-H03MFP14HD003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD003-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 4 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD004-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | ACTIVE | LTK-H03MFP14HD004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD004-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 5 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD005-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | ACTIVE | LTK-H03MFP14HD005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD005-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 6 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14HD006-ME-U | LTK0 | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | ACTIVE | LTK-H03MFP14HD006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14HD006-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 7 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | HD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD001-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.1 | ACTIVE | LTK-H03MFP14SD001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD001-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 8 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.1 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD002-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.2 | ACTIVE | LTK-H03MFP14SD002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD002-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 9 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.2 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD003-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.3 | ACTIVE | LTK-H03MFP14SD003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD003-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 10 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.3 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD004-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.4 | ACTIVE | LTK-H03MFP14SD004 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD004-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 11 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.4 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD005-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.5 | ACTIVE | LTK-H03MFP14SD005 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD005-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 12 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.5 | 41 | 2024-11-07 | 16:00:00
PO-02110-H03MFP14SD006-ME-U | LTK0 | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.6 | ACTIVE | LTK-H03MFP14SD006 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02110-H03MFP14SD006-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-41-H03MFP-ME-U | 0 | 13 | 1 | H03MFP | No_kks_found | U | ME | H03MFP14 | SD | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.6 | 41 | 2024-11-07 | 16:00:00
Group-42-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,MSP0-H010,PTW งานทั่วไป//PTW งานในที่อับอากาศ | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป//PTW งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 42 | 0 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 42 | 2024-11-14 | 16:00:00
PO-00370-H04MFA10HA001-ME-U | LTK0 | SPIRAL CASE | ACTIVE | LTK-H04MFA10HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00370-H04MFA10HA001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป//PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-42-H04MFA-ME-U | 0 | 1 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA10 | HA | SPIRAL CASE | SPIRAL CASE | 42 | 2024-11-14 | 16:00:00
PO-00500-H04MFA60HA001-ME-U | LTK0 | DRAFT TUBE | ACTIVE | LTK-H04MFA60HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00500-H04MFA60HA001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป//PTW งานในที่อับอากาศ | 1 | 7 | 08:00:00 | Group-42-H04MFA-ME-U | 0 | 2 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | HA | DRAFT TUBE SYSTEM | DRAFT TUBE | 42 | 2024-11-14 | 16:00:00
Group-43-H04QFB-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | LTK0-1D4 | หปฟนม-ธ._หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 43 | 1 | H04QFB | No_kks_found | U | ME |  |  |  |  | 43 | 2024-11-11 | 16:00:00
PO-01260-H04QFB30CP310-ME-U | LTK0 | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04QFB30CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01260-H04QFB30CP310-ME-U |  | 2024-11-11 | LTK0-1D4 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 1 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 43 | 2024-11-11 | 16:00:00
PO-01260-H04QFB30CP320-ME-U | LTK0 | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04QFB30CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01260-H04QFB30CP320-ME-U |  | 2024-11-11 | LTK0-1D4 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 2 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 43 | 2024-11-11 | 16:00:00
PO-01270-H04QFB30CP330-ME-U | LTK0 | AUX AIR TANK PRESSURE GAUGE - CP330 | ACTIVE | LTK-H04QFB30CP330 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01270-H04QFB30CP330-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 3 | 1 | H04QFB | No_kks_found | U | ME | H04QFB30 | CP | AIR Pressure System 1 | AUX AIR TANK PRESSURE GAUGE - CP330 | 43 | 2024-11-11 | 16:00:00
PO-01280-H04QFB31CP301-ME-U | LTK0 | BRAKE AIR TANK PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04QFB31CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01280-H04QFB31CP301-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 4 | 1 | H04QFB | No_kks_found | U | ME | H04QFB31 | CP | AIR Pressure System 2 | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 43 | 2024-11-11 | 16:00:00
PO-01290-H04QFB32CP301-ME-U | LTK0 | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04QFB32CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01290-H04QFB32CP301-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 5 | 1 | H04QFB | No_kks_found | U | ME | H04QFB32 | CP | AIR Pressure System 3 | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 43 | 2024-11-11 | 16:00:00
PO-01300-H04QFB33CP301-ME-U | LTK0 | SERVICE AIR TANK PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04QFB33CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01300-H04QFB33CP301-ME-U |  | 2024-11-11 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-43-H04QFB-ME-U | 0 | 6 | 1 | H04QFB | No_kks_found | U | ME | H04QFB33 | CP | AIR Pressure System 4 | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 43 | 2024-11-11 | 16:00:00
Group-44-H04PCM-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 44 | 0 | H04PCM | No_kks_found | U | ME |  |  |  |  | 44 | 2024-11-10 | 16:00:00
PO-00070-H04PCM20CF100-ME-U | LTK0 | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04PCM20CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04PCM20CF100-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 1 | 0 | H04PCM | No_kks_found | U | ME | H04PCM20 | CF | UGB Lub. Oil Instrument | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 44 | 2024-11-05 | 16:00:00
PO-00070-H04PCM20CP310-ME-U | LTK0 | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04PCM20CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04PCM20CP310-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 2 | 0 | H04PCM | No_kks_found | U | ME | H04PCM20 | CP | UGB Lub. Oil Instrument | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 44 | 2024-11-05 | 16:00:00
PO-00070-H04PCM20CP320-ME-U | LTK0 | UGB WATER RETURN PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04PCM20CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04PCM20CP320-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 3 | 0 | H04PCM | No_kks_found | U | ME | H04PCM20 | CP | UGB Lub. Oil Instrument | UGB WATER RETURN PRESSURE GAUGE - CP320 | 44 | 2024-11-05 | 16:00:00
PO-00090-H04PCM30CF100-ME-U | LTK0 | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04PCM30CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00090-H04PCM30CF100-ME-U |  | 2024-11-09 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 4 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CF | COOLING WATER SUPPLY FOR GEN AIR COOLER | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 44 | 2024-11-09 | 16:00:00
PO-00090-H04PCM30CP300-ME-U | LTK0 | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | ACTIVE | LTK-H04PCM30CP300 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00090-H04PCM30CP300-ME-U |  | 2024-11-09 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 5 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CP | COOLING WATER SUPPLY FOR GEN AIR COOLER | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 44 | 2024-11-09 | 16:00:00
PO-00090-H04PCM30CP301-ME-U | LTK0 | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04PCM30CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00090-H04PCM30CP301-ME-U |  | 2024-11-09 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 6 | 0 | H04PCM | No_kks_found | U | ME | H04PCM30 | CP | COOLING WATER SUPPLY FOR GEN AIR COOLER | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 44 | 2024-11-09 | 16:00:00
PO-00130-H04PCM10CF100-ME-U | LTK0 | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04PCM10CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04PCM10CF100-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 7 | 0 | H04PCM | No_kks_found | U | ME | H04PCM10 | CF | COOLING WATER SUPPLY FOR CGB SYSTEM | Flow detector with contacts for CGB C. WTR FLOW | 44 | 2024-11-10 | 16:00:00
PO-00130-H04PCM10CP310-ME-U | LTK0 | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04PCM10CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04PCM10CP310-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 8 | 0 | H04PCM | No_kks_found | U | ME | H04PCM10 | CP | COOLING WATER SUPPLY FOR CGB SYSTEM | "Pressure gauge,Type 233.50,0~2.5MPa, G1 | 44 | 2024-11-10 | 16:00:00
PO-00130-H04PCM10CP320-ME-U | LTK0 | CGB WATER RETURN PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04PCM10CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04PCM10CP320-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-44-H04PCM-ME-U | 0 | 9 | 0 | H04PCM | No_kks_found | U | ME | H04PCM10 | CP | COOLING WATER SUPPLY FOR CGB SYSTEM | "Pressure gauge,Type 233.50,0~2.5MPa, G1 | 44 | 2024-11-10 | 16:00:00
Group-45-H04PCB-ME-U | LTK0 | COOLING WATER SUPPLY,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 45 | 1 | H04PCB | COOLING WATER SUPPLY | U | ME |  |  |  |  | 45 | 2024-11-13 | 16:00:00
PO-00450-H04PCB20CF100-ME-U | LTK0 | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | ACTIVE | LTK-H04PCB20CF100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04PCB20CF100-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-45-H04PCB-ME-U | 0 | 1 | 1 | H04PCB | COOLING WATER SUPPLY | U | ME | H04PCB20 | CF | COOLING WATER SUPPLY FOR TURBINE BEARING SYSTEM | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 45 | 2024-11-13 | 16:00:00
PO-00450-H04PCB20CP310-ME-U | LTK0 | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04PCB20CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04PCB20CP310-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-45-H04PCB-ME-U | 0 | 2 | 1 | H04PCB | COOLING WATER SUPPLY | U | ME | H04PCB20 | CP | COOLING WATER SUPPLY FOR TURBINE BEARING SYSTEM | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 45 | 2024-11-13 | 16:00:00
PO-00450-H04PCB20CP320-ME-U | LTK0 | TGB WATER RETURN PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04PCB20CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04PCB20CP320-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-45-H04PCB-ME-U | 0 | 3 | 1 | H04PCB | COOLING WATER SUPPLY | U | ME | H04PCB20 | CP | COOLING WATER SUPPLY FOR TURBINE BEARING SYSTEM | TGB WATER RETURN PRESSURE GAUGE - CP320 | 45 | 2024-11-13 | 16:00:00
Group-46-H04PAC-ME-U | LTK0 | No_kks_found,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 46 | 0 | H04PAC | No_kks_found | U | ME |  |  |  |  | 46 | 2024-11-05 | 16:00:00
PO-00900-H04PAC10AP110-ME-U | LTK0 | MAIN COOLING WATER PUMP | ACTIVE | LTK-H04PAC10AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00900-H04PAC10AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-46-H04PAC-ME-U | 0 | 1 | 0 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MAIN COOLING WATER PUMP 4PAC10AP110 | 46 | 2024-11-05 | 16:00:00
PO-01020-H04PAC10AP120-ME-U | LTK0 | MAIN TRANS. COOLING WATER PUMP NO.1 | ACTIVE | LTK-H04PAC10AP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01020-H04PAC10AP120-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-46-H04PAC-ME-U | 0 | 2 | 0 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | WATER PUMP FOR MAIN TRANSFORMER 4PAC10AP120 | 46 | 2024-11-05 | 16:00:00
PO-01030-H04PAC10AP130-ME-U | LTK0 | MAIN TRANS. COOLING WATER PUMP NO.2 | ACTIVE | LTK-H04PAC10AP130 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01030-H04PAC10AP130-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-46-H04PAC-ME-U | 0 | 3 | 0 | H04PAC | No_kks_found | U | ME | H04PAC10 | AP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | WATER PUMP FOR MAIN TRANSFORMER 4PAC10AP130 | 46 | 2024-11-05 | 16:00:00
Group-47-H04PAC-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 47 | 1 | H04PAC | No_kks_found | U | ME |  |  |  |  | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP311-ME-U | LTK0 | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | ACTIVE | LTK-H04PAC10CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP311-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 1 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP315-ME-U | LTK0 | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | ACTIVE | LTK-H04PAC10CP315 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP315-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 2 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP321-ME-U | LTK0 | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | ACTIVE | LTK-H04PAC10CP321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP321-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 3 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP325-ME-U | LTK0 | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | ACTIVE | LTK-H04PAC10CP325 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP325-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 4 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP331-ME-U | LTK0 | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | ACTIVE | LTK-H04PAC10CP331 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP331-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 5 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 47 | 2024-11-05 | 16:00:00
PO-01010-H04PAC10CP335-ME-U | LTK0 | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | ACTIVE | LTK-H04PAC10CP335 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAC10CP335-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-47-H04PAC-ME-U | 0 | 6 | 1 | H04PAC | No_kks_found | U | ME | H04PAC10 | CP | MAIN COOLING WATER SYSTEM FOR UNIT 4 (PUMP) | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 47 | 2024-11-05 | 16:00:00
Group-48-H04PAB-ME-U | LTK0 | No_kks_found,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 48 | 0 | H04PAB | No_kks_found | U | ME |  |  |  |  | 48 | 2024-11-10 | 16:00:00
PO-01040-H04PAB10AT110-ME-U | LTK0 | MAIN COOLING WATER AUTOMATIC STRAINER | ACTIVE | LTK-H04PAB10AT110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01040-H04PAB10AT110-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H04PAB-ME-U | 0 | 1 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN AUTOMATIC STRAINER 4PAB10AT110 | 48 | 2024-11-07 | 16:00:00
PO-01180-H04PAB10AT301-ME-U | LTK0 | MTR OIL COOLER Y-STRAINER NO.1 | ACTIVE | LTK-H04PAB10AT301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01180-H04PAB10AT301-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H04PAB-ME-U | 0 | 2 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | No_kks_found | 48 | 2024-11-10 | 16:00:00
PO-01190-H04PAB10AT311-ME-U | LTK0 | MTR OIL COOLER Y-STRAINER NO.2 | ACTIVE | LTK-H04PAB10AT311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01190-H04PAB10AT311-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H04PAB-ME-U | 0 | 3 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | Y-STRAINER NO.1 | 48 | 2024-11-10 | 16:00:00
PO-01200-H04PAB10AT321-ME-U | LTK0 | MTR OIL COOLER Y-STRAINER NO.3 | ACTIVE | LTK-H04PAB10AT321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01200-H04PAB10AT321-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H04PAB-ME-U | 0 | 4 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | Y-STRAINER NO.2 | 48 | 2024-11-10 | 16:00:00
PO-02520-H04PAB10AA014-ME-U | LTK0 | SHUT OFF VALVE 4PAB10AA014 | ACTIVE | LTK-H04PAB10AA014 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02520-H04PAB10AA014-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-48-H04PAB-ME-U | 0 | 5 | 0 | H04PAB | No_kks_found | U | ME | H04PAB10 | AA | COOLING WATER PIPING AND CULVERT SYSTEM | SHUT OFF VALVE 4PAB10AA014 | 48 | 2024-11-08 | 16:00:00
Group-49-H04PAB-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 49 | 1 | H04PAB | No_kks_found | U | ME |  |  |  |  | 49 | 2024-11-05 | 16:00:00
PO-01010-H04PAB10CP320-ME-U | LTK0 | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04PAB10CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAB10CP320-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-49-H04PAB-ME-U | 0 | 1 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 49 | 2024-11-05 | 16:00:00
PO-01010-H04PAB10CP325-ME-U | LTK0 | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | ACTIVE | LTK-H04PAB10CP325 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01010-H04PAB10CP325-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-49-H04PAB-ME-U | 0 | 2 | 1 | H04PAB | No_kks_found | U | ME | H04PAB10 | CP | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 49 | 2024-11-05 | 16:00:00
Group-50-H04MLV-ME-U | LTK0 | BEARINGS SUPPLY SYSTEM,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 50 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME |  |  |  |  | 50 | 2024-11-11 | 16:00:00
PO-00220-H04MLV20AP110-ME-U | LTK0 | UPPER GUIDE BEARING OIL PUMP NO.1 | ACTIVE | LTK-H04MLV20AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00220-H04MLV20AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 1 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AP | UGB SUPPLY SYSTEM | UPPER GUIDE BEARING OIL PUMP NO.1 4MLV20AP110 | 50 | 2024-11-05 | 16:00:00
PO-00230-H04MLV20AP120-ME-U | LTK0 | UPPER GUIDE BEARING OIL PUMP NO.2 | ACTIVE | LTK-H04MLV20AP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00230-H04MLV20AP120-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 2 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AP | UGB SUPPLY SYSTEM | UPPER GUIDE BEARING OIL PUMP NO.2 4MLV20AP120 | 50 | 2024-11-05 | 16:00:00
PO-00270-H04MLV10AP110-ME-U | LTK0 | COMBINE GUIDE BEARING OIL PUMP NO.1 | ACTIVE | LTK-H04MLV10AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00270-H04MLV10AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 3 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AP | CGB SUPPLY SYSTEM | CGB OIL PUMP NO.1 - 3MLV10AP110 | 50 | 2024-11-05 | 16:00:00
PO-00280-H04MLV10AP120-ME-U | LTK0 | COMBINE GUIDE BEARING OIL PUMP NO.2 | ACTIVE | LTK-H04MLV10AP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00280-H04MLV10AP120-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 4 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AP | CGB SUPPLY SYSTEM | CGB OIL PUMP NO.2 - 3MLV10AP120 | 50 | 2024-11-05 | 16:00:00
PO-00310-H04MLV40AP110-ME-U | LTK0 | HIGH PRESSURE OIL LIFTING PUMP NO.1 | ACTIVE | LTK-H04MLV40AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00310-H04MLV40AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 5 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | AP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HIGH PRESSURE OIL PUMP NO.1 4MLV40AP110 | 50 | 2024-11-05 | 16:00:00
PO-00320-H04MLV40AP120-ME-U | LTK0 | HIGH PRESSURE OIL LIFTING PUMP NO.2 | ACTIVE | LTK-H04MLV40AP120 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00320-H04MLV40AP120-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 6 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | AP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HIGH PRESSURE OIL LIFTING PUMP NO.2 3MLV40AP120 | 50 | 2024-11-05 | 16:00:00
PO-00360-H04MLV70AP010-ME-U | LTK0 | COMBINE GUIDE BEARING OIL MIST SEPERATOR | ACTIVE | LTK-H04MLV70AP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00360-H04MLV70AP010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 7 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV70 | AP | CGB OIL MIST EXHAUST | Electric motor for CGB OIL MIST EXHAUST | 50 | 2024-11-11 | 16:00:00
PO-02230-H04MLV40BR001-ME-U | LTK0 | HIGH PRESSURE OIL PIPE | ACTIVE | LTK-H04MLV40BR001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02230-H04MLV40BR001-ME-U |  | 2024-11-09 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-50-H04MLV-ME-U | 0 | 8 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | BR | HIGH PRESSURE PUMP SUPPLY SYSTEM | HIGH PRESSURE OIL PIPE | 50 | 2024-11-11 | 16:00:00
Group-51-H04MLV-ME-U | LTK0 | BEARINGS SUPPLY SYSTEM,LTK0-1M2,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 51 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME |  |  |  |  | 51 | 2024-11-12 | 16:00:00
PO-00240-H04MLV20AC310-ME-U | LTK0 | UGB OIL COOLER NO.1 | ACTIVE | LTK-H04MLV20AC310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00240-H04MLV20AC310-ME-U |  | 2024-11-06 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-51-H04MLV-ME-U | 0 | 1 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AC | UGB SUPPLY SYSTEM | UGB OIL COOLER NO.1 | 51 | 2024-11-07 | 16:00:00
PO-00250-H04MLV20AC320-ME-U | LTK0 | UGB OIL COOLER NO.2 | ACTIVE | LTK-H04MLV20AC320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00250-H04MLV20AC320-ME-U |  | 2024-11-08 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-51-H04MLV-ME-U | 0 | 2 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | AC | UGB SUPPLY SYSTEM | UGB OIL COOLER NO.2 | 51 | 2024-11-09 | 16:00:00
PO-00290-H04MLV10AC310-ME-U | LTK0 | COMBINE GUIDE BEARING OIL COOLER NO.1 | ACTIVE | LTK-H04MLV10AC310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00290-H04MLV10AC310-ME-U |  | 2024-11-09 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-51-H04MLV-ME-U | 0 | 3 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AC | CGB SUPPLY SYSTEM | CGB OIL COOLER NO.1 4MLV10AC310 | 51 | 2024-11-09 | 16:00:00
PO-00300-H04MLV10AC320-ME-U | LTK0 | COMBINE GUIDE BEARING OIL COOLER NO.2 | ACTIVE | LTK-H04MLV10AC320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00300-H04MLV10AC320-ME-U |  | 2024-11-09 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-51-H04MLV-ME-U | 0 | 4 | 1 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | AC | CGB SUPPLY SYSTEM | CGB OIL COOLER NO.2 4MLV10AC320 | 51 | 2024-11-12 | 16:00:00
Group-52-H04MLV-ME-U | LTK0 | BEARINGS SUPPLY SYSTEM,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 52 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME |  |  |  |  | 52 | 2024-11-10 | 16:00:00
PO-00070-H04MLV20CP301-ME-U | LTK0 | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MLV20CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04MLV20CP301-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 1 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 52 | 2024-11-05 | 16:00:00
PO-00070-H04MLV20CP302-ME-U | LTK0 | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | ACTIVE | LTK-H04MLV20CP302 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04MLV20CP302-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 2 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 52 | 2024-11-05 | 16:00:00
PO-00070-H04MLV20CP310-ME-U | LTK0 | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MLV20CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04MLV20CP310-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 3 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 52 | 2024-11-05 | 16:00:00
PO-00070-H04MLV20CP320-ME-U | LTK0 | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04MLV20CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00070-H04MLV20CP320-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 4 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV20 | CP | UGB SUPPLY SYSTEM | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 52 | 2024-11-05 | 16:00:00
PO-00130-H04MLV10CP301-ME-U | LTK0 | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MLV10CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04MLV10CP301-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 5 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 52 | 2024-11-10 | 16:00:00
PO-00130-H04MLV10CP302-ME-U | LTK0 | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | ACTIVE | LTK-H04MLV10CP302 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04MLV10CP302-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 6 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 52 | 2024-11-10 | 16:00:00
PO-00130-H04MLV10CP310-ME-U | LTK0 | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MLV10CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04MLV10CP310-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 7 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 52 | 2024-11-10 | 16:00:00
PO-00130-H04MLV10CP320-ME-U | LTK0 | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04MLV10CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00130-H04MLV10CP320-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 8 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV10 | CP | CGB SUPPLY SYSTEM | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 52 | 2024-11-10 | 16:00:00
PO-00160-H04MLV40CP301-ME-U | LTK0 | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MLV40CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00160-H04MLV40CP301-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 9 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 52 | 2024-11-10 | 16:00:00
PO-00160-H04MLV40CP310-ME-U | LTK0 | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MLV40CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00160-H04MLV40CP310-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 10 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 52 | 2024-11-10 | 16:00:00
PO-00160-H04MLV40CP311-ME-U | LTK0 | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | ACTIVE | LTK-H04MLV40CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00160-H04MLV40CP311-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-52-H04MLV-ME-U | 0 | 11 | 0 | H04MLV | BEARINGS SUPPLY SYSTEM | U | ME | H04MLV40 | CP | HIGH PRESSURE PUMP SUPPLY SYSTEM | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 52 | 2024-11-10 | 16:00:00
Group-53-H04MLD-ME-U | LTK0 | CGB. BEARINGS,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 53 | 1 | H04MLD | CGB. BEARINGS | U | ME |  |  |  |  | 53 | 2024-11-13 | 16:00:00
PO-00030-H04MLD20HA001-ME-U | LTK0 | UPPER BRACKET | ACTIVE | LTK-H04MLD20HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00030-H04MLD20HA001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-53-H04MLD-ME-U | 0 | 1 | 1 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | HA | Upper Guide Bearing(UGB) | UPPER BRACKET | 53 | 2024-11-13 | 16:00:00
PO-00110-H04MLD10HA001-ME-U | LTK0 | LOWER BRACKET | ACTIVE | LTK-H04MLD10HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00110-H04MLD10HA001-ME-U |  | 2024-11-12 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-53-H04MLD-ME-U | 0 | 2 | 1 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | HA | Combined Guide Bearing(CGB) | LOWER BRACKET | 53 | 2024-11-12 | 16:00:00
PO-00210-H04MLD20BB001-ME-U | LTK0 | UPPER GUIDE BEARING OIL PAN | ACTIVE | LTK-H04MLD20BB001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00210-H04MLD20BB001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-53-H04MLD-ME-U | 0 | 3 | 1 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 | BB | Upper Guide Bearing(UGB) | UPPER GUIDE BEARING OIL PAN | 53 | 2024-11-07 | 16:00:00
PO-00260-H04MLD10BB001-ME-U | LTK0 | COMBINE GUIDE BEARING OIL PAN | ACTIVE | LTK-H04MLD10BB001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00260-H04MLD10BB001-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-53-H04MLD-ME-U | 0 | 4 | 1 | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | BB | Combined Guide Bearing(CGB) | CGB OIL PAN | 53 | 2024-11-12 | 16:00:00
PO-02480-H04MLD20-ME-U | LTK0 | UPPER GUIDE BEARING (ROUTE) | ACTIVE | LTK-H04MLD20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02480-H04MLD20-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-53-H04MLD-ME-U | 0 | 5 | 1 | H04MLD | CGB. BEARINGS | U | ME | H04MLD20 |  | Upper Guide Bearing(UGB) | Upper Guide Bearing(UGB) | 53 | 2024-11-05 | 16:00:00
Group-54-H04MLA-ME-U | LTK0 | STATOR,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 54 | 0 | H04MLA | STATOR | U | ME |  |  |  |  | 54 | 2024-11-13 | 16:00:00
PO-00330-H04MLA50-ME-U | LTK0 | MECHANICAL BRAKE (ROUTE) | ACTIVE | LTK-H04MLA50 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00330-H04MLA50-ME-U |  | 2024-11-12 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-54-H04MLA-ME-U | 0 | 1 | 0 | H04MLA | STATOR | U | ME | H04MLA50 |  | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKE SYSTEM | 54 | 2024-11-12 | 16:00:00
PO-00350-H04MLA60AP110-ME-U | LTK0 | UPPER GUIDE BEARING OIL MIST SEPERATOR | ACTIVE | LTK-H04MLA60AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00350-H04MLA60AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-54-H04MLA-ME-U | 0 | 2 | 0 | H04MLA | STATOR | U | ME | H04MLA60 | AP | UGB Oil Mist Exhaust | UGB Oil mist exhaust | 54 | 2024-11-11 | 16:00:00
PO-02210-H04MLA30HB002-ME-U | LTK0 | GEN UPPER SHAFT | ACTIVE | LTK-H04MLA30HB002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02210-H04MLA30HB002-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-54-H04MLA-ME-U | 0 | 3 | 0 | H04MLA | STATOR | U | ME | H04MLA30 | HB | ROTOR | GEN UPPER SHAFT | 54 | 2024-11-13 | 16:00:00
PO-02220-H04MLA30HB003-ME-U | LTK0 | Gen LOWER SHAFT | ACTIVE | LTK-H04MLA30HB003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02220-H04MLA30HB003-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-54-H04MLA-ME-U | 0 | 4 | 0 | H04MLA | STATOR | U | ME | H04MLA30 | HB | ROTOR | GEN LOWER SHAFT | 54 | 2024-11-13 | 16:00:00
Group-55-H04MLA-ME-U | LTK0 | STATOR,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 55 | 1 | H04MLA | STATOR | U | ME |  |  |  |  | 55 | 2024-11-10 | 16:00:00
PO-00180-H04MLA50CP301-ME-U | LTK0 | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MLA50CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00180-H04MLA50CP301-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-55-H04MLA-ME-U | 0 | 1 | 1 | H04MLA | STATOR | U | ME | H04MLA50 | CP | MECHANICAL BRAKE SYSTEM | MECHANICAL BRAKING AIR INLET PRESSURE GAUGE - CP301 | 55 | 2024-11-10 | 16:00:00
PO-00180-H04MLA50CP302-ME-U | LTK0 | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | ACTIVE | LTK-H04MLA50CP302 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00180-H04MLA50CP302-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-55-H04MLA-ME-U | 0 | 2 | 1 | H04MLA | STATOR | U | ME | H04MLA50 | CP | MECHANICAL BRAKE SYSTEM | MECHANIC AIR OUTLET PRESSURE GAUGE - CP302 | 55 | 2024-11-10 | 16:00:00
Group-56-H04MFX-ME-U | LTK0 | FLUID SUPPLY SYSTEM,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 56 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME |  |  |  |  | 56 | 2024-11-12 | 16:00:00
PO-00650-H04MFX60-ME-U | LTK0 | FLUID SUPPLY SYSTEM FOR MIV | ACTIVE | LTK-H04MFX60 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00650-H04MFX60-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 1 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 |  | FLUID SUPPLY SYSTEM for MIV | FLUID SUPPLY SYSTEM for MIV | 56 | 2024-11-08 | 16:00:00
PO-00720-H04MFX60AP110-ME-U | LTK0 | MAIN INLET VALVE OIL PUMP 1 | ACTIVE | LTK-H04MFX60AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00720-H04MFX60AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 2 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | AP | FLUID SUPPLY SYSTEM for MIV | Screw pump / L3 MF 70/112 IFOKSO- G for MIV HPU oil pump No.1 | 56 | 2024-11-06 | 16:00:00
PO-00740-H04MFX60AP111-ME-U | LTK0 | MAIN INLET VALVE OIL PUMP 2 | ACTIVE | LTK-H04MFX60AP111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00740-H04MFX60AP111-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 3 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX60 | AP | FLUID SUPPLY SYSTEM for MIV | Screw pump / L3 MF 70/112 IFOKSO- G for MIV HPU oil pump No.2 | 56 | 2024-11-06 | 16:00:00
PO-00760-H04MFX10-ME-U | LTK0 | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | ACTIVE | LTK-H04MFX10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00760-H04MFX10-ME-U |  | 2024-11-09 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 4 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 |  | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | 56 | 2024-11-12 | 16:00:00
PO-00840-H04MFX10AP110-ME-U | LTK0 | GOVERNOR OIL PUMP NO. 1 | ACTIVE | LTK-H04MFX10AP110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00840-H04MFX10AP110-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 5 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOVERNOR OIL PUMP NO.1 | 56 | 2024-11-10 | 16:00:00
PO-00850-H04MFX10AP111-ME-U | LTK0 | GOVERNOR OIL PUMP NO. 2 | ACTIVE | LTK-H04MFX10AP111 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00850-H04MFX10AP111-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 6 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | GOVERNOR OIL PUMP NO.2 | 56 | 2024-11-10 | 16:00:00
PO-00860-H04MFX20AA010-ME-U | LTK0 | DISTRIBUTING VALVE | ACTIVE | LTK-H04MFX20AA010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00860-H04MFX20AA010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 7 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX20 | AA | FLUID SUPPLY SYSTEM 2 (GOVERNOR) | Main distributing valve | 56 | 2024-11-05 | 16:00:00
PO-00870-H04MFX10BB730-ME-U | LTK0 | OIL LEAKAGE TANK | ACTIVE | LTK-H04MFX10BB730 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00870-H04MFX10BB730-ME-U |  | 2024-11-11 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 8 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | BB | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | Oil Leakage Tank (Total volume : 400L) | 56 | 2024-11-12 | 16:00:00
PO-00880-H04MFX10AP330-ME-U | LTK0 | OIL LEAKAGE PUMP | ACTIVE | LTK-H04MFX10AP330 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00880-H04MFX10AP330-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 9 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | RETURN OIL LEAK PUMP | 56 | 2024-11-10 | 16:00:00
PO-00890-H04MFX10AP710-ME-U | LTK0 | GOVERNOR OIL COOLING PUMP | ACTIVE | LTK-H04MFX10AP710 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00890-H04MFX10AP710-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-56-H04MFX-ME-U | 0 | 10 | 0 | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX10 | AP | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | Oil pump for Gov HPU cooling pump | 56 | 2024-11-10 | 16:00:00
Group-57-H04MFW-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 57 | 1 | H04MFW | No_kks_found | U | ME |  |  |  |  | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CF010-ME-U | LTK0 | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | ACTIVE | LTK-H04MFW40CF010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CF010-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 1 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CF | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP310-ME-U | LTK0 | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | ACTIVE | LTK-H04MFW40CP310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP310-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 2 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP320-ME-U | LTK0 | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | ACTIVE | LTK-H04MFW40CP320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP320-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 3 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP330-ME-U | LTK0 | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | ACTIVE | LTK-H04MFW40CP330 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP330-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 4 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP340-ME-U | LTK0 | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | ACTIVE | LTK-H04MFW40CP340 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP340-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 5 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP350-ME-U | LTK0 | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | ACTIVE | LTK-H04MFW40CP350 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP350-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 6 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 57 | 2024-11-10 | 16:00:00
PO-00470-H04MFW40CP355-ME-U | LTK0 | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | ACTIVE | LTK-H04MFW40CP355 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00470-H04MFW40CP355-ME-U |  | 2024-11-06 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-57-H04MFW-ME-U | 0 | 7 | 1 | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 57 | 2024-11-10 | 16:00:00
Group-58-H04MFV-ME-U | LTK0 | No_kks_found,MSP0-H020,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 58 | 0 | H04MFV | No_kks_found | U | ME |  |  |  |  | 58 | 2024-11-05 | 16:00:00
PO-00430-H04MFV20AP150-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | ACTIVE | LTK-H04MFV20AP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00430-H04MFV20AP150-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-58-H04MFV-ME-U | 0 | 1 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | AP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 4 | 58 | 2024-11-05 | 16:00:00
PO-00430-H04MFV20AP160-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | ACTIVE | LTK-H04MFV20AP160 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00430-H04MFV20AP160-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-58-H04MFV-ME-U | 0 | 2 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | AP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 4 | 58 | 2024-11-05 | 16:00:00
Group-59-H04MFV-ME-U | LTK0 | No_kks_found,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 59 | 1 | H04MFV | No_kks_found | U | ME |  |  |  |  | 59 | 2024-11-05 | 16:00:00
PO-00570-H04MFV20AP150-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PUMP NO.1 | ACTIVE | LTK-H04MFV20AP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00570-H04MFV20AP150-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-59-H04MFV-ME-U | 0 | 1 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | AP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 4 | 59 | 2024-11-05 | 16:00:00
PO-00580-H04MFV20AP160-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PUMP NO.2 | ACTIVE | LTK-H04MFV20AP160 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00580-H04MFV20AP160-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-59-H04MFV-ME-U | 0 | 2 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | AP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 4 | 59 | 2024-11-05 | 16:00:00
Group-60-H04MFV-ME-U | LTK0 | No_kks_found,LTK0-1M2,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-10 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 60 | 0 | H04MFV | No_kks_found | U | ME |  |  |  |  | 60 | 2024-11-13 | 16:00:00
PO-00590-H04MFV20AC310-ME-U | LTK0 | TURBINE GUIDE BEARING OIL COOLER NO.1 | ACTIVE | LTK-H04MFV20AC310 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00590-H04MFV20AC310-ME-U |  | 2024-11-10 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-60-H04MFV-ME-U | 0 | 1 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | AC | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB OIL COOLER (Heat EX-CHANGER) 4MFV20AC310 | 60 | 2024-11-11 | 16:00:00
PO-00600-H04MFV20AC320-ME-U | LTK0 | TURBINE GUIDE BEARING OIL COOLER NO.2 | ACTIVE | LTK-H04MFV20AC320 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00600-H04MFV20AC320-ME-U |  | 2024-11-12 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-60-H04MFV-ME-U | 0 | 2 | 0 | H04MFV | No_kks_found | U | ME | H04MFV20 | AC | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB OIL COOLER (Heat EX-CHANGER) 4MFV20AC320 | 60 | 2024-11-13 | 16:00:00
Group-61-H04MFV-ME-U | LTK0 | No_kks_found,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 61 | 1 | H04MFV | No_kks_found | U | ME |  |  |  |  | 61 | 2024-11-13 | 16:00:00
PO-00450-H04MFV20CP350-ME-U | LTK0 | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | ACTIVE | LTK-H04MFV20CP350 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04MFV20CP350-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-61-H04MFV-ME-U | 0 | 1 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 61 | 2024-11-13 | 16:00:00
PO-00450-H04MFV20CP351-ME-U | LTK0 | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | ACTIVE | LTK-H04MFV20CP351 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04MFV20CP351-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-61-H04MFV-ME-U | 0 | 2 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 61 | 2024-11-13 | 16:00:00
PO-00450-H04MFV20CP352-ME-U | LTK0 | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | ACTIVE | LTK-H04MFV20CP352 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04MFV20CP352-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-61-H04MFV-ME-U | 0 | 3 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 61 | 2024-11-13 | 16:00:00
PO-00450-H04MFV20CP360-ME-U | LTK0 | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | ACTIVE | LTK-H04MFV20CP360 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00450-H04MFV20CP360-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-61-H04MFV-ME-U | 0 | 4 | 1 | H04MFV | No_kks_found | U | ME | H04MFV20 | CP | TURBINE BEARING LUBRICANT SUPPLY SYSTEM | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 61 | 2024-11-13 | 16:00:00
Group-62-H04MFD-ME-U | LTK0 | TURBINE GUIDE BEARING,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 62 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME |  |  |  |  | 62 | 2024-11-16 | 16:00:00
PO-00560-H04MFD20BB001-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PAN | ACTIVE | LTK-H04MFD20BB001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00560-H04MFD20BB001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-62-H04MFD-ME-U | 0 | 1 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | BB | TURBINE GUIDE BEARING | TURBINE GUIDE BEARING OIL PAN | 62 | 2024-11-14 | 16:00:00
PO-02270-H04MFD20BB001-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PAN | ACTIVE | LTK-H04MFD20BB001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02270-H04MFD20BB001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-62-H04MFD-ME-U | 0 | 2 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | BB | TURBINE GUIDE BEARING | TURBINE GUIDE BEARING OIL PAN | 62 | 2024-11-13 | 16:00:00
PO-02280-H04MFD20-ME-U | LTK0 | TURBINE GUIDE BEARING (ROUTE) | ACTIVE | LTK-H04MFD20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02280-H04MFD20-ME-U |  | 2024-11-14 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-62-H04MFD-ME-U | 0 | 3 | 0 | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 |  | TURBINE GUIDE BEARING | TURBINE GUIDE BEARING | 62 | 2024-11-16 | 16:00:00
Group-63-H04MFB-ME-U | LTK0 | MAIN INLET VALVE,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 63 | 1 | H04MFB | MAIN INLET VALVE | U | ME |  |  |  |  | 63 | 2024-11-09 | 16:00:00
PO-00610-H04MFB10-ME-U | LTK0 | INLET VALVE | ACTIVE | LTK-H04MFB10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00610-H04MFB10-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-63-H04MFB-ME-U | 0 | 1 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 |  | INLET VALVE | INLET VALVE | 63 | 2024-11-06 | 16:00:00
PO-00620-H04MFB10AA403-ME-U | LTK0 | MIV BYPASS VALVE | ACTIVE | LTK-H04MFB10AA403 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00620-H04MFB10AA403-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-63-H04MFB-ME-U | 0 | 2 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | AA | INLET VALVE | MAIN BY-PASS VALVE | 63 | 2024-11-05 | 16:00:00
PO-00630-H04MFB10AS010-ME-U | LTK0 | MAIN INLET VALVE SERVOMOTOR NO.1 | ACTIVE | LTK-H04MFB10AS010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00630-H04MFB10AS010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-63-H04MFB-ME-U | 0 | 3 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | AS | INLET VALVE | SERVOMOTOR 4MFB10AS010 | 63 | 2024-11-05 | 16:00:00
PO-00640-H04MFB10AS020-ME-U | LTK0 | MAIN INLET VALVE SERVOMOTOR NO.2 | ACTIVE | LTK-H04MFB10AS020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00640-H04MFB10AS020-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-63-H04MFB-ME-U | 0 | 4 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | AS | INLET VALVE | SERVOMOTOR 4MFB10AS020 | 63 | 2024-11-05 | 16:00:00
PO-02510-H04MFB10AS010-ME-U | LTK0 | MAIN INLET VALVE SERVOMOTOR NO.1 (ADD) | ACTIVE | LTK-H04MFB10AS010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02510-H04MFB10AS010-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-63-H04MFB-ME-U | 0 | 5 | 1 | H04MFB | MAIN INLET VALVE | U | ME | H04MFB10 | AS | INLET VALVE | SERVOMOTOR 4MFB10AS010 | 63 | 2024-11-09 | 16:00:00
Group-64-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 64 | 0 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 64 | 2024-11-13 | 16:00:00
PO-00510-H04MFA90-ME-U | LTK0 | HEAD COVER | ACTIVE | LTK-H04MFA90 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00510-H04MFA90-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-64-H04MFA-ME-U | 0 | 1 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA90 |  | Head Cover | Head Cover | 64 | 2024-11-07 | 16:00:00
PO-00540-H04MFA20-ME-U | LTK0 | GUIDE VANE MECHANISM | ACTIVE | LTK-H04MFA20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00540-H04MFA20-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-64-H04MFA-ME-U | 0 | 2 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 |  | GUIDE VANE | GUIDE VANE | 64 | 2024-11-13 | 16:00:00
PO-00550-H04MFA20AS010-ME-U | LTK0 | GUIDE VANE SERVOMOTOR | ACTIVE | LTK-H04MFA20AS010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00550-H04MFA20AS010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-64-H04MFA-ME-U | 0 | 3 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | AS | GUIDE VANE | Servomotor No.1 | 64 | 2024-11-05 | 16:00:00
PO-01170-H04MFA60KE001-ME-U | LTK0 | LOCKING DEVICE | ACTIVE | LTK-H04MFA60KE001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01170-H04MFA60KE001-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-64-H04MFA-ME-U | 0 | 4 | 0 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | KE | DRAFT TUBE SYSTEM | LOCKING DEVIEC | 64 | 2024-11-05 | 16:00:00
Group-65-H04MFA-ME-U | LTK0 | TURBINE SYSTEM,LTK0-1D4,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 65 | 1 | H04MFA | TURBINE SYSTEM | U | ME |  |  |  |  | 65 | 2024-11-10 | 16:00:00
PO-00400-H04MFA10CP311-ME-U | LTK0 | SC INLET PRESSURE GAUGE - CP311 | ACTIVE | LTK-H04MFA10CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA10CP311-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 1 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA10 | CP | SPIRAL CASE | Pressure gauge | 65 | 2024-11-07 | 16:00:00
PO-00400-H04MFA20CP301-ME-U | LTK0 | VANELESS AREA PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MFA20CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA20CP301-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 2 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | VANELESS AREA PRESSURE GAUGE - CP301 | 65 | 2024-11-07 | 16:00:00
PO-00400-H04MFA60CP301-ME-U | LTK0 | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | ACTIVE | LTK-H04MFA60CP301 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA60CP301-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 3 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 65 | 2024-11-07 | 16:00:00
PO-00400-H04MFA60CP311-ME-U | LTK0 | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | ACTIVE | LTK-H04MFA60CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA60CP311-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 4 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 65 | 2024-11-07 | 16:00:00
PO-00400-H04MFA60CP321-ME-U | LTK0 | DT OUTLET PRESSURE GAUGE - CP321 | ACTIVE | LTK-H04MFA60CP321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA60CP321-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 5 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | DT OUTLET PRESSURE GAUGE - CP321 | 65 | 2024-11-07 | 16:00:00
PO-00400-H04MFA60CP331-ME-U | LTK0 | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | ACTIVE | LTK-H04MFA60CP331 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00400-H04MFA60CP331-ME-U |  | 2024-11-07 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 6 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 | CP | DRAFT TUBE SYSTEM | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 65 | 2024-11-07 | 16:00:00
PO-00420-H04MFA20CP311-ME-U | LTK0 | PRESSURE GAUGE OF SERVO NO.01 | ACTIVE | LTK-H04MFA20CP311 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00420-H04MFA20CP311-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 7 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | PRESSURE GAUGE OF SERVO NO.01 | 65 | 2024-11-10 | 16:00:00
PO-00420-H04MFA20CP312-ME-U | LTK0 | PRESSURE GAUGE OF SERVO NO.01 | ACTIVE | LTK-H04MFA20CP312 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00420-H04MFA20CP312-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 8 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | PRESSURE GAUGE OF SERVO NO.01 | 65 | 2024-11-10 | 16:00:00
PO-00420-H04MFA20CP321-ME-U | LTK0 | PRESSURE GAUGE OF SERVO NO.02 | ACTIVE | LTK-H04MFA20CP321 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00420-H04MFA20CP321-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 9 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | PRESSURE GAUGE OF SERVO NO.02 | 65 | 2024-11-10 | 16:00:00
PO-00420-H04MFA20CP322-ME-U | LTK0 | PRESSURE GAUGE OF SERVO NO.02 | ACTIVE | LTK-H04MFA20CP322 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00420-H04MFA20CP322-ME-U |  | 2024-11-10 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-65-H04MFA-ME-U | 0 | 10 | 1 | H04MFA | TURBINE SYSTEM | U | ME | H04MFA20 | CP | GUIDE VANE | PRESSURE GAUGE OF SERVO NO.02 | 65 | 2024-11-10 | 16:00:00
Group-66-H04LQY-ME-U | LTK0 | No_kks_found,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 66 | 0 | H04LQY | No_kks_found | U | ME |  |  |  |  | 66 | 2024-11-05 | 16:00:00
PO-01150-H04LQY10AP020-ME-U | LTK0 | DRAFT TUBE GATE MANUAL PUMP | ACTIVE | LTK-H04LQY10AP020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01150-H04LQY10AP020-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-66-H04LQY-ME-U | 0 | 1 | 0 | H04LQY | No_kks_found | U | ME | H04LQY10 | AP | No_kks_found | DRAFT TUBE GATE MANUAL PUMP | 66 | 2024-11-05 | 16:00:00
PO-01160-H04LQY10AP010-ME-U | LTK0 | DRAFT TUBE GATE MOTOR PUMP SET | ACTIVE | LTK-H04LQY10AP010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01160-H04LQY10AP010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-66-H04LQY-ME-U | 0 | 2 | 0 | H04LQY | No_kks_found | U | ME | H04LQY10 | AP | No_kks_found | DRAFT TUBE GATE MOTOR PUMP SET | 66 | 2024-11-05 | 16:00:00
Group-67-H04BAT-ME-U | LTK0 | No_kks_found,MSP0-H010,PTW งานทั่วไป | ACTIVE | LTK-H03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 67 | 1 | H04BAT | No_kks_found | U | ME |  |  |  |  | 67 | 2024-11-10 | 16:00:00
PO-01070-H04BAT01AC001-ME-U | LTK0 | MAIN TRANSFORMER OIL COOLER NO.1 | ACTIVE | LTK-H04BAT01AC001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01070-H04BAT01AC001-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 1 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AC | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL COOLER NO.1 | 67 | 2024-11-10 | 16:00:00
PO-01080-H04BAT01AC002-ME-U | LTK0 | MAIN TRANSFORMER OIL COOLER NO.2 | ACTIVE | LTK-H04BAT01AC002 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01080-H04BAT01AC002-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 2 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AC | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL COOLER NO.2 | 67 | 2024-11-10 | 16:00:00
PO-01090-H04BAT01AC003-ME-U | LTK0 | MAIN TRANSFORMER OIL COOLER NO.3 | ACTIVE | LTK-H04BAT01AC003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01090-H04BAT01AC003-ME-U |  | 2024-11-08 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 3 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AC | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL COOLER NO.3 | 67 | 2024-11-10 | 16:00:00
PO-01110-H04BAT01AP140-ME-U | LTK0 | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.1 | ACTIVE | LTK-H04BAT01AP140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01110-H04BAT01AP140-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 4 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL CURCULATING PUMP 1 | 67 | 2024-11-05 | 16:00:00
PO-01120-H04BAT01AP150-ME-U | LTK0 | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.2 | ACTIVE | LTK-H04BAT01AP150 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01120-H04BAT01AP150-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 5 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL CURCULATING PUMP 2 | 67 | 2024-11-05 | 16:00:00
PO-01130-H04BAT01AP160-ME-U | LTK0 | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.3 | ACTIVE | LTK-H04BAT01AP160 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01130-H04BAT01AP160-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 1 | 7 | 08:00:00 | Group-67-H04BAT-ME-U | 0 | 6 | 1 | H04BAT | No_kks_found | U | ME | H04BAT01 | AP | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL CURCULATING PUMP 3 | 67 | 2024-11-05 | 16:00:00
Group-68-H34CHE-ME-C34 | LTK0 | No_kks_found,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H34 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 68 | 0 | H34CHE | No_kks_found | C34 | ME |  |  |  |  | 68 | 2024-11-05 | 16:00:00
PO-02430-H34CHE20GH101-ME-C34 | LTK0 | UNIT 3-4 SST. PROTECTION SYSTEM A/B CUBICLE | ACTIVE | LTK-H34CHE20GH101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02430-H34CHE20GH101-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-68-H34CHE-ME-C34 | 0 | 1 | 0 | H34CHE | No_kks_found | C34 | ME | H34CHE20 | GH | CABINETS FOR STATION SERVICE TRANSFORMER PROTECTION | UNIT 3-4 SST. PROTECTION SYSTEM A/B CUBICLE | 68 | 2024-11-05 | 16:00:00
PO-02440-H34CHE20GH101-U01-ME-C34 | LTK0 | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | ACTIVE | LTK-H34CHE20GH101-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02440-H34CHE20GH101-U01-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-68-H34CHE-ME-C34 | 0 | 2 | 0 | H34CHE | No_kks_found | C34 | ME | H34CHE20 | GH | CABINETS FOR STATION SERVICE TRANSFORMER PROTECTION | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | 68 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02440-H34CHE20GH101-U02-ME-C34 | LTK0 | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | ACTIVE | LTK-H34CHE20GH101-U02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02440-H34CHE20GH101-U02-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-68-H34CHE-ME-C34 | 0 | 3 | 0 | H34CHE | No_kks_found | C34 | ME | H34CHE20 | GH | CABINETS FOR STATION SERVICE TRANSFORMER PROTECTION | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | 68 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02450-H34CHE20GH101-U03-ME-C34 | LTK0 | UNIT 3-4 SST. MECHNICAL PROTECTION RELAY | ACTIVE | LTK-H34CHE20GH101-U03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02450-H34CHE20GH101-U03-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-68-H34CHE-ME-C34 | 0 | 4 | 0 | H34CHE | No_kks_found | C34 | ME | H34CHE20 | GH | CABINETS FOR STATION SERVICE TRANSFORMER PROTECTION | UNIT 3-4 SST. MECHNICAL PROTECTION RELAY | 68 | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-69-H34BBT-ME-C34 | LTK0 | UNIT 3-4 AUXILIARY TRANSFORMER,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H34 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 69 | 1 | H34BBT | UNIT 3-4 AUXILIARY TRANSFORMER | C34 | ME |  |  |  |  | 69 | 2024-11-05 | 16:00:00
PO-02400-H34BBT10GS200-ME-C34 | LTK0 | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | ACTIVE | LTK-H34BBT10GS200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02400-H34BBT10GS200-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-69-H34BBT-ME-C34 | 0 | 1 | 1 | H34BBT | UNIT 3-4 AUXILIARY TRANSFORMER | C34 | ME | H34BBT10 | GS | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B | 16.5 KV DS 89SS, 1641B | 69 | 2024-11-05 | 16:00:00
PO-02410-H34BBT10-ME-C34 | LTK0 | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หปฟนม-ธ.) | ACTIVE | LTK-H34BBT10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02410-H34BBT10-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-69-H34BBT-ME-C34 | 0 | 2 | 1 | H34BBT | UNIT 3-4 AUXILIARY TRANSFORMER | C34 | ME | H34BBT10 |  | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B | 69 | 2024-11-05 | 16:00:00
Group-70-H14BCT-ME-C14 | LTK0 | STATION SERVICE TRANSFORMER,MSP0-H020,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H14 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 70 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME |  |  |  |  | 70 | 2024-11-11 | 16:00:00
PO-02310-H14BCT10GU100-B01-ME-C14 | LTK0 | SFC AC REACTOR: 20LGS001RT | ACTIVE | LTK-H14BCT10GU100-B01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02310-H14BCT10GU100-B01-ME-C14 |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-70-H14BCT-ME-C14 | 0 | 1 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC AC REACTOR: 20LGS001RT | 70 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02310-H14BCT10GU100-B02-ME-C14 | LTK0 | SFC AC REACTOR: 20LGS003RT | ACTIVE | LTK-H14BCT10GU100-B02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02310-H14BCT10GU100-B02-ME-C14 |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-70-H14BCT-ME-C14 | 0 | 2 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC AC REACTOR: 20LGS003RT | 70 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02310-H14BCT10GU100-B03-ME-C14 | LTK0 | SFC DC REACTOR ENCLOSURE: 20LGS002RT | ACTIVE | LTK-H14BCT10GU100-B03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02310-H14BCT10GU100-B03-ME-C14 |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-70-H14BCT-ME-C14 | 0 | 3 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 70 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02310-H14BCT10GU100-T01-ME-C14 | LTK0 | SFC INCOMING TRANSFORMER: 20LGS001TR | ACTIVE | LTK-H14BCT10GU100-T01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02310-H14BCT10GU100-T01-ME-C14 |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-70-H14BCT-ME-C14 | 0 | 4 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC INCOMING TRANSFORMER: 20LGS001TR | 70 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02310-H14BCT10GU100-T02-ME-C14 | LTK0 | SFC OUTGOING TRANSFORMER: 20LGS002TR | ACTIVE | LTK-H14BCT10GU100-T02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02310-H14BCT10GU100-T02-ME-C14 |  | 2024-11-11 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-70-H14BCT-ME-C14 | 0 | 5 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC OUTGOING TRANSFORMER: 20LGS002TR | 70 | 2024-11-11 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-71-H14BCT-ME-C14 | LTK0 | STATION SERVICE TRANSFORMER,MSP0-EA30,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H14 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 71 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME |  |  |  |  | 71 | 2024-11-16 | 16:00:00
PO-02320-H14BCT10GU100-B01-ME-C14 | LTK0 | SFC AC REACTOR: 20LGS001RT | ACTIVE | LTK-H14BCT10GU100-B01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02320-H14BCT10GU100-B01-ME-C14 |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 1 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC AC REACTOR: 20LGS001RT | 71 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02320-H14BCT10GU100-B02-ME-C14 | LTK0 | SFC AC REACTOR: 20LGS003RT | ACTIVE | LTK-H14BCT10GU100-B02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02320-H14BCT10GU100-B02-ME-C14 |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 2 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC AC REACTOR: 20LGS003RT | 71 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02320-H14BCT10GU100-B03-ME-C14 | LTK0 | SFC DC REACTOR ENCLOSURE: 20LGS002RT | ACTIVE | LTK-H14BCT10GU100-B03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02320-H14BCT10GU100-B03-ME-C14 |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 3 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 71 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02320-H14BCT10GU100-T01-ME-C14 | LTK0 | SFC INCOMING TRANSFORMER: 20LGS001TR | ACTIVE | LTK-H14BCT10GU100-T01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02320-H14BCT10GU100-T01-ME-C14 |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 4 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC INCOMING TRANSFORMER: 20LGS001TR | 71 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02320-H14BCT10GU100-T02-ME-C14 | LTK0 | SFC OUTGOING TRANSFORMER: 20LGS002TR | ACTIVE | LTK-H14BCT10GU100-T02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02320-H14BCT10GU100-T02-ME-C14 |  | 2024-11-11 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 5 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC OUTGOING TRANSFORMER: 20LGS002TR | 71 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02340-H14BCT10CE210-ME-C14 | LTK0 | CT: 16.5kV, 1200A/5A, 5P20 - 031TI-033TI | ACTIVE | LTK-H14BCT10CE210 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02340-H14BCT10CE210-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 6 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | CT: 16.5kV, 1200A/5A, 5P20 - 031TI-033TI | 71 | 2024-11-13 | 16:00:00
PO-02340-H14BCT10CE220-ME-C14 | LTK0 | CT: 16.5kV, 1200A/5A, 5FS5 - 034TI-036TI | ACTIVE | LTK-H14BCT10CE220 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02340-H14BCT10CE220-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 7 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | CT: 16.5kV, 1200A/5A, 5FS5 - 034TI-036TI | 71 | 2024-11-13 | 16:00:00
PO-02350-H14BCT10CE110-ME-C14 | LTK0 | PT: 16.5kV/115 V, CL1.2 - 001TU-002TU | ACTIVE | LTK-H14BCT10CE110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02350-H14BCT10CE110-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 8 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | PT: 16.5kV/115 V, CL1.2 - 001TU-002TU | 71 | 2024-11-13 | 16:00:00
PO-02350-H14BCT10CE230-ME-C14 | LTK0 | CT: 16.5kV, 1200A/5A, 5P20 - 037TI-039TI | ACTIVE | LTK-H14BCT10CE230 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02350-H14BCT10CE230-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 9 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | CT: 16.5kV, 1200A/5A, 5P20 - 037TI-039TI | 71 | 2024-11-13 | 16:00:00
PO-02350-H14BCT10CE240-ME-C14 | LTK0 | CT: 16.5kV, 1200A/5A, 5P20 - 040TI-042TI | ACTIVE | LTK-H14BCT10CE240 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02350-H14BCT10CE240-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 10 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | CT: 16.5kV, 1200A/5A, 5P20 - 040TI-042TI | 71 | 2024-11-13 | 16:00:00
PO-02350-H14BCT10CE250-ME-C14 | LTK0 | CT: 16.5kV, 4000A/5A, C400 - TA156-TA158 | ACTIVE | LTK-H14BCT10CE250 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02350-H14BCT10CE250-ME-C14 |  | 2024-11-13 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-71-H14BCT-ME-C14 | 0 | 11 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | CE | STATIC FREQUENCY CONVERTER ( SFC ) | CT: 16.5kV, 4000A/5A, C400 - TA156-TA158 | 71 | 2024-11-13 | 16:00:00
Group-72-H14BCT-ME-C14 | LTK0 | STATION SERVICE TRANSFORMER,MSP0-E840,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H14 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 72 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME |  |  |  |  | 72 | 2024-11-11 | 16:00:00
PO-02360-H14BCT10GS001-ME-C14 | LTK0 | VCB - 52SFC1 | ACTIVE | LTK-H14BCT10GS001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02360-H14BCT10GS001-ME-C14 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-72-H14BCT-ME-C14 | 0 | 1 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GS | STATIC FREQUENCY CONVERTER ( SFC ) | VCB - 52SFC1 | 72 | 2024-11-11 | 16:00:00
PO-02360-H14BCT10GS003-ME-C14 | LTK0 | VCB - 52SFC2 | ACTIVE | LTK-H14BCT10GS003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02360-H14BCT10GS003-ME-C14 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-72-H14BCT-ME-C14 | 0 | 2 | 0 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GS | STATIC FREQUENCY CONVERTER ( SFC ) | VCB - 52SFC2 | 72 | 2024-11-11 | 16:00:00
Group-73-H14BCT-ME-C14 | LTK0 | STATION SERVICE TRANSFORMER,MSP0-E830,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H14 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-E830 | หมปฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 73 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME |  |  |  |  | 73 | 2024-11-16 | 16:00:00
PO-02330-H14BCT10GU100-T01-ME-C14 | LTK0 | SFC INCOMING TRANSFORMER: 20LGS001TR | ACTIVE | LTK-H14BCT10GU100-T01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02330-H14BCT10GU100-T01-ME-C14 |  | 2024-11-11 | MSP0-E830 | หมปฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-73-H14BCT-ME-C14 | 0 | 1 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC INCOMING TRANSFORMER: 20LGS001TR | 73 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02330-H14BCT10GU100-T02-ME-C14 | LTK0 | SFC OUTGOING TRANSFORMER: 20LGS002TR | ACTIVE | LTK-H14BCT10GU100-T02 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02330-H14BCT10GU100-T02-ME-C14 |  | 2024-11-11 | MSP0-E830 | หมปฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-73-H14BCT-ME-C14 | 0 | 2 | 1 | H14BCT | STATION SERVICE TRANSFORMER | C14 | ME | H14BCT10 | GU | STATIC FREQUENCY CONVERTER ( SFC ) | SFC OUTGOING TRANSFORMER: 20LGS002TR | 73 | 2024-11-16 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
Group-74-H12ADA-ME-C12 | LTK0 | 230 KV SYSTEMS,MSP0-E840,PTW งานเกี่ยวกับไฟฟ้า | ACTIVE | LTK-H12 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS |  |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 74 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME |  |  |  |  | 74 | 2024-11-12 | 16:00:00
PO-02080-H12ADA30GS100-ME-C12 | LTK0 | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | ACTIVE | LTK-H12ADA30GS100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02080-H12ADA30GS100-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 1 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA30 | GS | 230KV. BAY 8: GENERATOR UNIT # 3 | BKR.LTK 80082, TRANSFORMER NO.3 (KG3A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS200-ME-C12 | LTK0 | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | ACTIVE | LTK-H12ADA31GS200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS200-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 2 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS201-ME-C12 | LTK0 | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | ACTIVE | LTK-H12ADA31GS201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS201-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 3 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS202-ME-C12 | LTK0 | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | ACTIVE | LTK-H12ADA31GS202 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS202-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 4 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS203-ME-C12 | LTK0 | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | ACTIVE | LTK-H12ADA31GS203 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS203-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 5 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS204-ME-C12 | LTK0 | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | ACTIVE | LTK-H12ADA31GS204 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS204-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 6 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 74 | 2024-11-12 | 16:00:00
PO-02090-H12ADA31GS205-ME-C12 | LTK0 | DS.LTK 80094GC, EARTH SW(HSG), KG4A | ACTIVE | LTK-H12ADA31GS205 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02090-H12ADA31GS205-ME-C12 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 1 | 7 | 08:00:00 | Group-74-H12ADA-ME-C12 | 0 | 7 | 0 | H12ADA | 230 KV SYSTEMS | C12 | ME | H12ADA31 | GS | 230KV. BAY 9: TL3-LTK NO.1 | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 74 | 2024-11-12 | 16:00:00
PO-00990-H04PAA10AT001-ME-U | LTK0 | DRAFT TUBE INTAKE SCREEN | ACTIVE | LTK-H04PAA10AT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00990-H04PAA10AT001-ME-U |  | 2024-11-07 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ//PTW งานที่เกี่ยวข้องกับสารเคมีอันตราย | 0 | 7 | 08:00:00 |  | 0 | 75 |  | H04PAA | No_kks_found | U | ME | H04PAA10 | AT | MAIN COOLING WATER SYSTEM FOR UNIT 4 | COOLING WATER SUCTION SCREEN |  | 2024-11-07 | 16:00:00
PO-00490-H04MFA30HB200-ME-U | LTK0 | RUNNER | ACTIVE | LTK-H04MFA30HB200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00490-H04MFA30HB200-ME-U |  | 2024-11-07 | MSP0-H010 | หปคนม-ธ. | PTW งานในที่อับอากาศ//PTW งานที่เกี่ยวข้องกับสารเคมีอันตราย | 0 | 7 | 08:00:00 |  | 0 | 76 |  | H04MFA | TURBINE SYSTEM | U | ME | H04MFA30 | HB | RUNNER & TURBINE SHAFT | RUNNER |  | 2024-11-07 | 16:00:00
PO-01000-H04PAA10AT001-ME-U | LTK0 | TURBINE DRAFT TUBE INTAKE SCREEN Unit4 | ACTIVE | LTK-H04PAA10AT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01000-H04PAA10AT001-ME-U |  | 2024-11-07 | LTK0-1C3 | หยลอ-ฟ. | PTW งานในที่อับอากาศ,PTW งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 77 |  | H04PAA | No_kks_found | U | ME | H04PAA10 | AT | MAIN COOLING WATER SYSTEM FOR UNIT 4 | COOLING WATER SUCTION SCREEN |  | 2024-11-12 | 16:00:00
PO-02300-H04PAA10AT001-ME-U | LTK0 | DRAFT TUBE INTAKE SCREEN | ACTIVE | LTK-H04PAA10AT001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02300-H04PAA10AT001-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานในที่อับอากาศ, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 0 | 7 | 08:00:00 |  | 0 | 78 |  | H04PAA | No_kks_found | U | ME | H04PAA10 | AT | MAIN COOLING WATER SYSTEM FOR UNIT 4 | COOLING WATER SUCTION SCREEN |  | 2024-11-11 | 16:00:00
PO-02190-H04L-ME-U | LTK0 | CIVIL INSPECTION | ACTIVE | LTK-H04L | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02190-H04L-ME-U |  | 2024-11-07 | LTK0-1C3 | หยลอ-ฟ. | PTW งานในที่อับอากาศ | 0 | 7 | 08:00:00 |  | 0 | 79 |  | H04L | DRAFT TUBE GATE | U | ME | H04L |  | DRAFT TUBE GATE | DRAFT TUBE GATE |  | 2024-11-07 | 16:00:00
PO-02060-H04MLC10GS140-ME-U | LTK0 | FIELD BREAKER (41E) | ACTIVE | LTK-H04MLC10GS140 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02060-H04MLC10GS140-ME-U |  | 2024-11-05 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 80 |  | H04MLC | EXCITATION | U | ME | H04MLC10 | GS | EXCITER SETS | FIELD BREAKER (41E) |  | 2024-11-12 | 16:00:00
PO-01900-H04MFX20-ME-U | LTK0 | GOVERNOR CONTROL ACTUATOR | ACTIVE | LTK-H04MFX20 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01900-H04MFX20-ME-U |  | 2024-11-05 | MSP0-E920 | หคมก-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 81 |  | H04MFX | FLUID SUPPLY SYSTEM | U | ME | H04MFX20 |  | FLUID SUPPLY SYSTEM 2 (GOVERNOR) | FLUID SUPPLY SYSTEM 2 (GOVERNOR) |  | 2024-11-12 | 16:00:00
PO-02570-H04MFW40CP001-ME-U | LTK0 | SHAFT SEAL WATER PRESSURE TRANSMITTER - CP001 (INSTALLATION) | ACTIVE | LTK-H04MFW40CP001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02570-H04MFW40CP001-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 82 |  | H04MFW | No_kks_found | U | ME | H04MFW40 | CP | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL WATER PRESSURE TRANSMITTER - CP001 |  | 2024-11-13 | 16:00:00
PO-02580-H04MFL30CL001-ME-U | LTK0 | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | ACTIVE | LTK-H04MFL30CL001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02580-H04MFL30CL001-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 83 |  | H04MFL | WATER DEPRESSION SYSTEM | U | ME | H04MFL30 | CL | WATER DEPRESSION AIR SUPPLY SYSTEM | DT CONE LEVEL TRANSMITTER - CL001 |  | 2024-11-16 | 16:00:00
PO-01890-H04MEY10GH001-ME-U | LTK0 | DIGITAL GOVERNOR CONTROL CUBICLE | ACTIVE | LTK-H04MEY10GH001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01890-H04MEY10GH001-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 84 |  | H04MEY | No_kks_found | U | ME | H04MEY10 | GH | GOVERNOR CONTROL SYSTEM | DIGITAL GOVERNOR CONTROL CUBICLE |  | 2024-11-12 | 16:00:00
PO-01620-H04EHS40-ME-U | LTK0 | SEALING END MTR SIDE | ACTIVE | LTK-H04EHS40 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01620-H04EHS40-ME-U |  | 2024-11-05 | MSP0-H020//MSP0-E250 | หปฟนม-ธ.//หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 85 |  | H04EHS | No_kks_found | U | ME | H04EHS40 |  | SEALING END MTR SIDE | SEALING END MTR SIDE |  | 2024-11-12 | 16:00:00
PO-02100-H04EHS30-ME-U | LTK0 | SEALING END GIS SIDE | ACTIVE | LTK-H04EHS30 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02100-H04EHS30-ME-U |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 86 |  | H04EHS | No_kks_found | U | ME | H04EHS30 |  | SEALING END GIS SIDE | SEALING END GIS SIDE |  | 2024-11-12 | 16:00:00
PO-01620-H04CHB10GH101-U03-ME-U | LTK0 | MAIN TRANSFORMER OLTC - AVR MODULE | ACTIVE | LTK-H04CHB10GH101-U03 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01620-H04CHB10GH101-U03-ME-U |  | 2024-11-05 | MSP0-H020//MSP0-E250 | หปฟนม-ธ.//หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 87 |  | H04CHB | No_kks_found | U | ME | H04CHB10 | GH | CABINETS FOR TRANSFORMER PROTECTION | MAIN TRANSFORMER OLTC - AVR MODULE |  | 2024-11-12 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-01510-H04BAW10GZ100-ME-U | LTK0 | 16.5 KV. BUS , CABLE, IPB. & ACCESSORIES (หปฟนม-ธ.) | ACTIVE | LTK-H04BAW10GZ100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01510-H04BAW10GZ100-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 88 |  | H04BAW | No_kks_found | U | ME | H04BAW10 | GZ | No_kks_found | 16.5 KV. BUS , CABLE, IPB. & ACCESSORIES |  | 2024-11-08 | 16:00:00
PO-01370-H04BAU10GS200-ME-U | LTK0 | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | ACTIVE | LTK-H04BAU10GS200 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01370-H04BAU10GS200-ME-U |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 89 |  | H04BAU | No_kks_found | U | ME | H04BAU10 | GS | EARTHING AND LIGHTNING PROTECTION SYSTEM | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) |  | 2024-11-05 | 16:00:00
PO-02500-H04PCM30-ME-U | LTK0 | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | ACTIVE | LTK-H04PCM30 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02500-H04PCM30-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 0 | 7 | 08:00:00 |  | 0 | 90 |  | H04PCM | No_kks_found | U | ME | H04PCM30 |  | COOLING WATER SUPPLY FOR GEN AIR COOLER | COOLING WATER SUPPLY FOR GEN AIR COOLER |  | 2024-11-10 | 16:00:00
PO-02590-H04MFL30CL001-ME-U | LTK0 | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | ACTIVE | LTK-H04MFL30CL001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02590-H04MFL30CL001-ME-U |  | 2024-11-05 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 0 | 7 | 08:00:00 |  | 0 | 91 |  | H04MFL | WATER DEPRESSION SYSTEM | U | ME | H04MFL30 | CL | WATER DEPRESSION AIR SUPPLY SYSTEM | DT CONE LEVEL TRANSMITTER - CL001 |  | 2024-11-16 | 16:00:00
PO-02540-H04MFD20BB001-ME-U | LTK0 | TURBINE GUIDE BEARING OIL PAN | ACTIVE | LTK-H04MFD20BB001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02540-H04MFD20BB001-ME-U |  | 2024-11-06 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป, PTW งานที่ทำให้เกิดความร้อน ประกายไฟ | 0 | 7 | 08:00:00 |  | 0 | 92 |  | H04MFD | TURBINE GUIDE BEARING | U | ME | H04MFD20 | BB | TURBINE GUIDE BEARING | TURBINE GUIDE BEARING OIL PAN |  | 2024-11-12 | 16:00:00
PO-01050-H04PAB10AT110-ME-U | LTK0 | MAIN COOLING WATER STRAINER UNIT 3 ชั้น 176.50 (CIVIL) | ACTIVE | LTK-H04PAB10AT110 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01050-H04PAB10AT110-ME-U |  | 2024-11-05 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป ,งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 93 |  | H04PAB | No_kks_found | U | ME | H04PAB10 | AT | COOLING WATER PIPING AND CULVERT SYSTEM | MAIN AUTOMATIC STRAINER 4PAB10AT110 |  | 2024-11-14 | 16:00:00
PO-00040-H04CMB10-ME-U | LTK0 | ต้องเปิดราวกันตก UPPER BRACKET Unit4 | ACTIVE | LTK-H04CMB10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00040-H04CMB10-ME-U |  | 2024-11-05 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป ,งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 94 |  | H04CMB | No_kks_found | U | ME | H04CMB10 |  | Upper Bracket | Upper Bracket |  | 2024-11-14 | 16:00:00
PO-01100-H04BAT01AC003-ME-U | LTK0 | ตั้งนั่งร้าน MAIN TRANSFORMER OIL COOLER NO.1-3 (CIVIL) | ACTIVE | LTK-H04BAT01AC003 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01100-H04BAT01AC003-ME-U |  | 2024-11-07 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป ,งานนั่งร้าน | 0 | 7 | 08:00:00 |  | 0 | 95 |  | H04BAT | No_kks_found | U | ME | H04BAT01 | AC | GENERATOR TRANSFORMERS | MAIN TRANSFORMER OIL COOLER NO.3 |  | 2024-11-11 | 16:00:00
PO-01140-H04SGC10AA020-ME-U | LTK0 | G/M FIRE SUCTION MANUAL VALVE (DELUDEGE VALVE) | ACTIVE | LTK-H04SGC10AA020 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01140-H04SGC10AA020-ME-U |  | 2024-11-05 | MSP0-H010 | หบคอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 96 |  | H04SGC | No_kks_found | U | ME | H04SGC10 | AA | No_kks_found | GEN. ROOM DELUGE VALVE SET |  | 2024-11-05 | 16:00:00
PO-02490-H04PCM30BR001-ME-U | LTK0 | GEN AIR COOLER PIPE | ACTIVE | LTK-H04PCM30BR001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02490-H04PCM30BR001-ME-U |  | 2024-11-08 | URD0-6S0 | หรงอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 97 |  | H04PCM | No_kks_found | U | ME | H04PCM30 | BR | COOLING WATER SUPPLY FOR GEN AIR COOLER | GEN AIR COOLER PIPE |  | 2024-11-10 | 16:00:00
PO-00340-H04PCM30-ME-U | LTK0 | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | ACTIVE | LTK-H04PCM30 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00340-H04PCM30-ME-U |  | 2024-11-06 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 98 |  | H04PCM | No_kks_found | U | ME | H04PCM30 |  | COOLING WATER SUPPLY FOR GEN AIR COOLER | COOLING WATER SUPPLY FOR GEN AIR COOLER |  | 2024-11-14 | 16:00:00
PO-02170-H04MLD10HA001-ME-U | LTK0 | CIVIL INSPECTION | ACTIVE | LTK-H04MLD10HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02170-H04MLD10HA001-ME-U |  | 2024-11-06 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 99 |  | H04MLD | CGB. BEARINGS | U | ME | H04MLD10 | HA | Combined Guide Bearing(CGB) | LOWER BRACKET |  | 2024-11-06 | 16:00:00
PO-02150-H04ML-ME-U | LTK0 | CIVIL INSPECTION | ACTIVE | LTK-H04ML | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02150-H04ML-ME-U |  | 2024-11-06 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 100 |  | H04ML | GENERATOR | U | ME | H04ML |  | GENERATOR | GENERATOR |  | 2024-11-06 | 16:00:00
PO-02290-H04MFW40HA001-ME-U | LTK0 | SHAFT SEAL | ACTIVE | LTK-H04MFW40HA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02290-H04MFW40HA001-ME-U |  | 2024-11-07 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 101 |  | H04MFW | No_kks_found | U | ME | H04MFW40 | HA | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL |  | 2024-11-10 | 16:00:00
PO-02530-H04MFW40BR001-ME-U | LTK0 | SHAFT SEAL PIPE | ACTIVE | LTK-H04MFW40BR001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02530-H04MFW40BR001-ME-U |  | 2024-11-08 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 102 |  | H04MFW | No_kks_found | U | ME | H04MFW40 | BR | TURBINE SHAFT SEAL SYSTEM | SHAFT SEAL PIPE |  | 2024-11-08 | 16:00:00
PO-01060-H04MFP14-ME-U | LTK0 | G/M FIRE EXRINGUISHER SYSTEM | ACTIVE | LTK-H04MFP14 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-01060-H04MFP14-ME-U |  | 2024-11-14 | LTK0-1M2 | หบคอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 103 |  | H04MFP | No_kks_found | U | ME | H04MFP14 |  | G/M FIRE EXRINGUISHER SYSTEM | G/M FIRE EXRINGUISHER SYSTEM |  | 2024-11-14 | 16:00:00
PO-02160-H04MFA-ME-U | LTK0 | CIVIL INSPECTION | ACTIVE | LTK-H04MFA | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02160-H04MFA-ME-U |  | 2024-11-06 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 104 |  | H04MFA | TURBINE SYSTEM | U | ME | H04MFA |  | TURBINE SYSTEM | TURBINE SYSTEM |  | 2024-11-06 | 16:00:00
PO-00020-H04L-ME-U | LTK0 | DRAFT TUBE GATE (หบฟอ-ฟ) | ACTIVE | LTK-H04L | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00020-H04L-ME-U |  | 2024-11-05 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 105 |  | H04L | DRAFT TUBE GATE | U | ME | H04L |  | DRAFT TUBE GATE | DRAFT TUBE GATE |  | 2024-11-14 | 16:00:00
PO-02180-H04CMB10-ME-U | LTK0 | CIVIL INSPECTION | ACTIVE | LTK-H04CMB10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02180-H04CMB10-ME-U |  | 2024-11-06 | LTK0-1C3 | หยลอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 106 |  | H04CMB | No_kks_found | U | ME | H04CMB10 |  | Upper Bracket | Upper Bracket |  | 2024-11-06 | 16:00:00
PO-02200-H04-ME-U | LTK0 | Unit | ACTIVE | LTK-H04 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02200-H04-ME-U |  | 2024-11-14 | LTK0 | หบฟอ-ฟ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 107 |  | H04 | LAM TAKONG HYDRO POWER PLANT UNIT 4 | U | ME | H04 |  | LAM TAKONG HYDRO POWER PLANT UNIT 4 | LAM TAKONG HYDRO POWER PLANT UNIT 4 |  | 2024-11-16 | 16:00:00
PO-00680-H03MFB10AA010-ME-U | LTK0 | MAIN CONTROL VALVE | ACTIVE | LTK-H03MFB10AA010 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00680-H03MFB10AA010-ME-U |  | 2024-11-05 | MSP0-H010 | หปคนม-ธ. | PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 108 |  | H03MFB | MAIN INLET VALVE | U | ME | H03MFB10 | AA | INLET VALVE | "Main control valve / DN50,PN7,0MPa" |  | 2024-11-05 | 16:00:00
PO-00010-H04MFA60-ME-U | LTK0 | DRAFT TUBE SYSTEM | ACTIVE | LTK-H04MFA60 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-00010-H04MFA60-ME-U |  | 2024-05-11 | LTK0-1M2 | หบคอ-ฟ//หบคอ-ฟ. | LOTO, PTW งานทั่วไป | 0 | 7 | 08:00:00 |  | 0 | 109 |  | H04MFA | TURBINE SYSTEM | U | ME | H04MFA60 |  | DRAFT TUBE SYSTEM | DRAFT TUBE SYSTEM |  | 2024-11-14 | 16:00:00
PO-02120-H34SGC10EA001-ME-C34 | LTK0 | TRANSFORMER FIRE EXTINGUISHER - CONTROL PANEL | ACTIVE | LTK-H34SGC10EA001 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02120-H34SGC10EA001-ME-C34 |  | 2024-11-08 | LTK0-1D4 | หบฟอ-ฟ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 110 |  | H34SGC | No_kks_found | C34 | ME | H34SGC10 | EA | No_kks_found | TRANSFORMER FIRE EXTINGUISHER - CONTROL PANEL |  | 2024-11-08 | 16:00:00
PO-02420-H34BBT10-ME-C34 | LTK0 | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หทอฟ-ธ.) | ACTIVE | LTK-H34BBT10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02420-H34BBT10-ME-C34 |  | 2024-11-05 | MSP0-EA30 | หทอฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 111 |  | H34BBT | UNIT 3-4 AUXILIARY TRANSFORMER | C34 | ME | H34BBT10 |  | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B |  | 2024-11-05 | 16:00:00
PO-02470-H34BBA50GS100-U01-ME-C34 | LTK0 | PROTECTION RELAY FOR BREAKER 652G | ACTIVE | LTK-H34BBA50GS100-U01 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02470-H34BBA50GS100-U01-ME-C34 |  | 2024-11-05 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 112 |  | H34BBA | 6.6 KV MV DISTRIBUTION BOARD | C34 | ME | H34BBA50 | GS | 6.6 KV MV DISTRIBUTION BOARD CUBICLE NO.5 | PROTECTION RELAY FOR BREAKER 652G |  | 2024-11-05 | 16:00:00 | PMNUM มีความยาวมากกว่า 30 ตัวอักษร
PO-02460-H34BBA50GS100-ME-C34 | LTK0 | 6.6 KV MV BREAKER - 652G | ACTIVE | LTK-H34BBA50GS100 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02460-H34BBA50GS100-ME-C34 |  | 2024-11-05 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 113 |  | H34BBA | 6.6 KV MV DISTRIBUTION BOARD | C34 | ME | H34BBA50 | GS | 6.6 KV MV DISTRIBUTION BOARD CUBICLE NO.5 | 6.6 KV MV BREAKER - 652G |  | 2024-11-05 | 16:00:00
PO-02380-H14BCY10GU205-ME-C14 | LTK0 | DS - 3WAY POSITION | ACTIVE | LTK-H14BCY10GU205 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02380-H14BCY10GU205-ME-C14 |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 114 |  | H14BCY | CONTROL AND PROTECTION EQUIPMENT | C14 | ME | H14BCY10 | GU | SFC REGULATE CONTROL | SFC DISCONNECTOR CUBICLE: 20LGS006AR |  | 2024-11-12 | 16:00:00
PO-02390-H14BCY10-ME-C14 | LTK0 | SFC REGULATE CONTROL | ACTIVE | LTK-H14BCY10 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02390-H14BCY10-ME-C14 |  | 2024-11-12 | MSP0-E250 | หรคฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 115 |  | H14BCY | CONTROL AND PROTECTION EQUIPMENT | C14 | ME | H14BCY10 |  | SFC REGULATE CONTROL | SFC REGULATE CONTROL |  | 2024-11-15 | 16:00:00
PO-02370-H14BCA10GU201-ME-C14 | LTK0 | DS - 89SFC | ACTIVE | LTK-H14BCA10GU201 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02370-H14BCA10GU201-ME-C14 |  | 2024-11-12 | MSP0-H020 | หปฟนม-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 116 |  | H14BCA | STATION 6.9 KV DISTRIBUTION BOARD CA | C14 | ME | H14BCA10 | GU | SFC DISTRIBUTION BOARD | SFC DS. CUBICLE: 20LGS008AR |  | 2024-11-12 | 16:00:00
PO-02070-H14ASU30GH101-ME-C14 | LTK0 | LCB/GIS, TRANSFORMER U #3 (KG3A) CUBICLE | ACTIVE | LTK-H14ASU30GH101 | APOO | AO2 | WSCH | O-LTKH03-67MI | O-LTKH03-67MI-WO | 4 | YEARS | JP-02070-H14ASU30GH101-ME-C14 |  | 2024-11-11 | MSP0-E840 | หอตฟ-ธ. | PTW งานเกี่ยวกับไฟฟ้า | 0 | 7 | 08:00:00 |  | 0 | 117 |  | H14ASU | LTK-H14ASU | C14 | ME | H14ASU30 | GH | LTK-H14ASU30 | LCB/GIS, TRANSFORMER U #3 (KG3A) CUBICLE |  | 2024-11-12 | 16:00:00