## Sheet1
JOB_NUM | ORGID | SITEID | PLUSCREVNUM | STATUS | EQUIPMENT | DURATION_TOTAL | TASK_ORDER_NEW | PLUSCJPREVNUM | DURATION_(HR.) | TASK_NEW | START_DATE | FINISH_DATE | GROUP | MOD | COMMENT
JP-00010-H04MFA60-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE SYSTEM | 3 | 10 | 0 | 0 | CLOSE DRAFT TUBE GATE AND WATER DRAIN | 2024-05-11 | 2024-05-11 | 1 | 1
JP-00010-H04MFA60-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE SYSTEM | 3 | 20 | 0 | 3 | OPEN DRAFT TUBE GATE AND FILL WATER | 2024-11-14 | 2024-11-14 | 1 | 1
JP-00020-H04L-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE (หบฟอ-ฟ) | 2 | 10 | 0 | 1 | CLOSE DRAFT TUBE GATE | 2024-11-05 | 2024-11-05 | 2 | 0
JP-00020-H04L-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE (หบฟอ-ฟ) | 2 | 20 | 0 | 1 | OPEN DRAFT TUBE GATE | 2024-11-14 | 2024-11-14 | 2 | 0
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 10 | 0 | 4 | DISASSEMBLY & REMOVE COVER PLATE | 2024-11-05 | 2024-11-05 | 3 | 1
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 20 | 0 | 7 | DISASSEMBLY & REMOVE FLOOR PLATE | 2024-11-05 | 2024-11-06 | 3 | 1
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 30 | 0 | 7 | ASSEMBLY FLOOR PLATE | 2024-11-12 | 2024-11-12 | 3 | 1
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 40 | 0 | 7 | ASSEMBLY COVER PLATE | 2024-11-13 | 2024-11-13 | 3 | 1
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 50 | 0 | 0.5 | VISUAL INSPECTION | 2024-11-12 | 2024-11-12 | 3 | 1
JP-00030-H04MLD20HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER BRACKET | 26.5 | 60 | 0 | 1 | CLEAN | 2024-11-12 | 2024-11-12 | 3 | 1
JP-00040-H04CMB10-ME-U | EGAT | LTK0 | 0 | ACTIVE | ต้องเปิดราวกันตก UPPER BRACKET Unit4 | 8 | 10 | 0 | 4 | ติดตั้งนั่งร้าน | 2024-11-05 | 2024-11-05 | 4 | 0
JP-00040-H04CMB10-ME-U | EGAT | LTK0 | 0 | ACTIVE | ต้องเปิดราวกันตก UPPER BRACKET Unit4 | 8 | 20 | 0 | 4 | รื้อถอน ราวกันตก | 2024-11-14 | 2024-11-14 | 4 | 0
JP-00050-H04MLV20AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | 1.1 | 10 | 0 | 0.15 | INSPECTION | 2024-11-05 | 2024-11-05 | 5 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | 1.1 | 20 | 0 | 0.15 | CLEANING | 2024-11-05 | 2024-11-05 | 5 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | 1.1 | 30 | 0 | 0.15 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 5 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | 1.1 | 40 | 0 | 0.15 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 5 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.1 - MLV20AP110 | 1.1 | 50 | 0 | 0.5 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 5 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | 1.1 | 10 | 0 | 0.15 | INSPECTION | 2024-11-05 | 2024-11-05 | 6 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | 1.1 | 20 | 0 | 0.15 | CLEANING | 2024-11-05 | 2024-11-05 | 6 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | 1.1 | 30 | 0 | 0.15 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 6 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | 1.1 | 40 | 0 | 0.15 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 6 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00050-H04MLV20AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL PUMP NO.2 - MLV20AP120 | 1.1 | 50 | 0 | 0.5 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 6 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00060-H04MLD20CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 7 | 1
JP-00060-H04MLD20CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 7 | 1
JP-00060-H04MLD20CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 7 | 1
JP-00060-H04MLD20CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 7 | 1
JP-00060-H04MLD20CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN LEVEL TRANSMITTER - CL010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 7 | 1
JP-00060-H04MLD20CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 8 | 0
JP-00060-H04MLD20CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 8 | 0
JP-00060-H04MLD20CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 8 | 0
JP-00060-H04MLD20CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 8 | 0
JP-00060-H04MLD20CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 8 | 0
JP-00060-H04MLD20CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER IN OIL RELAY | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 9 | 1
JP-00060-H04MLD20CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER IN OIL RELAY | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 9 | 1
JP-00060-H04MLD20CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER IN OIL RELAY | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 9 | 1
JP-00060-H04MLD20CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER IN OIL RELAY | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 9 | 1
JP-00060-H04MLD20CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER IN OIL RELAY | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 9 | 1
JP-00060-H04MLD20CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 10 | 0
JP-00060-H04MLD20CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 10 | 0
JP-00060-H04MLD20CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 10 | 0
JP-00060-H04MLD20CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 10 | 0
JP-00060-H04MLD20CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 10 | 0
JP-00060-H04MLD20CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 11 | 1
JP-00060-H04MLD20CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 11 | 1
JP-00060-H04MLD20CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 11 | 1
JP-00060-H04MLD20CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 11 | 1
JP-00060-H04MLD20CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 11 | 1
JP-00060-H04MLD20CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.3 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 12 | 0
JP-00060-H04MLD20CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.3 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 12 | 0
JP-00060-H04MLD20CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.3 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 12 | 0
JP-00060-H04MLD20CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.3 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 12 | 0
JP-00060-H04MLD20CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.3 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 12 | 0
JP-00060-H04MLD20CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.4 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 13 | 1
JP-00060-H04MLD20CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.4 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 13 | 1
JP-00060-H04MLD20CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.4 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 13 | 1
JP-00060-H04MLD20CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.4 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 13 | 1
JP-00060-H04MLD20CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.4 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 13 | 1
JP-00060-H04MLD20CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.5 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 14 | 0
JP-00060-H04MLD20CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.5 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 14 | 0
JP-00060-H04MLD20CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.5 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 14 | 0
JP-00060-H04MLD20CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.5 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 14 | 0
JP-00060-H04MLD20CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.5 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 14 | 0
JP-00060-H04MLD20CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.6 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 15 | 1
JP-00060-H04MLD20CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.6 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 15 | 1
JP-00060-H04MLD20CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.6 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 15 | 1
JP-00060-H04MLD20CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.6 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 15 | 1
JP-00060-H04MLD20CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.6 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 15 | 1
JP-00060-H04MLD20CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.7 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 16 | 0
JP-00060-H04MLD20CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.7 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 16 | 0
JP-00060-H04MLD20CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.7 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 16 | 0
JP-00060-H04MLD20CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.7 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 16 | 0
JP-00060-H04MLD20CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.7 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 16 | 0
JP-00060-H04MLD20CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.8 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 17 | 1
JP-00060-H04MLD20CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.8 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 17 | 1
JP-00060-H04MLD20CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.8 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 17 | 1
JP-00060-H04MLD20CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.8 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 17 | 1
JP-00060-H04MLD20CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.8 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 17 | 1
JP-00060-H04MLD20CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.10 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 18 | 0
JP-00060-H04MLD20CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.10 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 18 | 0
JP-00060-H04MLD20CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.10 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 18 | 0
JP-00060-H04MLD20CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.10 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 18 | 0
JP-00060-H04MLD20CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.10 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 18 | 0
JP-00060-H04MLD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.11 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 19 | 1
JP-00060-H04MLD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.11 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 19 | 1
JP-00060-H04MLD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.11 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 19 | 1
JP-00060-H04MLD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.11 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 19 | 1
JP-00060-H04MLD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.11 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 19 | 1
JP-00060-H04MLD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.12 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 20 | 0
JP-00060-H04MLD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.12 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 20 | 0
JP-00060-H04MLD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.12 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 20 | 0
JP-00060-H04MLD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.12 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 20 | 0
JP-00060-H04MLD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PAD TEMPERATURE RTD NO.12 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 20 | 0
JP-00060-H04MLD20CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR UGB PAD - CT100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 21 | 1
JP-00060-H04MLD20CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR UGB PAD - CT100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 21 | 1
JP-00060-H04MLD20CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR UGB PAD - CT100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 21 | 1
JP-00060-H04MLD20CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR UGB PAD - CT100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 21 | 1
JP-00060-H04MLD20CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR UGB PAD - CT100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 21 | 1
JP-00060-H04MLV20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 22 | 0
JP-00060-H04MLV20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 22 | 0
JP-00060-H04MLV20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 22 | 0
JP-00060-H04MLV20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 22 | 0
JP-00060-H04MLV20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 22 | 0
JP-00060-H04MLV20CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 23 | 1
JP-00060-H04MLV20CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 23 | 1
JP-00060-H04MLV20CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 23 | 1
JP-00060-H04MLV20CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 23 | 1
JP-00060-H04MLV20CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (UGB OIL FILTER) - CP100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 23 | 1
JP-00060-H04MLV20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 24 | 0
JP-00060-H04MLV20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 24 | 0
JP-00060-H04MLV20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 24 | 0
JP-00060-H04MLV20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 24 | 0
JP-00060-H04MLV20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE SWITCH - CP101 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 24 | 0
JP-00060-H04MLV20CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 25 | 1
JP-00060-H04MLV20CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 25 | 1
JP-00060-H04MLV20CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 25 | 1
JP-00060-H04MLV20CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 25 | 1
JP-00060-H04MLV20CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE SWITCH - CP102 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-06 | 25 | 1
JP-00070-H04MLV20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 26 | 0
JP-00070-H04MLV20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 26 | 0
JP-00070-H04MLV20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 26 | 0
JP-00070-H04MLV20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 26 | 0
JP-00070-H04MLV20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.1 PRESSURE GAUGE - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 26 | 0
JP-00070-H04MLV20CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 27 | 1
JP-00070-H04MLV20CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 27 | 1
JP-00070-H04MLV20CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 27 | 1
JP-00070-H04MLV20CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 27 | 1
JP-00070-H04MLV20CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB PUMP NO.2 PRESSURE GAUGE - CP302 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 27 | 1
JP-00070-H04MLV20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 28 | 0
JP-00070-H04MLV20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 28 | 0
JP-00070-H04MLV20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 28 | 0
JP-00070-H04MLV20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 28 | 0
JP-00070-H04MLV20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB OIL FILTER PRESSURE GAUGE - CP310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 28 | 0
JP-00070-H04MLV20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 29 | 1
JP-00070-H04MLV20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 29 | 1
JP-00070-H04MLV20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 29 | 1
JP-00070-H04MLV20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 29 | 1
JP-00070-H04MLV20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER UGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 29 | 1
JP-00070-H04PCM20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 30 | 0
JP-00070-H04PCM20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 30 | 0
JP-00070-H04PCM20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 30 | 0
JP-00070-H04PCM20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 30 | 0
JP-00070-H04PCM20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 30 | 0
JP-00070-H04PCM20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 31 | 1
JP-00070-H04PCM20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 31 | 1
JP-00070-H04PCM20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 31 | 1
JP-00070-H04PCM20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 31 | 1
JP-00070-H04PCM20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 31 | 1
JP-00070-H04PCM20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER RETURN PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 32 | 0
JP-00070-H04PCM20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER RETURN PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 32 | 0
JP-00070-H04PCM20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER RETURN PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 32 | 0
JP-00070-H04PCM20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER RETURN PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 32 | 0
JP-00070-H04PCM20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB WATER RETURN PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 32 | 0
JP-00080-H04PCM30CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER INLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 33 | 1
JP-00080-H04PCM30CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER INLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 33 | 1
JP-00080-H04PCM30CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER INLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 33 | 1
JP-00080-H04PCM30CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER INLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 33 | 1
JP-00080-H04PCM30CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER INLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 33 | 1
JP-00080-H04PCM30CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER INLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 34 | 0
JP-00080-H04PCM30CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER INLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 34 | 0
JP-00080-H04PCM30CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER INLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 34 | 0
JP-00080-H04PCM30CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER INLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 34 | 0
JP-00080-H04PCM30CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER INLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 34 | 0
JP-00080-H04PCM30CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER INLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 35 | 1
JP-00080-H04PCM30CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER INLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 35 | 1
JP-00080-H04PCM30CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER INLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 35 | 1
JP-00080-H04PCM30CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER INLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 35 | 1
JP-00080-H04PCM30CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER INLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 35 | 1
JP-00080-H04PCM30CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER INLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 36 | 0
JP-00080-H04PCM30CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER INLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 36 | 0
JP-00080-H04PCM30CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER INLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 36 | 0
JP-00080-H04PCM30CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER INLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 36 | 0
JP-00080-H04PCM30CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER INLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 36 | 0
JP-00080-H04PCM30CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER OUTLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 37 | 1
JP-00080-H04PCM30CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER OUTLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 37 | 1
JP-00080-H04PCM30CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER OUTLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 37 | 1
JP-00080-H04PCM30CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER OUTLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 37 | 1
JP-00080-H04PCM30CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | 1# AIR COOLER OUTLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 37 | 1
JP-00080-H04PCM30CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER OUTLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 38 | 0
JP-00080-H04PCM30CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER OUTLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 38 | 0
JP-00080-H04PCM30CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER OUTLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 38 | 0
JP-00080-H04PCM30CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER OUTLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 38 | 0
JP-00080-H04PCM30CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | 2# AIR COOLER OUTLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 38 | 0
JP-00080-H04PCM30CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER OUTLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 39 | 1
JP-00080-H04PCM30CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER OUTLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 39 | 1
JP-00080-H04PCM30CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER OUTLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 39 | 1
JP-00080-H04PCM30CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER OUTLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 39 | 1
JP-00080-H04PCM30CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | 3# AIR COOLER OUTLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 39 | 1
JP-00080-H04PCM30CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER OUTLET RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 40 | 0
JP-00080-H04PCM30CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER OUTLET RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 40 | 0
JP-00080-H04PCM30CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER OUTLET RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 40 | 0
JP-00080-H04PCM30CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER OUTLET RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 40 | 0
JP-00080-H04PCM30CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | 4# AIR COOLER OUTLET RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 40 | 0
JP-00080-H04PCM30CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER INLET | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 41 | 1
JP-00080-H04PCM30CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER INLET | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 41 | 1
JP-00080-H04PCM30CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER INLET | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 41 | 1
JP-00080-H04PCM30CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER INLET | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 41 | 1
JP-00080-H04PCM30CT100-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER INLET | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 41 | 1
JP-00080-H04PCM30CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER OUTLET | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 42 | 0
JP-00080-H04PCM30CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER OUTLET | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 42 | 0
JP-00080-H04PCM30CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER OUTLET | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 42 | 0
JP-00080-H04PCM30CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER OUTLET | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 42 | 0
JP-00080-H04PCM30CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR GENERATOR COOLING WATER OUTLET | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 42 | 0
JP-00080-H04PCM30CT200-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 43 | 1
JP-00080-H04PCM30CT200-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 43 | 1
JP-00080-H04PCM30CT200-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 43 | 1
JP-00080-H04PCM30CT200-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 43 | 1
JP-00080-H04PCM30CT200-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER COLD AIR | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 43 | 1
JP-00080-H04PCM30CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 44 | 0
JP-00080-H04PCM30CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 44 | 0
JP-00080-H04PCM30CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 44 | 0
JP-00080-H04PCM30CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 44 | 0
JP-00080-H04PCM30CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR GENERATOR COOLER HOT AIR | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 44 | 0
JP-00090-H04PCM30CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-09 | 2024-11-09 | 45 | 1
JP-00090-H04PCM30CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-09 | 2024-11-09 | 45 | 1
JP-00090-H04PCM30CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-09 | 45 | 1
JP-00090-H04PCM30CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-09 | 2024-11-09 | 45 | 1
JP-00090-H04PCM30CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | AIR COOLING WATER FLOW DETECTOR WITH CONTACT - CF100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-09 | 2024-11-09 | 45 | 1
JP-00090-H04PCM30CP300-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-09 | 2024-11-09 | 46 | 0
JP-00090-H04PCM30CP300-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-09 | 2024-11-09 | 46 | 0
JP-00090-H04PCM30CP300-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-09 | 46 | 0
JP-00090-H04PCM30CP300-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-09 | 2024-11-09 | 46 | 0
JP-00090-H04PCM30CP300-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER INLET PRESSURE GAUGE - CP300 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-09 | 2024-11-09 | 46 | 0
JP-00090-H04PCM30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-09 | 2024-11-09 | 47 | 1
JP-00090-H04PCM30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-09 | 2024-11-09 | 47 | 1
JP-00090-H04PCM30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-09 | 47 | 1
JP-00090-H04PCM30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-09 | 2024-11-09 | 47 | 1
JP-00090-H04PCM30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR COOLING WATER OUTLET PRESSURE GAUGE - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-09 | 2024-11-09 | 47 | 1
JP-00100-H04MLV10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 48 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 48 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-10 | 2024-11-10 | 48 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 48 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.1 - MLV10AP110 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-10 | 2024-11-10 | 48 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 49 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 49 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-10 | 2024-11-10 | 49 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 49 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00100-H04MLV10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL PUMP NO.2 - MLV10AP120 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-10 | 2024-11-10 | 49 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00110-H04MLD10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER BRACKET | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 50 | 0
JP-00110-H04MLD10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER BRACKET | 2 | 20 | 0 | 1 | CLEAN | 2024-11-12 | 2024-11-12 | 50 | 0
JP-00120-H04MLD10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 51 | 1
JP-00120-H04MLD10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 51 | 1
JP-00120-H04MLD10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 51 | 1
JP-00120-H04MLD10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 51 | 1
JP-00120-H04MLD10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN LEVEL TRANSMITTER - CL010 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 51 | 1
JP-00120-H04MLD10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 52 | 0
JP-00120-H04MLD10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 52 | 0
JP-00120-H04MLD10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 52 | 0
JP-00120-H04MLD10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 52 | 0
JP-00120-H04MLD10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL PAN MAGNETIC LEVEL INDICATOR - CL310 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 52 | 0
JP-00120-H04MLD10CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER IN OIL RELAY | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 53 | 1
JP-00120-H04MLD10CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER IN OIL RELAY | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 53 | 1
JP-00120-H04MLD10CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER IN OIL RELAY | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 53 | 1
JP-00120-H04MLD10CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER IN OIL RELAY | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 53 | 1
JP-00120-H04MLD10CM105-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER IN OIL RELAY | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 53 | 1
JP-00120-H04MLD10CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.1 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 54 | 0
JP-00120-H04MLD10CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.1 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 54 | 0
JP-00120-H04MLD10CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.1 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 54 | 0
JP-00120-H04MLD10CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.1 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 54 | 0
JP-00120-H04MLD10CT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.1 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 54 | 0
JP-00120-H04MLD10CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.3 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 55 | 1
JP-00120-H04MLD10CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.3 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 55 | 1
JP-00120-H04MLD10CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.3 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 55 | 1
JP-00120-H04MLD10CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.3 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 55 | 1
JP-00120-H04MLD10CT002-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.3 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 55 | 1
JP-00120-H04MLD10CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.5 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 56 | 0
JP-00120-H04MLD10CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.5 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 56 | 0
JP-00120-H04MLD10CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.5 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 56 | 0
JP-00120-H04MLD10CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.5 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 56 | 0
JP-00120-H04MLD10CT003-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.5 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 56 | 0
JP-00120-H04MLD10CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.7 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 57 | 1
JP-00120-H04MLD10CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.7 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 57 | 1
JP-00120-H04MLD10CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.7 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 57 | 1
JP-00120-H04MLD10CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.7 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 57 | 1
JP-00120-H04MLD10CT004-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.7 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 57 | 1
JP-00120-H04MLD10CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.9 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 58 | 0
JP-00120-H04MLD10CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.9 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 58 | 0
JP-00120-H04MLD10CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.9 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 58 | 0
JP-00120-H04MLD10CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.9 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 58 | 0
JP-00120-H04MLD10CT005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.9 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 58 | 0
JP-00120-H04MLD10CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.11 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 59 | 1
JP-00120-H04MLD10CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.11 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 59 | 1
JP-00120-H04MLD10CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.11 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 59 | 1
JP-00120-H04MLD10CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.11 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 59 | 1
JP-00120-H04MLD10CT006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.11 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 59 | 1
JP-00120-H04MLD10CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.13 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 60 | 0
JP-00120-H04MLD10CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.13 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 60 | 0
JP-00120-H04MLD10CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.13 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 60 | 0
JP-00120-H04MLD10CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.13 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 60 | 0
JP-00120-H04MLD10CT007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.13 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 60 | 0
JP-00120-H04MLD10CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.15 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 61 | 1
JP-00120-H04MLD10CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.15 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 61 | 1
JP-00120-H04MLD10CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.15 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 61 | 1
JP-00120-H04MLD10CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.15 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 61 | 1
JP-00120-H04MLD10CT008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.15 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 61 | 1
JP-00120-H04MLD10CT009-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.17 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 62 | 0
JP-00120-H04MLD10CT009-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.17 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 62 | 0
JP-00120-H04MLD10CT009-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.17 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 62 | 0
JP-00120-H04MLD10CT009-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.17 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 62 | 0
JP-00120-H04MLD10CT009-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.17 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 62 | 0
JP-00120-H04MLD10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.19 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 63 | 1
JP-00120-H04MLD10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.19 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 63 | 1
JP-00120-H04MLD10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.19 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 63 | 1
JP-00120-H04MLD10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.19 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 63 | 1
JP-00120-H04MLD10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.19 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 63 | 1
JP-00120-H04MLD10CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.21 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 64 | 0
JP-00120-H04MLD10CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.21 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 64 | 0
JP-00120-H04MLD10CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.21 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 64 | 0
JP-00120-H04MLD10CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.21 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 64 | 0
JP-00120-H04MLD10CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.21 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 64 | 0
JP-00120-H04MLD10CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.23 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 65 | 1
JP-00120-H04MLD10CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.23 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 65 | 1
JP-00120-H04MLD10CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.23 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 65 | 1
JP-00120-H04MLD10CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.23 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 65 | 1
JP-00120-H04MLD10CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | LGB PAD TEMPERATURE RTD NO.23 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 65 | 1
JP-00120-H04MLD10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR LGB PAD - CT110 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 66 | 0
JP-00120-H04MLD10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR LGB PAD - CT110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 66 | 0
JP-00120-H04MLD10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR LGB PAD - CT110 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 66 | 0
JP-00120-H04MLD10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR LGB PAD - CT110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 66 | 0
JP-00120-H04MLD10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR LGB PAD - CT110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 66 | 0
JP-00120-H04MLV10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 67 | 1
JP-00120-H04MLV10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 67 | 1
JP-00120-H04MLV10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 67 | 1
JP-00120-H04MLV10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 67 | 1
JP-00120-H04MLV10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB OIL FLOW DETECTOR WITH CONTACT - CF100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 67 | 1
JP-00120-H04MLV10CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 68 | 0
JP-00120-H04MLV10CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 68 | 0
JP-00120-H04MLV10CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 68 | 0
JP-00120-H04MLV10CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 68 | 0
JP-00120-H04MLV10CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (CGB OIL FILTER) - CP100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 68 | 0
JP-00120-H04MLV10CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 69 | 1
JP-00120-H04MLV10CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 69 | 1
JP-00120-H04MLV10CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 69 | 1
JP-00120-H04MLV10CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 69 | 1
JP-00120-H04MLV10CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 69 | 1
JP-00120-H04MLV10CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 70 | 0
JP-00120-H04MLV10CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 70 | 0
JP-00120-H04MLV10CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 70 | 0
JP-00120-H04MLV10CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 70 | 0
JP-00120-H04MLV10CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE SWITCH - CP102 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 70 | 0
JP-00130-H04MLV10CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 71 | 1
JP-00130-H04MLV10CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 71 | 1
JP-00130-H04MLV10CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 71 | 1
JP-00130-H04MLV10CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 71 | 1
JP-00130-H04MLV10CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.1 PRESSURE GAUGE - CP301 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 71 | 1
JP-00130-H04MLV10CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 72 | 0
JP-00130-H04MLV10CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 72 | 0
JP-00130-H04MLV10CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 72 | 0
JP-00130-H04MLV10CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 72 | 0
JP-00130-H04MLV10CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB PUMP NO.2 PRESSURE GAUGE - CP302 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 72 | 0
JP-00130-H04MLV10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 73 | 1
JP-00130-H04MLV10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 73 | 1
JP-00130-H04MLV10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 73 | 1
JP-00130-H04MLV10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 73 | 1
JP-00130-H04MLV10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB OIL FILTER PRESSURE GAUGE - CP310 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 73 | 1
JP-00130-H04MLV10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 74 | 0
JP-00130-H04MLV10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 74 | 0
JP-00130-H04MLV10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 74 | 0
JP-00130-H04MLV10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 74 | 0
JP-00130-H04MLV10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CGB HEAT EXCHANGER PRESSURE GAUGE - CP320 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 74 | 0
JP-00130-H04PCM10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 75 | 1
JP-00130-H04PCM10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 75 | 1
JP-00130-H04PCM10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 75 | 1
JP-00130-H04PCM10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 75 | 1
JP-00130-H04PCM10CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 75 | 1
JP-00130-H04PCM10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 76 | 0
JP-00130-H04PCM10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 76 | 0
JP-00130-H04PCM10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 76 | 0
JP-00130-H04PCM10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 76 | 0
JP-00130-H04PCM10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 76 | 0
JP-00130-H04PCM10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 77 | 1
JP-00130-H04PCM10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 77 | 1
JP-00130-H04PCM10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 77 | 1
JP-00130-H04PCM10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 77 | 1
JP-00130-H04PCM10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | CGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 77 | 1
JP-00140-H04MLV40AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 78 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 78 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-10 | 2024-11-10 | 78 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 78 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.1 - MLV40AP110 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-10 | 2024-11-10 | 78 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 79 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 79 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-10 | 2024-11-10 | 79 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 79 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00140-H04MLV40AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR HPO PUMP NO.2 - MLV40AP120 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-10 | 2024-11-10 | 79 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00150-H04MLV40CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 80 | 0
JP-00150-H04MLV40CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 80 | 0
JP-00150-H04MLV40CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 80 | 0
JP-00150-H04MLV40CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 80 | 0
JP-00150-H04MLV40CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPOS FLOW DETECTOR WITH CONTACT - CF100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 80 | 0
JP-00150-H04MLV40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 81 | 1
JP-00150-H04MLV40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 81 | 1
JP-00150-H04MLV40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 81 | 1
JP-00150-H04MLV40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 81 | 1
JP-00150-H04MLV40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (HPOS OIL FILTER) - CP100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 81 | 1
JP-00150-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 82 | 0
JP-00150-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 82 | 0
JP-00150-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 82 | 0
JP-00150-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 82 | 0
JP-00150-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 82 | 0
JP-00150-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 83 | 1
JP-00150-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 83 | 1
JP-00150-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 83 | 1
JP-00150-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 83 | 1
JP-00150-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 83 | 1
JP-00160-H04MLV40CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 3 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 84 | 0
JP-00160-H04MLV40CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 3 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 84 | 0
JP-00160-H04MLV40CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 3 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 84 | 0
JP-00160-H04MLV40CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 3 | 40 | 0 | 0.5 | CALIBRATION | 2024-11-10 | 2024-11-10 | 84 | 0
JP-00160-H04MLV40CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE GAUGE - CP301 | 3 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 84 | 0
JP-00160-H04MLV40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 3 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 85 | 1
JP-00160-H04MLV40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 3 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 85 | 1
JP-00160-H04MLV40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 3 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 85 | 1
JP-00160-H04MLV40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 3 | 40 | 0 | 0.5 | CALIBRATION | 2024-11-10 | 2024-11-10 | 85 | 1
JP-00160-H04MLV40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER HPOS OIL FILTER PRESSURE GAUGE - CP310 | 3 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 85 | 1
JP-00160-H04MLV40CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 3 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 86 | 0
JP-00160-H04MLV40CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 3 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 86 | 0
JP-00160-H04MLV40CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 3 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 86 | 0
JP-00160-H04MLV40CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 3 | 40 | 0 | 0.5 | CALIBRATION | 2024-11-10 | 2024-11-10 | 86 | 0
JP-00160-H04MLV40CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE GAUGE - CP311 | 3 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 86 | 0
JP-00170-H04MLA50AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 87 | 1
JP-00170-H04MLA50AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 87 | 1
JP-00170-H04MLA50AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 87 | 1
JP-00170-H04MLA50AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 87 | 1
JP-00170-H04MLA50AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 87 | 1
JP-00170-H04MLA50AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 88 | 0
JP-00170-H04MLA50AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 88 | 0
JP-00170-H04MLA50AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 88 | 0
JP-00170-H04MLA50AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 88 | 0
JP-00170-H04MLA50AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 88 | 0
JP-00170-H04MLA50AP012-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 89 | 1
JP-00170-H04MLA50AP012-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 89 | 1
JP-00170-H04MLA50AP012-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 89 | 1
JP-00170-H04MLA50AP012-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 89 | 1
JP-00170-H04MLA50AP012-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 89 | 1
JP-00170-H04MLA50AP013-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 90 | 0
JP-00170-H04MLA50AP013-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 90 | 0
JP-00170-H04MLA50AP013-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 90 | 0
JP-00170-H04MLA50AP013-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 90 | 0
JP-00170-H04MLA50AP013-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 90 | 0
JP-00170-H04MLA50AP014-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 91 | 1
JP-00170-H04MLA50AP014-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 91 | 1
JP-00170-H04MLA50AP014-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 91 | 1
JP-00170-H04MLA50AP014-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 91 | 1
JP-00170-H04MLA50AP014-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 91 | 1
JP-00170-H04MLA50AP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (G) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 92 | 0
JP-00170-H04MLA50AP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (G) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 92 | 0
JP-00170-H04MLA50AP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (G) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 92 | 0
JP-00170-H04MLA50AP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (G) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 92 | 0
JP-00170-H04MLA50AP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (G) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 92 | 0
JP-00170-H04MLA50AP016-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 93 | 1
JP-00170-H04MLA50AP016-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 93 | 1
JP-00170-H04MLA50AP016-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 93 | 1
JP-00170-H04MLA50AP016-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 93 | 1
JP-00170-H04MLA50AP016-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.1 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 93 | 1
JP-00170-H04MLA50AP017-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 94 | 0
JP-00170-H04MLA50AP017-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 94 | 0
JP-00170-H04MLA50AP017-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 94 | 0
JP-00170-H04MLA50AP017-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 94 | 0
JP-00170-H04MLA50AP017-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.2 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 94 | 0
JP-00170-H04MLA50AP018-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 95 | 1
JP-00170-H04MLA50AP018-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 95 | 1
JP-00170-H04MLA50AP018-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 95 | 1
JP-00170-H04MLA50AP018-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 95 | 1
JP-00170-H04MLA50AP018-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.3 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 95 | 1
JP-00170-H04MLA50AP019-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 96 | 0
JP-00170-H04MLA50AP019-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 96 | 0
JP-00170-H04MLA50AP019-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 96 | 0
JP-00170-H04MLA50AP019-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 96 | 0
JP-00170-H04MLA50AP019-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.4 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 96 | 0
JP-00170-H04MLA50AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 97 | 1
JP-00170-H04MLA50AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 97 | 1
JP-00170-H04MLA50AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 97 | 1
JP-00170-H04MLA50AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 97 | 1
JP-00170-H04MLA50AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.5 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 97 | 1
JP-00170-H04MLA50AP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (M) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 98 | 0
JP-00170-H04MLA50AP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (M) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 98 | 0
JP-00170-H04MLA50AP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (M) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 98 | 0
JP-00170-H04MLA50AP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (M) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 98 | 0
JP-00170-H04MLA50AP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKING DUS COLLECTOR NO.6 (M) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 98 | 0
JP-00170-H04MLA50CG201-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 99 | 1
JP-00170-H04MLA50CG201-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 99 | 1
JP-00170-H04MLA50CG201-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 99 | 1
JP-00170-H04MLA50CG201-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 99 | 1
JP-00170-H04MLA50CG201-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 99 | 1
JP-00170-H04MLA50CG202-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 100 | 0
JP-00170-H04MLA50CG202-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 100 | 0
JP-00170-H04MLA50CG202-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 100 | 0
JP-00170-H04MLA50CG202-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 100 | 0
JP-00170-H04MLA50CG202-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 100 | 0
JP-00170-H04MLA50CG203-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 101 | 1
JP-00170-H04MLA50CG203-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 101 | 1
JP-00170-H04MLA50CG203-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 101 | 1
JP-00170-H04MLA50CG203-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 101 | 1
JP-00170-H04MLA50CG203-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 101 | 1
JP-00170-H04MLA50CG204-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 102 | 0
JP-00170-H04MLA50CG204-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 102 | 0
JP-00170-H04MLA50CG204-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 102 | 0
JP-00170-H04MLA50CG204-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 102 | 0
JP-00170-H04MLA50CG204-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 102 | 0
JP-00170-H04MLA50CG205-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 103 | 1
JP-00170-H04MLA50CG205-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 103 | 1
JP-00170-H04MLA50CG205-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 103 | 1
JP-00170-H04MLA50CG205-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 103 | 1
JP-00170-H04MLA50CG205-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 103 | 1
JP-00170-H04MLA50CG206-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 104 | 0
JP-00170-H04MLA50CG206-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 104 | 0
JP-00170-H04MLA50CG206-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 104 | 0
JP-00170-H04MLA50CG206-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 104 | 0
JP-00170-H04MLA50CG206-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - ON DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 104 | 0
JP-00170-H04MLA50CG211-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 105 | 1
JP-00170-H04MLA50CG211-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 105 | 1
JP-00170-H04MLA50CG211-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 105 | 1
JP-00170-H04MLA50CG211-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 105 | 1
JP-00170-H04MLA50CG211-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 1 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 105 | 1
JP-00170-H04MLA50CG212-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 106 | 0
JP-00170-H04MLA50CG212-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 106 | 0
JP-00170-H04MLA50CG212-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 106 | 0
JP-00170-H04MLA50CG212-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 106 | 0
JP-00170-H04MLA50CG212-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 2 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 106 | 0
JP-00170-H04MLA50CG213-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 107 | 1
JP-00170-H04MLA50CG213-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 107 | 1
JP-00170-H04MLA50CG213-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 107 | 1
JP-00170-H04MLA50CG213-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 107 | 1
JP-00170-H04MLA50CG213-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 3 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 107 | 1
JP-00170-H04MLA50CG214-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 108 | 0
JP-00170-H04MLA50CG214-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 108 | 0
JP-00170-H04MLA50CG214-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 108 | 0
JP-00170-H04MLA50CG214-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 108 | 0
JP-00170-H04MLA50CG214-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 4 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 108 | 0
JP-00170-H04MLA50CG215-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 109 | 1
JP-00170-H04MLA50CG215-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 109 | 1
JP-00170-H04MLA50CG215-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 109 | 1
JP-00170-H04MLA50CG215-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 109 | 1
JP-00170-H04MLA50CG215-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 5 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 109 | 1
JP-00170-H04MLA50CG216-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 110 | 0
JP-00170-H04MLA50CG216-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 110 | 0
JP-00170-H04MLA50CG216-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 110 | 0
JP-00170-H04MLA50CG216-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 110 | 0
JP-00170-H04MLA50CG216-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKING 6 LIMIT SWITCH - OFF DETECT | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 110 | 0
JP-00170-H04MLA50CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 111 | 1
JP-00170-H04MLA50CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 111 | 1
JP-00170-H04MLA50CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 111 | 1
JP-00170-H04MLA50CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 111 | 1
JP-00170-H04MLA50CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE INLET PRESSURE SWITCH - CP101 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 111 | 1
JP-00170-H04MLA50CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 112 | 0
JP-00170-H04MLA50CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 112 | 0
JP-00170-H04MLA50CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 112 | 0
JP-00170-H04MLA50CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 112 | 0
JP-00170-H04MLA50CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC BREAKE OUTLET PRESSURE SWITCH - CP102 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 112 | 0
JP-00180-H04MLA50CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 113 | 1
JP-00180-H04MLA50CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 113 | 1
JP-00180-H04MLA50CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 113 | 1
JP-00180-H04MLA50CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 113 | 1
JP-00180-H04MLA50CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP301 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 113 | 1
JP-00180-H04MLA50CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 114 | 0
JP-00180-H04MLA50CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 114 | 0
JP-00180-H04MLA50CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 114 | 0
JP-00180-H04MLA50CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-10 | 2024-11-10 | 114 | 0
JP-00180-H04MLA50CP302-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANIC AIR INLET PRESSURE GAUGE - CP302 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 114 | 0
JP-00190-H04MLA60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR UGB OIL MIST EXHAUST - MLA60AP110 | 0.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-09 | 2024-11-09 | 115 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00200-H04MLV70AP010-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL MIST EXHAUST - MLV70AP010 | 3 | 10 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-09 | 116 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00200-H04MLV70AP010-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL MIST EXHAUST - MLV70AP010 | 3 | 20 | 0 | 0.5 | RETIGHTENING | 2024-11-09 | 2024-11-09 | 116 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00200-H04MLV70AP010-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL MIST EXHAUST - MLV70AP010 | 3 | 30 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-09 | 2024-11-09 | 116 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00200-H04MLV70AP010-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR CGB OIL MIST EXHAUST - MLV70AP010 | 3 | 40 | 0 | 1 | FUNCTION TEST | 2024-11-09 | 2024-11-09 | 116 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00210-H04MLD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PAN | 32 | 10 | 0 | 30 | OIL PURIFY | 2024-11-05 | 2024-11-07 | 117 | 1
JP-00210-H04MLD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PAN | 32 | 20 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-07 | 117 | 1
JP-00220-H04MLV20AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 118 | 0
JP-00220-H04MLV20AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 118 | 0
JP-00220-H04MLV20AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.1 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 118 | 0
JP-00220-H04MLV20AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.1 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 118 | 0
JP-00230-H04MLV20AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 119 | 1
JP-00230-H04MLV20AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 119 | 1
JP-00230-H04MLV20AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.2 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 119 | 1
JP-00230-H04MLV20AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL PUMP NO.2 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 119 | 1
JP-00240-H04MLV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.1 | 10 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 120 | 0
JP-00240-H04MLV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.1 | 10 | 20 | 0 | 5 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 120 | 0
JP-00240-H04MLV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.1 | 10 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-07 | 2024-11-07 | 120 | 0
JP-00250-H04MLV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.2 | 10 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-08 | 2024-11-08 | 121 | 1
JP-00250-H04MLV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.2 | 10 | 20 | 0 | 5 | ASSEMBLY | 2024-11-08 | 2024-11-09 | 121 | 1
JP-00250-H04MLV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | UGB OIL COOLER NO.2 | 10 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-09 | 2024-11-09 | 121 | 1
JP-00260-H04MLD10BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PAN | 52 | 10 | 0 | 50 | OIL PURIFY | 2024-11-08 | 2024-11-12 | 122 | 0
JP-00260-H04MLD10BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PAN | 52 | 20 | 0 | 2 | INSPECTION | 2024-11-08 | 2024-11-12 | 122 | 0
JP-00270-H04MLV10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 123 | 1
JP-00270-H04MLV10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 123 | 1
JP-00270-H04MLV10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 123 | 1
JP-00270-H04MLV10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 123 | 1
JP-00280-H04MLV10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 124 | 0
JP-00280-H04MLV10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 124 | 0
JP-00280-H04MLV10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 124 | 0
JP-00280-H04MLV10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 124 | 0
JP-00290-H04MLV10AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL COOLER NO.1 | 7 | 10 | 0 | 7 | INSPECTION & HYDROSTATIC TEST | 2024-11-09 | 2024-11-09 | 125 | 1
JP-00300-H04MLV10AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL COOLER NO.2 | 28 | 10 | 0 | 21 | DISASSEMBLY | 2024-11-09 | 2024-11-11 | 126 | 0
JP-00300-H04MLV10AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL COOLER NO.2 | 28 | 20 | 0 | 7 | CLEAN | 2024-11-12 | 2024-11-12 | 126 | 0
JP-00310-H04MLV40AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 127 | 1
JP-00310-H04MLV40AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 127 | 1
JP-00310-H04MLV40AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.1 | 0.3 | 30 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 127 | 1
JP-00310-H04MLV40AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.1 | 0.3 | 40 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 127 | 1
JP-00320-H04MLV40AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECT | 2024-11-05 | 2024-11-05 | 128 | 0
JP-00320-H04MLV40AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 128 | 0
JP-00320-H04MLV40AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.2 | 0.3 | 30 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 128 | 0
JP-00320-H04MLV40AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL LIFTING PUMP NO.2 | 0.3 | 40 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 128 | 0
JP-00330-H04MLA50-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKE (ROUTE) | 4 | 10 | 0 | 2 | BRAKE TRACK INSPECT | 2024-11-12 | 2024-11-12 | 129 | 1
JP-00330-H04MLA50-ME-U | EGAT | LTK0 | 0 | ACTIVE | MECHANICAL BRAKE (ROUTE) | 4 | 20 | 0 | 2 | BRAKE SHOE INSPECT | 2024-11-12 | 2024-11-12 | 129 | 1
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 10 | 0 | 14 | DISASSEMBLY & REMOVE | 2024-11-06 | 2024-11-07 | 130 | 0
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 20 | 0 | 3 | INSPECTION | 2024-11-08 | 2024-11-10 | 130 | 0
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 30 | 0 | 18 | CLEAN | 2024-11-08 | 2024-11-10 | 130 | 0
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 40 | 0 | 12 | HYDROSTATIC TEST | 2024-11-08 | 2024-10-10 | 130 | 0
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 50 | 0 | 14 | ASSEMBLY | 2024-11-11 | 2024-11-12 | 130 | 0
JP-00340-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 63 | 60 | 0 | 2 | LEAKAGE CHECK | 2024-11-14 | 2024-11-14 | 130 | 0
JP-00350-H04MLA60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 131 | 1
JP-00350-H04MLA60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 20 | 0 | 1.5 | FILTER REPLACE | 2024-11-11 | 2024-11-11 | 131 | 1
JP-00350-H04MLA60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 30 | 0 | 0.1 | VIBRATION MEASUREMENT | 2024-11-05 | 2024-11-05 | 131 | 1
JP-00350-H04MLA60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 40 | 0 | 1 | OPERATE TEST | 2024-11-05 | 2024-11-11 | 131 | 1
JP-00360-H04MLV70AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 132 | 0
JP-00360-H04MLV70AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 20 | 0 | 1.5 | FILTER REPLACE | 2024-11-11 | 2024-11-11 | 132 | 0
JP-00360-H04MLV70AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 30 | 0 | 0.1 | VIBRATION MEASUREMENT | 2024-11-05 | 2024-11-05 | 132 | 0
JP-00360-H04MLV70AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | COMBINE GUIDE BEARING OIL MIST SEPERATOR | 3.1 | 40 | 0 | 1 | OPERATE TEST | 2024-11-05 | 2024-11-11 | 132 | 0
JP-00370-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 10 | 10 | 0 | 2 | OPEN MANHOLE | 2024-11-05 | 2024-11-05 | 133 | 1
JP-00370-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 10 | 20 | 0 | 2 | INSPECTION | 2024-11-06 | 2024-11-06 | 133 | 1
JP-00370-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 10 | 30 | 0 | 1 | CLEAN | 2024-11-13 | 2024-11-13 | 133 | 1
JP-00370-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 10 | 40 | 0 | 4 | CLOSE MANHOLE | 2024-11-13 | 2024-11-13 | 133 | 1
JP-00370-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 10 | 50 | 0 | 1 | LEAKAGE CHECK | 2024-11-14 | 2024-11-14 | 133 | 1
JP-00380-H04MFA10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPIRAL CASE | 24 | 10 | 0 | 24 | REPAIRING | 2024-11-08 | 2024-11-11 | 134 | 0
JP-00390-H04MFA10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE TRANSDUCER - CP020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 135 | 1
JP-00390-H04MFA10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE TRANSDUCER - CP020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 135 | 1
JP-00390-H04MFA10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE TRANSDUCER - CP020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 135 | 1
JP-00390-H04MFA10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE TRANSDUCER - CP020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 135 | 1
JP-00390-H04MFA10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE TRANSDUCER - CP020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 135 | 1
JP-00390-H04MFA20CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 136 | 0
JP-00390-H04MFA20CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 136 | 0
JP-00390-H04MFA20CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 136 | 0
JP-00390-H04MFA20CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 136 | 0
JP-00390-H04MFA20CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE TRANSDUCER - CP010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 136 | 0
JP-00390-H04MFA20CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 137 | 1
JP-00390-H04MFA20CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 137 | 1
JP-00390-H04MFA20CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 137 | 1
JP-00390-H04MFA20CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 137 | 1
JP-00390-H04MFA20CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM RING PRESSURE TRANSDUCER - CP020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 137 | 1
JP-00390-H04MFA20CP105-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE SWITCH - CP105 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 138 | 0
JP-00390-H04MFA20CP105-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE SWITCH - CP105 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 138 | 0
JP-00390-H04MFA20CP105-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE SWITCH - CP105 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 138 | 0
JP-00390-H04MFA20CP105-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE SWITCH - CP105 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 138 | 0
JP-00390-H04MFA20CP105-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE SWITCH - CP105 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 138 | 0
JP-00390-H04MFA30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 139 | 1
JP-00390-H04MFA30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 139 | 1
JP-00390-H04MFA30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 139 | 1
JP-00390-H04MFA30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 139 | 1
JP-00390-H04MFA30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 139 | 1
JP-00390-H04MFA30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 140 | 0
JP-00390-H04MFA30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 140 | 0
JP-00390-H04MFA30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 140 | 0
JP-00390-H04MFA30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 140 | 0
JP-00390-H04MFA30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 140 | 0
JP-00390-H04MFA30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 141 | 1
JP-00390-H04MFA30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 141 | 1
JP-00390-H04MFA30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 141 | 1
JP-00390-H04MFA30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 141 | 1
JP-00390-H04MFA30CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE WEARING RING PRESSURE TRANSDUCER - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 141 | 1
JP-00390-H04MFA30CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 142 | 0
JP-00390-H04MFA30CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 142 | 0
JP-00390-H04MFA30CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 142 | 0
JP-00390-H04MFA30CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 142 | 0
JP-00390-H04MFA30CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER WEARING RING PRESSURE TRANSDUCER - CP311 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 142 | 0
JP-00390-H04MFA60CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 143 | 1
JP-00390-H04MFA60CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 143 | 1
JP-00390-H04MFA60CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 143 | 1
JP-00390-H04MFA60CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 143 | 1
JP-00390-H04MFA60CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE TRANSDUCER - CP020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 143 | 1
JP-00390-H04MFA60CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE TRANSDUCER - CP030 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-14 | 144 | 0
JP-00390-H04MFA60CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE TRANSDUCER - CP030 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-14 | 144 | 0
JP-00390-H04MFA60CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE TRANSDUCER - CP030 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-14 | 144 | 0
JP-00390-H04MFA60CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE TRANSDUCER - CP030 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-14 | 144 | 0
JP-00390-H04MFA60CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE TRANSDUCER - CP030 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-14 | 144 | 0
JP-00400-H04MFA10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE GAUGE - CP311 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 145 | 1
JP-00400-H04MFA10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE GAUGE - CP311 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 145 | 1
JP-00400-H04MFA10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE GAUGE - CP311 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 145 | 1
JP-00400-H04MFA10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE GAUGE - CP311 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 145 | 1
JP-00400-H04MFA10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | SC INLET PRESSURE GAUGE - CP311 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 145 | 1
JP-00400-H04MFA20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE GAUGE - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 146 | 0
JP-00400-H04MFA20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE GAUGE - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 146 | 0
JP-00400-H04MFA20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE GAUGE - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 146 | 0
JP-00400-H04MFA20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE GAUGE - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 146 | 0
JP-00400-H04MFA20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | VANELESS AREA PRESSURE GAUGE - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 146 | 0
JP-00400-H04MFA60CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 147 | 1
JP-00400-H04MFA60CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 147 | 1
JP-00400-H04MFA60CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 147 | 1
JP-00400-H04MFA60CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 147 | 1
JP-00400-H04MFA60CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 147 | 1
JP-00400-H04MFA60CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 148 | 0
JP-00400-H04MFA60CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 148 | 0
JP-00400-H04MFA60CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 148 | 0
JP-00400-H04MFA60CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 148 | 0
JP-00400-H04MFA60CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PUMP MODE WINTER-KENNEDY PRESSURE GAUGE - CP311 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 148 | 0
JP-00400-H04MFA60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE GAUGE - CP321 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 149 | 1
JP-00400-H04MFA60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE GAUGE - CP321 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 149 | 1
JP-00400-H04MFA60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE GAUGE - CP321 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 149 | 1
JP-00400-H04MFA60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE GAUGE - CP321 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 149 | 1
JP-00400-H04MFA60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT OUTLET PRESSURE GAUGE - CP321 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 149 | 1
JP-00400-H04MFA60CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-07 | 150 | 0
JP-00400-H04MFA60CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 150 | 0
JP-00400-H04MFA60CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-07 | 150 | 0
JP-00400-H04MFA60CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-07 | 150 | 0
JP-00400-H04MFA60CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT MANDOOR BOTTOM PRESSURE GAUGE - CP331 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-07 | 150 | 0
JP-00410-H04MFA20CG001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 151 | 1
JP-00410-H04MFA20CG001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 151 | 1
JP-00410-H04MFA20CG001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 151 | 1
JP-00410-H04MFA20CG001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 151 | 1
JP-00410-H04MFA20CG001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 151 | 1
JP-00410-H04MFA20CG002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 152 | 0
JP-00410-H04MFA20CG002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 152 | 0
JP-00410-H04MFA20CG002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 152 | 0
JP-00410-H04MFA20CG002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 152 | 0
JP-00410-H04MFA20CG002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION - DISPLACEMENT SENSOR NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 152 | 0
JP-00410-H04MFA20CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 153 | 1
JP-00410-H04MFA20CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 153 | 1
JP-00410-H04MFA20CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 153 | 1
JP-00410-H04MFA20CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 153 | 1
JP-00410-H04MFA20CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK OFF | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 153 | 1
JP-00410-H04MFA20CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 154 | 0
JP-00410-H04MFA20CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 154 | 0
JP-00410-H04MFA20CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 154 | 0
JP-00410-H04MFA20CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 154 | 0
JP-00410-H04MFA20CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - MANUAL LOCK ON | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 154 | 0
JP-00410-H04MFA20CG123-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 155 | 1
JP-00410-H04MFA20CG123-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 155 | 1
JP-00410-H04MFA20CG123-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 155 | 1
JP-00410-H04MFA20CG123-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 155 | 1
JP-00410-H04MFA20CG123-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK ON | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 155 | 1
JP-00410-H04MFA20CG124-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 156 | 0
JP-00410-H04MFA20CG124-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 156 | 0
JP-00410-H04MFA20CG124-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 156 | 0
JP-00410-H04MFA20CG124-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 156 | 0
JP-00410-H04MFA20CG124-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - MANUAL LOCK OFF | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 156 | 0
JP-00410-H04MFA20CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 157 | 1
JP-00410-H04MFA20CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 157 | 1
JP-00410-H04MFA20CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 157 | 1
JP-00410-H04MFA20CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 157 | 1
JP-00410-H04MFA20CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK OFF | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 157 | 1
JP-00410-H04MFA20CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 158 | 0
JP-00410-H04MFA20CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 158 | 0
JP-00410-H04MFA20CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 158 | 0
JP-00410-H04MFA20CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 158 | 0
JP-00410-H04MFA20CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.1 - AUTO LOCK ON | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 158 | 0
JP-00410-H04MFA20CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 159 | 1
JP-00410-H04MFA20CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 159 | 1
JP-00410-H04MFA20CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 159 | 1
JP-00410-H04MFA20CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 159 | 1
JP-00410-H04MFA20CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK OFF | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 159 | 1
JP-00410-H04MFA20CG142-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 160 | 0
JP-00410-H04MFA20CG142-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 160 | 0
JP-00410-H04MFA20CG142-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 160 | 0
JP-00410-H04MFA20CG142-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 160 | 0
JP-00410-H04MFA20CG142-ME-U | EGAT | LTK0 | 0 | ACTIVE | LIMIT SWITCH SERVOMOTOR NO.2 - AUTO LOCK ON | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 160 | 0
JP-00410-H04MFA20CG910-B1-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 161 | 1
JP-00410-H04MFA20CG910-B1-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 161 | 1
JP-00410-H04MFA20CG910-B1-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 161 | 1
JP-00410-H04MFA20CG910-B1-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 161 | 1
JP-00410-H04MFA20CG910-B1-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 161 | 1
JP-00410-H04MFA20CG910-B2-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 162 | 0
JP-00410-H04MFA20CG910-B2-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 162 | 0
JP-00410-H04MFA20CG910-B2-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 162 | 0
JP-00410-H04MFA20CG910-B2-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 162 | 0
JP-00410-H04MFA20CG910-B2-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 162 | 0
JP-00410-H04MFA20CG910-B3-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.3 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 163 | 1
JP-00410-H04MFA20CG910-B3-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.3 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 163 | 1
JP-00410-H04MFA20CG910-B3-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.3 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 163 | 1
JP-00410-H04MFA20CG910-B3-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.3 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 163 | 1
JP-00410-H04MFA20CG910-B3-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.3 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 163 | 1
JP-00410-H04MFA20CG910-B4-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.4 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 164 | 0
JP-00410-H04MFA20CG910-B4-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.4 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 164 | 0
JP-00410-H04MFA20CG910-B4-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.4 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 164 | 0
JP-00410-H04MFA20CG910-B4-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.4 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 164 | 0
JP-00410-H04MFA20CG910-B4-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.4 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 164 | 0
JP-00410-H04MFA20CG910-B5-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.5 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 165 | 1
JP-00410-H04MFA20CG910-B5-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.5 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 165 | 1
JP-00410-H04MFA20CG910-B5-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.5 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 165 | 1
JP-00410-H04MFA20CG910-B5-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.5 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 165 | 1
JP-00410-H04MFA20CG910-B5-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.5 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 165 | 1
JP-00410-H04MFA20CG910-B6-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.6 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 166 | 0
JP-00410-H04MFA20CG910-B6-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.6 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 166 | 0
JP-00410-H04MFA20CG910-B6-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.6 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 166 | 0
JP-00410-H04MFA20CG910-B6-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.6 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 166 | 0
JP-00410-H04MFA20CG910-B6-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE POSITION SWITCH NO.6 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 166 | 0
JP-00410-H04MFA20CG910-ME-U | EGAT | LTK0 | 0 | ACTIVE | LVDT FOR GUIDE VANE POSITION | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 167 | 1
JP-00410-H04MFA20CG910-ME-U | EGAT | LTK0 | 0 | ACTIVE | LVDT FOR GUIDE VANE POSITION | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 167 | 1
JP-00410-H04MFA20CG910-ME-U | EGAT | LTK0 | 0 | ACTIVE | LVDT FOR GUIDE VANE POSITION | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 167 | 1
JP-00410-H04MFA20CG910-ME-U | EGAT | LTK0 | 0 | ACTIVE | LVDT FOR GUIDE VANE POSITION | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 167 | 1
JP-00410-H04MFA20CG910-ME-U | EGAT | LTK0 | 0 | ACTIVE | LVDT FOR GUIDE VANE POSITION | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 167 | 1
JP-00420-H04MFA20CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 168 | 0
JP-00420-H04MFA20CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 168 | 0
JP-00420-H04MFA20CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 168 | 0
JP-00420-H04MFA20CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 168 | 0
JP-00420-H04MFA20CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 168 | 0
JP-00420-H04MFA20CP312-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 169 | 1
JP-00420-H04MFA20CP312-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 169 | 1
JP-00420-H04MFA20CP312-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 169 | 1
JP-00420-H04MFA20CP312-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 169 | 1
JP-00420-H04MFA20CP312-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.01 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 169 | 1
JP-00420-H04MFA20CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 170 | 0
JP-00420-H04MFA20CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 170 | 0
JP-00420-H04MFA20CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 170 | 0
JP-00420-H04MFA20CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 170 | 0
JP-00420-H04MFA20CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 170 | 0
JP-00420-H04MFA20CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 171 | 1
JP-00420-H04MFA20CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 171 | 1
JP-00420-H04MFA20CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 171 | 1
JP-00420-H04MFA20CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 171 | 1
JP-00420-H04MFA20CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE GAUGE OF SERVO NO.02 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 171 | 1
JP-00430-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 172 | 0
JP-00430-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 172 | 0
JP-00430-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 172 | 0
JP-00430-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 172 | 0
JP-00430-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 UNIT 3 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 172 | 0
JP-00430-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 173 | 1
JP-00430-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 173 | 1
JP-00430-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | 3 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 173 | 1
JP-00430-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | 3 | 40 | 0 | 0.5 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 173 | 1
JP-00430-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 UNIT 3 | 3 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 173 | 1
JP-00440-H04MFD20CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 174 | 0
JP-00440-H04MFD20CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 174 | 0
JP-00440-H04MFD20CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 174 | 0
JP-00440-H04MFD20CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 174 | 0
JP-00440-H04MFD20CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL TRANSMITTER - CL020 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 174 | 0
JP-00440-H04MFD20CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 175 | 1
JP-00440-H04MFD20CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 175 | 1
JP-00440-H04MFD20CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 175 | 1
JP-00440-H04MFD20CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 175 | 1
JP-00440-H04MFD20CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL120 (LL TRIP) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 175 | 1
JP-00440-H04MFD20CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 176 | 0
JP-00440-H04MFD20CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 176 | 0
JP-00440-H04MFD20CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 176 | 0
JP-00440-H04MFD20CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 176 | 0
JP-00440-H04MFD20CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL121 (L ALARM) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 176 | 0
JP-00440-H04MFD20CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 177 | 1
JP-00440-H04MFD20CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 177 | 1
JP-00440-H04MFD20CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 177 | 1
JP-00440-H04MFD20CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 177 | 1
JP-00440-H04MFD20CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL122 (H ALARM) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 177 | 1
JP-00440-H04MFD20CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 178 | 0
JP-00440-H04MFD20CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 178 | 0
JP-00440-H04MFD20CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 178 | 0
JP-00440-H04MFD20CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 178 | 0
JP-00440-H04MFD20CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN LEVEL SWITCH - CL123 (HH TRIP) | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 178 | 0
JP-00440-H04MFD20CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 179 | 1
JP-00440-H04MFD20CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 179 | 1
JP-00440-H04MFD20CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 179 | 1
JP-00440-H04MFD20CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 179 | 1
JP-00440-H04MFD20CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL PAN MAGNETIC LEVEL INDICATOR - CL320 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 179 | 1
JP-00440-H04MFD20CM115-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER IN OIL RELAY | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 180 | 0
JP-00440-H04MFD20CM115-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER IN OIL RELAY | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 180 | 0
JP-00440-H04MFD20CM115-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER IN OIL RELAY | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 180 | 0
JP-00440-H04MFD20CM115-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER IN OIL RELAY | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 180 | 0
JP-00440-H04MFD20CM115-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER IN OIL RELAY | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 180 | 0
JP-00440-H04MFD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.1 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 181 | 1
JP-00440-H04MFD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.1 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 181 | 1
JP-00440-H04MFD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.1 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 181 | 1
JP-00440-H04MFD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.1 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 181 | 1
JP-00440-H04MFD20CT011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.1 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 181 | 1
JP-00440-H04MFD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.2 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 182 | 0
JP-00440-H04MFD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.2 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 182 | 0
JP-00440-H04MFD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.2 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 182 | 0
JP-00440-H04MFD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.2 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 182 | 0
JP-00440-H04MFD20CT012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.2 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 182 | 0
JP-00440-H04MFD20CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.3 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 183 | 1
JP-00440-H04MFD20CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.3 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 183 | 1
JP-00440-H04MFD20CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.3 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 183 | 1
JP-00440-H04MFD20CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.3 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 183 | 1
JP-00440-H04MFD20CT013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.3 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 183 | 1
JP-00440-H04MFD20CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.4 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 184 | 0
JP-00440-H04MFD20CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.4 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 184 | 0
JP-00440-H04MFD20CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.4 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 184 | 0
JP-00440-H04MFD20CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.4 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 184 | 0
JP-00440-H04MFD20CT014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.4 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 184 | 0
JP-00440-H04MFD20CT015-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.5 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 185 | 1
JP-00440-H04MFD20CT015-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.5 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 185 | 1
JP-00440-H04MFD20CT015-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.5 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 185 | 1
JP-00440-H04MFD20CT015-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.5 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 185 | 1
JP-00440-H04MFD20CT015-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.5 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 185 | 1
JP-00440-H04MFD20CT016-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.6 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 186 | 0
JP-00440-H04MFD20CT016-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.6 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 186 | 0
JP-00440-H04MFD20CT016-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.6 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 186 | 0
JP-00440-H04MFD20CT016-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.6 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 186 | 0
JP-00440-H04MFD20CT016-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.6 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 186 | 0
JP-00440-H04MFD20CT017-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.7 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 187 | 1
JP-00440-H04MFD20CT017-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.7 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 187 | 1
JP-00440-H04MFD20CT017-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.7 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 187 | 1
JP-00440-H04MFD20CT017-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.7 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 187 | 1
JP-00440-H04MFD20CT017-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.7 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 187 | 1
JP-00440-H04MFD20CT018-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.8 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 188 | 0
JP-00440-H04MFD20CT018-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.8 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 188 | 0
JP-00440-H04MFD20CT018-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.8 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 188 | 0
JP-00440-H04MFD20CT018-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.8 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 188 | 0
JP-00440-H04MFD20CT018-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.8 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 188 | 0
JP-00440-H04MFD20CT019-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.9 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 189 | 1
JP-00440-H04MFD20CT019-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.9 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 189 | 1
JP-00440-H04MFD20CT019-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.9 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 189 | 1
JP-00440-H04MFD20CT019-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.9 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 189 | 1
JP-00440-H04MFD20CT019-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.9 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 189 | 1
JP-00440-H04MFD20CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.10 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 190 | 0
JP-00440-H04MFD20CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.10 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 190 | 0
JP-00440-H04MFD20CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.10 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 190 | 0
JP-00440-H04MFD20CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.10 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 190 | 0
JP-00440-H04MFD20CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.10 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 190 | 0
JP-00440-H04MFD20CT021-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.11 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 191 | 1
JP-00440-H04MFD20CT021-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.11 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 191 | 1
JP-00440-H04MFD20CT021-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.11 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 191 | 1
JP-00440-H04MFD20CT021-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.11 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 191 | 1
JP-00440-H04MFD20CT021-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PAD TEMPERATURE RTD NO.11 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 191 | 1
JP-00440-H04MFD20CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR TGB PAD - CT101 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 192 | 0
JP-00440-H04MFD20CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR TGB PAD - CT101 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 192 | 0
JP-00440-H04MFD20CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR TGB PAD - CT101 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 192 | 0
JP-00440-H04MFD20CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR TGB PAD - CT101 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 192 | 0
JP-00440-H04MFD20CT101-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIAL THERMOMETER FOR TGB PAD - CT101 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 192 | 0
JP-00440-H04MFV20CF110-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 193 | 1
JP-00440-H04MFV20CF110-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 193 | 1
JP-00440-H04MFV20CF110-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 193 | 1
JP-00440-H04MFV20CF110-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 193 | 1
JP-00440-H04MFV20CF110-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB OIL FLOW DETECTOR WITH CONTACT - CF110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 193 | 1
JP-00440-H04MFV20CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 194 | 0
JP-00440-H04MFV20CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 194 | 0
JP-00440-H04MFV20CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 194 | 0
JP-00440-H04MFV20CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 194 | 0
JP-00440-H04MFV20CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (TGB OIL FILTER) - CP110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 194 | 0
JP-00440-H04MFV20CP151-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 195 | 1
JP-00440-H04MFV20CP151-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 195 | 1
JP-00440-H04MFV20CP151-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 195 | 1
JP-00440-H04MFV20CP151-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 195 | 1
JP-00440-H04MFV20CP151-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE SWITCH - CP151 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 195 | 1
JP-00440-H04MFV20CP152-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 196 | 0
JP-00440-H04MFV20CP152-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 196 | 0
JP-00440-H04MFV20CP152-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 196 | 0
JP-00440-H04MFV20CP152-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 196 | 0
JP-00440-H04MFV20CP152-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE SWITCH - CP152 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 196 | 0
JP-00450-H04MFV20CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 197 | 1
JP-00450-H04MFV20CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 197 | 1
JP-00450-H04MFV20CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 197 | 1
JP-00450-H04MFV20CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 197 | 1
JP-00450-H04MFV20CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB OIL FILTER PRESSURE GAUGE - CP350 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 197 | 1
JP-00450-H04MFV20CP351-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 198 | 0
JP-00450-H04MFV20CP351-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 198 | 0
JP-00450-H04MFV20CP351-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 198 | 0
JP-00450-H04MFV20CP351-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 198 | 0
JP-00450-H04MFV20CP351-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.1 PRESSURE GAUGE - CP351 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 198 | 0
JP-00450-H04MFV20CP352-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 199 | 1
JP-00450-H04MFV20CP352-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 199 | 1
JP-00450-H04MFV20CP352-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 199 | 1
JP-00450-H04MFV20CP352-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 199 | 1
JP-00450-H04MFV20CP352-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB PUMP NO.2 PRESSURE GAUGE - CP352 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 199 | 1
JP-00450-H04MFV20CP360-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 200 | 0
JP-00450-H04MFV20CP360-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 200 | 0
JP-00450-H04MFV20CP360-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 200 | 0
JP-00450-H04MFV20CP360-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 200 | 0
JP-00450-H04MFV20CP360-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER TGB HEAT EXCHANGER PRESSURE GAUGE - CP360 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 200 | 0
JP-00450-H04PCB20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 201 | 1
JP-00450-H04PCB20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 201 | 1
JP-00450-H04PCB20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 201 | 1
JP-00450-H04PCB20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 201 | 1
JP-00450-H04PCB20CF100-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER FLOW DETECTOR WITH CONTACT - CF100 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 201 | 1
JP-00450-H04PCB20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 202 | 0
JP-00450-H04PCB20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 202 | 0
JP-00450-H04PCB20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 202 | 0
JP-00450-H04PCB20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 202 | 0
JP-00450-H04PCB20CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER SUPPLY LINE PRESSURE GAUGE - CP310 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 202 | 0
JP-00450-H04PCB20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 203 | 1
JP-00450-H04PCB20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 203 | 1
JP-00450-H04PCB20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 203 | 1
JP-00450-H04PCB20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-05 | 2024-11-05 | 203 | 1
JP-00450-H04PCB20CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TGB WATER RETURN PRESSURE GAUGE - CP320 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 203 | 1
JP-00460-H04MFW40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 204 | 0
JP-00460-H04MFW40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 204 | 0
JP-00460-H04MFW40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 204 | 0
JP-00460-H04MFW40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 204 | 0
JP-00460-H04MFW40CP100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE SWITCH - CP100 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 204 | 0
JP-00460-H04MFW40CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 205 | 1
JP-00460-H04MFW40CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 205 | 1
JP-00460-H04MFW40CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 205 | 1
JP-00460-H04MFW40CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 205 | 1
JP-00460-H04MFW40CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP110 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 205 | 1
JP-00460-H04MFW40CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 206 | 0
JP-00460-H04MFW40CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 206 | 0
JP-00460-H04MFW40CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 206 | 0
JP-00460-H04MFW40CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 206 | 0
JP-00460-H04MFW40CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (FILTER) - CP120 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 206 | 0
JP-00460-H04MFW40CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 207 | 1
JP-00460-H04MFW40CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 207 | 1
JP-00460-H04MFW40CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 207 | 1
JP-00460-H04MFW40CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 207 | 1
JP-00460-H04MFW40CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 207 | 1
JP-00460-H04MFW40CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 208 | 0
JP-00460-H04MFW40CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 208 | 0
JP-00460-H04MFW40CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 208 | 0
JP-00460-H04MFW40CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 208 | 0
JP-00460-H04MFW40CT020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL TEMPERATURE RTD NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 208 | 0
JP-00470-H04MFW40CF010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 209 | 1
JP-00470-H04MFW40CF010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 209 | 1
JP-00470-H04MFW40CF010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 209 | 1
JP-00470-H04MFW40CF010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 209 | 1
JP-00470-H04MFW40CF010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER FLOW DETECTOR WITH CONTACT - CF010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 209 | 1
JP-00470-H04MFW40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 210 | 0
JP-00470-H04MFW40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 210 | 0
JP-00470-H04MFW40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 210 | 0
JP-00470-H04MFW40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 210 | 0
JP-00470-H04MFW40CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL SUPPLY PRESSURE GAUGE - CP310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 210 | 0
JP-00470-H04MFW40CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 211 | 1
JP-00470-H04MFW40CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 211 | 1
JP-00470-H04MFW40CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 211 | 1
JP-00470-H04MFW40CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 211 | 1
JP-00470-H04MFW40CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FILTER SHAFT SEAL PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 211 | 1
JP-00470-H04MFW40CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 212 | 0
JP-00470-H04MFW40CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 212 | 0
JP-00470-H04MFW40CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 212 | 0
JP-00470-H04MFW40CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 212 | 0
JP-00470-H04MFW40CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP330 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 212 | 0
JP-00470-H04MFW40CP340-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 213 | 1
JP-00470-H04MFW40CP340-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 213 | 1
JP-00470-H04MFW40CP340-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 213 | 1
JP-00470-H04MFW40CP340-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 213 | 1
JP-00470-H04MFW40CP340-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER CYCLONE SHAFT SEAL PRESSURE GAUGE - CP340 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 213 | 1
JP-00470-H04MFW40CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 214 | 0
JP-00470-H04MFW40CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 214 | 0
JP-00470-H04MFW40CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 214 | 0
JP-00470-H04MFW40CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 214 | 0
JP-00470-H04MFW40CP350-ME-U | EGAT | LTK0 | 0 | ACTIVE | BEFORE CYCLONE SHAFT SEAL PRESSURE GAUGE - CP350 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 214 | 0
JP-00470-H04MFW40CP355-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-06 | 215 | 1
JP-00470-H04MFW40CP355-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 215 | 1
JP-00470-H04MFW40CP355-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 215 | 1
JP-00470-H04MFW40CP355-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-06 | 215 | 1
JP-00470-H04MFW40CP355-ME-U | EGAT | LTK0 | 0 | ACTIVE | AFTER FLOW SHAFT SEAL PRESSURE GAUGE - CP355 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 215 | 1
JP-00480-H04MFA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE (ROUTE) | 5 | 10 | 0 | 2 | INSPECTION | 2024-11-06 | 2024-11-06 | 216 | 0
JP-00480-H04MFA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE (ROUTE) | 5 | 20 | 0 | 0.5 | CLEAN | 2024-11-07 | 2024-11-07 | 216 | 0
JP-00480-H04MFA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE (ROUTE) | 5 | 30 | 0 | 2.5 | GAP CHECK | 2024-11-07 | 2024-11-07 | 216 | 0
JP-00490-H04MFA30HB200-ME-U | EGAT | LTK0 | 0 | ACTIVE | RUNNER | 4 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 217 | 1
JP-00490-H04MFA30HB200-ME-U | EGAT | LTK0 | 0 | ACTIVE | RUNNER | 4 | 20 | 0 | 0.5 | CLEAN | 2024-11-07 | 2024-11-07 | 217 | 1
JP-00490-H04MFA30HB200-ME-U | EGAT | LTK0 | 0 | ACTIVE | RUNNER | 4 | 30 | 0 | 2.5 | PT CHECK | 2024-11-07 | 2024-11-07 | 217 | 1
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 10 | 0 | 1 | OPEN MANHOLE (DRAFT TUBE) | 2024-11-05 | 2024-11-05 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 20 | 0 | 7 | SCAFFOLDING INSTALLATION | 2024-11-06 | 2024-11-06 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 30 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 40 | 0 | 1 | CLEAN | 2024-11-07 | 2024-11-07 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 50 | 0 | 3 | SCAFFOLDING REMOVING | 2024-11-13 | 2024-11-13 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 60 | 0 | 2 | CLOSE MANHOLE (DRAFT TUBE) | 2024-11-13 | 2024-11-13 | 218 | 0
JP-00500-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 16 | 70 | 0 | 1 | LEAKAGE CHECK | 2024-11-14 | 2024-11-14 | 218 | 0
JP-00510-H04MFA90-ME-U | EGAT | LTK0 | 0 | ACTIVE | HEAD COVER | 3 | 10 | 0 | 2 | INSPECTION | 2024-11-06 | 2024-11-07 | 219 | 1
JP-00510-H04MFA90-ME-U | EGAT | LTK0 | 0 | ACTIVE | HEAD COVER | 3 | 20 | 0 | 1 | CLEAN | 2024-11-07 | 2024-11-07 | 219 | 1
JP-00520-H04MFA60HA021-ME-U | EGAT | LTK0 | 0 | ACTIVE | BOTTOM COVER | 2 | 10 | 0 | 2 | INSPECTION | 2024-11-06 | 2024-11-07 | 220 | 0
JP-00530-H04MFA60HA011-ME-U | EGAT | LTK0 | 0 | ACTIVE | DISCHARGE RING | 0.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-07 | 221 | 1
JP-00540-H04MFA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE MECHANISM | 3.5 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-13 | 222 | 0
JP-00540-H04MFA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE MECHANISM | 3.5 | 20 | 0 | 0.5 | CLEAN | 2024-11-05 | 2024-11-05 | 222 | 0
JP-00550-H04MFA20AS010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE SERVOMOTOR | 2.5 | 10 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-05 | 223 | 1
JP-00550-H04MFA20AS010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GUIDE VANE SERVOMOTOR | 2.5 | 20 | 0 | 0.5 | CLEAN | 2024-11-05 | 2024-11-05 | 223 | 1
JP-00560-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 23 | 10 | 0 | 20 | OIL DRAIN & PURIFY | 2024-11-05 | 2024-11-13 | 224 | 0
JP-00560-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 23 | 20 | 0 | 3 | INSPECTION (AFTER ASSEMBLY) | 2024-11-13 | 2024-11-14 | 224 | 0
JP-00570-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 225 | 1
JP-00570-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 225 | 1
JP-00570-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 225 | 1
JP-00570-H04MFV20AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.1 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 225 | 1
JP-00580-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 226 | 0
JP-00580-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 226 | 0
JP-00580-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 226 | 0
JP-00580-H04MFV20AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PUMP NO.2 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 226 | 0
JP-00590-H04MFV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.1 | 12 | 10 | 0 | 5 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 227 | 1
JP-00590-H04MFV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.1 | 12 | 20 | 0 | 5 | ASSEMBLY | 2024-11-10 | 2024-11-11 | 227 | 1
JP-00590-H04MFV20AC310-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.1 | 12 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-11 | 2024-11-11 | 227 | 1
JP-00600-H04MFV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.2 | 12 | 10 | 0 | 5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 228 | 0
JP-00600-H04MFV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.2 | 12 | 20 | 0 | 5 | ASSEMBLY | 2024-11-12 | 2024-11-13 | 228 | 0
JP-00600-H04MFV20AC320-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL COOLER NO.2 | 12 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-13 | 2024-11-13 | 228 | 0
JP-00610-H04MFB10-ME-U | EGAT | LTK0 | 0 | ACTIVE | INLET VALVE | 1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-06 | 229 | 1
JP-00610-H04MFB10-ME-U | EGAT | LTK0 | 0 | ACTIVE | INLET VALVE | 1 | 20 | 0 | 0.5 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 229 | 1
JP-00620-H04MFB10AA403-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV BYPASS VALVE | 1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 230 | 0
JP-00620-H04MFB10AA403-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV BYPASS VALVE | 1 | 20 | 0 | 0.5 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 230 | 0
JP-00630-H04MFB10AS010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE SERVOMOTOR NO.1 | 0.75 | 10 | 0 | 0.25 | INSPECTION | 2024-11-05 | 2024-11-05 | 231 | 1
JP-00630-H04MFB10AS010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE SERVOMOTOR NO.1 | 0.75 | 20 | 0 | 0.5 | CLEAN | 2024-11-05 | 2024-11-05 | 231 | 1
JP-00640-H04MFB10AS020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE SERVOMOTOR NO.2 | 0.75 | 10 | 0 | 0.25 | INSPECTION | 2024-11-05 | 2024-11-05 | 232 | 0
JP-00640-H04MFB10AS020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE SERVOMOTOR NO.2 | 0.75 | 20 | 0 | 0.5 | CLEAN | 2024-11-05 | 2024-11-05 | 232 | 0
JP-00650-H04MFX60-ME-U | EGAT | LTK0 | 0 | ACTIVE | FLUID SUPPLY SYSTEM FOR MIV | 40 | 10 | 0 | 40 | OIL PURIFY | 2024-11-05 | 2024-11-08 | 233 | 1
JP-00660-H04MFX60BB520-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.1 | 7.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 234 | 0
JP-00660-H04MFX60BB520-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.1 | 7.5 | 20 | 0 | 7 | CLEAN | 2024-11-06 | 2024-11-07 | 234 | 0
JP-00670-H04MFX60BB530-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.2 | 1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 235 | 1
JP-00670-H04MFX60BB530-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE PRESSURE TANK (OIL & AIR PRESURE TANK) NO.2 | 1 | 20 | 0 | 0.5 | CLEAN | 2024-11-06 | 2024-11-07 | 235 | 1
JP-00680-H03MFB10AA010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN CONTROL VALVE | 0.5 | 10 | 0 | 0.5 | CHECK LEAK | 2024-11-05 | 2024-11-05 | 236 | 0
JP-00690-H04MFX60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-09 | 2024-11-10 | 237 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | 7 | 20 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-10 | 237 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | 7 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-09 | 2024-11-10 | 237 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | 7 | 40 | 0 | 4 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-09 | 2024-11-10 | 237 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.1 | 7 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-09 | 2024-11-10 | 237 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP111-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-09 | 2024-11-10 | 238 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP111-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | 7 | 20 | 0 | 0.5 | CLEANING | 2024-11-09 | 2024-11-10 | 238 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP111-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | 7 | 30 | 0 | 0.5 | RETIGHTENING | 2024-11-09 | 2024-11-10 | 238 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP111-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | 7 | 40 | 0 | 4 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-09 | 2024-11-10 | 238 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00690-H04MFX60AP111-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | ELECTRICAL MOTOR MIV HPU OIL PUMP NO.2 | 7 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-09 | 2024-11-10 | 238 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00700-H04MFX60BB010-ME-U | EGAT | LTK0 | 0 | ACTIVE | INLET VALVE OIL SUMP TANK | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-07 | 239 | 1
JP-00700-H04MFX60BB010-ME-U | EGAT | LTK0 | 0 | ACTIVE | INLET VALVE OIL SUMP TANK | 8 | 20 | 0 | 7 | CLEAN | 2024-11-06 | 2024-11-07 | 239 | 1
JP-00710-H04MFB10CG114-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 240 | 0
JP-00710-H04MFB10CG114-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 240 | 0
JP-00710-H04MFB10CG114-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 240 | 0
JP-00710-H04MFB10CG114-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 240 | 0
JP-00710-H04MFB10CG114-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (OPENED) - PROXIMITY SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 240 | 0
JP-00710-H04MFB10CG115-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 241 | 1
JP-00710-H04MFB10CG115-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 241 | 1
JP-00710-H04MFB10CG115-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 241 | 1
JP-00710-H04MFB10CG115-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 241 | 1
JP-00710-H04MFB10CG115-ME-U | EGAT | LTK0 | 0 | ACTIVE | BYPASS VALVE-03 (CLOSED) - PROXIMITY SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 241 | 1
JP-00710-H04MFB10CG140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 242 | 0
JP-00710-H04MFB10CG140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 242 | 0
JP-00710-H04MFB10CG140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 242 | 0
JP-00710-H04MFB10CG140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 242 | 0
JP-00710-H04MFB10CG140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 242 | 0
JP-00710-H04MFB10CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 243 | 1
JP-00710-H04MFB10CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 243 | 1
JP-00710-H04MFB10CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 243 | 1
JP-00710-H04MFB10CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 243 | 1
JP-00710-H04MFB10CG141-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION - PROXIMITY SENSOR NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 243 | 1
JP-00710-H04MFB10CG150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 244 | 0
JP-00710-H04MFB10CG150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 244 | 0
JP-00710-H04MFB10CG150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 244 | 0
JP-00710-H04MFB10CG150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 244 | 0
JP-00710-H04MFB10CG150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL INTERLOCK ON - LIMIT SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 244 | 0
JP-00710-H04MFB10CG151-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 245 | 1
JP-00710-H04MFB10CG151-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 245 | 1
JP-00710-H04MFB10CG151-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 245 | 1
JP-00710-H04MFB10CG151-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 245 | 1
JP-00710-H04MFB10CG151-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY OPEN) - PROXIMITY SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 245 | 1
JP-00710-H04MFB10CG152-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 246 | 0
JP-00710-H04MFB10CG152-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 246 | 0
JP-00710-H04MFB10CG152-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 246 | 0
JP-00710-H04MFB10CG152-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 246 | 0
JP-00710-H04MFB10CG152-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV POSITION (FULLY CLOSE) - PROXIMITY SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 246 | 0
JP-00710-H04MFB10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 247 | 1
JP-00710-H04MFB10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 247 | 1
JP-00710-H04MFB10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 247 | 1
JP-00710-H04MFB10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 247 | 1
JP-00710-H04MFB10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 247 | 1
JP-00710-H04MFB10CP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 248 | 0
JP-00710-H04MFB10CP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 248 | 0
JP-00710-H04MFB10CP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 248 | 0
JP-00710-H04MFB10CP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 248 | 0
JP-00710-H04MFB10CP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL CHAMBER - PRESSURE TRANSMITTER | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 248 | 0
JP-00710-H04MFB10CP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 249 | 1
JP-00710-H04MFB10CP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 249 | 1
JP-00710-H04MFB10CP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 249 | 1
JP-00710-H04MFB10CP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 249 | 1
JP-00710-H04MFB10CP015-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV INLET PRESSURE - PRESSURE TRANSMITTER | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 249 | 1
JP-00710-H04MFB10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 250 | 0
JP-00710-H04MFB10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 250 | 0
JP-00710-H04MFB10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 250 | 0
JP-00710-H04MFB10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 250 | 0
JP-00710-H04MFB10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV OUTLETLET PRESSURE - PRESSURE TRANSMITTER | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 250 | 0
JP-00710-H04MFB10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 251 | 1
JP-00710-H04MFB10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 251 | 1
JP-00710-H04MFB10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 251 | 1
JP-00710-H04MFB10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 251 | 1
JP-00710-H04MFB10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SV PRESS UNBALANCE - PRESSURE DIFFERENCE SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 251 | 1
JP-00710-H04MFB10CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-07 | 2024-11-08 | 252 | 0
JP-00710-H04MFB10CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-07 | 2024-11-08 | 252 | 0
JP-00710-H04MFB10CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-07 | 2024-11-08 | 252 | 0
JP-00710-H04MFB10CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-07 | 2024-11-08 | 252 | 0
JP-00710-H04MFB10CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEAL WT FILTER - PRESSURE DIFFERENCE SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-07 | 2024-11-08 | 252 | 0
JP-00720-H04MFX60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 1 | 0.95 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-06 | 253 | 1
JP-00720-H04MFX60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 1 | 0.95 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 253 | 1
JP-00720-H04MFX60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 1 | 0.95 | 30 | 0 | 0.3 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 253 | 1
JP-00720-H04MFX60AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 1 | 0.95 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 253 | 1
JP-00730-H04MFX60CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 254 | 0
JP-00730-H04MFX60CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 254 | 0
JP-00730-H04MFX60CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 254 | 0
JP-00730-H04MFX60CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 254 | 0
JP-00730-H04MFX60CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 254 | 0
JP-00730-H04MFX60CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 255 | 1
JP-00730-H04MFX60CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 255 | 1
JP-00730-H04MFX60CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 255 | 1
JP-00730-H04MFX60CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 255 | 1
JP-00730-H04MFX60CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 255 | 1
JP-00730-H04MFX60CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 256 | 0
JP-00730-H04MFX60CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 256 | 0
JP-00730-H04MFX60CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 256 | 0
JP-00730-H04MFX60CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 256 | 0
JP-00730-H04MFX60CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 256 | 0
JP-00730-H04MFX60CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 257 | 1
JP-00730-H04MFX60CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 257 | 1
JP-00730-H04MFX60CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 257 | 1
JP-00730-H04MFX60CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 257 | 1
JP-00730-H04MFX60CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 257 | 1
JP-00730-H04MFX60CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 258 | 0
JP-00730-H04MFX60CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 258 | 0
JP-00730-H04MFX60CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 258 | 0
JP-00730-H04MFX60CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 258 | 0
JP-00730-H04MFX60CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 258 | 0
JP-00730-H04MFX60CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 259 | 1
JP-00730-H04MFX60CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 259 | 1
JP-00730-H04MFX60CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 259 | 1
JP-00730-H04MFX60CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 259 | 1
JP-00730-H04MFX60CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 259 | 1
JP-00730-H04MFX60CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 260 | 0
JP-00730-H04MFX60CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 260 | 0
JP-00730-H04MFX60CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 260 | 0
JP-00730-H04MFX60CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 260 | 0
JP-00730-H04MFX60CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 260 | 0
JP-00730-H04MFX60CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 261 | 1
JP-00730-H04MFX60CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 261 | 1
JP-00730-H04MFX60CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 261 | 1
JP-00730-H04MFX60CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 261 | 1
JP-00730-H04MFX60CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 261 | 1
JP-00730-H04MFX60CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 262 | 0
JP-00730-H04MFX60CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 262 | 0
JP-00730-H04MFX60CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 262 | 0
JP-00730-H04MFX60CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 262 | 0
JP-00730-H04MFX60CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 262 | 0
JP-00730-H04MFX60CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 263 | 1
JP-00730-H04MFX60CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 263 | 1
JP-00730-H04MFX60CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 263 | 1
JP-00730-H04MFX60CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 263 | 1
JP-00730-H04MFX60CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 263 | 1
JP-00730-H04MFX60CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 264 | 0
JP-00730-H04MFX60CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 264 | 0
JP-00730-H04MFX60CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 264 | 0
JP-00730-H04MFX60CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 264 | 0
JP-00730-H04MFX60CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 264 | 0
JP-00730-H04MFX60CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK WATER IN OIL RELAY | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 265 | 1
JP-00730-H04MFX60CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK WATER IN OIL RELAY | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 265 | 1
JP-00730-H04MFX60CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK WATER IN OIL RELAY | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 265 | 1
JP-00730-H04MFX60CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK WATER IN OIL RELAY | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 265 | 1
JP-00730-H04MFX60CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV SUMP TANK WATER IN OIL RELAY | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 265 | 1
JP-00730-H04MFX60CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 266 | 0
JP-00730-H04MFX60CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 266 | 0
JP-00730-H04MFX60CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 266 | 0
JP-00730-H04MFX60CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 266 | 0
JP-00730-H04MFX60CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE TRANSMITTER - CP001 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 266 | 0
JP-00730-H04MFX60CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 267 | 1
JP-00730-H04MFX60CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 267 | 1
JP-00730-H04MFX60CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 267 | 1
JP-00730-H04MFX60CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 267 | 1
JP-00730-H04MFX60CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP101 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 267 | 1
JP-00730-H04MFX60CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 268 | 0
JP-00730-H04MFX60CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 268 | 0
JP-00730-H04MFX60CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 268 | 0
JP-00730-H04MFX60CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 268 | 0
JP-00730-H04MFX60CP102-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV CONTROL CIRCUIT PRESSURE SWITCH - CP102 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 268 | 0
JP-00730-H04MFX60CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 269 | 1
JP-00730-H04MFX60CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 269 | 1
JP-00730-H04MFX60CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 269 | 1
JP-00730-H04MFX60CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 269 | 1
JP-00730-H04MFX60CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MIV OIL FILTER) - CP150 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 269 | 1
JP-00740-H04MFX60AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 2 | 0.95 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-06 | 270 | 0
JP-00740-H04MFX60AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 2 | 0.95 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 270 | 0
JP-00740-H04MFX60AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 2 | 0.95 | 30 | 0 | 0.3 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 270 | 0
JP-00740-H04MFX60AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE OIL PUMP 2 | 0.95 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 270 | 0
JP-00750-H04MFB10CG120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 271 | 1
JP-00750-H04MFB10CG120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 271 | 1
JP-00750-H04MFB10CG120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 271 | 1
JP-00750-H04MFB10CG120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 271 | 1
JP-00750-H04MFB10CG120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 271 | 1
JP-00750-H04MFB10CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 272 | 0
JP-00750-H04MFB10CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 272 | 0
JP-00750-H04MFB10CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 272 | 0
JP-00750-H04MFB10CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 272 | 0
JP-00750-H04MFB10CG121-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 272 | 0
JP-00750-H04MFB10CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 273 | 1
JP-00750-H04MFB10CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 273 | 1
JP-00750-H04MFB10CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 273 | 1
JP-00750-H04MFB10CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 273 | 1
JP-00750-H04MFB10CG122-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINENACNCE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 273 | 1
JP-00750-H04MFB10CG130-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 274 | 0
JP-00750-H04MFB10CG130-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 274 | 0
JP-00750-H04MFB10CG130-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 274 | 0
JP-00750-H04MFB10CG130-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 274 | 0
JP-00750-H04MFB10CG130-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.1 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 274 | 0
JP-00750-H04MFB10CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 275 | 1
JP-00750-H04MFB10CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 275 | 1
JP-00750-H04MFB10CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 275 | 1
JP-00750-H04MFB10CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 275 | 1
JP-00750-H04MFB10CG131-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.2 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 275 | 1
JP-00750-H04MFB10CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 276 | 0
JP-00750-H04MFB10CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 276 | 0
JP-00750-H04MFB10CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 276 | 0
JP-00750-H04MFB10CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 276 | 0
JP-00750-H04MFB10CG132-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE SEAL (OFF) - LIMIT SWITCH NO.3 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 276 | 0
JP-00750-H04MFX60CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 277 | 1
JP-00750-H04MFX60CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 277 | 1
JP-00750-H04MFX60CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 277 | 1
JP-00750-H04MFX60CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 277 | 1
JP-00750-H04MFX60CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 277 | 1
JP-00750-H04MFX60CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 278 | 0
JP-00750-H04MFX60CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 278 | 0
JP-00750-H04MFX60CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 278 | 0
JP-00750-H04MFX60CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 278 | 0
JP-00750-H04MFX60CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 278 | 0
JP-00750-H04MFX60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 279 | 1
JP-00750-H04MFX60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 279 | 1
JP-00750-H04MFX60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 279 | 1
JP-00750-H04MFX60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 279 | 1
JP-00750-H04MFX60CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.1 PRESSURE GAUGE - CP321 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 279 | 1
JP-00750-H04MFX60CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-07 | 280 | 0
JP-00750-H04MFX60CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 280 | 0
JP-00750-H04MFX60CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 280 | 0
JP-00750-H04MFX60CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-06 | 2024-11-07 | 280 | 0
JP-00750-H04MFX60CP322-ME-U | EGAT | LTK0 | 0 | ACTIVE | MIV ACCUMULATOR TANK NO.2 PRESSURE GAUGE - CP322 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-07 | 280 | 0
JP-00760-H04MFX10-ME-U | EGAT | LTK0 | 0 | ACTIVE | FLUID SUPPLY SYSTEM 1 (GOVERNOR) | 40 | 10 | 0 | 40 | OIL PURIFY | 2024-11-09 | 2024-11-12 | 281 | 1
JP-00770-H04MFX10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 282 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 282 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 282 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 282 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.1 - MFX10AP110 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 282 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP111-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 283 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP111-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 283 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP111-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 283 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP111-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 283 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00770-H04MFX10AP111-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR GOVERNOR OIL PUMP NO.2 - MFX10AP111 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 283 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00780-H04MFX10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 284 | 0
JP-00780-H04MFX10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 284 | 0
JP-00780-H04MFX10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 284 | 0
JP-00780-H04MFX10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 284 | 0
JP-00780-H04MFX10CL010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK OIL LEVEL TRANSMITTER - CL010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 284 | 0
JP-00780-H04MFX10CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 285 | 1
JP-00780-H04MFX10CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 285 | 1
JP-00780-H04MFX10CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 285 | 1
JP-00780-H04MFX10CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 285 | 1
JP-00780-H04MFX10CL020-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL TRANSMITTER - CL020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 285 | 1
JP-00780-H04MFX10CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 286 | 0
JP-00780-H04MFX10CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 286 | 0
JP-00780-H04MFX10CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 286 | 0
JP-00780-H04MFX10CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 286 | 0
JP-00780-H04MFX10CL111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL111 (LL TRIP) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 286 | 0
JP-00780-H04MFX10CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 287 | 1
JP-00780-H04MFX10CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 287 | 1
JP-00780-H04MFX10CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 287 | 1
JP-00780-H04MFX10CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 287 | 1
JP-00780-H04MFX10CL112-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL112 (L ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 287 | 1
JP-00780-H04MFX10CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 288 | 0
JP-00780-H04MFX10CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 288 | 0
JP-00780-H04MFX10CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 288 | 0
JP-00780-H04MFX10CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 288 | 0
JP-00780-H04MFX10CL113-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK LEVEL SWITCH - CL113 (H ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 288 | 0
JP-00780-H04MFX10CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 289 | 1
JP-00780-H04MFX10CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 289 | 1
JP-00780-H04MFX10CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 289 | 1
JP-00780-H04MFX10CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 289 | 1
JP-00780-H04MFX10CL120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL120 (LL TRIP) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 289 | 1
JP-00780-H04MFX10CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 290 | 0
JP-00780-H04MFX10CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 290 | 0
JP-00780-H04MFX10CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 290 | 0
JP-00780-H04MFX10CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 290 | 0
JP-00780-H04MFX10CL121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL121 (L ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 290 | 0
JP-00780-H04MFX10CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 291 | 1
JP-00780-H04MFX10CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 291 | 1
JP-00780-H04MFX10CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 291 | 1
JP-00780-H04MFX10CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 291 | 1
JP-00780-H04MFX10CL122-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL122 (H ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 291 | 1
JP-00780-H04MFX10CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 292 | 0
JP-00780-H04MFX10CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 292 | 0
JP-00780-H04MFX10CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 292 | 0
JP-00780-H04MFX10CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 292 | 0
JP-00780-H04MFX10CL123-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK OIL LEVEL SWITCH - CL123 (HH ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 292 | 0
JP-00780-H04MFX10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 293 | 1
JP-00780-H04MFX10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 293 | 1
JP-00780-H04MFX10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 293 | 1
JP-00780-H04MFX10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 293 | 1
JP-00780-H04MFX10CL310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK MAGNETIC LEVEL INDICATOR - CL310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 293 | 1
JP-00780-H04MFX10CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 294 | 0
JP-00780-H04MFX10CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 294 | 0
JP-00780-H04MFX10CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 294 | 0
JP-00780-H04MFX10CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 294 | 0
JP-00780-H04MFX10CL320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR TANK MAGNETIC LEVEL INDICATOR - CL320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 294 | 0
JP-00780-H04MFX10CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK WATER IN OIL RELAY | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 295 | 1
JP-00780-H04MFX10CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK WATER IN OIL RELAY | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 295 | 1
JP-00780-H04MFX10CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK WATER IN OIL RELAY | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 295 | 1
JP-00780-H04MFX10CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK WATER IN OIL RELAY | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 295 | 1
JP-00780-H04MFX10CM110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK WATER IN OIL RELAY | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 295 | 1
JP-00780-H04MFX10CP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 296 | 0
JP-00780-H04MFX10CP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 296 | 0
JP-00780-H04MFX10CP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 296 | 0
JP-00780-H04MFX10CP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 296 | 0
JP-00780-H04MFX10CP021-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE TRANSMITTER - CP021 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 296 | 0
JP-00780-H04MFX10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 297 | 1
JP-00780-H04MFX10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 297 | 1
JP-00780-H04MFX10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 297 | 1
JP-00780-H04MFX10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 297 | 1
JP-00780-H04MFX10CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER COOLING LINE) - CP110 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 297 | 1
JP-00780-H04MFX10CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 298 | 0
JP-00780-H04MFX10CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 298 | 0
JP-00780-H04MFX10CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 298 | 0
JP-00780-H04MFX10CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 298 | 0
JP-00780-H04MFX10CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP120 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 298 | 0
JP-00780-H04MFX10CP121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 299 | 1
JP-00780-H04MFX10CP121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 299 | 1
JP-00780-H04MFX10CP121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 299 | 1
JP-00780-H04MFX10CP121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 299 | 1
JP-00780-H04MFX10CP121-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL CIRCUIT PRESSURE SWITCH - CP121 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 299 | 1
JP-00780-H04MFX10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE RTD | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 300 | 0
JP-00780-H04MFX10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE RTD | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 300 | 0
JP-00780-H04MFX10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE RTD | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 300 | 0
JP-00780-H04MFX10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE RTD | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 300 | 0
JP-00780-H04MFX10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE RTD | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 300 | 0
JP-00780-H04MFX10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE SWITCH | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 301 | 1
JP-00780-H04MFX10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE SWITCH | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 301 | 1
JP-00780-H04MFX10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE SWITCH | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 301 | 1
JP-00780-H04MFX10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE SWITCH | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 301 | 1
JP-00780-H04MFX10CT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV SUMP TANK TEMPERATURE SWITCH | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 301 | 1
JP-00780-H04MFX20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 302 | 0
JP-00780-H04MFX20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 302 | 0
JP-00780-H04MFX20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 302 | 0
JP-00780-H04MFX20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 302 | 0
JP-00780-H04MFX20CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (GOV OIL FILTER) - CP101 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 302 | 0
JP-00790-H04MFX10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 303 | 1
JP-00790-H04MFX10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 303 | 1
JP-00790-H04MFX10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 303 | 1
JP-00790-H04MFX10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 303 | 1
JP-00790-H04MFX10CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.1 PRESSURE GAUGE - CP310 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 303 | 1
JP-00790-H04MFX10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 304 | 0
JP-00790-H04MFX10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 304 | 0
JP-00790-H04MFX10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 304 | 0
JP-00790-H04MFX10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 304 | 0
JP-00790-H04MFX10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV PUMP NO.2 PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 304 | 0
JP-00790-H04MFX10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 305 | 1
JP-00790-H04MFX10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 305 | 1
JP-00790-H04MFX10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 305 | 1
JP-00790-H04MFX10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 305 | 1
JP-00790-H04MFX10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR PRESSURE GAUGE - CP321 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 305 | 1
JP-00790-H04MFX20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 306 | 0
JP-00790-H04MFX20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 306 | 0
JP-00790-H04MFX20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 306 | 0
JP-00790-H04MFX20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 306 | 0
JP-00790-H04MFX20CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOV ACCUMULATOR SUPPLY LINE PRESSURE GAUGE - CP301 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 306 | 0
JP-00800-H04MFX10AP330-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 307 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00800-H04MFX10AP330-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 307 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00800-H04MFX10AP330-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 307 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00800-H04MFX10AP330-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 307 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00800-H04MFX10AP330-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR RETURN OIL LEAK PUMP - MFX10AP330 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 307 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00810-H04MFX10CL131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 308 | 0
JP-00810-H04MFX10CL131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 308 | 0
JP-00810-H04MFX10CL131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 308 | 0
JP-00810-H04MFX10CL131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 308 | 0
JP-00810-H04MFX10CL131-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL131 (STOP) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 308 | 0
JP-00810-H04MFX10CL132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 309 | 1
JP-00810-H04MFX10CL132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 309 | 1
JP-00810-H04MFX10CL132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 309 | 1
JP-00810-H04MFX10CL132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 309 | 1
JP-00810-H04MFX10CL132-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL132 (START) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 309 | 1
JP-00810-H04MFX10CL133-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 310 | 0
JP-00810-H04MFX10CL133-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 310 | 0
JP-00810-H04MFX10CL133-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 310 | 0
JP-00810-H04MFX10CL133-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 310 | 0
JP-00810-H04MFX10CL133-ME-U | EGAT | LTK0 | 0 | ACTIVE | LEAKAGE OIL TANK LEVEL SWITCH - CL133 (H ALARM) | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 310 | 0
JP-00810-H04MFX10CM130-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE WATER IN OIL RELAY | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-10 | 2024-11-10 | 311 | 1
JP-00810-H04MFX10CM130-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE WATER IN OIL RELAY | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-10 | 311 | 1
JP-00810-H04MFX10CM130-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE WATER IN OIL RELAY | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-10 | 2024-11-10 | 311 | 1
JP-00810-H04MFX10CM130-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE WATER IN OIL RELAY | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-10 | 2024-11-10 | 311 | 1
JP-00810-H04MFX10CM130-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE WATER IN OIL RELAY | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-10 | 2024-11-10 | 311 | 1
JP-00820-H04MFX10BB610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL SUMP TANK | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-10 | 2024-11-11 | 312 | 0
JP-00820-H04MFX10BB610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL SUMP TANK | 8 | 20 | 0 | 7 | CLEAN | 2024-11-10 | 2024-11-11 | 312 | 0
JP-00830-H04MFX10BB520-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PRESSURE TANK | 7.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-10 | 2024-11-11 | 313 | 1
JP-00830-H04MFX10BB520-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PRESSURE TANK | 7.5 | 20 | 0 | 7 | CLEAN | 2024-11-10 | 2024-11-11 | 313 | 1
JP-00840-H04MFX10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 1 | 0.95 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-10 | 314 | 0
JP-00840-H04MFX10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 1 | 0.95 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 314 | 0
JP-00840-H04MFX10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 1 | 0.95 | 30 | 0 | 0.3 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 314 | 0
JP-00840-H04MFX10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 1 | 0.95 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 314 | 0
JP-00850-H04MFX10AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 2 | 0.95 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-10 | 315 | 1
JP-00850-H04MFX10AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 2 | 0.95 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 315 | 1
JP-00850-H04MFX10AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 2 | 0.95 | 30 | 0 | 0.3 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 315 | 1
JP-00850-H04MFX10AP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL PUMP NO. 2 | 0.95 | 40 | 0 | 0.1 | VIBRATION CHECKK | 2024-11-05 | 2024-11-05 | 315 | 1
JP-00860-H04MFX20AA010-ME-U | EGAT | LTK0 | 0 | ACTIVE | DISTRIBUTING VALVE | 0.5 | 10 | 0 | 0.5 | CHECK LEAK | 2024-11-05 | 2024-11-05 | 316 | 0
JP-00870-H04MFX10BB730-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE TANK | 3.2 | 10 | 0 | 0.2 | INSPECTION | 2024-11-11 | 2024-11-12 | 317 | 1
JP-00870-H04MFX10BB730-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE TANK | 3.2 | 20 | 0 | 3 | CLEAN | 2024-11-11 | 2024-11-12 | 317 | 1
JP-00880-H04MFX10AP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE PUMP | 0.95 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-10 | 318 | 0
JP-00880-H04MFX10AP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE PUMP | 0.95 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 318 | 0
JP-00880-H04MFX10AP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE PUMP | 0.95 | 30 | 0 | 0.3 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 318 | 0
JP-00880-H04MFX10AP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | OIL LEAKAGE PUMP | 0.95 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 318 | 0
JP-00890-H04MFX10AP710-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL COOLING PUMP | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-10 | 319 | 1
JP-00890-H04MFX10AP710-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL COOLING PUMP | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 319 | 1
JP-00890-H04MFX10AP710-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL COOLING PUMP | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 319 | 1
JP-00890-H04MFX10AP710-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR OIL COOLING PUMP | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 319 | 1
JP-00900-H04PAC10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER PUMP | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 320 | 0
JP-00900-H04PAC10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER PUMP | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 320 | 0
JP-00900-H04PAC10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER PUMP | 0.3 | 30 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 320 | 0
JP-00900-H04PAC10AP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER PUMP | 0.3 | 40 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 320 | 0
JP-00910-H04PAC10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MAIN COOLING WATER SUPPLY | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 321 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00910-H04PAC10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MAIN COOLING WATER SUPPLY | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 321 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00910-H04PAC10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MAIN COOLING WATER SUPPLY | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 321 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00910-H04PAC10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MAIN COOLING WATER SUPPLY | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 321 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00910-H04PAC10AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MAIN COOLING WATER SUPPLY | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 321 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 322 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 322 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 322 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 322 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 322 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 323 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 323 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 323 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 323 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00920-H04PAC10AP130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR AT NOLOAD OIL PUMP NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-05 | 2024-11-05 | 323 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 324 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 324 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 324 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 324 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 324 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 325 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 325 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 325 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 325 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MAIN COOLING AUTOMATIC STRAINER | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 325 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 326 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 326 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 326 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 326 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00930-H04PAB10AT110-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MAIN COOLING AUTOMATIC STRAINER | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 326 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 327 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 327 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 327 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 327 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 327 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 328 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 328 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 328 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 328 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 328 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 329 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 329 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 329 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 329 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00940-H04PAB10AT120-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 329 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 330 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 330 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 330 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 330 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 330 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 331 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 331 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 331 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 331 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 331 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-06 | 332 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-06 | 332 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 332 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-06 | 332 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00950-H04PAB10AT130-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - MTR AT NOLOAD AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-06 | 332 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 333 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 333 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 333 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 333 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 333 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 334 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 334 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 334 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 334 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 334 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 335 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 335 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 335 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 335 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00960-H04PAB10AT150-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.1 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 335 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 336 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 336 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 336 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 336 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FLUSHING FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 336 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 337 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 337 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 337 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 337 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-M02-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOV FOR FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 337 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 10 | 0 | 0.5 | INSPECTION | 2024-11-06 | 2024-11-07 | 338 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 20 | 0 | 0.5 | CLEANING | 2024-11-06 | 2024-11-07 | 338 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-07 | 338 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-06 | 2024-11-07 | 338 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00970-H04PAB10AT155-N01-ME-U | EGAT | LTK0 | 0 | ACTIVE | CONTROL CUBICLE - FIRE FIGHTING AUTOMATIC STRAINER NO.2 | 4 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-07 | 338 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-00980-H04PAB10CP116-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 339 | 1
JP-00980-H04PAB10CP116-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 339 | 1
JP-00980-H04PAB10CP116-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 339 | 1
JP-00980-H04PAB10CP116-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 339 | 1
JP-00980-H04PAB10CP116-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (LL) - CP116 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 339 | 1
JP-00980-H04PAB10CP117-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 340 | 0
JP-00980-H04PAB10CP117-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 340 | 0
JP-00980-H04PAB10CP117-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 340 | 0
JP-00980-H04PAB10CP117-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 340 | 0
JP-00980-H04PAB10CP117-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY LINE PRESSURE SWITCH (HH) - CP117 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 340 | 0
JP-00980-H04PAB10CP126-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 341 | 1
JP-00980-H04PAB10CP126-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 341 | 1
JP-00980-H04PAB10CP126-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 341 | 1
JP-00980-H04PAB10CP126-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 341 | 1
JP-00980-H04PAB10CP126-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (L) - CP126 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 341 | 1
JP-00980-H04PAB10CP136-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 342 | 0
JP-00980-H04PAB10CP136-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 342 | 0
JP-00980-H04PAB10CP136-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 342 | 0
JP-00980-H04PAB10CP136-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 342 | 0
JP-00980-H04PAB10CP136-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD WATER SUPPLY PRESSURE SWITCH (H) - CP136 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 342 | 0
JP-00980-H04PAB10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 343 | 1
JP-00980-H04PAB10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 343 | 1
JP-00980-H04PAB10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 343 | 1
JP-00980-H04PAB10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 343 | 1
JP-00980-H04PAB10CT010-ME-U | EGAT | LTK0 | 0 | ACTIVE | WATER SUPPLY INLET TEMPERATURE RTD - CT010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 343 | 1
JP-00980-H04PAC10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 344 | 0
JP-00980-H04PAC10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 344 | 0
JP-00980-H04PAC10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 344 | 0
JP-00980-H04PAC10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 344 | 0
JP-00980-H04PAC10CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MAIN WATER SUPPLY PUMP) - CP010 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 344 | 0
JP-00980-H04PAC10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 345 | 1
JP-00980-H04PAC10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 345 | 1
JP-00980-H04PAC10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 345 | 1
JP-00980-H04PAC10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 345 | 1
JP-00980-H04PAC10CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.1) - CP020 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 345 | 1
JP-00980-H04PAC10CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 346 | 0
JP-00980-H04PAC10CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 346 | 0
JP-00980-H04PAC10CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 346 | 0
JP-00980-H04PAC10CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 346 | 0
JP-00980-H04PAC10CP030-ME-U | EGAT | LTK0 | 0 | ACTIVE | PRESSURE DIFFERENCE SWITCH (MTR AT NOLOAD NO.2) - CP030 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 346 | 0
JP-00990-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE INTAKE SCREEN | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 347 | 1
JP-00990-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE INTAKE SCREEN | 6 | 20 | 0 | 2 | CLEAN | 2024-11-07 | 2024-11-07 | 347 | 1
JP-00990-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE INTAKE SCREEN | 6 | 30 | 0 | 3 | PT CHECK | 2024-11-07 | 2024-11-07 | 347 | 1
JP-01000-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE DRAFT TUBE INTAKE SCREEN Unit4 | 8 | 10 | 0 | 4 | ติดตั้งนั่งร้านล้างอุปกรณ์ | 2024-11-07 | 2024-11-07 | 348 | 0
JP-01000-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE DRAFT TUBE INTAKE SCREEN Unit4 | 8 | 20 | 0 | 4 | รื้อถอน นั่งร้านล้างอุปกรณ์ | 2024-11-12 | 2024-11-12 | 348 | 0
JP-01010-H04PAB10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 349 | 1
JP-01010-H04PAB10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 349 | 1
JP-01010-H04PAB10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 349 | 1
JP-01010-H04PAB10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 349 | 1
JP-01010-H04PAB10CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER INLET PRESSURE GAUGE - CP320 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 349 | 1
JP-01010-H04PAB10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 350 | 0
JP-01010-H04PAB10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 350 | 0
JP-01010-H04PAB10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 350 | 0
JP-01010-H04PAB10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 350 | 0
JP-01010-H04PAB10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER WATER OUTLET PRESSURE GAUGE - CP325 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 350 | 0
JP-01010-H04PAC10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 351 | 1
JP-01010-H04PAC10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 351 | 1
JP-01010-H04PAC10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 351 | 1
JP-01010-H04PAC10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 351 | 1
JP-01010-H04PAC10CP311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP OUTLET PRESSURE GAUGE - CP311 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 351 | 1
JP-01010-H04PAC10CP315-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 352 | 0
JP-01010-H04PAC10CP315-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 352 | 0
JP-01010-H04PAC10CP315-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 352 | 0
JP-01010-H04PAC10CP315-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 352 | 0
JP-01010-H04PAC10CP315-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN WATER SUPPLY PUMP INLET PRESSURE GAUGE - CP315 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 352 | 0
JP-01010-H04PAC10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 353 | 1
JP-01010-H04PAC10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 353 | 1
JP-01010-H04PAC10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 353 | 1
JP-01010-H04PAC10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 353 | 1
JP-01010-H04PAC10CP321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 OUTLET PRESSURE GAUGE - CP321 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 353 | 1
JP-01010-H04PAC10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 354 | 0
JP-01010-H04PAC10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 354 | 0
JP-01010-H04PAC10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 354 | 0
JP-01010-H04PAC10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 354 | 0
JP-01010-H04PAC10CP325-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.1 INLET PRESSURE GAUGE - CP325 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 354 | 0
JP-01010-H04PAC10CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 355 | 1
JP-01010-H04PAC10CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 355 | 1
JP-01010-H04PAC10CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 355 | 1
JP-01010-H04PAC10CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 355 | 1
JP-01010-H04PAC10CP331-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 OUTLET PRESSURE GAUGE - CP331 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 355 | 1
JP-01010-H04PAC10CP335-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-05 | 2024-11-05 | 356 | 0
JP-01010-H04PAC10CP335-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 356 | 0
JP-01010-H04PAC10CP335-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-05 | 356 | 0
JP-01010-H04PAC10CP335-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-05 | 2024-11-05 | 356 | 0
JP-01010-H04PAC10CP335-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR AT NOLOAD PUMP NO.2 INLET PRESSURE GAUGE - CP335 | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-05 | 2024-11-05 | 356 | 0
JP-01020-H04PAC10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 357 | 1
JP-01020-H04PAC10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 357 | 1
JP-01020-H04PAC10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.1 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 357 | 1
JP-01020-H04PAC10AP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.1 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 357 | 1
JP-01030-H04PAC10AP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 358 | 0
JP-01030-H04PAC10AP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 358 | 0
JP-01030-H04PAC10AP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.2 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 358 | 0
JP-01030-H04PAC10AP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANS. COOLING WATER PUMP NO.2 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 358 | 0
JP-01040-H04PAB10AT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER AUTOMATIC STRAINER | 20 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-07 | 359 | 1
JP-01040-H04PAB10AT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER AUTOMATIC STRAINER | 20 | 20 | 0 | 14 | CLEAN | 2024-11-06 | 2024-11-07 | 359 | 1
JP-01040-H04PAB10AT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER AUTOMATIC STRAINER | 20 | 30 | 0 | 5 | PAINT REPAIR | 2024-11-06 | 2024-11-07 | 359 | 1
JP-01050-H04PAB10AT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER STRAINER UNIT 3 ชั้น 176.50 (CIVIL) | 8 | 10 | 0 | 4 | ติดตั้งนั่งร้านล้างอุปกรณ์ | 2024-11-05 | 2024-11-05 | 360 | 0
JP-01050-H04PAB10AT110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN COOLING WATER STRAINER UNIT 3 ชั้น 176.50 (CIVIL) | 8 | 20 | 0 | 4 | รื้อถอน นั่งร้านล้างอุปกรณ์ | 2024-11-14 | 2024-11-14 | 360 | 0
JP-01060-H04MFP14-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXRINGUISHER SYSTEM | 1 | 10 | 0 | 1 | OPERATE TEST | 2024-11-14 | 2024-11-14 | 361 | 1
JP-01070-H04BAT01AC001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.1 | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-10 | 362 | 0
JP-01070-H04BAT01AC001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.1 | 6 | 20 | 0 | 3 | CLEAN | 2024-11-08 | 2024-11-10 | 362 | 0
JP-01070-H04BAT01AC001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.1 | 6 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-08 | 2024-11-10 | 362 | 0
JP-01080-H04BAT01AC002-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.2 | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-10 | 363 | 1
JP-01080-H04BAT01AC002-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.2 | 6 | 20 | 0 | 3 | CLEAN | 2024-11-08 | 2024-11-10 | 363 | 1
JP-01080-H04BAT01AC002-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.2 | 6 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-08 | 2024-11-10 | 363 | 1
JP-01090-H04BAT01AC003-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.3 | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-10 | 364 | 0
JP-01090-H04BAT01AC003-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.3 | 6 | 20 | 0 | 3 | CLEAN | 2024-11-08 | 2024-11-10 | 364 | 0
JP-01090-H04BAT01AC003-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL COOLER NO.3 | 6 | 30 | 0 | 2 | HYDROSTATIC TEST | 2024-11-08 | 2024-11-10 | 364 | 0
JP-01100-H04BAT01AC003-ME-U | EGAT | LTK0 | 0 | ACTIVE | ตั้งนั่งร้าน MAIN TRANSFORMER OIL COOLER NO.1-3 (CIVIL) | 8 | 10 | 0 | 4 | ติดตั้งนั่งร้าน | 2024-11-07 | 2024-11-07 | 365 | 1
JP-01100-H04BAT01AC003-ME-U | EGAT | LTK0 | 0 | ACTIVE | ตั้งนั่งร้าน MAIN TRANSFORMER OIL COOLER NO.1-3 (CIVIL) | 8 | 20 | 0 | 4 | รื้อถอน นั่งร้าน | 2024-11-11 | 2024-11-11 | 365 | 1
JP-01110-H04BAT01AP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.1 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 366 | 0
JP-01110-H04BAT01AP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.1 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 366 | 0
JP-01110-H04BAT01AP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.1 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 366 | 0
JP-01110-H04BAT01AP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.1 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 366 | 0
JP-01120-H04BAT01AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.2 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 367 | 1
JP-01120-H04BAT01AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.2 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 367 | 1
JP-01120-H04BAT01AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.2 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 367 | 1
JP-01120-H04BAT01AP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.2 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 367 | 1
JP-01130-H04BAT01AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.3 | 0.3 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 368 | 0
JP-01130-H04BAT01AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.3 | 0.3 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 368 | 0
JP-01130-H04BAT01AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.3 | 0.3 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 368 | 0
JP-01130-H04BAT01AP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OIL CIRCULATING PUMP NO.3 | 0.3 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 368 | 0
JP-01140-H04SGC10AA020-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE SUCTION MANUAL VALVE (DELUDEGE VALVE) | 0.2 | 10 | 0 | 0.1 | INSPECTION | 2024-11-05 | 2024-11-05 | 369 | 1
JP-01140-H04SGC10AA020-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE SUCTION MANUAL VALVE (DELUDEGE VALVE) | 0.2 | 20 | 0 | 0.05 | CLEAN | 2024-11-05 | 2024-11-05 | 369 | 1
JP-01140-H04SGC10AA020-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE SUCTION MANUAL VALVE (DELUDEGE VALVE) | 0.2 | 30 | 0 | 0.05 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 369 | 1
JP-01150-H04LQY10AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MANUAL PUMP | 0.4 | 10 | 0 | 0.2 | INSPECTION | 2024-11-05 | 2024-11-05 | 370 | 0
JP-01150-H04LQY10AP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MANUAL PUMP | 0.4 | 20 | 0 | 0.2 | CLEAN | 2024-11-05 | 2024-11-05 | 370 | 0
JP-01160-H04LQY10AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MOTOR PUMP SET | 0.6 | 10 | 0 | 0.2 | INSPECTION | 2024-11-05 | 2024-11-05 | 371 | 1
JP-01160-H04LQY10AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MOTOR PUMP SET | 0.6 | 20 | 0 | 0.1 | CLEAN | 2024-11-05 | 2024-11-05 | 371 | 1
JP-01160-H04LQY10AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MOTOR PUMP SET | 0.6 | 30 | 0 | 0.2 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 371 | 1
JP-01160-H04LQY10AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE GATE MOTOR PUMP SET | 0.6 | 40 | 0 | 0.1 | VIBRATION CHECK | 2024-11-05 | 2024-11-05 | 371 | 1
JP-01170-H04MFA60KE001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKING DEVICE | 1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-05 | 372 | 0
JP-01170-H04MFA60KE001-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKING DEVICE | 1 | 20 | 0 | 0.5 | OPERATE TEST | 2024-11-05 | 2024-11-05 | 372 | 0
JP-01180-H04PAB10AT301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR OIL COOLER Y-STRAINER NO.1 | 2 | 10 | 0 | 2 | INSPECTION & CLEAN | 2024-11-08 | 2024-11-10 | 373 | 1
JP-01190-H04PAB10AT311-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR OIL COOLER Y-STRAINER NO.2 | 2 | 10 | 0 | 2 | INSPECTION & CLEAN | 2024-11-08 | 2024-11-10 | 374 | 0
JP-01200-H04PAB10AT321-ME-U | EGAT | LTK0 | 0 | ACTIVE | MTR OIL COOLER Y-STRAINER NO.3 | 2 | 10 | 0 | 2 | INSPECTION & CLEAN | 2024-11-08 | 2024-11-10 | 375 | 1
JP-01210-H04QFB30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 376 | 0
JP-01210-H04QFB30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 376 | 0
JP-01210-H04QFB30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 376 | 0
JP-01210-H04QFB30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 376 | 0
JP-01210-H04QFB30CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 376 | 0
JP-01210-H04QFB30CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 377 | 1
JP-01210-H04QFB30CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 377 | 1
JP-01210-H04QFB30CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 377 | 1
JP-01210-H04QFB30CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 377 | 1
JP-01210-H04QFB30CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.70 MPa) - CP110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 377 | 1
JP-01210-H04QFB30CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 378 | 0
JP-01210-H04QFB30CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 378 | 0
JP-01210-H04QFB30CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 378 | 0
JP-01210-H04QFB30CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 378 | 0
JP-01210-H04QFB30CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.55 MPa) - CP120 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 378 | 0
JP-01210-H04QFB30CP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 379 | 1
JP-01210-H04QFB30CP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 379 | 1
JP-01210-H04QFB30CP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 379 | 1
JP-01210-H04QFB30CP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 379 | 1
JP-01210-H04QFB30CP130-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.20 MPa) - CP130 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 379 | 1
JP-01210-H04QFB30CP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 380 | 0
JP-01210-H04QFB30CP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 380 | 0
JP-01210-H04QFB30CP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 380 | 0
JP-01210-H04QFB30CP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 380 | 0
JP-01210-H04QFB30CP140-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (7.00 MPa) - CP140 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 380 | 0
JP-01210-H04QFB30CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 381 | 1
JP-01210-H04QFB30CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 381 | 1
JP-01210-H04QFB30CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 381 | 1
JP-01210-H04QFB30CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 381 | 1
JP-01210-H04QFB30CP150-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK PRESSURE SWITCH (5.80 MPa) - CP150 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 381 | 1
JP-01220-H04QFB30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 382 | 0
JP-01220-H04QFB30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 382 | 0
JP-01220-H04QFB30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 382 | 0
JP-01220-H04QFB30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 382 | 0
JP-01220-H04QFB30CP020-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE TRANSMITTER - CP020 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 382 | 0
JP-01220-H04QFB30CP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 383 | 1
JP-01220-H04QFB30CP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 383 | 1
JP-01220-H04QFB30CP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 383 | 1
JP-01220-H04QFB30CP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 383 | 1
JP-01220-H04QFB30CP160-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (2.40 MPa) - CP160 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 383 | 1
JP-01220-H04QFB30CP170-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 384 | 0
JP-01220-H04QFB30CP170-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 384 | 0
JP-01220-H04QFB30CP170-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 384 | 0
JP-01220-H04QFB30CP170-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 384 | 0
JP-01220-H04QFB30CP170-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE SWITCH (1.80 MPa) - CP170 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 384 | 0
JP-01230-H04QFB31CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 385 | 1
JP-01230-H04QFB31CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 385 | 1
JP-01230-H04QFB31CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 385 | 1
JP-01230-H04QFB31CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 385 | 1
JP-01230-H04QFB31CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 385 | 1
JP-01230-H04QFB31CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 386 | 0
JP-01230-H04QFB31CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 386 | 0
JP-01230-H04QFB31CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 386 | 0
JP-01230-H04QFB31CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 386 | 0
JP-01230-H04QFB31CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.80 MPa) - CP110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 386 | 0
JP-01230-H04QFB31CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 387 | 1
JP-01230-H04QFB31CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 387 | 1
JP-01230-H04QFB31CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 387 | 1
JP-01230-H04QFB31CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 387 | 1
JP-01230-H04QFB31CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE SWITCH (0.70 MPa) - CP120 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 387 | 1
JP-01240-H04QFB32CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 388 | 0
JP-01240-H04QFB32CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 388 | 0
JP-01240-H04QFB32CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 388 | 0
JP-01240-H04QFB32CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 388 | 0
JP-01240-H04QFB32CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 388 | 0
JP-01240-H04QFB32CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 389 | 1
JP-01240-H04QFB32CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 389 | 1
JP-01240-H04QFB32CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 389 | 1
JP-01240-H04QFB32CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 389 | 1
JP-01240-H04QFB32CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.20 MPa) - CP110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 389 | 1
JP-01240-H04QFB32CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 390 | 0
JP-01240-H04QFB32CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 390 | 0
JP-01240-H04QFB32CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 390 | 0
JP-01240-H04QFB32CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 390 | 0
JP-01240-H04QFB32CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE SWITCH (1.10 MPa) - CP120 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 390 | 0
JP-01250-H04QFB33CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 391 | 1
JP-01250-H04QFB33CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 391 | 1
JP-01250-H04QFB33CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 391 | 1
JP-01250-H04QFB33CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 391 | 1
JP-01250-H04QFB33CP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE TRANSMITTER - CP010 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 391 | 1
JP-01250-H04QFB33CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 392 | 0
JP-01250-H04QFB33CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 392 | 0
JP-01250-H04QFB33CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 392 | 0
JP-01250-H04QFB33CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 392 | 0
JP-01250-H04QFB33CP110-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.75 MPa) - CP110 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 392 | 0
JP-01250-H04QFB33CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-12 | 2024-11-12 | 393 | 1
JP-01250-H04QFB33CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-12 | 2024-11-12 | 393 | 1
JP-01250-H04QFB33CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 393 | 1
JP-01250-H04QFB33CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-12 | 2024-11-12 | 393 | 1
JP-01250-H04QFB33CP120-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE SWITCH (0.55 MPa) - CP120 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-12 | 2024-11-12 | 393 | 1
JP-01260-H04QFB30CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 394 | 0
JP-01260-H04QFB30CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 394 | 0
JP-01260-H04QFB30CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 394 | 0
JP-01260-H04QFB30CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 394 | 0
JP-01260-H04QFB30CP310-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.1 PRESSURE GAUGE - CP310 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 394 | 0
JP-01260-H04QFB30CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 395 | 1
JP-01260-H04QFB30CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 395 | 1
JP-01260-H04QFB30CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 395 | 1
JP-01260-H04QFB30CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 395 | 1
JP-01260-H04QFB30CP320-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN AIR TANK NO.2 PRESSURE GAUGE - CP320 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 395 | 1
JP-01270-H04QFB30CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE GAUGE - CP330 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 396 | 0
JP-01270-H04QFB30CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE GAUGE - CP330 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 396 | 0
JP-01270-H04QFB30CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE GAUGE - CP330 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 396 | 0
JP-01270-H04QFB30CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE GAUGE - CP330 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 396 | 0
JP-01270-H04QFB30CP330-ME-U | EGAT | LTK0 | 0 | ACTIVE | AUX AIR TANK PRESSURE GAUGE - CP330 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 396 | 0
JP-01280-H04QFB31CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 397 | 1
JP-01280-H04QFB31CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 397 | 1
JP-01280-H04QFB31CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 397 | 1
JP-01280-H04QFB31CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 397 | 1
JP-01280-H04QFB31CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | BRAKE AIR TANK PRESSURE GAUGE - CP301 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 397 | 1
JP-01290-H04QFB32CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 398 | 0
JP-01290-H04QFB32CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 398 | 0
JP-01290-H04QFB32CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 398 | 0
JP-01290-H04QFB32CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 398 | 0
JP-01290-H04QFB32CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAINTENANCE SEAL AIR TANK PRESSURE GAUGE - CP301 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 398 | 0
JP-01300-H04QFB33CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 4 | 10 | 0 | 0.5 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 399 | 1
JP-01300-H04QFB33CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 4 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 399 | 1
JP-01300-H04QFB33CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 4 | 30 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 399 | 1
JP-01300-H04QFB33CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 4 | 40 | 0 | 1 | CALIBRATION | 2024-11-11 | 2024-11-11 | 399 | 1
JP-01300-H04QFB33CP301-ME-U | EGAT | LTK0 | 0 | ACTIVE | SERVICE AIR TANK PRESSURE GAUGE - CP301 | 4 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 399 | 1
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 10 | 0 | 3 | PREPARATION EQUIPMENT & FACILITY | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 20 | 0 | 3 | SHORT CIRCUIT RTD | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 30 | 0 | 3 | DISCONNECTION & REMOVE MAIN LEAD | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 40 | 0 | 3 | DISCONNECTION & REMOVE NEUTRAL STAR POINT | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 50 | 0 | 3 | INSPECTION (BORESCOPE) | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 60 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 70 | 0 | 3 | ASSEMBLY RTD, CONNECT MAIN LEAD & NEUTRAL STAR POINT | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01310-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หกฟ-ธ.) | 24 | 80 | 0 | 3 | FINAL INSPECTION & FINAL WORK | 2024-11-05 | 2024-11-12 | 400 | 0
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 10 | 0 | 3 | INSULATION RESISTANCE MEASUREMENT (PRETEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 20 | 0 | 3 | D.C. RESISTANCE MEASUREMENT (PRETEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 30 | 0 | 3 | CAPACITANCE MEASUREMENT (PRETEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 40 | 0 | 3 | IMPEDANCE MEASUREMENT (PRETEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 50 | 0 | 3 | INSULATION RESISTANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 60 | 0 | 3 | DC. RESISTANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 70 | 0 | 3 | CAPACITANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 80 | 0 | 3 | IMPEDANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01320-H04MLA10-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR STATOR (หทอฟ-ธ.) | 27 | 90 | 0 | 3 | INSULATION POWER FACTOR TIP UP MEASUEMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 401 | 1
JP-01330-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หกฟ-ธ.) | 12 | 10 | 0 | 3 | PREPARATION EQUIPMENT & FACILITY | 2024-11-05 | 2024-11-12 | 402 | 0
JP-01330-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หกฟ-ธ.) | 12 | 20 | 0 | 3 | INSPECTION (BORESCOPE) | 2024-11-05 | 2024-11-12 | 402 | 0
JP-01330-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หกฟ-ธ.) | 12 | 30 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-12 | 402 | 0
JP-01330-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หกฟ-ธ.) | 12 | 40 | 0 | 3 | FINAL INSPECTION & FINAL WORK | 2024-11-05 | 2024-11-12 | 402 | 0
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 10 | 0 | 3 | INSULATION RESISTANCE MEASUREMENT (PRE TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 20 | 0 | 3 | DC. RESISTANCE MEASUREMENT (PRE TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 30 | 0 | 3 | CAPACITANCE MEASUREMENT (PRE TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 40 | 0 | 3 | IMPEDANCE MEASUREMENT (PRE TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 50 | 0 | 3 | INSULATION RESISTANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 60 | 0 | 3 | DC. RESISTANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 70 | 0 | 3 | CAPACITANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01340-H04MLA30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN. ROTOR (หทอฟ-ธ.) | 24 | 80 | 0 | 3 | IMPEDANCE MEASUREMENT (FINAL TEST) | 2024-11-08 | 2024-11-08 | 403 | 1
JP-01350-H04MLA20CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.1 | 5 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-12 | 404 | 0
JP-01350-H04MLA20CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.1 | 5 | 20 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-12 | 404 | 0
JP-01350-H04MLA20CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.1 | 5 | 30 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-12 | 404 | 0
JP-01350-H04MLA20CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.1 | 5 | 40 | 0 | 1 | CALIBRATION | 2024-11-06 | 2024-11-12 | 404 | 0
JP-01350-H04MLA20CT201-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.1 | 5 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-12 | 404 | 0
JP-01350-H04MLA20CT202-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.2 | 5 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-06 | 2024-11-12 | 405 | 1
JP-01350-H04MLA20CT202-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.2 | 5 | 20 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-12 | 405 | 1
JP-01350-H04MLA20CT202-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.2 | 5 | 30 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-12 | 405 | 1
JP-01350-H04MLA20CT202-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.2 | 5 | 40 | 0 | 1 | CALIBRATION | 2024-11-06 | 2024-11-12 | 405 | 1
JP-01350-H04MLA20CT202-ME-U | EGAT | LTK0 | 0 | ACTIVE | RTD FOR SLIP RING ROOM NO.2 | 5 | 50 | 0 | 1 | ASSEMBLY | 2024-11-06 | 2024-11-12 | 405 | 1
JP-01360-H04MLA20AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.1 | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-12 | 406 | 0
JP-01360-H04MLA20AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.1 | 5 | 20 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-12 | 406 | 0
JP-01360-H04MLA20AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.1 | 5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-12 | 406 | 0
JP-01360-H04MLA20AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.1 | 5 | 40 | 0 | 1 | FILTER REPLACE (IF REQUIRE) | 2024-11-06 | 2024-11-12 | 406 | 0
JP-01360-H04MLA20AP010-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.1 | 5 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-12 | 406 | 0
JP-01360-H04MLA20AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.2 | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-12 | 407 | 1
JP-01360-H04MLA20AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.2 | 5 | 20 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-12 | 407 | 1
JP-01360-H04MLA20AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.2 | 5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-06 | 2024-11-12 | 407 | 1
JP-01360-H04MLA20AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.2 | 5 | 40 | 0 | 1 | FILTER REPLACE (IF REQUIRE) | 2024-11-06 | 2024-11-12 | 407 | 1
JP-01360-H04MLA20AP011-ME-U | EGAT | LTK0 | 0 | ACTIVE | CARBON DUST EXHAUST NO.2 | 5 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-06 | 2024-11-12 | 407 | 1
JP-01370-H04BAU10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 408 | 0
JP-01370-H04BAU10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | 7 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 408 | 0
JP-01370-H04BAU10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | 7 | 30 | 0 | 1 | LUBRICANT | 2024-11-05 | 2024-11-05 | 408 | 0
JP-01370-H04BAU10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | 7 | 40 | 0 | 3 | ELECTRICAL TEST (RESISTANCE MEASUREMENT, INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 408 | 0 | JOBTASK มีความยาวมากกว่า 100 ตัวอักษร
JP-01370-H04BAU10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | NEUTRAL GROUND DISCONNECTING SWITCH (89NGR) | 7 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-05 | 2024-11-05 | 408 | 0
JP-01380-H04BAU10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | NGR CURRENT TRANSFORMER - CE110 | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT, POWER FACTOR MEASUREMENT) | 2024-11-05 | 2024-11-05 | 409 | 1
JP-01380-H04BAU10CE210-ME-U | EGAT | LTK0 | 0 | ACTIVE | NGR POTENTIAL TRANSFORMER - CE210 | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT, POWER FACTOR MEASUREMENT) | 2024-11-05 | 2024-11-05 | 410 | 0
JP-01390-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 411 | 1
JP-01390-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 411 | 1
JP-01390-H04BAA10CE140-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 412 | 0
JP-01390-H04BAA10CE140-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 412 | 0
JP-01390-H04BAA10CE151-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 413 | 1
JP-01390-H04BAA10CE151-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 413 | 1
JP-01390-H04BAA10CE152-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 414 | 0
JP-01390-H04BAA10CE152-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 414 | 0
JP-01390-H04BAA10CE161-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 415 | 1
JP-01390-H04BAA10CE161-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 415 | 1
JP-01390-H04BAA10CE162-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 416 | 0
JP-01390-H04BAA10CE162-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 416 | 0
JP-01390-H04BAA10CE163-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 417 | 1
JP-01390-H04BAA10CE163-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 417 | 1
JP-01390-H04BAB10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 418 | 0
JP-01390-H04BAB10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 418 | 0
JP-01390-H04BAB10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-05 | 419 | 1
JP-01390-H04BAB10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 6 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-05 | 419 | 1
JP-01400-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 420 | 0
JP-01400-H04BAA10CE140-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 421 | 1
JP-01400-H04BAA10CE151-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & GOVERNOR SYSTEM | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 422 | 0
JP-01400-H04BAA10CE152-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C1.2-1.8 - EXCITATION & METERING | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 423 | 1
JP-01400-H04BAA10CE161-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 424 | 0
JP-01400-H04BAA10CE162-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 425 | 1
JP-01400-H04BAA10CE163-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 12000A/5A, C800 - G/M PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 426 | 0
JP-01400-H04BAB10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 427 | 1
JP-01400-H04BAB10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - SPLIT PHASE PROTECTION RELAY | 9 | 10 | 0 | 9 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 428 | 0
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 10 | 0 | 9 | INSPECTION | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 20 | 0 | 2 | CLEANING | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 30 | 0 | 1 | LUBRICANT | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 40 | 0 | 0.5 | MOTOR CURRENT MEASUREMENT | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 50 | 0 | 0.5 | POSITION SENSOR CALIBRATION | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 60 | 0 | 3 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 70 | 0 | 1 | FINAL INSPECTION | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01410-H04BAA10GS600-ME-U | EGAT | LTK0 | 0 | ACTIVE | DYNAMIC BRAKING DISCONNECTING SWITCH (57DB) | 18 | 80 | 0 | 1 | OPERATION TEST | 2024-11-09 | 2024-11-09 | 429 | 1
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 10 | 0 | 9 | INSPECTION | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 20 | 0 | 2 | CLEANING | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 30 | 0 | 1 | LUBRICANT | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 40 | 0 | 0.5 | MOTOR CURRENT MEASUREMENT | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 50 | 0 | 0.5 | POSITION SENSOR CALIBRATION | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 60 | 0 | 3 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 70 | 0 | 1 | FINAL INSPECTION | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01420-H04BAA10GS270-ME-U | EGAT | LTK0 | 0 | ACTIVE | SFC DISCONNECTING SWITCH - 89SB4 (หปฟนม-ธ.) | 18 | 80 | 0 | 1 | OPERATION TEST | 2024-11-10 | 2024-11-10 | 430 | 0
JP-01430-H04BAACE210-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - SYNC & METERING | 6 | 10 | 0 | 2 | INSPECTION | 2024-11-10 | 2024-11-10 | 431 | 1
JP-01430-H04BAACE210-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - SYNC & METERING | 6 | 20 | 0 | 2 | CLEANING | 2024-11-10 | 2024-11-10 | 431 | 1
JP-01430-H04BAACE210-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - SYNC & METERING | 6 | 30 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 431 | 1
JP-01430-H04BAACE220-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION & G/M PROTECTION RELAY | 6 | 10 | 0 | 2 | INSPECTION | 2024-11-10 | 2024-11-10 | 432 | 0
JP-01430-H04BAACE220-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION & G/M PROTECTION RELAY | 6 | 20 | 0 | 2 | CLEANING | 2024-11-10 | 2024-11-10 | 432 | 0
JP-01430-H04BAACE220-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION & G/M PROTECTION RELAY | 6 | 30 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 432 | 0
JP-01430-H04BAACE230-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION, GOVERNOR & G/M PROTECTION RELAY | 6 | 10 | 0 | 2 | INSPECTION | 2024-11-10 | 2024-11-10 | 433 | 1
JP-01430-H04BAACE230-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION, GOVERNOR & G/M PROTECTION RELAY | 6 | 20 | 0 | 2 | CLEANING | 2024-11-10 | 2024-11-10 | 433 | 1
JP-01430-H04BAACE230-ME-U | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5/√3kV:115/√3,1.2, 200VA - EXCITATION, GOVERNOR & G/M PROTECTION RELAY | 6 | 30 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-10 | 2024-11-10 | 433 | 1
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 10 | 0 | 3 | INSPECTION | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 20 | 0 | 3 | CLEANING | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 30 | 0 | 3 | LUBRICANT | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 40 | 0 | 3 | AUX CONTACT MOTOR INSPECTION & REPLACE (IF REQUIRE) | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 50 | 0 | 3 | SF6 GAS TEST (PURITY, DEWPOINT, MOISTURE CONTENT, HF, SO2) | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 60 | 0 | 3 | SF6 GAS FILLING (IF REQUIRE) | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 70 | 0 | 3 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 80 | 0 | 3 | FINAL INSPECTION | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01440-H04BAA10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER (52G) | 27 | 90 | 0 | 3 | OPERATION TEST | 2024-11-05 | 2024-11-08 | 434 | 0
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 20 | 0 | 0.5 | CLEANING | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 30 | 0 | 0.5 | LUBRICANT | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 50 | 0 | 2 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 60 | 0 | 1 | FINAL INSPECTION | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS610-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGG) | 6.5 | 70 | 0 | 1 | OPERATION TEST | 2024-11-08 | 2024-11-08 | 435 | 1
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 20 | 0 | 0.5 | CLEANING | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 30 | 0 | 0.5 | LUBRICANT | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 50 | 0 | 2 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 60 | 0 | 1 | FINAL INSPECTION | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01450-H04BAA10GS620-ME-U | EGAT | LTK0 | 0 | ACTIVE | GCB EARTH SWITCH (MKGT) | 6.5 | 70 | 0 | 1 | OPERATION TEST | 2024-11-08 | 2024-11-08 | 436 | 0
JP-01460-H04BAA10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 437 | 1
JP-01460-H04BAA10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 2 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 437 | 1
JP-01460-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 438 | 0
JP-01460-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 2 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 438 | 0
JP-01460-H04BAA10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER SURGE CAPACITOR | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 439 | 1
JP-01460-H04BAA10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER SURGE CAPACITOR | 2 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 439 | 1
JP-01470-H04BAA10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR CIRCUIT BREAKER SURGE CAPACITOR | 2 | 10 | 0 | 2 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, POWER FACTOR MEASUREMENT, CAPACITOR MEASUREMENT) | 2024-11-08 | 2024-11-08 | 440 | 0
JP-01480-H04BAA10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 3 | 10 | 0 | 3 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 441 | 1
JP-01480-H04BAA10CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 3000A/5A, C800 - TRANSFORMER PROTECTION RELAY | 3 | 10 | 0 | 3 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 442 | 0
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 10 | 0 | 9 | INSPECTION | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 20 | 0 | 2 | CLEANING | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 30 | 0 | 1 | LUBRICANT | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 40 | 0 | 0.5 | MOTOR CURRENT MEASUREMENT | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 50 | 0 | 0.5 | POSITION SENSOR CALIBRATION | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 60 | 0 | 3 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 70 | 0 | 1 | FINAL INSPECTION | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01490-H04BAA10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE DISCONNECTING SWITCH (89PRD) | 18 | 80 | 0 | 1 | OPERATION TEST | 2024-11-08 | 2024-11-08 | 443 | 1
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 10 | 0 | 0.5 | INSPECTION | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 20 | 0 | 0.5 | CLEANING | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 30 | 0 | 0.5 | LUBRICANT | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 40 | 0 | 0.5 | MOTOR CURRENT MEASUREMENT | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 50 | 0 | 0.5 | FINAL INSPECTION | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01500-H04BAA10GS630-ME-U | EGAT | LTK0 | 0 | ACTIVE | PHASE REVERSE EARTHING SWITCH (89PRD-ES) | 3 | 60 | 0 | 0.5 | OPERATION TEST | 2024-11-08 | 2024-11-08 | 444 | 0
JP-01510-H04BAW10GZ100-ME-U | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV. BUS , CABLE, IPB. & ACCESSORIES (หปฟนม-ธ.) | 6 | 10 | 0 | 2 | IPB AIR PRESSURISE CONTROL INSPECTION & CLEAN | 2024-11-05 | 2024-11-08 | 445 | 1
JP-01510-H04BAW10GZ100-ME-U | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV. BUS , CABLE, IPB. & ACCESSORIES (หปฟนม-ธ.) | 6 | 20 | 0 | 2 | IPB TEMPERATURE MONITORING INSPECTION & CLEAN | 2024-11-05 | 2024-11-08 | 445 | 1
JP-01510-H04BAW10GZ100-ME-U | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV. BUS , CABLE, IPB. & ACCESSORIES (หปฟนม-ธ.) | 6 | 30 | 0 | 2 | IPB TEMPERATURE INSTRUMENTS CALIBRATION | 2024-11-05 | 2024-11-08 | 445 | 1
JP-01520-H04BAT01GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER KG4A | 10 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 446 | 0
JP-01520-H04BAT01GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER KG4A | 10 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 446 | 0
JP-01520-H04BAT01GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER KG4A | 10 | 30 | 0 | 2 | SELF PROTECTION INSTRUMENTS INPECTION, CLEANING & TEST | 2024-11-11 | 2024-11-11 | 446 | 0
JP-01520-H04BAT01GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER KG4A | 10 | 40 | 0 | 2 | SF6 PRESSURE INSTRUMENTS INPECTION & CLEANING | 2024-11-11 | 2024-11-11 | 446 | 0
JP-01520-H04BAT01GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER KG4A | 10 | 50 | 0 | 2 | FINAL CHECK | 2024-11-11 | 2024-11-11 | 446 | 0
JP-01530-H04BAT01CD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | 2 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 447 | 1
JP-01530-H04BAT01CD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | 2 | 20 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 447 | 1
JP-01530-H04BAT01CD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | 2 | 30 | 0 | 0.5 | BACK UP | 2024-11-11 | 2024-11-11 | 447 | 1
JP-01530-H04BAT01CD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLINE GAS MONITORING SYSTEM - HYDRAN M2 | 2 | 40 | 0 | 0.5 | TEST | 2024-11-11 | 2024-11-11 | 447 | 1
JP-01540-H04BAT01GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH001 | 5 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 448 | 0
JP-01540-H04BAT01GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH001 | 5 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 448 | 0
JP-01540-H04BAT01GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH001 | 5 | 30 | 0 | 1 | AC & DC SUPPLY FUNCTION TEST | 2024-11-11 | 2024-11-11 | 448 | 0
JP-01540-H04BAT01GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH002 | 5 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 449 | 1
JP-01540-H04BAT01GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH002 | 5 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 449 | 1
JP-01540-H04BAT01GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR TRANSFORMER CONTROL CABINET - GH002 | 5 | 30 | 0 | 1 | AC & DC SUPPLY FUNCTION TEST | 2024-11-11 | 2024-11-11 | 449 | 1
JP-01550-H04BAT01CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 450 | 0
JP-01550-H04BAT01CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1200A/5A, C400 - MTR PROTECTION RELAY (PHASE) | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 451 | 1
JP-01550-H04BAT01CE130-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1000A/5A - MTR PROTECTION RELAY (NEUTRAL) | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 452 | 0
JP-01550-H04BAT01CE150-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1000A/5A - AVR OF OLTC | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 453 | 1
JP-01550-H04BAT01CE160-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 454 | 0
JP-01550-H04BAT01CE170-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230kV, 1000A/5A - WINDING TEMP. TRANSMITTER | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 455 | 1
JP-01550-H04BAT01CE180-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 26000A/5A - WINDING TEMP. TRANSMITTER | 3 | 10 | 0 | 3 | ELECTRICAL TEST ( INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 456 | 0
JP-01560-H04BAT10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SURGE ARRESTER 192kV, 10kA (หปฟนม-ธ.) | 2.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 457 | 1
JP-01560-H04BAT10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SURGE ARRESTER 192kV, 10kA (หปฟนม-ธ.) | 2.5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 457 | 1
JP-01560-H04BAT10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SURGE ARRESTER 192kV, 10kA (หปฟนม-ธ.) | 2.5 | 30 | 0 | 0.5 | SF6 GAS TEST (PURITY, DEWPOINT, MOISTURE CONTENT, HF, SO2) | 2024-11-11 | 2024-11-11 | 457 | 1
JP-01560-H04BAT10GV100-ME-U | EGAT | LTK0 | 0 | ACTIVE | SURGE ARRESTER 192kV, 10kA (หปฟนม-ธ.) | 2.5 | 40 | 0 | 0.5 | SF6 GAS FILLING (IF REQUIRE) | 2024-11-11 | 2024-11-11 | 457 | 1
JP-01570-H04BAT01GH004-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLOAD TAP CHANGER (หปฟนม-ธ.) | 3.5 | 10 | 0 | 1 | INSPECTION | 2024-11-11 | 2024-11-11 | 458 | 0
JP-01570-H04BAT01GH004-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLOAD TAP CHANGER (หปฟนม-ธ.) | 3.5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 458 | 0
JP-01570-H04BAT01GH004-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLOAD TAP CHANGER (หปฟนม-ธ.) | 3.5 | 30 | 0 | 0.5 | MOTOR CURRENT MEASUREMENT | 2024-11-11 | 2024-11-11 | 458 | 0
JP-01570-H04BAT01GH004-ME-U | EGAT | LTK0 | 0 | ACTIVE | ONLOAD TAP CHANGER (หปฟนม-ธ.) | 3.5 | 40 | 0 | 1 | FINAL CHECK | 2024-11-11 | 2024-11-11 | 458 | 0
JP-01580-H04BAT01AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 4.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 459 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01580-H04BAT01AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 4.5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 459 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01580-H04BAT01AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 4.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-11 | 2024-11-11 | 459 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01580-H04BAT01AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 459 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01580-H04BAT01AP110-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.1 - AP110 | 4.5 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-11 | 2024-11-11 | 459 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01590-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 4.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 460 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01590-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 4.5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 460 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01590-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 4.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-11 | 2024-11-11 | 460 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01590-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 460 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01590-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.2 - AP120 | 4.5 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-11 | 2024-11-11 | 460 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01600-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | 4.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 461 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01600-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | 4.5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 461 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01600-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | 4.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-11 | 2024-11-11 | 461 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01600-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | 4.5 | 40 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-11 | 461 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01600-H04BAT01AP120-M01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MOTOR FOR MTR OIL CIRCULATE PUMP NO.3 - AP130 | 4.5 | 50 | 0 | 1 | FUNCTION TEST | 2024-11-11 | 2024-11-11 | 461 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 462 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 462 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 462 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 462 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 462 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 463 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 463 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 463 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 463 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 463 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 464 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 464 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 464 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 464 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 464 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 465 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 465 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 465 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 465 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 465 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 466 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 466 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 466 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 466 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 466 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 467 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 467 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 467 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 467 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 467 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 7 | 10 | 0 | 1 | DISASSEMBLY | 2024-11-11 | 2024-11-11 | 468 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 7 | 20 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-11 | 468 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 7 | 30 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-11 | 468 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 7 | 40 | 0 | 4 | CALIBRATION | 2024-11-11 | 2024-11-11 | 468 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01610-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 7 | 50 | 0 | 1 | ASSEMBLY | 2024-11-11 | 2024-11-11 | 468 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01620-H04CHB10GH101-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OLTC - AVR MODULE | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 469 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01620-H04CHB10GH101-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OLTC - AVR MODULE | 5 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 469 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01620-H04CHB10GH101-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OLTC - AVR MODULE | 5 | 20 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-12 | 469 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01620-H04CHB10GH101-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER OLTC - AVR MODULE | 5 | 30 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 469 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01620-H04EHS40-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END MTR SIDE | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 470 | 0
JP-01620-H04EHS40-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END MTR SIDE | 5 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 470 | 0
JP-01620-H04EHS40-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END MTR SIDE | 5 | 20 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-12 | 470 | 0
JP-01620-H04EHS40-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END MTR SIDE | 5 | 30 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 470 | 0
JP-01630-H04CJA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 471 | 1
JP-01630-H04CJA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 8 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 471 | 1
JP-01630-H04CJA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 8 | 30 | 0 | 3 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 471 | 1
JP-01630-H04CJA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 8 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-05 | 2024-11-05 | 471 | 1
JP-01630-H04CJA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - LOCAL CONTROL PANEL, METERING | 8 | 50 | 0 | 2 | METERING CALIBRATION | 2024-11-05 | 2024-11-05 | 471 | 1
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 20 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 30 | 0 | 3 | RETIGHTENING | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 50 | 0 | 1 | CONTROLLER BACKUP | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 60 | 0 | 1 | CONTROLLER REDUNDANCY TEST | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01640-H04CJA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - DROP 12/62, THOUCHSCREEN | 9 | 70 | 0 | 1 | CONTROLLER POWER LOSS TEST | 2024-11-06 | 2024-11-06 | 472 | 0
JP-01650-H04CJA10GH103-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 473 | 1
JP-01650-H04CJA10GH103-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 7 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 473 | 1
JP-01650-H04CJA10GH103-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 7 | 30 | 0 | 3 | RETIGHTENING | 2024-11-07 | 2024-11-07 | 473 | 1
JP-01650-H04CJA10GH103-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 7 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-07 | 2024-11-07 | 473 | 1
JP-01650-H04CJA10GH103-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-1 (I/O CUBICLE), WINDOWS ANNUNCIATOR | 7 | 50 | 0 | 1 | ANNUNCIATOR SIGNAL TEST | 2024-11-07 | 2024-11-07 | 473 | 1
JP-01660-H04CJA10GH104-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 474 | 0
JP-01660-H04CJA10GH104-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | 6 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 474 | 0
JP-01660-H04CJA10GH104-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | 6 | 30 | 0 | 3 | RETIGHTENING | 2024-11-08 | 2024-11-08 | 474 | 0
JP-01660-H04CJA10GH104-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 LCU - EXT DROP 12-2 (I/O CUBICLE) | 6 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-08 | 2024-11-08 | 474 | 0
JP-01670-H04CJA10GH105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-09 | 2024-11-09 | 475 | 1
JP-01670-H04CJA10GH105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 7 | 20 | 0 | 1 | CLEANING | 2024-11-09 | 2024-11-09 | 475 | 1
JP-01670-H04CJA10GH105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 7 | 30 | 0 | 3 | RETIGHTENING | 2024-11-09 | 2024-11-09 | 475 | 1
JP-01670-H04CJA10GH105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 7 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-09 | 2024-11-09 | 475 | 1
JP-01670-H04CJA10GH105-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - REMOTE I/O CUBICLE, TOUCHSCREEN, METERING | 7 | 50 | 0 | 1 | METERING CALIBRATION | 2024-11-09 | 2024-11-09 | 475 | 1
JP-01680-H04CJA10GH106-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-10 | 2024-11-10 | 476 | 0
JP-01680-H04CJA10GH106-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 7 | 20 | 0 | 1 | CLEANING | 2024-11-10 | 2024-11-10 | 476 | 0
JP-01680-H04CJA10GH106-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 7 | 30 | 0 | 3 | RETIGHTENING | 2024-11-10 | 2024-11-10 | 476 | 0
JP-01680-H04CJA10GH106-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 7 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-10 | 2024-11-10 | 476 | 0
JP-01680-H04CJA10GH106-ME-U | EGAT | LTK0 | 0 | ACTIVE | UNIT 4 RIO - EXT 12-1-1(I/O CUBICLE), WINDOW ANNUNCIATOR | 7 | 50 | 0 | 1 | ANNUNCIATOR SIGNAL TEST | 2024-11-10 | 2024-11-10 | 476 | 0
JP-01690-H04CKA20GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | VIBRATION MONITORING SYSTEM (MMS) | 6 | 10 | 0 | 1 | INSPECTION | 2024-11-11 | 2024-11-11 | 477 | 1
JP-01690-H04CKA20GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | VIBRATION MONITORING SYSTEM (MMS) | 6 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 477 | 1
JP-01690-H04CKA20GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | VIBRATION MONITORING SYSTEM (MMS) | 6 | 30 | 0 | 3 | RETIGHTENING | 2024-11-11 | 2024-11-11 | 477 | 1
JP-01690-H04CKA20GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | VIBRATION MONITORING SYSTEM (MMS) | 6 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-11 | 2024-11-11 | 477 | 1
JP-01700-H04CKA20CY001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - SHAFT RUNOUT X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 478 | 0
JP-01700-H04CKA20CY001-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - SHAFT RUNOUT X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 478 | 0
JP-01700-H04CKA20CY002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - SHAFT RUNOUT Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 479 | 1
JP-01700-H04CKA20CY002-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - SHAFT RUNOUT Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 479 | 1
JP-01700-H04CKA20CY003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - VIBRATION X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 480 | 0
JP-01700-H04CKA20CY003-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - VIBRATION X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 480 | 0
JP-01700-H04CKA20CY004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - VIBRATION Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 481 | 1
JP-01700-H04CKA20CY004-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING - VIBRATION Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 481 | 1
JP-01700-H04CKA20CY005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - SHAFT RUNOUT X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 482 | 0
JP-01700-H04CKA20CY005-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - SHAFT RUNOUT X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 482 | 0
JP-01700-H04CKA20CY006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - SHAFT RUNOUT Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 483 | 1
JP-01700-H04CKA20CY006-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - SHAFT RUNOUT Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 483 | 1
JP-01700-H04CKA20CY007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - VIBRATION X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 484 | 0
JP-01700-H04CKA20CY007-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - VIBRATION X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 484 | 0
JP-01700-H04CKA20CY008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - VIBRATION Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 485 | 1
JP-01700-H04CKA20CY008-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOWER GUIDE BEARING - VIBRATION Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 485 | 1
JP-01700-H04CKA20CY009-ME-U | EGAT | LTK0 | 0 | ACTIVE | STATOR FRAME - VIBRATION X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 486 | 0
JP-01700-H04CKA20CY009-ME-U | EGAT | LTK0 | 0 | ACTIVE | STATOR FRAME - VIBRATION X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 486 | 0
JP-01700-H04CKA20CY010-ME-U | EGAT | LTK0 | 0 | ACTIVE | STATOR FRAME - VIBRATION Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 487 | 1
JP-01700-H04CKA20CY010-ME-U | EGAT | LTK0 | 0 | ACTIVE | STATOR FRAME - VIBRATION Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 487 | 1
JP-01700-H04CKA20CY011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - VIBRATION X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 488 | 0
JP-01700-H04CKA20CY011-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - VIBRATION X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 488 | 0
JP-01700-H04CKA20CY012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - VIBRATION Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 489 | 1
JP-01700-H04CKA20CY012-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - VIBRATION Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 489 | 1
JP-01700-H04CKA20CY013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - SHAFT RUNOUT X | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 490 | 0
JP-01700-H04CKA20CY013-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - SHAFT RUNOUT X | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 490 | 0
JP-01700-H04CKA20CY014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - SHAFT RUNOUT Y | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 491 | 1
JP-01700-H04CKA20CY014-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING - SHAFT RUNOUT Y | 2 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 491 | 1
JP-01710-H04CHA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM A CUBICLE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 492 | 0
JP-01710-H04CHA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM A CUBICLE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 492 | 0
JP-01710-H04CHA10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM A CUBICLE | 3 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-13 | 492 | 0
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 30 | 0 | 1 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 40 | 0 | 7 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 50 | 0 | 7 | OPERATING CHARECTERISTIC TEST (87, 87S, 24G) | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 60 | 0 | 7 | OPERATING CHARECTERISTIC TEST (64G1, 64G2, 40) | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01720-H04CHA10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM A | 31 | 70 | 0 | 7 | OPERATING CHARECTERISTIC TEST (51V, 51GN, 51M, 51B) | 2024-11-05 | 2024-11-13 | 493 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01730-H04CHA10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | SPLIT PHASE PROTECTION RELAY | 7 | 10 | 0 | 7 | 87GW | 2024-11-05 | 2024-11-13 | 494 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01740-H04CHA10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM A) | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 495 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01740-H04CHA10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM A) | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 495 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01740-H04CHA10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM A) | 3 | 30 | 0 | 1 | OPERATION TEST | 2024-11-05 | 2024-11-13 | 495 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01750-H04CHA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM B CUBICLE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 496 | 0
JP-01750-H04CHA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM B CUBICLE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 496 | 0
JP-01750-H04CHA10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR PROTECTION SYSTEM B CUBICLE | 3 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-13 | 496 | 0
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 30 | 0 | 1 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 40 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 50 | 0 | 4 | OPERATING CHARECTERISTIC TEST (81G, 81M,) | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 60 | 0 | 4 | OPERATING CHARECTERISTIC TEST (78S, 50BF) | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01760-H04CHA10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M ELECTRICAL PROTECTION RELAY - SYSTEM B | 16 | 70 | 0 | 4 | OPERATING CHARECTERISTIC TEST (64E, 49G) | 2024-11-05 | 2024-11-13 | 497 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01770-H04CHA10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M MECHANICAL PROTECTION RELAY | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 498 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01770-H04CHA10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M MECHANICAL PROTECTION RELAY | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 498 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01770-H04CHA10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M MECHANICAL PROTECTION RELAY | 3 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 498 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01780-H04CHA10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM B) | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 499 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01780-H04CHA10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM B) | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 499 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01780-H04CHA10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-1 (SYSTEM B) | 3 | 30 | 0 | 1 | OPERATION TEST | 2024-11-05 | 2024-11-13 | 499 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01790-H04CHA10GH102-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-2 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 500 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01790-H04CHA10GH102-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-2 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 500 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01790-H04CHA10GH102-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-2 | 3 | 30 | 0 | 1 | OPERATION TEST | 2024-11-05 | 2024-11-13 | 500 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01800-H04CHB10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM A CUBICLE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 501 | 1
JP-01800-H04CHB10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM A CUBICLE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 501 | 1
JP-01800-H04CHB10GH101-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM A CUBICLE | 3 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-13 | 501 | 1
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 30 | 0 | 1 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 40 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 50 | 0 | 4 | OPERATING CHARECTERISTIC TEST (81T, 51T, 51TN) | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01810-H04CHB10GH101-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM A | 12 | 60 | 0 | 4 | OPERATING CHARECTERISTIC TEST (64B, 24T) | 2024-11-05 | 2024-11-13 | 502 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01820-H04CHB10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 503 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01820-H04CHB10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 8 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 503 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01820-H04CHB10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 8 | 30 | 0 | 1 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-13 | 503 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01820-H04CHB10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 8 | 40 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 503 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01820-H04CHB10GH101-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM A | 8 | 50 | 0 | 4 | OPERATING CHARECTERISTIC TEST (87ET, 51ET, 49ET) | 2024-11-05 | 2024-11-13 | 503 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01830-H04CHB10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM A) | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 504 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01830-H04CHB10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM A) | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 504 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01830-H04CHB10GH101-K01-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM A) | 3 | 30 | 0 | 1 | OPERATION TEST | 2024-11-05 | 2024-11-13 | 504 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01840-H04CHB10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM B CUBICLE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 505 | 1
JP-01840-H04CHB10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM B CUBICLE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 505 | 1
JP-01840-H04CHB10GH102-ME-U | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER PROTECTION SYSTEM B CUBICLE | 3 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-13 | 505 | 1
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 30 | 0 | 1 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 40 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 50 | 0 | 4 | OPERATING CHARECTERISTIC TEST (81T, 51T, 51TN) | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01850-H04CHB10GH102-U01-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER ELECTRICAL PROTECTION RELAY - SYSTEM B | 12 | 60 | 0 | 4 | OPERATING CHARECTERISTIC TEST (64B, 24T) | 2024-11-05 | 2024-11-13 | 506 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01860-H04CHB10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | 4 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 507 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01860-H04CHB10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | 4 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 507 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01860-H04CHB10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | 4 | 40 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 507 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01860-H04CHB10GH102-U02-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER PROTECTION RELAY - SYSTEM B | 4 | 50 | 0 | 1 | OPERATING CHARECTERISTIC TEST (87ET, 51ET, 49ET) | 2024-11-05 | 2024-11-13 | 507 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01870-H04CHB10GH102-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER MECHNICAL PROTECTION RELAY | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-13 | 508 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01870-H04CHB10GH102-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER MECHNICAL PROTECTION RELAY | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-13 | 508 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01870-H04CHB10GH102-U03-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN TRANSFORMER MECHNICAL PROTECTION RELAY | 3 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-13 | 508 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01880-H04CHB10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM B) | 1.5 | 10 | 0 | 0.5 | INSPECTION | 2024-11-05 | 2024-11-13 | 509 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01880-H04CHB10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM B) | 1.5 | 20 | 0 | 0.5 | CLEANING | 2024-11-05 | 2024-11-13 | 509 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01880-H04CHB10GH102-K02-ME-U | EGAT | LTK0 | 0 | ACTIVE | LOCKOUT RELAY 86-T (SYSTEM B) | 1.5 | 30 | 0 | 0.5 | OPERATION TEST | 2024-11-05 | 2024-11-13 | 509 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 40 | 0 | 1 | AIR FILTER REPLACE | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 50 | 0 | 4 | CONTROLLER BACKUP | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01890-H04MEY10GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DIGITAL GOVERNOR CONTROL CUBICLE | 12 | 60 | 0 | 4 | METERING CALIBRATION | 2024-11-05 | 2024-11-12 | 510 | 0
JP-01900-H04MFX20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL ACTUATOR | 51 | 10 | 0 | 35 | INEPECTION | 2024-11-05 | 2024-11-12 | 511 | 1
JP-01900-H04MFX20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL ACTUATOR | 51 | 20 | 0 | 12 | CLEANING | 2024-11-05 | 2024-11-12 | 511 | 1
JP-01900-H04MFX20-ME-U | EGAT | LTK0 | 0 | ACTIVE | GOVERNOR CONTROL ACTUATOR | 51 | 30 | 0 | 4 | CHARACTERISTIC TEST | 2024-11-05 | 2024-11-12 | 511 | 1
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 20 | 0 | 1 | CLEANING | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 30 | 0 | 1 | LUBRICANT | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 50 | 0 | 1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 60 | 0 | 1 | FINAL INSPECTION | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01910-H04BAA10GS290-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER DISCONNECTING SWITCH (89E) | 7 | 70 | 0 | 1 | OPERATION TEST | 2024-11-06 | 2024-11-06 | 512 | 0
JP-01920-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หปฟนม-ธ.) | 6 | 10 | 0 | 2 | INSPECTION | 2024-11-07 | 2024-11-07 | 513 | 1
JP-01920-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หปฟนม-ธ.) | 6 | 20 | 0 | 2 | CLEANING | 2024-11-07 | 2024-11-07 | 513 | 1
JP-01920-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หปฟนม-ธ.) | 6 | 30 | 0 | 2 | FAN TEST | 2024-11-07 | 2024-11-07 | 513 | 1
JP-01930-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หทอฟ-ธ.) | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 514 | 0
JP-01930-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หทอฟ-ธ.) | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 514 | 0
JP-01930-H04MLC10GT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION TRANSFORMER (หทอฟ-ธ.) | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-08 | 2024-11-08 | 514 | 0
JP-01940-H04MLC10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 515 | 1
JP-01940-H04MLC10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | 2 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 515 | 1
JP-01950-H04MLC10CE110-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 300A/5A, C100 - TRANSFORMER PROTECTION (หทอฟ-ธ.) | 3 | 10 | 0 | 3 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 516 | 0
JP-01960-H04MLC10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | 2 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 517 | 1
JP-01960-H04MLC10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION (หบฟนม-ธ.) | 2 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 517 | 1
JP-01970-H04MLC10CE120-ME-U | EGAT | LTK0 | 0 | ACTIVE | CT: 230V, 3000A/5A, C200 - TRANSFORMER PROTECTION (หทอฟ-ธ.) | 3 | 10 | 0 | 3 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-08 | 2024-11-08 | 518 | 0
JP-01980-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-12 | 519 | 1
JP-01980-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | 8 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 519 | 1
JP-01980-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | 8 | 30 | 0 | 2 | BRUSH PRESSURE MEASUREMENT | 2024-11-05 | 2024-11-12 | 519 | 1
JP-01980-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | 8 | 40 | 0 | 2 | BRUSH LENGHT MEASUREMENT | 2024-11-05 | 2024-11-12 | 519 | 1
JP-01980-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หกฟ-ธ.) | 8 | 50 | 0 | 2 | POLISH SURFACE | 2024-11-05 | 2024-11-12 | 519 | 1
JP-01990-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-12 | 520 | 0
JP-01990-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | 8 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 520 | 0
JP-01990-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | 8 | 30 | 0 | 2 | BRUSH PRESSURE MEASUREMENT | 2024-11-05 | 2024-11-12 | 520 | 0
JP-01990-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | 8 | 40 | 0 | 2 | BRUSH LENGHT MEASUREMENT | 2024-11-05 | 2024-11-12 | 520 | 0
JP-01990-H04MLA20-ME-U | EGAT | LTK0 | 0 | ACTIVE | SLIP RING AND CARBON BRUSH (หบฟนม-ธ.) | 8 | 50 | 0 | 2 | POLISH SURFACE | 2024-11-05 | 2024-11-12 | 520 | 0
JP-02000-H04MLC10GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROLLER CUBICLE (หรคฟ-ธ.) | 9 | 10 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-12 | 521 | 1
JP-02000-H04MLC10GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROLLER CUBICLE (หรคฟ-ธ.) | 9 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 521 | 1
JP-02000-H04MLC10GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROLLER CUBICLE (หรคฟ-ธ.) | 9 | 30 | 0 | 3 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 521 | 1
JP-02000-H04MLC10GH100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROLLER CUBICLE (หรคฟ-ธ.) | 9 | 40 | 0 | 3 | METERING CALIBRATION | 2024-11-05 | 2024-11-12 | 521 | 1
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 10 | 0 | 3 | POWER SUPPLY CHECK | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 20 | 0 | 3 | PARAMETER SETTING CHECK & BACKUP | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 30 | 0 | 3 | ANALOG INPUT CHECK | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 40 | 0 | 3 | TRANSDUCER CALIBRATION | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 50 | 0 | 4 | LIMITER TEST | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02010-H04MLC10DE100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION CONTROL (AVR) | 20 | 60 | 0 | 4 | STATIC OR PULSE FIRING CONTROL TEST | 2024-11-05 | 2024-11-12 | 522 | 0
JP-02020-H04MLC10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION INCOMING BUS CUBICLE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-12 | 523 | 1
JP-02020-H04MLC10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION INCOMING BUS CUBICLE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 523 | 1
JP-02020-H04MLC10GS100-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION INCOMING BUS CUBICLE | 3 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 523 | 1
JP-02030-H04MLC10GH200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 1 CUBICLE | 6.5 | 10 | 0 | 1.5 | INSPECTION | 2024-11-05 | 2024-11-12 | 524 | 0
JP-02030-H04MLC10GH200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 1 CUBICLE | 6.5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 524 | 0
JP-02030-H04MLC10GH200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 1 CUBICLE | 6.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 524 | 0
JP-02030-H04MLC10GH200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 1 CUBICLE | 6.5 | 40 | 0 | 1 | FAN TEST | 2024-11-05 | 2024-11-12 | 524 | 0
JP-02030-H04MLC10GH200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 1 CUBICLE | 6.5 | 50 | 0 | 2 | POWER CONVERTER JUNCTION RESISTANCE TEST | 2024-11-05 | 2024-11-12 | 524 | 0
JP-02040-H04MLC10GH201-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 2 CUBICLE | 6.5 | 10 | 0 | 1.5 | INSPECTION | 2024-11-05 | 2024-11-12 | 525 | 1
JP-02040-H04MLC10GH201-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 2 CUBICLE | 6.5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 525 | 1
JP-02040-H04MLC10GH201-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 2 CUBICLE | 6.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 525 | 1
JP-02040-H04MLC10GH201-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 2 CUBICLE | 6.5 | 40 | 0 | 1 | FAN TEST | 2024-11-05 | 2024-11-12 | 525 | 1
JP-02040-H04MLC10GH201-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION POWER CONVERTER 2 CUBICLE | 6.5 | 50 | 0 | 2 | POWER CONVERTER JUNCTION RESISTANCE TEST | 2024-11-05 | 2024-11-12 | 525 | 1
JP-02050-H04MLC10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION FIELD BREAKER (41E) CUBICLE | 3.5 | 10 | 0 | 1.5 | INSPECTION | 2024-11-05 | 2024-11-12 | 526 | 0
JP-02050-H04MLC10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION FIELD BREAKER (41E) CUBICLE | 3.5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 526 | 0
JP-02050-H04MLC10GS200-ME-U | EGAT | LTK0 | 0 | ACTIVE | EXCITATION FIELD BREAKER (41E) CUBICLE | 3.5 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-12 | 526 | 0
JP-02060-H04MLC10GS140-ME-U | EGAT | LTK0 | 0 | ACTIVE | FIELD BREAKER (41E) | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-12 | 527 | 1
JP-02060-H04MLC10GS140-ME-U | EGAT | LTK0 | 0 | ACTIVE | FIELD BREAKER (41E) | 5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-12 | 527 | 1
JP-02060-H04MLC10GS140-ME-U | EGAT | LTK0 | 0 | ACTIVE | FIELD BREAKER (41E) | 5 | 30 | 0 | 1 | LUBRICANT | 2024-11-05 | 2024-11-12 | 527 | 1
JP-02060-H04MLC10GS140-ME-U | EGAT | LTK0 | 0 | ACTIVE | FIELD BREAKER (41E) | 5 | 40 | 0 | 1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-05 | 2024-11-12 | 527 | 1
JP-02060-H04MLC10GS140-ME-U | EGAT | LTK0 | 0 | ACTIVE | FIELD BREAKER (41E) | 5 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-05 | 2024-11-12 | 527 | 1
JP-02070-H14ASU30GH101-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | LCB/GIS, TRANSFORMER U #3 (KG3A) CUBICLE | 1 | 10 | 0 | 0.5 | INSPECTION | 2024-11-11 | 2024-11-12 | 528 | 0
JP-02070-H14ASU30GH101-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | LCB/GIS, TRANSFORMER U #3 (KG3A) CUBICLE | 1 | 20 | 0 | 0.5 | CLEANING | 2024-11-11 | 2024-11-12 | 528 | 0
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 10 | 0 | 2.1 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 20 | 0 | 2.1 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 30 | 0 | 2.1 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 40 | 0 | 2.1 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 50 | 0 | 2.1 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 60 | 0 | 2.1 | SF6 GAS TEST (PURITY, DEWPOINT, MOISTURE CONTENT, HF, SO2) | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 70 | 0 | 2.1 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 80 | 0 | 2.1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 90 | 0 | 2.1 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02080-H12ADA30GS100-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | BKR.LTK 80092, TRANSFORMER NO.4 (KG4A) | 21 | 100 | 0 | 2.1 | OPERATION TEST | 2024-11-11 | 2024-11-12 | 529 | 1
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS200-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80096, TRANSFORMER NO.4 (KG4A) GIS | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 530 | 0
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS201-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80097, TRANSFORMER NO.4 (KG4A) | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 531 | 1
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS202-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094, TRANSFORMER NO.4 (KG4A) | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 532 | 0
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS203-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GA, TRANSFORMER NO.4 (KG4A) | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 533 | 1
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS204-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GB, TRANSFORMER NO.4 (KG4A) | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 534 | 0
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 10 | 0 | 0.33 | ISOLATE EQUIPMENT | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 20 | 0 | 0.33 | COMPARTMENT INSPECTION | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 30 | 0 | 0.33 | COMPARTMENT CLEANING | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 40 | 0 | 0.33 | OPERATING MECHANISM INSPECTION | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 50 | 0 | 0.33 | LUBRICANT (if require) | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 60 | 0 | 0.33 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 70 | 0 | 0.33 | ELECTRICAL TEST (CONTACT RESISTANCE TEST) | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 80 | 0 | 0.33 | FINAL INSPECTION | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02090-H12ADA31GS205-ME-C12 | EGAT | LTK0 | 0 | ACTIVE | DS.LTK 80094GC, EARTH SW(HSG), KG4A | 2.97 | 90 | 0 | 0.33 | OPERATION TEST (Except DS. LTK-80086, DS LTK-80087) | 2024-11-11 | 2024-11-12 | 535 | 1
JP-02100-H04EHS30-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END GIS SIDE | 4.5 | 10 | 0 | 1.5 | INSPECTION & CLEANING | 2024-11-11 | 2024-11-12 | 536 | 0
JP-02100-H04EHS30-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END GIS SIDE | 4.5 | 20 | 0 | 1.5 | SF6 GAS QUALITY MEASUREMENT | 2024-11-11 | 2024-11-12 | 536 | 0
JP-02100-H04EHS30-ME-U | EGAT | LTK0 | 0 | ACTIVE | SEALING END GIS SIDE | 4.5 | 30 | 0 | 1.5 | SF6 GAS FILLING (if require) | 2024-11-11 | 2024-11-12 | 536 | 0
JP-02110-H03MFP14GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - CONTROL PANEL | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 537 | 1
JP-02110-H03MFP14GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - CONTROL PANEL | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 537 | 1
JP-02110-H03MFP14GH002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - CONTROL PANEL | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 537 | 1
JP-02110-H03MFP14HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 538 | 0
JP-02110-H03MFP14HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 538 | 0
JP-02110-H03MFP14HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 538 | 0
JP-02110-H03MFP14HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 539 | 1
JP-02110-H03MFP14HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 539 | 1
JP-02110-H03MFP14HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 539 | 1
JP-02110-H03MFP14HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 540 | 0
JP-02110-H03MFP14HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 540 | 0
JP-02110-H03MFP14HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 540 | 0
JP-02110-H03MFP14HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 541 | 1
JP-02110-H03MFP14HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 541 | 1
JP-02110-H03MFP14HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 541 | 1
JP-02110-H03MFP14HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 542 | 0
JP-02110-H03MFP14HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 542 | 0
JP-02110-H03MFP14HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 542 | 0
JP-02110-H03MFP14HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 543 | 1
JP-02110-H03MFP14HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 543 | 1
JP-02110-H03MFP14HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 543 | 1
JP-02110-H03MFP14SD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.1 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 544 | 0
JP-02110-H03MFP14SD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.1 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 544 | 0
JP-02110-H03MFP14SD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 544 | 0
JP-02110-H03MFP14SD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.2 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 545 | 1
JP-02110-H03MFP14SD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.2 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 545 | 1
JP-02110-H03MFP14SD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 545 | 1
JP-02110-H03MFP14SD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.3 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 546 | 0
JP-02110-H03MFP14SD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.3 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 546 | 0
JP-02110-H03MFP14SD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.3 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 546 | 0
JP-02110-H03MFP14SD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.4 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 547 | 1
JP-02110-H03MFP14SD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.4 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 547 | 1
JP-02110-H03MFP14SD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.4 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 547 | 1
JP-02110-H03MFP14SD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.5 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 548 | 0
JP-02110-H03MFP14SD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.5 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 548 | 0
JP-02110-H03MFP14SD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.5 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 548 | 0
JP-02110-H03MFP14SD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.6 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 549 | 1
JP-02110-H03MFP14SD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.6 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 549 | 1
JP-02110-H03MFP14SD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SMOKE DETECTOR NO.6 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 549 | 1
JP-02110-H04MFP14AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SOLINOID DRIVE DELUGE VALVE | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 550 | 0
JP-02110-H04MFP14AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SOLINOID DRIVE DELUGE VALVE | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 550 | 0
JP-02110-H04MFP14AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - SOLINOID DRIVE DELUGE VALVE | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 550 | 0
JP-02110-H04MFP14CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER WATER DISCHARGE PRESSURE SWITCH - CP001 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 551 | 1
JP-02110-H04MFP14CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER WATER DISCHARGE PRESSURE SWITCH - CP001 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 551 | 1
JP-02110-H04MFP14CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER WATER DISCHARGE PRESSURE SWITCH - CP001 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 551 | 1
JP-02110-H04MFP14GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - MODULE BOX | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-07 | 2024-11-07 | 552 | 0
JP-02110-H04MFP14GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - MODULE BOX | 3 | 20 | 0 | 1 | CLEANING | 2024-11-07 | 2024-11-07 | 552 | 0
JP-02110-H04MFP14GH001-ME-U | EGAT | LTK0 | 0 | ACTIVE | G/M FIRE EXTINGUISHER - MODULE BOX | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-07 | 2024-11-07 | 552 | 0
JP-02120-H04SGC10AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.1 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 553 | 1
JP-02120-H04SGC10AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.1 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 553 | 1
JP-02120-H04SGC10AA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 553 | 1
JP-02120-H04SGC10AA002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.2 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 554 | 0
JP-02120-H04SGC10AA002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.2 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 554 | 0
JP-02120-H04SGC10AA002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER - SOLINOID DRIVE DELUGE VALVE NO.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 554 | 0
JP-02120-H04SGC10CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY LINE PRESSURE GAUGE - CP001 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 555 | 1
JP-02120-H04SGC10CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY LINE PRESSURE GAUGE - CP001 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 555 | 1
JP-02120-H04SGC10CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY LINE PRESSURE GAUGE - CP001 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 555 | 1
JP-02120-H04SGC10CP002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY DELUGE PRESSURE GAUGE - CP002 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 556 | 0
JP-02120-H04SGC10CP002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY DELUGE PRESSURE GAUGE - CP002 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 556 | 0
JP-02120-H04SGC10CP002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER SUPPLY DELUGE PRESSURE GAUGE - CP002 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 556 | 0
JP-02120-H04SGC10CP003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER DISCHARGE PRESSURE SWITCH - CP003 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 557 | 1
JP-02120-H04SGC10CP003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER DISCHARGE PRESSURE SWITCH - CP003 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 557 | 1
JP-02120-H04SGC10CP003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISGER WATER DISCHARGE PRESSURE SWITCH - CP003 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 557 | 1
JP-02120-H04SGC10HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 558 | 0
JP-02120-H04SGC10HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 558 | 0
JP-02120-H04SGC10HD001-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.1 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 558 | 0
JP-02120-H04SGC10HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 559 | 1
JP-02120-H04SGC10HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 559 | 1
JP-02120-H04SGC10HD002-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.2 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 559 | 1
JP-02120-H04SGC10HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 560 | 0
JP-02120-H04SGC10HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 560 | 0
JP-02120-H04SGC10HD003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.3 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 560 | 0
JP-02120-H04SGC10HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 561 | 1
JP-02120-H04SGC10HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 561 | 1
JP-02120-H04SGC10HD004-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.4 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 561 | 1
JP-02120-H04SGC10HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 562 | 0
JP-02120-H04SGC10HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 562 | 0
JP-02120-H04SGC10HD005-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.5 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 562 | 0
JP-02120-H04SGC10HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 563 | 1
JP-02120-H04SGC10HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 563 | 1
JP-02120-H04SGC10HD006-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.6 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 563 | 1
JP-02120-H04SGC10HD007-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.7 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 564 | 0
JP-02120-H04SGC10HD007-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.7 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 564 | 0
JP-02120-H04SGC10HD007-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.7 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 564 | 0
JP-02120-H04SGC10HD008-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.8 | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 565 | 1
JP-02120-H04SGC10HD008-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.8 | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 565 | 1
JP-02120-H04SGC10HD008-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A FIRE EXTINGUISHER - HEAT DETECTOR NO.8 | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 565 | 1
JP-02120-H34SGC10EA001-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER FIRE EXTINGUISHER - CONTROL PANEL | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 566 | 0
JP-02120-H34SGC10EA001-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER FIRE EXTINGUISHER - CONTROL PANEL | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 566 | 0
JP-02120-H34SGC10EA001-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | TRANSFORMER FIRE EXTINGUISHER - CONTROL PANEL | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 566 | 0
JP-02130-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 567 | 1
JP-02130-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 567 | 1
JP-02130-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KG4A TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 567 | 1
JP-02140-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KW3B TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-08 | 2024-11-08 | 568 | 0
JP-02140-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KW3B TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 20 | 0 | 1 | CLEANING | 2024-11-08 | 2024-11-08 | 568 | 0
JP-02140-H04BAT01GH003-ME-U | EGAT | LTK0 | 0 | ACTIVE | KW3B TRANSFORMER FIRE PROTECTION SYSTEM (SERGI) | 3 | 30 | 0 | 1 | FUNCTION TEST | 2024-11-08 | 2024-11-08 | 568 | 0
JP-02150-H04ML-ME-U | EGAT | LTK0 | 0 | ACTIVE | CIVIL INSPECTION | 1.5 | 10 | 0 | 1.5 | ตรวจสอบคอนกรีต VISUALl INSP. GENERATOR | 2024-11-06 | 2024-11-06 | 569 | 1
JP-02160-H04MFA-ME-U | EGAT | LTK0 | 0 | ACTIVE | CIVIL INSPECTION | 1.5 | 10 | 0 | 1.5 | ตรวจสอบสภาพผนังภายนอก ชั้น TURBINE FLOOR | 2024-11-06 | 2024-11-06 | 570 | 0
JP-02170-H04MLD10HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | CIVIL INSPECTION | 1.5 | 10 | 0 | 1.5 | ตรวจสอบสภาพคอนกรีต ที่ LOWER BRACKET | 2024-11-06 | 2024-11-06 | 571 | 1
JP-02180-H04CMB10-ME-U | EGAT | LTK0 | 0 | ACTIVE | CIVIL INSPECTION | 1.5 | 10 | 0 | 1.5 | ตรวจสอบสภาพคอนกรีต ที่ UPPER BRACKET | 2024-11-06 | 2024-11-06 | 572 | 0
JP-02190-H04L-ME-U | EGAT | LTK0 | 0 | ACTIVE | CIVIL INSPECTION | 3 | 10 | 0 | 3 | ตรวจสอบสภาพคอนกรีต ที่ DRAFT TUBE | 2024-11-07 | 2024-11-07 | 573 | 1
JP-02200-H04-ME-U | EGAT | LTK0 | 0 | ACTIVE | Unit | 21 | 10 | 0 | 21 | Heat run | 2024-11-14 | 2024-11-16 | 574 | 0
JP-02210-H04MLA30HB002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN UPPER SHAFT | 3 | 10 | 0 | 2 | Shaft keeping | 2024-11-05 | 2024-11-05 | 575 | 1
JP-02210-H04MLA30HB002-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN UPPER SHAFT | 3 | 20 | 0 | 1 | Shaft unkeeping | 2024-11-13 | 2024-11-13 | 575 | 1
JP-02220-H04MLA30HB003-ME-U | EGAT | LTK0 | 0 | ACTIVE | Gen LOWER SHAFT | 3 | 10 | 0 | 2 | Shaft keeping | 2024-11-05 | 2024-11-05 | 576 | 0
JP-02220-H04MLA30HB003-ME-U | EGAT | LTK0 | 0 | ACTIVE | Gen LOWER SHAFT | 3 | 20 | 0 | 1 | Shaft unkeeping | 2024-11-13 | 2024-11-13 | 576 | 0
JP-02230-H04MLV40BR001-ME-U | EGAT | LTK0 | 0 | ACTIVE | HIGH PRESSURE OIL PIPE | 24 | 10 | 0 | 24 | SEAL REPLACEMENT | 2024-11-09 | 2024-11-11 | 577 | 1
JP-02240-H04MFA30HB200-ME-U | EGAT | LTK0 | 0 | ACTIVE | RUNNER | 14 | 10 | 0 | 14 | REPAIR | 2024-11-08 | 2024-11-11 | 578 | 0
JP-02250-H04MFA60HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE | 14 | 10 | 0 | 14 | REPAIR (UPPER DRAFT TUBE) | 2024-11-08 | 2024-11-11 | 579 | 1
JP-02260-H04MFA60HA011-ME-U | EGAT | LTK0 | 0 | ACTIVE | DISCHARGE RING | 1 | 10 | 0 | 1 | REPAIR | 2024-11-08 | 2024-11-11 | 580 | 0
JP-02270-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 60 | 10 | 0 | 20 | DIASSEMBLY | 2024-11-05 | 2024-11-06 | 581 | 1
JP-02270-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 60 | 20 | 0 | 10 | CLEAN & INSPECTION | 2024-11-08 | 2024-11-09 | 581 | 1
JP-02270-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 60 | 30 | 0 | 30 | ASSEMBLY | 2024-11-11 | 2024-11-13 | 581 | 1
JP-02280-H04MFD20-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING (ROUTE) | 30 | 10 | 0 | 30 | GAP ADJUSTMENT | 2024-11-14 | 2024-11-16 | 582 | 0
JP-02290-H04MFW40HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL | 50 | 10 | 0 | 10 | INSPECT | 2024-11-08 | 2024-11-08 | 583 | 1
JP-02290-H04MFW40HA001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL | 50 | 20 | 0 | 40 | REPLACEMENT | 2024-11-07 | 2024-11-10 | 583 | 1
JP-02300-H04PAA10AT001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DRAFT TUBE INTAKE SCREEN | 24 | 10 | 0 | 24 | REPAIR | 2024-11-08 | 2024-11-11 | 584 | 0
JP-02310-H14BCT10GU100-B01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS001RT | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 585 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-B01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS001RT | 4 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 585 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-B02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS003RT | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 586 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-B02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS003RT | 4 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 586 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-B03-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 587 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-B03-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 4 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 587 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 588 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 4 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 588 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-11 | 2024-11-11 | 589 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02310-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 4 | 20 | 0 | 2 | CLEANING | 2024-11-11 | 2024-11-11 | 589 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS001RT | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 590 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS001RT | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 590 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS001RT | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-11 | 2024-11-16 | 590 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS003RT | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 591 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS003RT | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 591 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC AC REACTOR: 20LGS003RT | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-11 | 2024-11-16 | 591 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B03-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 592 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B03-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 592 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-B03-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC DC REACTOR ENCLOSURE: 20LGS002RT | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-11 | 2024-11-16 | 592 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 593 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 593 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-11 | 2024-11-16 | 593 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 594 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-11 | 2024-11-16 | 594 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02320-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-11 | 2024-11-16 | 594 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 92 | 10 | 0 | 72 | HOT OIL PURIFY | 2024-11-11 | 2024-11-16 | 595 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 92 | 20 | 0 | 5 | TRANSFORMER INSPECTION | 2024-11-11 | 2024-11-16 | 595 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 92 | 30 | 0 | 5 | INSTRUMENTS INSPECTION | 2024-11-11 | 2024-11-16 | 595 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 92 | 40 | 0 | 5 | INSTRUMENTS TEST & CALIBRATION | 2024-11-11 | 2024-11-16 | 595 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T01-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC INCOMING TRANSFORMER: 20LGS001TR | 92 | 50 | 0 | 5 | FUNCTION TEST | 2024-11-11 | 2024-11-16 | 595 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 92 | 10 | 0 | 72 | HOT OIL PURIFY | 2024-11-11 | 2024-11-16 | 596 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 92 | 20 | 0 | 5 | TRANSFORMER INSPECTION | 2024-11-11 | 2024-11-16 | 596 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 92 | 30 | 0 | 5 | INSTRUMENTS INSPECTION | 2024-11-11 | 2024-11-16 | 596 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 92 | 40 | 0 | 5 | INSTRUMENTS TEST & CALIBRATION | 2024-11-11 | 2024-11-16 | 596 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02330-H14BCT10GU100-T02-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC OUTGOING TRANSFORMER: 20LGS002TR | 92 | 50 | 0 | 5 | FUNCTION TEST | 2024-11-11 | 2024-11-16 | 596 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02340-H14BCT10CE210-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5P20 - 031TI-033TI | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-13 | 2024-11-13 | 597 | 1
JP-02340-H14BCT10CE210-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5P20 - 031TI-033TI | 4 | 20 | 0 | 2 | CLEANING | 2024-11-13 | 2024-11-13 | 597 | 1
JP-02340-H14BCT10CE220-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5FS5 - 034TI-036TI | 4 | 10 | 0 | 2 | INSPECTION | 2024-11-13 | 2024-11-13 | 598 | 0
JP-02340-H14BCT10CE220-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5FS5 - 034TI-036TI | 4 | 20 | 0 | 2 | CLEANING | 2024-11-13 | 2024-11-13 | 598 | 0
JP-02350-H14BCT10CE110-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | PT: 16.5kV/115 V, CL1.2 - 001TU-002TU | 2 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-13 | 2024-11-13 | 599 | 1
JP-02350-H14BCT10CE230-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5P20 - 037TI-039TI | 2 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-13 | 2024-11-13 | 600 | 0
JP-02350-H14BCT10CE240-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 1200A/5A, 5P20 - 040TI-042TI | 2 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-13 | 2024-11-13 | 601 | 1
JP-02350-H14BCT10CE250-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | CT: 16.5kV, 4000A/5A, C400 - TA156-TA158 | 2 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-13 | 2024-11-13 | 602 | 0
JP-02360-H14BCT10GS001-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC1 | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-11 | 2024-11-11 | 603 | 1
JP-02360-H14BCT10GS001-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC1 | 5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 603 | 1
JP-02360-H14BCT10GS001-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC1 | 5 | 30 | 0 | 1 | LUBRICANT | 2024-11-11 | 2024-11-11 | 603 | 1
JP-02360-H14BCT10GS001-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC1 | 5 | 40 | 0 | 1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-11 | 2024-11-11 | 603 | 1
JP-02360-H14BCT10GS001-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC1 | 5 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-11 | 2024-11-11 | 603 | 1
JP-02360-H14BCT10GS003-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC2 | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-11 | 2024-11-11 | 604 | 0
JP-02360-H14BCT10GS003-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC2 | 5 | 20 | 0 | 1 | CLEANING | 2024-11-11 | 2024-11-11 | 604 | 0
JP-02360-H14BCT10GS003-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC2 | 5 | 30 | 0 | 1 | LUBRICANT | 2024-11-11 | 2024-11-11 | 604 | 0
JP-02360-H14BCT10GS003-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC2 | 5 | 40 | 0 | 1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-11 | 2024-11-11 | 604 | 0
JP-02360-H14BCT10GS003-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | VCB - 52SFC2 | 5 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-11 | 2024-11-11 | 604 | 0
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 30 | 0 | 1 | LUBRICANT | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 50 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 60 | 0 | 1 | FINAL INSPECTION | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02370-H14BCA10GU201-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 89SFC | 7 | 70 | 0 | 1 | OPERATION TEST | 2024-11-12 | 2024-11-12 | 605 | 1
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 10 | 0 | 1 | INSPECTION | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 20 | 0 | 1 | CLEANING | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 30 | 0 | 1 | LUBRICANT | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 50 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 60 | 0 | 1 | FINAL INSPECTION | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02380-H14BCY10GU205-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | DS - 3WAY POSITION | 7 | 70 | 0 | 1 | OPERATION TEST | 2024-11-12 | 2024-11-12 | 606 | 0
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 10 | 0 | 3 | INSPECTION | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 20 | 0 | 3 | CLEANING | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 30 | 0 | 3 | JUNCTION RESISTANCE MEASUREMENT | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 40 | 0 | 3 | PULSE FIRING TEST | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 50 | 0 | 3 | CT CURRENT DETECTOR TEST & CALIBRATION | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 60 | 0 | 3 | BACK UP | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02390-H14BCY10-ME-C14 | EGAT | LTK0 | 0 | ACTIVE | SFC REGULATE CONTROL | 21 | 70 | 0 | 3 | FINAL CHECK | 2024-11-12 | 2024-11-15 | 607 | 1
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 30 | 0 | 1 | LUBRICANT | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 40 | 0 | 1 | MOTOR CURRENT MEASUREMENT | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 50 | 0 | 1 | POSITION SENSOR CALIBRATION | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 60 | 0 | 1 | ELECTRICAL TEST (INSULATION RESISTANCE MEASUREMENT, CONTACT RESISTANCE TEST) | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 70 | 0 | 1 | FINAL INSPECTION | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02400-H34BBT10GS200-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5 KV DS 89SS, 1641B (หปฟนม-ธ.) | 8 | 80 | 0 | 1 | OPERATION TEST | 2024-11-05 | 2024-11-05 | 608 | 0
JP-02410-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หปฟนม-ธ.) | 8 | 10 | 0 | 2 | INSPECTION | 2024-11-05 | 2024-11-05 | 609 | 1
JP-02410-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หปฟนม-ธ.) | 8 | 20 | 0 | 2 | CLEANING | 2024-11-05 | 2024-11-05 | 609 | 1
JP-02410-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หปฟนม-ธ.) | 8 | 30 | 0 | 2 | SELF PROTECTION INSTRUMENTS INPECTION, CLEANING & TEST | 2024-11-05 | 2024-11-05 | 609 | 1
JP-02410-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หปฟนม-ธ.) | 8 | 40 | 0 | 2 | FINAL CHECK | 2024-11-05 | 2024-11-05 | 609 | 1
JP-02420-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หทอฟ-ธ.) | 6 | 10 | 0 | 2 | ELECTRICAL TEST (RATIO & POLARITY TEST, INSULATION RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 610 | 0
JP-02420-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หทอฟ-ธ.) | 6 | 20 | 0 | 2 | ELECTRICAL TEST (EXCITING CURRENT MEASUREMENT, DC RESISTANCE MEASUREMENT) | 2024-11-05 | 2024-11-05 | 610 | 0
JP-02420-H34BBT10-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 16.5/6.6 KV STATION TRANSFORMER 3 - KW3B (หทอฟ-ธ.) | 6 | 30 | 0 | 2 | ELECTRICAL TEST (INSULATION POWER FACTOR MEASUREMENT) | 2024-11-05 | 2024-11-05 | 610 | 0
JP-02430-H34CHE20GH101-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. PROTECTION SYSTEM A/B CUBICLE | 2 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 611 | 1
JP-02430-H34CHE20GH101-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. PROTECTION SYSTEM A/B CUBICLE | 2 | 30 | 0 | 1 | RETIGHTENING | 2024-11-05 | 2024-11-05 | 611 | 1
JP-02440-H34CHE20GH101-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | 4 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 612 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | 4 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 612 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | 4 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-05 | 612 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM A | 4 | 40 | 0 | 1 | OPERATING CHARECTERISTIC TEST (87HT, 51HT, 251T, 49HT) | 2024-11-05 | 2024-11-05 | 612 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U02-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | 4 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 613 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U02-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | 4 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 613 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U02-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | 4 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-05 | 613 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02440-H34CHE20GH101-U02-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. ELECTRICAL PROTECTION RELAY - SYSTEM B | 4 | 40 | 0 | 1 | OPERATING CHARECTERISTIC TEST (87HT, 51HT, 251T, 49HT) | 2024-11-05 | 2024-11-05 | 613 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02450-H34CHE20GH101-U03-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. MECHNICAL PROTECTION RELAY | 3 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 614 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02450-H34CHE20GH101-U03-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. MECHNICAL PROTECTION RELAY | 3 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 614 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02450-H34CHE20GH101-U03-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | UNIT 3-4 SST. MECHNICAL PROTECTION RELAY | 3 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-05 | 614 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02460-H34BBA50GS100-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 6.6 KV MV BREAKER - 652G | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 615 | 1
JP-02460-H34BBA50GS100-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 6.6 KV MV BREAKER - 652G | 5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 615 | 1
JP-02460-H34BBA50GS100-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 6.6 KV MV BREAKER - 652G | 5 | 30 | 0 | 1 | LUBRICANT | 2024-11-05 | 2024-11-05 | 615 | 1
JP-02460-H34BBA50GS100-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 6.6 KV MV BREAKER - 652G | 5 | 40 | 0 | 1 | ELECTRICAL TEST (CONTACT RESISTANCE TEST, TIMMING TEST) | 2024-11-05 | 2024-11-05 | 615 | 1
JP-02460-H34BBA50GS100-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | 6.6 KV MV BREAKER - 652G | 5 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-05 | 2024-11-05 | 615 | 1
JP-02470-H34BBA50GS100-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | PROTECTION RELAY FOR BREAKER 652G | 5 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 616 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02470-H34BBA50GS100-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | PROTECTION RELAY FOR BREAKER 652G | 5 | 20 | 0 | 1 | CLEANING | 2024-11-05 | 2024-11-05 | 616 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02470-H34BBA50GS100-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | PROTECTION RELAY FOR BREAKER 652G | 5 | 30 | 0 | 1 | BINARY INPUT CHECK | 2024-11-05 | 2024-11-05 | 616 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02470-H34BBA50GS100-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | PROTECTION RELAY FOR BREAKER 652G | 5 | 40 | 0 | 1 | OPERATING CHARECTERISTIC TEST (59N, 51, 251T, 49HT) | 2024-11-05 | 2024-11-05 | 616 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02470-H34BBA50GS100-U01-ME-C34 | EGAT | LTK0 | 0 | ACTIVE | PROTECTION RELAY FOR BREAKER 652G | 5 | 50 | 0 | 1 | FINAL INSPECTION | 2024-11-05 | 2024-11-05 | 616 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02480-H04MLD20-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING (ROUTE) | 8 | 10 | 0 | 1 | INSPECTION | 2024-11-05 | 2024-11-05 | 617 | 1
JP-02480-H04MLD20-ME-U | EGAT | LTK0 | 0 | ACTIVE | UPPER GUIDE BEARING (ROUTE) | 8 | 20 | 0 | 7 | GAP ADJUSTMENT | 2024-11-05 | 2024-11-05 | 617 | 1
JP-02490-H04PCM30BR001-ME-U | EGAT | LTK0 | 0 | ACTIVE | GEN AIR COOLER PIPE | 16 | 10 | 0 | 16 | REPAIR | 2024-11-08 | 2024-11-10 | 618 | 0
JP-02500-H04PCM30-ME-U | EGAT | LTK0 | 0 | ACTIVE | GENERATOR AIR COOLER NO.1 - NO.6 (ROUTE) | 16 | 10 | 0 | 16 | MODIFICATION AIR VANT VALVE&DRAIN VALVE (CHANGE SOCKET WELD BOSS 12 EA) | 2024-11-08 | 2024-11-10 | 619 | 1
JP-02510-H04MFB10AS010-ME-U | EGAT | LTK0 | 0 | ACTIVE | MAIN INLET VALVE SERVOMOTOR NO.1 (ADD) | 20 | 10 | 0 | 20 | SEAL REPLACEMENT (STEM SEAL) | 2024-11-08 | 2024-11-09 | 620 | 0
JP-02520-H04PAB10AA014-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHUT OFF VALVE 4PAB10AA014 | 12 | 10 | 0 | 12 | REPLACEMENT | 2024-11-08 | 2024-11-08 | 621 | 1
JP-02530-H04MFW40BR001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL PIPE | 4 | 10 | 0 | 4 | MODIFICATION | 2024-11-08 | 2024-11-08 | 622 | 0
JP-02540-H04MFD20BB001-ME-U | EGAT | LTK0 | 0 | ACTIVE | TURBINE GUIDE BEARING OIL PAN | 18 | 10 | 0 | 18 | MODIFICATION | 2024-11-06 | 2024-11-12 | 623 | 1
JP-02550-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 624 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 624 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 624 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT001XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE OIL TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 624 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 625 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 625 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 625 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT002XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE OIL TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 625 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 626 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 626 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 626 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT003XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE OIL TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 626 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 627 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 627 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 627 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT004XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | B PHASE WINDING TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 627 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 628 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 628 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 628 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT005XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | A PHASE WINDING TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 628 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 629 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 629 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 629 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT006XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | b PHASE WINDING TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 629 | 1 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 12 | 10 | 0 | 3 | DISASSEMBLY | 2024-11-05 | 2024-11-10 | 630 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 12 | 20 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-10 | 630 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 12 | 30 | 0 | 3 | INSTALLATION NEW INSTRUMENTS | 2024-11-05 | 2024-11-10 | 630 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02550-H04BAT01CT007XQ01-ME-U | EGAT | LTK0 | 0 | ACTIVE | C PHASE WINDING TEMPERATURE | 12 | 40 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-10 | 630 | 0 | JPNUM มีความยาวมากกว่า 30 ตัวอักษร
JP-02560-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 6 | 10 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-10 | 2024-11-11 | 631 | 1
JP-02560-H04MLV40CP101-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.1 PRESSURE SWITCH - CP101 | 6 | 20 | 0 | 3 | FUNTION TEST | 2024-11-10 | 2024-11-11 | 631 | 1
JP-02560-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 6 | 10 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-10 | 2024-11-11 | 632 | 0
JP-02560-H04MLV40CP111-ME-U | EGAT | LTK0 | 0 | ACTIVE | HPO PUMP NO.2 PRESSURE SWITCH - CP111 | 6 | 20 | 0 | 3 | FUNTION TEST | 2024-11-10 | 2024-11-11 | 632 | 0
JP-02570-H04MFW40CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE TRANSMITTER - CP001 (INSTALLATION) | 9 | 10 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-13 | 633 | 1
JP-02570-H04MFW40CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE TRANSMITTER - CP001 (INSTALLATION) | 9 | 20 | 0 | 3 | INSTALLATION | 2024-11-05 | 2024-11-13 | 633 | 1
JP-02570-H04MFW40CP001-ME-U | EGAT | LTK0 | 0 | ACTIVE | SHAFT SEAL WATER PRESSURE TRANSMITTER - CP001 (INSTALLATION) | 9 | 30 | 0 | 3 | FUNCTION TEST | 2024-11-05 | 2024-11-13 | 633 | 1
JP-02580-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 15 | 10 | 0 | 3 | LAYING & WIRING NEW CABLE | 2024-11-05 | 2024-11-16 | 634 | 0
JP-02580-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 15 | 20 | 0 | 3 | INSTALLATION | 2024-11-05 | 2024-11-16 | 634 | 0
JP-02580-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 15 | 30 | 0 | 3 | CALIBRATION | 2024-11-05 | 2024-11-16 | 634 | 0
JP-02580-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 15 | 40 | 0 | 3 | FUNCTION TEST (WET M1) | 2024-11-05 | 2024-11-16 | 634 | 0
JP-02580-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 15 | 50 | 0 | 3 | FUNCTION TEST (WET M2) | 2024-11-05 | 2024-11-16 | 634 | 0
JP-02590-H04MFL30CL001-ME-U | EGAT | LTK0 | 0 | ACTIVE | DT CONE LEVEL TRANSMITTER - CL001 (INSTALLATION & TEST) | 18 | 10 | 0 | 18 | PIPE INSTALLATION | 2024-11-05 | 2024-11-16 | 635 | 1